## REVISED 08072021
F1 |  | F2 |  |  | F3 |  |  | F4 |  |  | F5 |  |  | F6
PROJECT TYPE |  | TRADE |  |  | HOR.WBS (HIGH LEVEL) |  |  | HOR.WBS (SUB LEVEL) |  |  | Vertical WBS |  |  | SUB LOCATION
2 digits |  | 2 digits |  |  | 2 digits |  |  | 2 digits |  |  | 3 digits |  |  | 2 digits
Code | Description | Code | Abbreviation | Description | Code | Abbreviation | Description | Code | Abbreviation | Description | Code | Abbreviation | Description | Code | Abbreviation | Description
01 | Building | 01 | CIV | Civil | 01 | MUS | Museum | 01 | Z1A | Zone 01A | 001 | BS | L-B1 Basement Level | 01 | CIR/COM | Circulation / Common Areas
|  | 02 | PSS | Primary Steel Structure | 02 | MOU | Mound Works | 02 | Z1B | Zone 01B | 002 | BS-MZ | L-BM Basement Mezzanine Level | 02 | MEP/SR | MEP / Service Rooms
|  | 03 | SSS | Secondary Steel Structure | 03 | TLG | Time Line Garden | 03 | Z1C | Zone 01C | 003 | GR | L00 Ground Level | 03 | WAR | Wet Areas
|  | 04 | ARC | Architecture | 04 | EXT | External Works | 04 | Z1D | Zone 01D | 004 | MZ | L01 Mezzanine Level | 04 | ZNM-SA | ZNM Specific Areas
|  | 05 | FAC | Façade/Envelope |  |  |  | 05 | Z1E | Zone 01E | 005 | GA | L02 Gallery level | 05 | SOA | Storage / Offices / Admin Areas
|  | 06 | HVAC | HVAC |  |  |  | 06 | Z1F | Zone 01F | 006 | PL | L03 Plenum Level | 06 | WW1 | Mound Walkway -1
|  | 07 | ELE | Electrical |  |  |  | 07 | Z2A | Zone 02A | 007 | OA | L04 Oasis Level | 07 | WW2 | Mound Walkway -2
|  | 08 | PLU | Plumbing |  |  |  | 08 | Z2B | Zone 02B | 008 | CL | Central Lobby | 08 | EXT | Mound External
|  | 09 | FF | Firefighting |  |  |  | 09 | Z2C | Zone 02C | 009 | DR | Drum / Ring Beam | 09 | INT | Mound Internal
|  | 10 | CCTV | CCTV |  |  |  | 10 | Z2D | Zone 02D | 010 | POD | Pod | 10 | PER | Mound Perimeter
|  | 11 | RO-LAN | Roads & Landscaping |  |  |  | 11 | Z2E | Zone 02E | 011 | WIN | Wing | 11 | UA | Urban Area
|  | 12 | UTI | Underground Utilities |  |  |  | 12 | Z2F | Zone 02F | 012 | MLL | Mound Lower Level | 12 | OA | Oasis Area
|  | 13 | VTR | Vertical Transportation |  |  |  | 13 | Z2G | Zone 02G | 013 | MUL | Mound Upper Level | 13 | DA | Desert Area
|  | 14 | GMEP | General MEP |  |  |  | 14 | Z2H | Zone 02H | 014 | EGL | External Ground Level (External / TLG) | 14 | CA | Coast Area
[8 empty] | 15 | Z3A | Zone 03A |  |  |  | 15 | PW | Parking - West
[8 empty] | 16 | Z3B | Zone 03B |  |  |  | 16 | PE | Parking - East
[8 empty] | 17 | Z3C | Zone 03C |  |  |  | 17 | BS | Bicycle Storage
[8 empty] | 18 | Z04 | Zone 04 |  |  |  | 18 | TER1 | TLG Electrical Room 1 / Toilets - 1
[8 empty] | 19 | Z05 | Zone 05 |  |  |  | 19 | CK1 | Café Kiosk 1
[8 empty] | 21 | M1A | Zone M1A |  |  |  | 20 | TER2 | TLG Electrical Room 2 / Stair 12
[8 empty] | 22 | M2A | Zone M2A |  |  |  | 21 | TLO | TLG Office / Prayer / Ablutions
[8 empty] | 23 | M3A | Zone M3A |  |  |  | 22 | CK3 | Café Kiosk 3
[8 empty] | 24 | M4A | Zone M4A |  |  |  | 23 | TER4 | TLG Electrical Room 4 / Toilets - 2
[8 empty] | 25 | M5A | Zone M5A |  |  |  | 24 | CK2 | Café Kiosk 2
[8 empty] | 26 | M6A | Zone M6A |  |  |  | 25 | TUN | Tunnel (Near to Zone E)
[8 empty] | 27 | M7A | Zone M7A |  |  |  | 26 | RMP1 | Ramp 01
[8 empty] | 28 | M08 | Zone M8 |  |  |  | 27 | RMP2 | Ramp 02
[8 empty] | 29 | M1B-W1 | Zone M1B (Walkway 1) |  |  |  | 30 | CSZ | Civil SubZones
[8 empty] | 30 | M1B-W2 | Zone M1B (Walkway 2) |  |  |  | 50 | ASZ | Architectural SubZones
[8 empty] | 31 | M2B | Zone M2B |  |  |  | 70 | MSZ | MEP SubZones
[8 empty] | 32 | M3B | Zone M3B
[8 empty] | 33 | M4B | Zone M4B
[8 empty] | 34 | M5B | Zone M5B
[8 empty] | 35 | M6B | Zone M6B
[8 empty] | 36 | M7B | Zone M7B
[8 empty] | 37 | VIP | VIP Canopy & Courtyard
[8 empty] | 38 | TLG1 | Zone TLG1
[8 empty] | 39 | TLG2 | Zone TLG2
[8 empty] | 40 | OCY | Office Courtyard 1 & 2
[8 empty] | 41 | PAR | Parking Area
[8 empty] | 43 | ANC | Ancillary Buildings
[8 empty] | 44 | NE | North East
[8 empty] | 45 | SE | South East
[8 empty] | 46 | NW | North West
[8 empty] | 47 | SW | South West
[8 empty] | 48 | MB | Minibox
[8 empty] | 49 | L03 Z2&Z3 SA | L03 Z02 & Z03 Service Area
[8 empty] | 50 | L04 R | L04 Roof
[8 empty] | 51 | BFW | Building Façade Works
[8 empty] | 52 | GEW | General External Works
[8 empty] | 53 | SF | Specialist Fitout

## Sheet2
F1 |  | F2 |  |  | F3 |  |  | F4 |  |  | F5 |  |  | F6
PROJECT TYPE |  | TRADE |  |  | HOR.WBS (HIGH LEVEL) |  |  | HOR.WBS (SUB LEVEL) |  |  | Vertical WBS |  |  | SUB LOCATION
2 digits |  | 2 digits |  |  | 2 digits |  |  | 2 digits |  |  | 3 digits |  |  | 2 digits
Code | Description | Code | Abbreviation | Description | Code | Abbreviation | Description | Code | Abbreviation | Description | Code | Abbreviation | Description | Code | Abbreviation | Description
01 | Building | 01 | CIV | Civil | 01 | MUS | Museum | 01 | Z1A | Zone 01A | 001 | BS | L-B1 Basement Level | 01 | CIR/COM | Circulation / Common Areas
|  | 02 | PSS | Primary Steel Structure | 02 | MOU | Mound Works | 02 | Z1B | Zone 01B | 002 | BS-MZ | L-BM Basement Mezzanine Level | 02 | MEP/SR | MEP / Service Rooms
|  | 03 | SSS | Secondary Steel Structure | 03 | TLG | Time Line Garden | 03 | Z1C | Zone 01C | 003 | GR | L00 Ground Level | 03 | WAR | Wet Areas
|  | 04 | ARC | Architecture | 04 | EXT | External Works | 04 | Z1D | Zone 01D | 004 | MZ | L01 Mezzanine Level | 04 | ZNM-SA | ZNM Specific Areas
|  | 05 | FAC | Façade/Envelope |  |  |  | 05 | Z1E | Zone 01E | 005 | GA | L02 Gallery level | 05 | SOA | Storage / Offices / Admin Areas
|  | 06 | HVAC | HVAC |  |  |  | 06 | Z1F | Zone 01F | 006 | PL | L03 Plenum Level | 06 | WW1 | Mound Walkway -1
|  | 07 | ELE | Electrical |  |  |  | 07 | Z2A | Zone 02A | 007 | OA | L04 Oasis Level | 07 | WW2 | Mound Walkway -2
|  | 08 | PLU | Plumbing |  |  |  | 08 | Z2B | Zone 02B | 008 | CL | Central Lobby | 08 | EXT | Mound External
|  | 09 | FF | Firefighting |  |  |  | 09 | Z2C | Zone 02C | 009 | DR | Drum / Ring Beam | 09 | INT | Mound Internal
|  | 10 | CCTV | CCTV |  |  |  | 10 | Z2D | Zone 02D | 010 | POD | Pod | 10 | PER | Mound Perimeter
|  | 11 | RO-LAN | Roads & Landscaping |  |  |  | 11 | Z2E | Zone 02E | 011 | WIN | Wing | 11 | UA | Urban Area
|  | 12 | UTI | Underground Utilities |  |  |  | 12 | Z2F | Zone 02F | 012 | MLL | Mound Lower Level | 12 | OA | Oasis Area
|  | 13 | VTR | Vertical Transportation |  |  |  | 13 | Z2G | Zone 02G | 013 | MUL | Mound Upper Level | 13 | DA | Desert Area
|  | 14 | GMEP | General MEP |  |  |  | 14 | Z2H | Zone 02H | 014 | EGL | External Ground Level (External / TLG) | 14 | CA | Coast Area
[8 empty] | 15 | Z3A | Zone 03A |  |  |  | 15 | PW | Parking - West
[8 empty] | 16 | Z3B | Zone 03B |  |  |  | 16 | PE | Parking - East
[8 empty] | 17 | Z3C | Zone 03C |  |  |  | 17 | BS | Bicycle Storage
[8 empty] | 18 | Z04 | Zone 04 |  |  |  | 18 | TER1 | TLG Electrical Room 1 / Toilets - 1
[8 empty] | 19 | Z05 | Zone 05 |  |  |  | 19 | CK1 | Café Kiosk 1
[8 empty] | 21 | M1A | Zone M1A |  |  |  | 20 | TER2 | TLG Electrical Room 2 / Stair 12
[8 empty] | 22 | M2A | Zone M2A |  |  |  | 21 | TLO | TLG Office / Prayer / Ablutions
[8 empty] | 23 | M3A | Zone M3A |  |  |  | 22 | CK3 | Café Kiosk 3
[8 empty] | 24 | M4A | Zone M4A |  |  |  | 23 | TER4 | TLG Electrical Room 4 / Toilets - 2
[8 empty] | 25 | M5A | Zone M5A |  |  |  | 24 | CK2 | Café Kiosk 2
[8 empty] | 26 | M6A | Zone M6A |  |  |  | 25 | TUN | Tunnel (Near to Zone E)
[8 empty] | 27 | M7A | Zone M7A |  |  |  | 26 | RMP1 | Ramp 01
[8 empty] | 28 | M08 | Zone M8 |  |  |  | 27 | RMP2 | Ramp 02
[8 empty] | 29 | M1B-W1 | Zone M1B (Walkway 1) |  |  |  | 30 | CSZ | Civil SubZones
[8 empty] | 30 | M1B-W2 | Zone M1B (Walkway 2) |  |  |  | 50 | ASZ | Architectural SubZones
[8 empty] | 31 | M2B | Zone M2B |  |  |  | 70 | MSZ | MEP SubZones
[8 empty] | 32 | M3B | Zone M3B
[8 empty] | 33 | M4B | Zone M4B
[8 empty] | 34 | M5B | Zone M5B
[8 empty] | 35 | M6B | Zone M6B
[8 empty] | 36 | M7B | Zone M7B
[8 empty] | 37 | VIP | VIP Canopy & Courtyard
[8 empty] | 38 | TLG1 | Zone TLG1
[8 empty] | 39 | TLG2 | Zone TLG2
[8 empty] | 40 | OCY | Office Courtyard 1 & 2
[8 empty] | 41 | PAR | Parking Area
[8 empty] | 43 | ANC | Ancillary Buildings
[8 empty] | 44 | NE | North East
[8 empty] | 45 | SE | South East
[8 empty] | 46 | NW | North West
[8 empty] | 47 | SW | South West
[8 empty] | 48 | MB | Minibox
[8 empty] | 49 | L03 Z2&Z3 SA | L03 Z02 & Z03 Service Area
[8 empty] | 50 | L04 R | L04 Roof
[8 empty] | 51 | BFW | Building Façade Works
[8 empty] | 52 | GEW | General External Works
[8 empty] | 53 | SF | Specialist Fitout

## Programme (Construction)
Activity ID | Activity Name | Original Duration | Start | Finish | F1 | F2 | F3 | F4 | F5 | F6 |  | F1 | F2 | F3 | F4 | F5 | F6
Zayed National Museum - Detailed Programme - Rev. 1 |  | 700 | 2021-04-21 | 2023-08-15
Construction |  | 700 | 2021-04-21 | 2023-08-15
Permanent work |  | 700 | 2021-04-21 | 2023-08-15
Museum |  | 700 | 2021-04-21 | 2023-08-15
Zone 1 - DRUMS, PODS, WINGS & CENTRAL LOBBY | Preparation, Honing, and Protection - RB Vertical | 687 | 2021-05-06 | 2023-08-15
Zone 1D - Drum 1 |  | 607 | 2021-05-25 | 2023-05-26
Civil Works |  | 476 | 2021-05-25 | 2022-12-20
Grey Concrete |  | 47 | 2022-10-26 | 2022-12-20
C-PW-032960 | Ground Level Slab (leave out area) | 12 | 2022-10-26 | 2022-11-08 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032970 | Filling of EPS Void Former | 6 | 2022-11-09 | 2022-11-15 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032980 | Composite slab SSL +19.95 | 21 | 2022-10-26 | 2022-11-19 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032990 | Composite slab SSL +19.95 (Leaveout) | 3 | 2022-11-20 | 2022-11-22 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-033000 | Construction of Raised Floor Slab | 15 | 2022-11-16 | 2022-12-04 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-033010 | Stairs to POD | 26 | 2022-11-20 | 2022-12-20 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
White Concrete |  | 215 | 2021-05-25 | 2022-02-08
Drum Wall 1 |  | 56 | 2021-05-25 | 2021-08-01
Wall/Other Area |  | 24 | 2021-05-29 | 2021-06-24
C-PW-032640 | Reinforcement Cleaning | 18 | 2021-05-29 | 2021-06-17 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032650 | Formwork QA/QC Insp., Joint Insp., Repairs, Clean. & Approval | 18 | 2021-06-05 | 2021-06-24 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
Arches/Bull-Nose Area |  | 19 | 2021-05-29 | 2021-06-19
C-PW-032660 | Reinforcement Shifting/Removal and Cleaning Bull Nose | 9 | 2021-05-29 | 2021-06-07 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032670 | Bull Nose QA/QC Insp., Joint Insp., Repairs, Clean. & Approval | 15 | 2021-06-02 | 2021-06-19 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
General |  | 56 | 2021-05-25 | 2021-08-01
C-PW-032680 | Initial Formwork Survey/Report | 3 | 2021-05-25 | 2021-05-27 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032690 | Final Cleaning of Formwork/Drum wall | 24 | 2021-06-01 | 2021-06-28 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032700 | Final Fromwork Survey/Report and Final Inspection | 4 | 2021-06-24 | 2021-06-28 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032710 | Casting of White Concrete - Drum Wall 1 | 1 | 2021-06-29 | 2021-06-29 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032720 | Curing of Drum Wall 1 - Stage 3 | 7 | 2021-06-30 | 2021-07-07 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032730 | Deshutter Formwork Drum Wall 1 - Stage 3 | 12 | 2021-07-08 | 2021-07-25 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032740 | Installation of Protection for Drum Wall 1 - Stage 3 | 12 | 2021-07-15 | 2021-08-01 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
Ring Beam 1 |  | 165 | 2021-07-26 | 2022-02-08
C-PW-032750 | Extension of DOKA Scaffolding up to lvl +24.0 m | 12 | 2021-07-26 | 2021-08-08 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032760 | Site survey markings for Internal formwork installation | 4 | 2021-08-09 | 2021-08-14 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032770 | Installation of Internal Ring beam formwork | 12 | 2021-08-15 | 2021-08-28 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032780 | Installation of Access Scaffolding for reinforcement | 12 | 2021-08-18 | 2021-08-31 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032790 | Installation of reinforcement - Stage 1 | 38 | 2021-08-22 | 2021-10-04 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032800 | Installation of Steel Embeds - Stage 1 | 6 | 2021-09-28 | 2021-10-04 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032810 | Work Inspection for reinforcement - Stage 1 | 6 | 2021-09-30 | 2021-10-06 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032820 | Site survey markings for External formwork installation | 12 | 2021-10-02 | 2021-10-14 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032830 | Installation of External Ring beam formwork | 12 | 2021-10-02 | 2021-10-14 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032840 | Extend Access Scaffolding | 12 | 2021-10-03 | 2021-10-16 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032850 | Inserting MEP Conduits | 2 | 2021-10-17 | 2021-10-18 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032860 | QA/QC/Work Inspections - Stage 1 | 4 | 2021-10-17 | 2021-10-21 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032870 | Casting of White Concrete - Stage 1 | 1 | 2021-10-23 | 2021-10-23 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032880 | Installation of Plywood - Stage 2 | 12 | 2021-10-31 | 2021-11-13 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032890 | Installation of reinforcement - Stage 2 | 38 | 2021-11-07 | 2021-12-22 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032900 | Installation of Steel Embeds - Stage 2 | 6 | 2021-12-18 | 2021-12-23 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032910 | QA/QC/Work Inspections - Stage 2 | 4 | 2021-12-22 | 2021-12-26 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032920 | Casting of White Concrete - Stage 2 | 1 | 2021-12-27 | 2021-12-27 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032930 | Curing, Removal Formwork & Access for Honing | 18 | 2021-12-28 | 2022-01-18 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032940 | Preparation, Honing, and Protection - RB Vertical | 18 | 2022-01-09 | 2022-01-29 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
C-PW-032950 | Remove Scaffolding and Doka Shoring | 18 | 2022-01-19 | 2022-02-08 | 01 | 01 | 01 | 04 | 009 | 30 |  | Building | Civil | Museum | Zone 01D | Drum / Ring Beam | Civil SubZones
Architectural |  | 125 | 2022-12-05 | 2023-05-26
C-MS-G-FN-MLB-36525 | Void Former & Floor Screed Works | 8 | 2022-12-05 | 2022-12-14 | 01 | 04 | 01 | 04 | 009 | 50 |  | Building | Architecture | Museum | Zone 01D | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36530 | Specialist Fixtures (Framing for Precast Panels/Glass display cases) | 24 | 2022-12-15 | 2023-01-17 | 01 | 04 | 01 | 04 | 009 | 50 |  | Building | Architecture | Museum | Zone 01D | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36535 | Wall Finishes (in-situ White Conc Finish) | 21 | 2023-01-09 | 2023-02-06 | 01 | 04 | 01 | 04 | 009 | 50 |  | Building | Architecture | Museum | Zone 01D | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36540 | Floor Finishes (Polished Conc floor finish) | 14 | 2023-01-31 | 2023-02-17 | 01 | 04 | 01 | 04 | 009 | 50 |  | Building | Architecture | Museum | Zone 01D | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36545 | Specialist Fixtures (Precast Panels/Glass display cases) | 24 | 2023-02-20 | 2023-03-23 | 01 | 04 | 01 | 04 | 009 | 50 |  | Building | Architecture | Museum | Zone 01D | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36550 | Fitout & Step Finishes | 28 | 2023-03-24 | 2023-05-02 | 01 | 04 | 01 | 04 | 009 | 50 |  | Building | Architecture | Museum | Zone 01D | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36555 | Installation of Signage | 10 | 2023-05-03 | 2023-05-16 | 01 | 04 | 01 | 04 | 009 | 50 |  | Building | Architecture | Museum | Zone 01D | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36560 | Final Finishes & Fittings | 8 | 2023-05-17 | 2023-05-26 | 01 | 04 | 01 | 04 | 009 | 50 |  | Building | Architecture | Museum | Zone 01D | Drum / Ring Beam | Architectural SubZones
MEP |  | 87 | 2022-12-15 | 2023-04-14
C-MS-G-MP-46495 | Wall & Floor MEP works 1st & 2nd Fix | 17 | 2022-12-15 | 2023-01-06 | 01 | 14 | 01 | 04 | 009 | 70 |  | Building | General MEP | Museum | Zone 01D | Drum / Ring Beam | MEP SubZones
C-MS-G-MP-46500 | Final Fix MEP works | 10 | 2023-04-03 | 2023-04-14 | 01 | 14 | 01 | 04 | 009 | 70 |  | Building | General MEP | Museum | Zone 01D | Drum / Ring Beam | MEP SubZones
Zone 1D - POD 1 |  | 615 | 2021-06-22 | 2023-07-04
Civil works |  | 439 | 2021-06-22 | 2022-12-05
Steel Structure |  | 439 | 2021-06-22 | 2022-12-05
Temporary Access / Steel Support |  | 201 | 2021-06-22 | 2022-02-20
C-PW-033080 | Erection of Temporary Steel - Preassembly Area | 17 | 2021-06-22 | 2021-07-11 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
C-PW-033090 | Installation of temporary towers / Struts / to support wing & POD - Stage 02 | 20 | 2021-07-12 | 2021-08-07 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
C-PW-033100 | De-Propping and dismantling of temporary towers | 6 | 2021-10-14 | 2021-10-21 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
C-PW-033110 | Erection of Temporary Steel - Stage 01 within drum | 10 | 2022-02-09 | 2022-02-20 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
Erection of POD |  | 396 | 2021-07-17 | 2022-11-08
C-PW-033120 | POD 1 - Stage 01 assembly | 48 | 2021-07-17 | 2021-09-14 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
C-PW-033130 | POD 1 - Stage 02 assembly | 31 | 2021-09-15 | 2021-10-21 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
C-PW-033140 | Inspection works at Ring beam for POD erection | 6 | 2022-02-14 | 2022-02-20 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
C-PW-033150 | Lifting & Installation of Pre-assembled POD 1 steel frame | 12 | 2022-02-21 | 2022-03-06 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
C-PW-033160 | Installation of POD Leaveout Steel Structure | 12 | 2022-10-26 | 2022-11-08 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
Fire Proofing of POD |  | 37 | 2022-10-22 | 2022-12-05
C-PW-033170 | Fire Proofing works on POD Steel Structure (Except Leave out area) | 37 | 2022-10-22 | 2022-12-05 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
C-PW-033180 | Fire Proofing works on POD Steel Structure for Leave out area | 8 | 2022-11-24 | 2022-12-05 | 01 | 02 | 01 | 04 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Pod | Civil SubZones
Cladding Works |  | 193 | 2022-06-22 | 2023-02-09
C-PW-033190 | Install access platform at ring beam level & Inclined MonoRails | 18 | 2022-06-22 | 2022-07-16 | 01 | 05 | 01 | 04 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Pod | Architectural SubZones
C-PW-033200 | Install POD Facade Phase 1 (Belly & mid panels) | 25 | 2022-07-17 | 2022-08-15 | 01 | 05 | 01 | 04 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Pod | Architectural SubZones
C-PW-033210 | Install POD Facade Phase 2 (Belly & mid panels) | 30 | 2022-08-16 | 2022-09-19 | 01 | 05 | 01 | 04 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Pod | Architectural SubZones
C-PW-033220 | Remove access platform at ring beam level & Inclined MonoRails | 12 | 2022-09-20 | 2022-10-03 | 01 | 05 | 01 | 04 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Pod | Architectural SubZones
C-PW-033230 | Install POD Facade Phase 3 (Soffit) | 76 | 2022-07-23 | 2022-10-22 | 01 | 05 | 01 | 04 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Pod | Architectural SubZones
C-PW-033240 | Install POD Facade Phase 4 (Upper panels) | 6 | 2022-11-09 | 2022-11-15 | 01 | 05 | 01 | 04 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Pod | Architectural SubZones
C-PW-033250 | Install POD Skylight - Phase 1 | 18 | 2022-11-09 | 2022-11-29 | 01 | 05 | 01 | 04 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Pod | Architectural SubZones
C-PW-033260 | Install POD Facade Phase 5 (Leaveouts) | 18 | 2022-11-16 | 2022-12-07 | 01 | 05 | 01 | 04 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Pod | Architectural SubZones
C-PW-033270 | Install POD BMU | 18 | 2022-12-08 | 2022-12-28 | 01 | 05 | 01 | 04 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Pod | Architectural SubZones
C-PW-033280 | Install POD Skylight - Phase 2 (including metal works and cladding) | 60 | 2022-12-01 | 2023-02-09 | 01 | 05 | 01 | 04 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Pod | Architectural SubZones
Architectural |  | 64 | 2023-01-30 | 2023-04-27
FLOOR |  | 23 | 2023-03-27 | 2023-04-27
C-MS-P-FN-P1-71880 | Secondary Steel / Metal Decking / Screed | 7 | 2023-03-27 | 2023-04-05 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-71890 | Void Former | 6 | 2023-04-05 | 2023-04-13 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-71895 | Polished concrete Floor | 5 | 2023-04-13 | 2023-04-20 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-71900 | Bronze Grill/Skirting | 5 | 2023-04-20 | 2023-04-27 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
WALLS |  | 58 | 2023-01-30 | 2023-04-19
STAGE 1 (BELLY) |  | 45 | 2023-02-15 | 2023-04-18
Pod Internal |  | 45 | 2023-02-15 | 2023-04-18
C-MS-P-FN-P1-72030 | Secondary Steel A - wall void | 7 | 2023-02-15 | 2023-02-23 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-72035 | Ladders A including Platforms etc - wall void | 5 | 2023-02-24 | 2023-03-02 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-72000 | Secondary Steel A | 9 | 2023-02-27 | 2023-03-09 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-72015 | Pod Internal Cladding | 18 | 2023-03-23 | 2023-04-18 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
STAGE 2 (MID) |  | 35 | 2023-02-07 | 2023-03-27
Pod Internal |  | 35 | 2023-02-07 | 2023-03-27
C-MS-P-FN-P1-72110 | Secondary Steel B - wall void | 6 | 2023-02-07 | 2023-02-14 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-72115 | Ladders B including Platforms etc - wall void | 5 | 2023-02-15 | 2023-02-21 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-72080 | Secondary Steel B | 7 | 2023-02-16 | 2023-02-24 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-72090 | Pod Internal Cladding | 18 | 2023-03-01 | 2023-03-27 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
STAGE 3 (UPPER) |  | 58 | 2023-01-30 | 2023-04-19
Pod Internal |  | 58 | 2023-01-30 | 2023-04-19
C-MS-P-FN-P1-72195 | Secondary Steel C - wall void | 6 | 2023-01-30 | 2023-02-06 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-72200 | Ladders C including Platforms etc - wall void | 5 | 2023-02-07 | 2023-02-13 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-72160 | Secondary Steel C | 6 | 2023-02-08 | 2023-02-15 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-72170 | Pod Internal Cladding | 18 | 2023-03-01 | 2023-03-27 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-72185 | Internal Finishes in leave out areas C | 17 | 2023-03-27 | 2023-04-19 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
STAGE 4(SOFFIT) |  | 12 | 2023-03-10 | 2023-03-27
WALL VOID |  | 12 | 2023-03-10 | 2023-03-27
C-MS-P-FN-P1-71950 | Secondary Steel D | 7 | 2023-03-10 | 2023-03-20 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
C-MS-P-FN-P1-71955 | Ladders D including Platforms etc | 5 | 2023-03-21 | 2023-03-27 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
MEP |  | 111 | 2022-12-05 | 2023-05-09
C-MS-P-MP-MA-73520 | MEP Access for POD Soffit Structure ( New Activity ) | 0 | 2022-12-05 |  | 01 | 14 | 01 | 04 | 010 | 70 |  | Building | General MEP | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-MA-73530 | MEP Access for Phase 2 (BELLY) ( New Activity ) | 0 | 2022-12-05 |  | 01 | 14 | 01 | 04 | 010 | 70 |  | Building | General MEP | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-MA-73550 | MEP Access for Phase 1 (MID & UPPER) ( New Activity ) | 0 | 2022-12-05 |  | 01 | 14 | 01 | 04 | 010 | 70 |  | Building | General MEP | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-MA-73540 | MEP Access for Finishes ( New Activity ) | 0 | 2023-04-18 |  | 01 | 14 | 01 | 04 | 010 | 70 |  | Building | General MEP | Museum | Zone 01D | Pod | MEP SubZones
MECHANICAL |  | 106 | 2022-12-05 | 2023-05-02
HVAC SYSTEM WORKS |  | 106 | 2022-12-05 | 2023-05-02
C-MS-P-MP-AC-72275 | 1st & 2nd Fix HVAC (Supports, Ducts & Insulation at Stage 1 Steel Frame) | 21 | 2022-12-05 | 2023-01-03 | 01 | 06 | 01 | 04 | 010 | 70 |  | Building | HVAC | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-AC-72270 | 1st Fix HVAC (Supports, Ducts & Insulation at Bottom Steel Trusses) | 26 | 2022-12-05 | 2023-01-10 | 01 | 06 | 01 | 04 | 010 | 70 |  | Building | HVAC | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-AC-72280 | 1st & 2nd Fix HVAC (Supports, Ducts & Insulation at Stage 2 Steel Frame) | 21 | 2023-01-10 | 2023-02-08 | 01 | 06 | 01 | 04 | 010 | 70 |  | Building | HVAC | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-AC-72285 | Completion of Bottom Ducting & insulation after removal of Temp. tower | 14 | 2023-01-26 | 2023-02-15 | 01 | 06 | 01 | 04 | 010 | 70 |  | Building | HVAC | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-AC-72290 | Final Fix HVAC (Grills, Diffusers) | 10 | 2023-04-18 | 2023-05-02 | 01 | 06 | 01 | 04 | 010 | 70 |  | Building | HVAC | Museum | Zone 01D | Pod | MEP SubZones
ELECTRICAL WORKS |  | 109 | 2022-12-07 | 2023-05-09
C-MS-P-MP-EL-73725 | 1st Fix Electrical (Supports and Cable trays at Stage 1 Steel Structure) | 18 | 2022-12-07 | 2023-01-02 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-73745 | 1st Fix Electrical (Conduiting & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-15 | 2023-01-02 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-72305 | 1st Fix Electrical (Conduiting & Boxes at Bottom Steel Trusses) | 12 | 2022-12-23 | 2023-01-10 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-72300 | 1st Fix Electrical (Supports and Cable trays at Bottom Steel Trusses) | 24 | 2022-12-07 | 2023-01-10 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-73735 | 1st Fix Electrical (Supports and Cable trays at Stage 2 Steel Structure) | 18 | 2023-01-02 | 2023-01-26 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-73755 | 1st Fix Electrical (Conduiting & Boxes at Stage 2 Steel Structure) | 12 | 2023-01-10 | 2023-01-26 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-72310 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2023-01-26 | 2023-02-21 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-72330 | 2nd Fix Electrical (Installation of Lighting Control Panels) | 6 | 2023-02-21 | 2023-03-01 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-72315 | Cable/Wire Termination & Dressing | 10 | 2023-03-01 | 2023-03-15 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-73905 | Final Fix Electrical (Light Fixtures-Strip Light below Sky light) | 4 | 2023-04-19 | 2023-04-25 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-72335 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2023-04-18 | 2023-05-02 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-72320 | Final Fix Electrical (Power Sockets/ Isolators) | 10 | 2023-04-21 | 2023-05-05 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-EL-73695 | Final Fix Electrical (Light Fixtures) | 10 | 2023-04-25 | 2023-05-09 | 01 | 07 | 01 | 04 | 010 | 70 |  | Building | Electrical | Museum | Zone 01D | Pod | MEP SubZones
ELV |  | 102 | 2022-12-07 | 2023-04-28
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 98 | 2022-12-07 | 2023-04-24
C-MS-P-MP-ELV-72350 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-07 | 2022-12-23 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72355 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 12 | 2022-12-23 | 2023-01-10 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72360 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 4 | 2023-04-18 | 2023-04-24 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
INTRUDER & HOLD-UPS ALARMS |  | 94 | 2022-12-15 | 2023-04-26
C-MS-P-MP-ELV-72370 | 1st Fix Intruder & Hold-Ups Alarms (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-15 | 2023-01-02 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-74390 | 1st Fix Intruder & Hold-Ups Alarms (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-12-15 | 2023-01-02 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72375 | 2nd Fix Intruder & Hold-Ups Alarms Works (Cable Wiring) | 12 | 2023-01-02 | 2023-01-18 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72380 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 4 | 2023-04-20 | 2023-04-26 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
VIDEO SURVEILLANCE SYSTEM |  | 90 | 2022-12-19 | 2023-04-24
C-MS-P-MP-ELV-72430 | 1st Fix Video Surveillance System Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-19 | 2023-01-04 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-74400 | 1st Fix Video Surveillance System Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-12-19 | 2023-01-04 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72435 | 2nd Fix Video Surveillance System Works (Cable Wiring) | 12 | 2023-01-04 | 2023-01-20 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72440 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 4 | 2023-04-18 | 2023-04-24 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
DATA AND TELECOMMUNICATION |  | 90 | 2022-12-21 | 2023-04-26
C-MS-P-MP-ELV-72450 | 1st Fix Data & Telecommunication Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-21 | 2023-01-06 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-74410 | 1st Fix Data & Telecommunication Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2023-01-06 | 2023-01-24 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72455 | 2nd Fix Data & Telecommunication Works (Cables Wiring) | 12 | 2023-01-24 | 2023-02-09 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72460 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 4 | 2023-04-20 | 2023-04-26 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
BMS AND AUTOMATIC CONTROLS |  | 88 | 2022-12-23 | 2023-04-26
C-MS-P-MP-ELV-72470 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-23 | 2023-01-10 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-74420 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2023-01-10 | 2023-01-26 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72475 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 12 | 2023-01-26 | 2023-02-13 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72480 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 4 | 2023-04-20 | 2023-04-26 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
EMERGENCY LIGHTING |  | 86 | 2022-12-23 | 2023-04-24
C-MS-P-MP-ELV-72520 | 1st Fix Emergency Lighting (Conduits & Boxes at Stage 1 Steel Structure | 12 | 2022-12-23 | 2023-01-10 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-74430 | 1st Fix Emergency Lighting (Conduits & Boxes at Stage 2 Steel Structure | 12 | 2023-01-10 | 2023-01-26 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72525 | 2nd Fix Emergency Lighting (Cable & Wiring) | 12 | 2023-01-26 | 2023-02-13 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72530 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 4 | 2023-04-18 | 2023-04-24 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
FIRE ALARM & PUBLIC ADDRESS |  | 90 | 2022-12-23 | 2023-04-28
C-MS-P-MP-ELV-72540 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes)along Bottom Steel Trusses | 12 | 2022-12-23 | 2023-01-10 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-74440 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes at Stage 1 Steel Structure | 12 | 2023-01-10 | 2023-01-26 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-74450 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes at Stage 2 Steel Structure | 12 | 2023-01-26 | 2023-02-13 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72545 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 12 | 2023-02-13 | 2023-03-01 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-ELV-72550 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 4 | 2023-04-24 | 2023-04-28 | 01 | 10 | 01 | 04 | 010 | 70 |  | Building | CCTV | Museum | Zone 01D | Pod | MEP SubZones
LIFE AND SAFETY SYSTEMS |  | 106 | 2022-12-05 | 2023-05-02
FIRE FIGHTING WORKS |  | 106 | 2022-12-05 | 2023-05-02
C-MS-P-MP-FF-72565 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Bottom Steel Trusses | 18 | 2022-12-05 | 2022-12-29 | 01 | 09 | 01 | 04 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-FF-73755 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Stage 1 Steel Structure) | 18 | 2022-12-21 | 2023-01-16 | 01 | 09 | 01 | 04 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-FF-73865 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Bottom Steel Trusses 2nd Layer | 18 | 2023-01-10 | 2023-02-03 | 01 | 09 | 01 | 04 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-FF-73775 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Stage 2 Steel Structure) | 18 | 2023-01-16 | 2023-02-09 | 01 | 09 | 01 | 04 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-FF-72570 | Fire fighting Pipes Pressure Testing | 3 | 2023-02-09 | 2023-02-14 | 01 | 09 | 01 | 04 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-FF-73905 | Final Fix Piping System (Sprinkler Heads below Sky Light) | 4 | 2023-02-14 | 2023-02-20 | 01 | 09 | 01 | 04 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01D | Pod | MEP SubZones
C-MS-P-MP-FF-72575 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 10 | 2023-04-18 | 2023-05-02 | 01 | 09 | 01 | 04 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01D | Pod | MEP SubZones
Close Out Works |  | 40 | 2023-05-09 | 2023-07-04
C-MS-W-CL-W1-72730 | Testing & Commissioning Works - Wing 1 & Pod 1 | 20 | 2023-05-09 | 2023-06-06 | 01 | 14 | 01 | 04 | 010 | 70 |  | Building | General MEP | Museum | Zone 01D | Pod | MEP SubZones
C-MS-W-CL-W1-72735 | Snagging & De-snagging Works - Wing 1 & Pod 1 | 28 | 2023-05-25 | 2023-07-04 | 01 | 04 | 01 | 04 | 010 | 50 |  | Building | Architecture | Museum | Zone 01D | Pod | Architectural SubZones
Zone 1D - Wing 1 |  | 447 | 2021-12-05 | 2023-05-24
Civil works |  | 312 | 2021-12-05 | 2022-12-14
Steel Structure |  | 312 | 2021-12-05 | 2022-12-14
Temporary Access / Steel Support |  | 264 | 2021-12-12 | 2022-10-25
C-PW-033350 | Temporary Steel Platform - Tier - 1 - Pre-assembly | 18 | 2021-12-12 | 2022-01-02 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033360 | Lifting and Installation of Preassembled Temporary Steel Platform - Tier - 1 | 3 | 2022-03-03 | 2022-03-06 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033370 | Erection of Temporary Steel for Tier - 2 | 19 | 2022-05-17 | 2022-06-07 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033380 | Erection of Temporary Steel for Cantilever | 4 | 2022-09-01 | 2022-09-05 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033390 | Dismantling of temporary steel - bracing | 4 | 2022-09-01 | 2022-09-05 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033400 | De-Propping of Permanent steel | 2 | 2022-09-06 | 2022-09-07 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033410 | Erection , alignment , welding and inspection of Verticals,Mullions & Arches Cantilever | 22 | 2022-09-08 | 2022-10-03 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033420 | Dismantling of Temporary Steel for Cantilever | 4 | 2022-10-04 | 2022-10-08 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033430 | Dismantling of temporary steel - Tier 2 , Tier 1 | 18 | 2022-10-04 | 2022-10-25 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
Erection of Wing |  | 312 | 2021-12-05 | 2022-12-14
C-PW-033440 | Wing 1- Tier 1 A-Frames Pre-assembly | 18 | 2021-12-05 | 2021-12-25 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033450 | Lifting & Installation of Pre-assembled Wing 1 A-Frame | 6 | 2022-02-28 | 2022-03-06 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033460 | Wing 1- Tier 1 Erection (Front & Back) | 77 | 2022-03-07 | 2022-06-07 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033470 | Wing 1- Tier 2 Erection (Front & Back) | 69 | 2022-06-08 | 2022-08-31 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
C-PW-033480 | Installation of Wing Leaveout Steel Structure | 12 | 2022-12-01 | 2022-12-14 | 01 | 02 | 01 | 04 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01D | Wing | Civil SubZones
Architectural works |  | 135 | 2022-12-15 | 2023-05-24
Facade Works |  | 135 | 2022-12-15 | 2023-05-24
C-OW-033490 | Facade/ MEP/ BMU installation works for Wing 1 (Top Area - 5 levels) | 91 | 2022-12-15 | 2023-04-01 | 01 | 05 | 01 | 04 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Wing | Architectural SubZones
C-OW-033500 | Facade/ MEP/ BMU installation works for Wing 1 (Bottom Area - 7 levels) | 135 | 2022-12-15 | 2023-05-24 | 01 | 05 | 01 | 04 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01D | Wing | Architectural SubZones
Zone 1E - Drum 2 |  | 681 | 2021-05-06 | 2023-08-08
Civil Works |  | 515 | 2021-05-06 | 2023-01-21
White Concrete |  | 269 | 2021-05-06 | 2022-03-28
Drum Wall 2 |  | 110 | 2021-05-06 | 2021-09-19
C-PW-033510 | Initial Formwork Survey/Report | 9 | 2021-05-06 | 2021-05-19 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033520 | Survey/Identification of Available Rebar Stock | 28 | 2021-05-06 | 2021-06-10 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033530 | Decision Regarding Usability of Available Rebar Stock | 0 | 2021-06-12 |  | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033540 | Order and Delivery of New Rebar (If any) | 12 | 2021-06-12 | 2021-06-24 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033550 | Installed Formwork QA/QC Insp., Joint Insp., Repairs, Clean. & Approval | 9 | 2021-06-19 | 2021-06-28 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033560 | Cleaning of All Rebar - Installed/Laydown Area | 18 | 2021-06-12 | 2021-07-01 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033570 | Laydown Area Formwork/Bull-Nose QA/QC Insp., Joint Insp., Repairs, Clean. & Approval | 18 | 2021-06-19 | 2021-07-08 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033580 | Installation of Bull Nose | 18 | 2021-06-26 | 2021-07-15 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033590 | Reinforcement Installation | 24 | 2021-07-03 | 2021-08-02 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033600 | Formwork Shifting to place and Closing | 24 | 2021-07-13 | 2021-08-14 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033610 | Final Formwork Survey/Report and Final Inspection | 5 | 2021-08-15 | 2021-08-19 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033620 | Casting of White Concrete - DW2 | 1 | 2021-08-21 | 2021-08-21 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033630 | Curing of Drum Wall 2 - Stage 3 | 7 | 2021-08-22 | 2021-08-29 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033640 | Deshutter Formwork Drum Wall 2 - Stage 3 | 12 | 2021-08-30 | 2021-09-12 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033650 | Installation of Protection for Drum Wall 2 - Stage 3 | 12 | 2021-09-06 | 2021-09-19 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
Ring Beam 2 |  | 165 | 2021-09-13 | 2022-03-28
C-PW-033660 | Extension of DOKA Scaffolding up to lvl +24.0 m | 12 | 2021-09-13 | 2021-09-26 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033670 | Site survey markings for Internal formwork installation | 4 | 2021-09-27 | 2021-09-30 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033680 | Reinstallation of Internal Ring beam formwork | 12 | 2021-10-02 | 2021-10-14 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033690 | Installation of Access Scaffolding for reinforcement | 12 | 2021-10-05 | 2021-10-18 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033700 | Installation of reinforcement - Stage 1 | 38 | 2021-10-09 | 2021-11-22 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033710 | Installation of Steel Embeds - Stage 1 | 6 | 2021-11-16 | 2021-11-22 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033720 | Work Inspection for reinforcement - Stage 1 | 6 | 2021-11-18 | 2021-11-24 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033730 | Site survey markings for External formwork installation | 12 | 2021-11-20 | 2021-12-05 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033740 | Installation of External Ring beam formwork | 12 | 2021-11-20 | 2021-12-05 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033750 | Extend Access Scaffolding | 12 | 2021-11-21 | 2021-12-06 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033760 | Inserting MEP Conduits | 2 | 2021-12-07 | 2021-12-08 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033770 | QA/QC/Work Inspections - Stage 1 | 4 | 2021-12-07 | 2021-12-11 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033780 | Casting of White Concrete - Stage 1 | 1 | 2021-12-12 | 2021-12-12 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033790 | Installation of Plywood - Stage 2 | 12 | 2021-12-20 | 2022-01-03 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033800 | Installation of reinforcement - Stage 2 | 38 | 2021-12-27 | 2022-02-09 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033810 | Installation of Steel Embeds - Stage 2 | 6 | 2022-02-05 | 2022-02-10 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033820 | QA/QC/Work Inspections - Stage 2 | 1 | 2022-02-13 | 2022-02-13 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033830 | Casting of White Concrete - Stage 2 | 1 | 2022-02-14 | 2022-02-14 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033840 | Curing, Removal Formwork & Access for Honing | 18 | 2022-02-15 | 2022-03-07 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033850 | Preparation, Honing, and Protection - RB Vertical | 18 | 2022-02-26 | 2022-03-17 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033860 | Remove Scaffolding and Doka Shoring | 18 | 2022-03-08 | 2022-03-28 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
Grey Concrete |  | 50 | 2022-11-22 | 2023-01-21
C-PW-033870 | Ground Level Slab (leave out area) | 12 | 2022-11-22 | 2022-12-06 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033880 | Construction of Verticals to Raised Floor Slab | 8 | 2022-12-07 | 2022-12-15 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033890 | Composite slab SSL +19.95 | 21 | 2022-11-22 | 2022-12-17 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033900 | Composite slab SSL +19.95 (Leaveout) | 3 | 2022-12-18 | 2022-12-20 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033910 | Filling of EPS Void Former | 6 | 2022-12-17 | 2022-12-22 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033920 | Stairs to POD | 26 | 2022-12-18 | 2023-01-17 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
C-PW-033930 | Construction of Raised Floor Slab | 24 | 2022-12-24 | 2023-01-21 | 01 | 01 | 01 | 05 | 009 | 30 |  | Building | Civil | Museum | Zone 01E | Drum / Ring Beam | Civil SubZones
Architectural |  | 142 | 2023-01-23 | 2023-08-08
C-MS-G-FN-MLB-36575 | Void Former & Floor Screed Works | 12 | 2023-01-23 | 2023-02-07 | 01 | 04 | 01 | 05 | 009 | 50 |  | Building | Architecture | Museum | Zone 01E | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36580 | Specialist Fixtures (Framing for Precast Panels/Precast Mould elements) | 21 | 2023-02-08 | 2023-03-08 | 01 | 04 | 01 | 05 | 009 | 50 |  | Building | Architecture | Museum | Zone 01E | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36585 | Wall Finishes (in-situ White Conc Finish) | 24 | 2023-03-02 | 2023-04-04 | 01 | 04 | 01 | 05 | 009 | 50 |  | Building | Architecture | Museum | Zone 01E | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36590 | Floor Finishes (Polished Conc floor finish) | 14 | 2023-04-05 | 2023-04-24 | 01 | 04 | 01 | 05 | 009 | 50 |  | Building | Architecture | Museum | Zone 01E | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36595 | Specialist Fixtures (Precast Panels/Precast Mould elements) | 24 | 2023-04-25 | 2023-05-26 | 01 | 04 | 01 | 05 | 009 | 50 |  | Building | Architecture | Museum | Zone 01E | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36600 | Specialist Fixtures (GRC inlay Panels) | 14 | 2023-05-17 | 2023-06-05 | 01 | 04 | 01 | 05 | 009 | 50 |  | Building | Architecture | Museum | Zone 01E | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36605 | Fitout & Step Finishes | 28 | 2023-06-06 | 2023-07-13 | 01 | 04 | 01 | 05 | 009 | 50 |  | Building | Architecture | Museum | Zone 01E | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36615 | Balustrades and Handrails | 6 | 2023-07-14 | 2023-07-21 | 01 | 04 | 01 | 05 | 009 | 50 |  | Building | Architecture | Museum | Zone 01E | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36610 | Installation of Signage | 10 | 2023-07-14 | 2023-07-27 | 01 | 04 | 01 | 05 | 009 | 50 |  | Building | Architecture | Museum | Zone 01E | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36620 | Final Finishes & Fittings | 8 | 2023-07-28 | 2023-08-08 | 01 | 04 | 01 | 05 | 009 | 50 |  | Building | Architecture | Museum | Zone 01E | Drum / Ring Beam | Architectural SubZones
MEP |  | 100 | 2023-02-08 | 2023-06-27
C-MS-G-MP-46510 | Wall & Floor MEP works 1st & 2nd Fix | 20 | 2023-02-08 | 2023-03-07 | 01 | 14 | 01 | 05 | 009 | 70 |  | Building | General MEP | Museum | Zone 01E | Drum / Ring Beam | MEP SubZones
C-MS-G-MP-46515 | Final Fix MEP works | 10 | 2023-06-14 | 2023-06-27 | 01 | 14 | 01 | 05 | 009 | 70 |  | Building | General MEP | Museum | Zone 01E | Drum / Ring Beam | MEP SubZones
Zone 1E - POD 2 |  | 585 | 2021-09-11 | 2023-08-15
Civil Works |  | 395 | 2021-09-11 | 2022-12-29
Steel Structure |  | 395 | 2021-09-11 | 2022-12-29
Temporary Access / Steel Support |  | 167 | 2021-09-11 | 2022-03-28
C-PW-034010 | Erection of Temporary Steel - Preassembly Area | 17 | 2021-09-11 | 2021-09-29 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
C-PW-034020 | Installation of temporary towers / Struts / to support wing & POD - Stage 02 | 20 | 2021-09-30 | 2021-10-24 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
C-PW-034030 | De-Propping and dismantling of temporary towers | 6 | 2022-01-04 | 2022-01-10 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
C-PW-034040 | Erection of Temporary Steel - Stage 01 within drum | 10 | 2022-03-17 | 2022-03-28 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
Erection of POD |  | 358 | 2021-09-30 | 2022-12-06
C-PW-034050 | POD 2 - Stage 01 assembly | 53 | 2021-09-30 | 2021-12-04 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
C-PW-034060 | POD 2 - Stage 02 assembly | 31 | 2021-12-05 | 2022-01-10 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
C-PW-034070 | Inspection works at Ring Beam for POD erection | 6 | 2022-03-22 | 2022-03-28 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
C-PW-034080 | Lifting & Installation of Pre-assembled POD 2 steel frame | 12 | 2022-03-29 | 2022-04-11 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
C-PW-034090 | Installation of POD Leaveout Steel Structure | 12 | 2022-11-22 | 2022-12-06 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
Fire Proofing of POD |  | 59 | 2022-10-22 | 2022-12-29
C-PW-034100 | Fire Proofing works on POD Steel Structure (Except Leave out area) | 37 | 2022-10-22 | 2022-12-04 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
C-PW-034110 | Fire Proofing works on POD Steel Structure for Leave out area | 8 | 2022-12-21 | 2022-12-29 | 01 | 02 | 01 | 05 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Pod | Civil SubZones
Cladding Works |  | 218 | 2022-07-14 | 2023-03-29
C-PW-034120 | Install access platform at ring beam level & Inclined MonoRails | 18 | 2022-07-14 | 2022-08-04 | 01 | 05 | 01 | 05 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Pod | Architectural SubZones
C-PW-034130 | Install POD Facade Phase 1 (Belly & mid panels) | 30 | 2022-08-06 | 2022-09-08 | 01 | 05 | 01 | 05 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Pod | Architectural SubZones
C-PW-034140 | Install POD Facade Phase 3 (Soffit) | 80 | 2022-07-14 | 2022-10-17 | 01 | 05 | 01 | 05 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Pod | Architectural SubZones
C-PW-034150 | Install POD Facade Phase 2 (Belly & mid panels) | 35 | 2022-09-10 | 2022-10-20 | 01 | 05 | 01 | 05 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Pod | Architectural SubZones
C-PW-034160 | Remove access platform at ring beam level & Inclined MonoRails | 12 | 2022-10-22 | 2022-11-03 | 01 | 05 | 01 | 05 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Pod | Architectural SubZones
C-PW-034170 | Install POD Facade Phase 4 (Upper panels) | 4 | 2022-12-07 | 2022-12-11 | 01 | 05 | 01 | 05 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Pod | Architectural SubZones
C-PW-034180 | Install POD Facade Phase 5 (Leaveouts) | 12 | 2022-12-12 | 2022-12-25 | 01 | 05 | 01 | 05 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Pod | Architectural SubZones
C-PW-034190 | Install POD Skylight - Phase 1 | 24 | 2022-12-07 | 2023-01-04 | 01 | 05 | 01 | 05 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Pod | Architectural SubZones
C-PW-034200 | Install POD BMU | 18 | 2022-12-26 | 2023-01-16 | 01 | 05 | 01 | 05 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Pod | Architectural SubZones
C-PW-034210 | Install POD Skylight - Phase 2 (including metal works and cladding) | 72 | 2023-01-05 | 2023-03-29 | 01 | 05 | 01 | 05 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Pod | Architectural SubZones
Architectural |  | 58 | 2023-03-20 | 2023-06-07
FLOOR |  | 20 | 2023-05-11 | 2023-06-07
C-MS-P-FN-P2-72940 | Secondary Steel / Metal Decking / Screed | 7 | 2023-05-11 | 2023-05-19 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-72950 | Void Former | 5 | 2023-05-22 | 2023-05-26 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-72955 | Polished concrete Floor | 4 | 2023-05-29 | 2023-06-01 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-72960 | Bronze Grill/Skirting | 4 | 2023-06-02 | 2023-06-07 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
WALLS |  | 54 | 2023-03-20 | 2023-06-01
STAGE 1 (BELLY) |  | 42 | 2023-04-05 | 2023-06-01
Pod Internal |  | 42 | 2023-04-05 | 2023-06-01
C-MS-P-FN-P2-73090 | Secondary Steel A - wall void | 7 | 2023-04-05 | 2023-04-13 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73095 | Ladders A including Platforms etc - wall void | 5 | 2023-04-14 | 2023-04-20 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73060 | Secondary Steel A | 7 | 2023-04-17 | 2023-04-25 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73070 | Pod Internal Cladding | 18 | 2023-05-09 | 2023-06-01 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
STAGE 2 (MID) |  | 32 | 2023-03-28 | 2023-05-10
Pod Internal |  | 32 | 2023-03-28 | 2023-05-10
C-MS-P-FN-P2-73170 | Secondary Steel B - wall void | 6 | 2023-03-28 | 2023-04-04 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73175 | Ladders B including Platforms etc - wall void | 5 | 2023-04-05 | 2023-04-11 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73140 | Secondary Steel B | 7 | 2023-04-06 | 2023-04-14 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73150 | Pod Internal Cladding | 18 | 2023-04-17 | 2023-05-10 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
STAGE 3 (UPPER) |  | 48 | 2023-03-20 | 2023-05-24
Pod Internal |  | 48 | 2023-03-20 | 2023-05-24
C-MS-P-FN-P2-73255 | Secondary Steel C - wall void | 6 | 2023-03-20 | 2023-03-27 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73260 | Ladders C including Platforms etc - wall void | 5 | 2023-03-28 | 2023-04-03 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73220 | Secondary Steel C | 6 | 2023-03-29 | 2023-04-05 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73230 | Pod Internal Cladding | 18 | 2023-04-06 | 2023-05-01 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73245 | Internal Finishes in leave out areas C | 17 | 2023-05-02 | 2023-05-24 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
STAGE 4(SOFFIT) |  | 12 | 2023-04-14 | 2023-05-01
WALL VOID |  | 12 | 2023-04-14 | 2023-05-01
C-MS-P-FN-P2-73010 | Secondary Steel D | 7 | 2023-04-14 | 2023-04-24 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
C-MS-P-FN-P2-73015 | Ladders D including Platforms etc | 5 | 2023-04-25 | 2023-05-01 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
MEP |  | 142 | 2022-12-05 | 2023-06-20
C-MS-P-MP-MA-73560 | MEP Access for POD Soffit Structure ( New Activity ) | 0 | 2022-12-05 |  | 01 | 14 | 01 | 05 | 010 | 70 |  | Building | General MEP | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-MA-73570 | MEP Access for Phase 2 (BELLY) ( New Activity ) | 0 | 2022-12-05 |  | 01 | 14 | 01 | 05 | 010 | 70 |  | Building | General MEP | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-MA-73590 | MEP Access for Phase 1 (MID & UPPER) ( New Activity ) | 0 | 2022-12-05 |  | 01 | 14 | 01 | 05 | 010 | 70 |  | Building | General MEP | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-MA-73580 | MEP Access for Finishes ( New Activity ) | 0 | 2023-06-02 |  | 01 | 14 | 01 | 05 | 010 | 70 |  | Building | General MEP | Museum | Zone 01E | Pod | MEP SubZones
MECHANICAL |  | 139 | 2022-12-05 | 2023-06-15
HVAC SYSTEM WORKS |  | 139 | 2022-12-05 | 2023-06-15
C-MS-P-MP-AC-73330 | 1st Fix HVAC (Supports, Ducts & Insulation at Bottom Steel Trusses) | 26 | 2022-12-05 | 2023-01-09 | 01 | 06 | 01 | 05 | 010 | 70 |  | Building | HVAC | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-AC-73335 | 1st & 2nd Fix HVAC (Supports, Ducts & Insulation at Stage 1 Steel Frame) | 21 | 2022-12-12 | 2023-01-09 | 01 | 06 | 01 | 05 | 010 | 70 |  | Building | HVAC | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-AC-73340 | 1st & 2nd Fix HVAC (Supports, Ducts & Insulation at Stage 2 Steel Frame) | 21 | 2023-01-10 | 2023-02-07 | 01 | 06 | 01 | 05 | 010 | 70 |  | Building | HVAC | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-AC-73345 | Completion of Bottom Ducting & insulation after removal of Temp. tower | 14 | 2023-01-26 | 2023-02-14 | 01 | 06 | 01 | 05 | 010 | 70 |  | Building | HVAC | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-AC-73350 | Final Fix HVAC (Grills, Diffusers) | 10 | 2023-06-02 | 2023-06-15 | 01 | 06 | 01 | 05 | 010 | 70 |  | Building | HVAC | Museum | Zone 01E | Pod | MEP SubZones
ELECTRICAL WORKS |  | 139 | 2022-12-05 | 2023-06-15
C-MS-P-MP-EL-73865 | 1st Fix Electrical (Conduiting & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-05 | 2022-12-20 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73360 | 1st Fix Electrical (Conduiting & Boxes at Bottom Steel Trusses) | 12 | 2022-12-12 | 2022-12-27 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73845 | 1st Fix Electrical (Supports and Cable trays at Stage 1 Steel Structure) | 18 | 2022-12-05 | 2022-12-28 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73365 | 1st Fix Electrical (Supports and Cable trays at Bottom Steel Trusses) | 24 | 2022-12-05 | 2023-01-05 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73875 | 1st Fix Electrical (Conduiting & Boxes at Stage 2 Steel Structure) | 12 | 2022-12-29 | 2023-01-13 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73855 | 1st Fix Electrical (Supports and Cable trays at Stage 2 Steel Structure) | 18 | 2022-12-29 | 2023-01-23 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73370 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2023-01-24 | 2023-02-16 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73390 | 2nd Fix Electrical (Installation of Lighting Control Panels) | 6 | 2023-02-17 | 2023-02-24 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73375 | Cable/Wire Termination & Dressing | 10 | 2023-02-27 | 2023-03-10 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73915 | Final Fix Electrical (Light Fixtures-Strip Light below Sky light) | 4 | 2023-03-30 | 2023-04-04 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73380 | Final Fix Electrical (Power Sockets/ Isolators) | 10 | 2023-06-02 | 2023-06-15 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73385 | Final Fix Electrical (Light Fixtures) | 10 | 2023-06-02 | 2023-06-15 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-EL-73395 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2023-06-02 | 2023-06-15 | 01 | 07 | 01 | 05 | 010 | 70 |  | Building | Electrical | Museum | Zone 01E | Pod | MEP SubZones
ELV |  | 139 | 2022-12-05 | 2023-06-15
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 133 | 2022-12-05 | 2023-06-07
C-MS-P-MP-ELV-73410 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-05 | 2022-12-20 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73415 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 12 | 2022-12-21 | 2023-01-05 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73420 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 4 | 2023-06-02 | 2023-06-07 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
INTRUDER & HOLD-UPS ALARMS |  | 135 | 2022-12-05 | 2023-06-09
C-MS-P-MP-ELV-73430 | 1st Fix Intruder & Hold-Ups Alarms (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-05 | 2022-12-20 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-74670 | 1st Fix Intruder & Hold-Ups Alarms (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-12-05 | 2022-12-20 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73435 | 2nd Fix Intruder & Hold-Ups Alarms Works (Cable Wiring) | 12 | 2022-12-21 | 2023-01-05 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73440 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 4 | 2023-06-06 | 2023-06-09 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
VIDEO SURVEILLANCE SYSTEM |  | 131 | 2022-12-07 | 2023-06-07
C-MS-P-MP-ELV-73490 | 1st Fix Video Surveillance System Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-07 | 2022-12-22 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-74680 | 1st Fix Video Surveillance System Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-12-07 | 2022-12-22 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73495 | 2nd Fix Video Surveillance System Works (Cable Wiring) | 12 | 2022-12-23 | 2023-01-09 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73500 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 4 | 2023-06-02 | 2023-06-07 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
DATA AND TELECOMMUNICATION |  | 131 | 2022-12-09 | 2023-06-09
C-MS-P-MP-ELV-73510 | 1st Fix Data & Telecommunication Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-09 | 2022-12-26 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-74690 | 1st Fix Data & Telecommunication Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-12-27 | 2023-01-11 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73515 | 2nd Fix Data & Telecommunication Works (Cables Wiring) | 12 | 2023-01-12 | 2023-01-27 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73520 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 4 | 2023-06-06 | 2023-06-09 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
BMS AND AUTOMATIC CONTROLS |  | 129 | 2022-12-13 | 2023-06-09
C-MS-P-MP-ELV-73530 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-12-13 | 2022-12-28 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-74700 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-12-29 | 2023-01-13 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73535 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 12 | 2023-01-16 | 2023-01-31 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73540 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 4 | 2023-06-06 | 2023-06-09 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
EMERGENCY LIGHTING |  | 127 | 2022-12-15 | 2023-06-09
C-MS-P-MP-ELV-73580 | 1st Fix Emergency Lighting (Conduits & Boxes at Stage 1 Steel Structure | 12 | 2022-12-15 | 2022-12-30 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-74710 | 1st Fix Emergency Lighting (Conduits & Boxes at Stage 2 Steel Structure | 12 | 2023-01-02 | 2023-01-17 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73585 | 2nd Fix Emergency Lighting (Cable & Wiring) | 12 | 2023-01-18 | 2023-02-02 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73590 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 4 | 2023-06-06 | 2023-06-09 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
FIRE ALARM & PUBLIC ADDRESS |  | 134 | 2022-12-12 | 2023-06-15
C-MS-P-MP-ELV-73600 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes)along Bottom Steel Trusses | 12 | 2022-12-12 | 2022-12-27 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-74720 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes at Stage 1 Steel Structure | 12 | 2022-12-28 | 2023-01-12 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-74730 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes at Stage 2 Steel Structure | 12 | 2023-01-13 | 2023-01-30 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73605 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 12 | 2023-01-31 | 2023-02-15 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-ELV-73610 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 4 | 2023-06-12 | 2023-06-15 | 01 | 10 | 01 | 05 | 010 | 70 |  | Building | CCTV | Museum | Zone 01E | Pod | MEP SubZones
LIFE AND SAFETY SYSTEMS |  | 137 | 2022-12-12 | 2023-06-20
FIRE FIGHTING WORKS |  | 137 | 2022-12-12 | 2023-06-20
C-MS-P-MP-FF-73625 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Bottom Steel Trusses | 18 | 2022-12-12 | 2023-01-04 | 01 | 09 | 01 | 05 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-FF-73805 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Stage 1 Steel Structure) | 18 | 2022-12-28 | 2023-01-20 | 01 | 09 | 01 | 05 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-FF-73875 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Bottom Steel Trusses 2nd Layer | 18 | 2023-01-10 | 2023-02-02 | 01 | 09 | 01 | 05 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-FF-73630 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Stage 2 Steel Structure) | 18 | 2023-01-23 | 2023-02-15 | 01 | 09 | 01 | 05 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-FF-73835 | Fire fighting Pipes Pressure Testing | 3 | 2023-02-16 | 2023-02-20 | 01 | 09 | 01 | 05 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-FF-73915 | Final Fix Piping System (Sprinkler Heads below Sky Light) | 4 | 2023-03-30 | 2023-04-04 | 01 | 09 | 01 | 05 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01E | Pod | MEP SubZones
C-MS-P-MP-FF-73635 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 10 | 2023-06-07 | 2023-06-20 | 01 | 09 | 01 | 05 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01E | Pod | MEP SubZones
Close Out Works |  | 40 | 2023-06-21 | 2023-08-15
C-MS-W-CL-W2-73790 | Testing & Commissioning Works - Wing 2 & Pod 2 | 20 | 2023-06-21 | 2023-07-18 | 01 | 14 | 01 | 05 | 010 | 70 |  | Building | General MEP | Museum | Zone 01E | Pod | MEP SubZones
C-MS-W-CL-W2-73795 | Snagging & De-snagging Works - Wing 2 & Pod 2 | 28 | 2023-07-07 | 2023-08-15 | 01 | 04 | 01 | 05 | 010 | 50 |  | Building | Architecture | Museum | Zone 01E | Pod | Architectural SubZones
Zone 1E - Wing 2 |  | 458 | 2021-12-05 | 2023-06-06
Civil works |  | 341 | 2021-12-05 | 2023-01-18
Steel Structure |  | 341 | 2021-12-05 | 2023-01-18
Temporary Access / Steel Support |  | 269 | 2022-01-03 | 2022-11-21
C-PW-034280 | Temporary Steel Platform - Tier - 1 - Pre-assembly | 18 | 2022-01-03 | 2022-01-23 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034290 | Lifting and Installation of Preassembled Temporary Steel Platform - Tier - 1 | 3 | 2022-04-09 | 2022-04-11 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034300 | Erection of Temporary Steel for Tier - 2 | 19 | 2022-06-05 | 2022-06-26 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034310 | Erection of Temporary Steel for Cantilever | 4 | 2022-09-12 | 2022-09-15 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034320 | Dismantling of temporary steel - bracing | 4 | 2022-09-12 | 2022-09-15 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034330 | De-Propping of Permanent Steel | 2 | 2022-09-17 | 2022-09-18 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034340 | Dismantling of Temporary Steel for Cantilever | 4 | 2022-09-19 | 2022-09-22 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034350 | Erection , alignment , welding and inspection of Verticals,Mullions & Arches Cantilever | 14 | 2022-09-19 | 2022-10-04 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034360 | Dismantling of temporary steel - Tier 2 , Tier 1 | 15 | 2022-11-05 | 2022-11-21 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
Erection of Wing |  | 341 | 2021-12-05 | 2023-01-18
C-PW-034370 | Wing 2- Tier 1 A-Frames Pre-assembly | 18 | 2021-12-05 | 2021-12-25 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034380 | Lifting & Installation of Pre-assembled Wing 2 A-Frame | 6 | 2022-04-05 | 2022-04-11 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034390 | Wing 2- Tier 1 Erection (Front & Back) | 62 | 2022-04-12 | 2022-06-26 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034400 | Wing 2- Tier 2 Erection (Front & Back) | 62 | 2022-06-27 | 2022-09-11 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
C-PW-034410 | Installation of Wing Leaveout Steel Structure | 12 | 2023-01-05 | 2023-01-18 | 01 | 02 | 01 | 05 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01E | Wing | Civil SubZones
Architectural works |  | 117 | 2023-01-19 | 2023-06-06
Facade Works |  | 117 | 2023-01-19 | 2023-06-06
C-OW-034420 | Facade/ MEP/ BMU installation works for Wing 2 (Top Area - 5 levels) | 66 | 2023-01-19 | 2023-04-05 | 01 | 05 | 01 | 05 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Wing | Architectural SubZones
C-OW-034430 | Facade/ MEP/ BMU installation works for Wing 2 (Bottom Area - 5 levels) | 117 | 2023-01-19 | 2023-06-06 | 01 | 05 | 01 | 05 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01E | Wing | Architectural SubZones
Zone 1B - Drum 3 |  | 671 | 2021-05-06 | 2023-07-28
Civil Works |  | 495 | 2021-05-06 | 2022-12-27
White Concrete |  | 252 | 2021-05-06 | 2022-03-08
Drum Wall 3 |  | 105 | 2021-05-06 | 2021-09-13
C-PW-034440 | Initial Formwork Survey/Report | 9 | 2021-05-18 | 2021-05-27 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034450 | Survey/Identification of Available Rebar Stock | 28 | 2021-05-06 | 2021-06-10 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034460 | Decision Regarding Usability of Available Rebar Stock | 0 | 2021-06-12 |  | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034470 | Order and Delivery of New Rebar (If any) | 12 | 2021-06-12 | 2021-06-24 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034480 | Laydown Area Formwork/Bull-Nose QA/QC Insp., Joint Insp., Repairs, Clean. & Approval | 9 | 2021-06-21 | 2021-06-30 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034490 | Cleaning of All Rebar - Installed/Laydown Area | 18 | 2021-06-14 | 2021-07-04 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034500 | Installed Formwork QA/QC Insp., Joint Insp., Repairs, Clean. & Approval | 15 | 2021-06-21 | 2021-07-07 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034510 | Installation of Bull Nose | 12 | 2021-06-28 | 2021-07-11 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034520 | Reinforcement Installation | 18 | 2021-07-05 | 2021-07-28 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034530 | Formwork Shifting to place and Closing | 18 | 2021-07-15 | 2021-08-08 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034540 | Final Fromwork Survey/Report and Final Inspection | 4 | 2021-08-09 | 2021-08-14 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034550 | Casting of White Concrete - DW3 | 1 | 2021-08-15 | 2021-08-15 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034560 | Curing of Drum Wall 3 - Stage 3 | 7 | 2021-08-16 | 2021-08-23 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034570 | Deshutter Formwork Drum Wall 3 - Stage 3 | 12 | 2021-08-24 | 2021-09-06 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034580 | Installation of Protection for Drum Wall 3 - Stage 3 | 12 | 2021-08-31 | 2021-09-13 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
Ring Beam 3 |  | 153 | 2021-09-07 | 2022-03-08
C-PW-034590 | Extension of DOKA Scaffolding up to lvl +24.0 m | 12 | 2021-09-07 | 2021-09-20 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034600 | Site survey markings for Internal formwork installation | 4 | 2021-09-21 | 2021-09-25 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034610 | Reinstallation of Internal Ring beam formwork | 12 | 2021-09-26 | 2021-10-09 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034620 | Installation of Access Scaffolding for reinforcement | 12 | 2021-09-29 | 2021-10-12 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034630 | Installation of reinforcement - Stage 1 | 36 | 2021-10-03 | 2021-11-14 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034640 | Installation of Steel Embeds - Stage 1 | 6 | 2021-11-08 | 2021-11-14 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034650 | Work Inspection for reinforcement - Stage 1 | 6 | 2021-11-10 | 2021-11-16 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034660 | Site survey markings for External formwork installation | 12 | 2021-11-11 | 2021-11-24 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034670 | Reinstallation of External Ring beam formwork | 12 | 2021-11-11 | 2021-11-24 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034680 | Extend Access Scaffolding | 12 | 2021-11-13 | 2021-11-25 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034690 | Inserting MEP Conduits | 2 | 2021-11-27 | 2021-11-28 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034700 | QA/QC/Work Inspections - Stage 1 | 4 | 2021-11-27 | 2021-12-01 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034710 | Casting of White Concrete - Stage 1 | 1 | 2021-12-04 | 2021-12-04 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034720 | Installation of Plywood - Stage 2 | 12 | 2021-12-12 | 2021-12-25 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034730 | Installation of reinforcement - Stage 2 | 28 | 2021-12-19 | 2022-01-20 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034740 | Installation of Steel Embeds - Stage 2 | 6 | 2022-01-16 | 2022-01-22 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034750 | QA/QC/Work Inspections - Stage 2 | 1 | 2022-01-24 | 2022-01-24 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034760 | Casting of White Concrete - Stage 2 | 1 | 2022-01-25 | 2022-01-25 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034770 | Curing, Removal Formwork & Access for Honing | 18 | 2022-01-26 | 2022-02-15 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034780 | Preparation, Honing, and Protection - RB Vertical | 18 | 2022-02-06 | 2022-02-26 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034790 | Remove Scaffolding and Doka Shoring | 18 | 2022-02-16 | 2022-03-08 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
Grey Concrete |  | 86 | 2022-09-17 | 2022-12-27
C-PW-034800 | Composite slab SSL +19.95 | 21 | 2022-09-17 | 2022-10-11 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034810 | Ground Level Slab (leave out area) | 14 | 2022-10-08 | 2022-10-24 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034820 | Construction of Verticals to Raised Floor Slab | 14 | 2022-10-25 | 2022-11-09 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034830 | Stairs to POD | 26 | 2022-10-12 | 2022-11-10 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034840 | Filling of EPS Void Former | 14 | 2022-11-10 | 2022-11-26 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
C-PW-034850 | Construction of Raised Floor Slab | 26 | 2022-11-27 | 2022-12-27 | 01 | 01 | 01 | 02 | 009 | 30 |  | Building | Civil | Museum | Zone 01B | Drum / Ring Beam | Civil SubZones
Architectural |  | 132 | 2022-12-28 | 2023-06-29
C-MS-G-FN-MLB-36635 | Void Former & Floor Screed Works | 12 | 2022-12-28 | 2023-01-12 | 01 | 04 | 01 | 02 | 009 | 50 |  | Building | Architecture | Museum | Zone 01B | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36640 | Wall Finishes (in-situ White Conc Finish) | 24 | 2023-02-10 | 2023-03-15 | 01 | 04 | 01 | 02 | 009 | 50 |  | Building | Architecture | Museum | Zone 01B | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36645 | Floor Finishes (Polished Conc floor finish) | 14 | 2023-03-16 | 2023-04-04 | 01 | 04 | 01 | 02 | 009 | 50 |  | Building | Architecture | Museum | Zone 01B | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36650 | Specialist Fixtures (Precast Panels) | 28 | 2023-04-05 | 2023-05-12 | 01 | 04 | 01 | 02 | 009 | 50 |  | Building | Architecture | Museum | Zone 01B | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36655 | Fitout Works | 12 | 2023-05-15 | 2023-05-30 | 01 | 04 | 01 | 02 | 009 | 50 |  | Building | Architecture | Museum | Zone 01B | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36660 | Installation of Signage | 10 | 2023-06-06 | 2023-06-19 | 01 | 04 | 01 | 02 | 009 | 50 |  | Building | Architecture | Museum | Zone 01B | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36665 | Final Finishes & Fittings | 8 | 2023-06-20 | 2023-06-29 | 01 | 04 | 01 | 02 | 009 | 50 |  | Building | Architecture | Museum | Zone 01B | Drum / Ring Beam | Architectural SubZones
MEP |  | 102 | 2023-01-13 | 2023-06-05
C-MS-G-MP-46525 | Wall & Floor MEP works 1st & 2nd Fix | 20 | 2023-01-13 | 2023-02-09 | 01 | 14 | 01 | 02 | 009 | 70 |  | Building | General MEP | Museum | Zone 01B | Drum / Ring Beam | MEP SubZones
C-MS-G-MP-46530 | Final Fix MEP works | 10 | 2023-05-23 | 2023-06-05 | 01 | 14 | 01 | 02 | 009 | 70 |  | Building | General MEP | Museum | Zone 01B | Drum / Ring Beam | MEP SubZones
Close Out Works |  | 39 | 2023-06-06 | 2023-07-28
C-MS-W-CL-W3-69535 | Testing & Commissioning Works | 15 | 2023-06-06 | 2023-06-26 | 01 | 14 | 01 | 02 | 009 | 70 |  | Building | General MEP | Museum | Zone 01B | Drum / Ring Beam | MEP SubZones
C-MS-W-CL-W3-69540 | Snagging & De-snagging Works - Wing 3 | 21 | 2023-06-30 | 2023-07-28 | 01 | 04 | 01 | 02 | 009 | 50 |  | Building | Architecture | Museum | Zone 01B | Drum / Ring Beam | Architectural SubZones
Zone 1B - Wing 3 |  | 464 | 2021-11-20 | 2023-05-31
Civil works |  | 278 | 2021-11-20 | 2022-10-22
Steel Structure |  | 278 | 2021-11-20 | 2022-10-22
Temporary Access / Steel Support |  | 266 | 2021-11-20 | 2022-10-06
C-PW-034920 | Temporary Steel Platform - Tier - 1 - Pre-assembly | 18 | 2021-11-20 | 2021-12-12 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-034930 | Lifting and Installation of Preassembled Temporary Steel Platform - Tier - 1 | 3 | 2022-02-02 | 2022-02-05 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-034940 | Erection of Temporary Steel for Tier - 2 | 17 | 2022-03-29 | 2022-04-17 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-034950 | Erection of Temporary Steel for Tier - 3 | 17 | 2022-06-16 | 2022-07-05 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-034960 | Erection of Temporary Steel for Cantilever | 4 | 2022-09-10 | 2022-09-13 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-034970 | Dismantling of temporary steel - bracing | 4 | 2022-09-10 | 2022-09-13 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-034980 | De-Propping of Permanent steel | 2 | 2022-09-14 | 2022-09-15 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-034990 | Erection , alignment , welding and inspection of Verticals,Mullions & Arches Cantilever | 14 | 2022-09-17 | 2022-10-02 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-035000 | Dismantling of temporary steel - Tier 3 ,Tier 2 & Tier 1 | 18 | 2022-09-17 | 2022-10-06 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-035010 | Dismantling of Temporary Steel for Cantilever | 4 | 2022-10-03 | 2022-10-06 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
Erection of Wing |  | 267 | 2021-12-05 | 2022-10-22
C-PW-035020 | Wing 3- Tier 1 A-Frames Pre-assembly | 18 | 2021-12-05 | 2021-12-25 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-035030 | Lifting & Installation of Pre-assembled Wing 3 A-Frame | 6 | 2022-01-30 | 2022-02-05 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-035040 | Wing 3- Tier 1 Erection (Front & Back) | 61 | 2022-02-06 | 2022-04-17 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-035050 | Wing 3- Tier 2 Erection (Front & Back) | 61 | 2022-04-18 | 2022-06-30 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-035060 | Wing 3- Tier 3 Erection (Front & Back) | 52 | 2022-07-06 | 2022-09-08 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
C-PW-035070 | Installation of Wing Leaveout Steel Structure | 12 | 2022-10-08 | 2022-10-22 | 01 | 02 | 01 | 02 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01B | Wing | Civil SubZones
Architectural works |  | 186 | 2022-10-23 | 2023-05-31
Facade Works |  | 186 | 2022-10-23 | 2023-05-31
C-OW-035080 | Facade/ MEP/ BMU installation works for Wing 3 (Middle Area - 6 levels) | 105 | 2022-10-23 | 2023-02-23 | 01 | 05 | 01 | 02 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01B | Wing | Architectural SubZones
C-OW-035090 | Facade/ MEP/ BMU installation works for Wing 3 (Bottom Area - 6 levels) | 128 | 2022-10-23 | 2023-03-22 | 01 | 05 | 01 | 02 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01B | Wing | Architectural SubZones
C-OW-035100 | Facade/ MEP/ BMU installation works for Wing 3 (Top Area - 7 levels) | 118 | 2023-01-12 | 2023-05-31 | 01 | 05 | 01 | 02 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01B | Wing | Architectural SubZones
Zone 1C - Drum 4 |  | 596 | 2021-05-06 | 2023-04-28
Civil Works |  | 439 | 2021-05-06 | 2022-10-22
White Concrete |  | 180 | 2021-05-06 | 2021-12-13
Ring Beam 4 |  | 180 | 2021-05-06 | 2021-12-13
C-PW-035110 | Survey/Identification of Available Rebar Stock | 17 | 2021-05-06 | 2021-05-29 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035120 | Descision Regarding Usability of Available Rebar Stock | 0 | 2021-05-30 |  | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035130 | Preparation of Available Rebar / Order of New Rebar | 18 | 2021-05-30 | 2021-06-19 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035140 | Formwork QA/QC Insp., Joint Insp., Repairs Clean. & Approval - External (Laydown Area) | 18 | 2021-06-15 | 2021-07-05 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035150 | Cleaning of Reinforcement - Stage 1 | 24 | 2021-06-15 | 2021-07-12 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035160 | Formwork QA/QC Insp., Joint Insp., Repairs Clean. & Approval - Internal | 24 | 2021-06-29 | 2021-07-29 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035170 | Installation of Steel Embeds - Stage 1 | 6 | 2021-08-07 | 2021-08-14 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035180 | Installation of Reinforcement - Stage 1 | 38 | 2021-06-27 | 2021-08-14 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035190 | Work Inspection for reinforcement - Stage 1 | 6 | 2021-08-09 | 2021-08-16 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035200 | Site survey markings for External formwork installation | 12 | 2021-08-12 | 2021-08-25 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035210 | Installation of External Ring beam formwork | 12 | 2021-08-12 | 2021-08-25 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035220 | Extend Access Scaffolding | 12 | 2021-08-14 | 2021-08-26 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035230 | Inserting MEP Conduits | 2 | 2021-08-28 | 2021-08-29 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035240 | QA/QC/Work Inspections - Stage 1 | 4 | 2021-08-28 | 2021-08-31 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035250 | Casting of White Concrete - Stage 1 | 1 | 2021-09-01 | 2021-09-01 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035260 | Installation of Plywood - Stage 2 | 12 | 2021-09-09 | 2021-09-22 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035270 | Installation of Reinforcement - Stage 2 | 33 | 2021-09-16 | 2021-10-25 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035280 | Installation of Structural Steel Embed. | 6 | 2021-10-19 | 2021-10-26 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035290 | QA/QC/Work Inspections - Stage 2 | 4 | 2021-10-25 | 2021-10-28 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035300 | Casting of White Concrete - Stage 2 | 1 | 2021-10-30 | 2021-10-30 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035310 | Curing, Removal Formwork & Access for Honing | 18 | 2021-10-31 | 2021-11-20 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035320 | Preparation, Honing, and Protection - RB Vertical | 18 | 2021-11-10 | 2021-12-01 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035330 | Remove Scaffolding and Doka Shoring | 18 | 2021-11-21 | 2021-12-13 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
Grey Concrete |  | 47 | 2022-08-28 | 2022-10-22
C-PW-035340 | Ground Level Slab (leave out area) | 12 | 2022-08-28 | 2022-09-10 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035350 | Construction of Verticals to Raised Floor Slab | 8 | 2022-09-11 | 2022-09-19 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035360 | Composite slab SSL +19.95 | 21 | 2022-08-28 | 2022-09-20 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035370 | Filling of EPS Void Former | 6 | 2022-09-20 | 2022-09-26 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035380 | Composite slab SSL +19.95 (Leaveout) | 6 | 2022-09-21 | 2022-09-27 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035390 | Construction of Raised Floor Slab | 15 | 2022-09-27 | 2022-10-15 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
C-PW-035400 | Stairs to POD | 26 | 2022-09-21 | 2022-10-22 | 01 | 01 | 01 | 03 | 009 | 30 |  | Building | Civil | Museum | Zone 01C | Drum / Ring Beam | Civil SubZones
Architectural |  | 140 | 2022-10-17 | 2023-04-28
C-MS-G-FN-MLB-36680 | Void Former & Floor Screed Works | 12 | 2022-10-17 | 2022-11-01 | 01 | 04 | 01 | 03 | 009 | 50 |  | Building | Architecture | Museum | Zone 01C | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36690 | Specialist Fixtures (Framing for Precast Panels/Seating arrangements) | 21 | 2022-11-02 | 2022-11-30 | 01 | 04 | 01 | 03 | 009 | 50 |  | Building | Architecture | Museum | Zone 01C | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36685 | Wall Finishes (in-situ White Conc Finish) | 24 | 2022-11-24 | 2022-12-27 | 01 | 04 | 01 | 03 | 009 | 50 |  | Building | Architecture | Museum | Zone 01C | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36695 | Floor Finishes (Polished Conc floor finish) | 14 | 2022-12-28 | 2023-01-16 | 01 | 04 | 01 | 03 | 009 | 50 |  | Building | Architecture | Museum | Zone 01C | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36705 | Balustrades and Handrails | 6 | 2023-01-17 | 2023-01-24 | 01 | 04 | 01 | 03 | 009 | 50 |  | Building | Architecture | Museum | Zone 01C | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36700 | Specialist Fixtures (Precast Panels/Precast Mould elements) | 28 | 2023-01-17 | 2023-02-23 | 01 | 04 | 01 | 03 | 009 | 50 |  | Building | Architecture | Museum | Zone 01C | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36710 | Fitout & Step Finishes | 28 | 2023-02-24 | 2023-04-04 | 01 | 04 | 01 | 03 | 009 | 50 |  | Building | Architecture | Museum | Zone 01C | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36715 | Installation of Signage | 10 | 2023-04-05 | 2023-04-18 | 01 | 04 | 01 | 03 | 009 | 50 |  | Building | Architecture | Museum | Zone 01C | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36720 | Final Finishes & Fittings | 8 | 2023-04-19 | 2023-04-28 | 01 | 04 | 01 | 03 | 009 | 50 |  | Building | Architecture | Museum | Zone 01C | Drum / Ring Beam | Architectural SubZones
MEP |  | 98 | 2022-11-02 | 2023-03-17
C-MS-G-MP-46540 | Wall & Floor MEP works 1st & 2nd Fix | 20 | 2022-11-02 | 2022-11-29 | 01 | 14 | 01 | 03 | 009 | 70 |  | Building | General MEP | Museum | Zone 01C | Drum / Ring Beam | MEP SubZones
C-MS-G-MP-46545 | Final Fix MEP works | 10 | 2023-03-06 | 2023-03-17 | 01 | 14 | 01 | 03 | 009 | 70 |  | Building | General MEP | Museum | Zone 01C | Drum / Ring Beam | MEP SubZones
Zone 1C - POD 4 |  | 564 | 2021-06-08 | 2023-04-17
Civil works |  | 402 | 2021-06-08 | 2022-10-06
Steel Structure |  | 402 | 2021-06-08 | 2022-10-06
Temporary Access / Steel Support |  | 155 | 2021-06-08 | 2021-12-13
C-PW-035480 | Erection of Temporary Steel - Preassembly Area | 22 | 2021-06-08 | 2021-07-03 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
C-PW-035490 | Installation of temporary towers / Struts / to support wing & POD - Stage 02 | 20 | 2021-07-04 | 2021-07-29 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
C-PW-035500 | De-Propping and dismantling of temporary towers | 6 | 2021-10-11 | 2021-10-17 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
C-PW-035510 | Erection of Temporary Steel - Stage 01 within Drum | 9 | 2021-12-04 | 2021-12-13 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
Erection of POD |  | 357 | 2021-07-04 | 2022-09-10
C-PW-035520 | POD 4 - Stage 01 assembly | 55 | 2021-07-04 | 2021-09-09 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
C-PW-035530 | POD 4 - Stage 02 assembly | 32 | 2021-09-11 | 2021-10-17 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
C-PW-035540 | Inspection works at Ring beam for POD erection | 6 | 2021-12-07 | 2021-12-13 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
C-PW-035550 | Lifting & Installation of Pre-assembled POD 4 steel frame | 12 | 2021-12-14 | 2021-12-27 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
C-PW-035560 | Installation of POD Leaveout Steel Structure | 12 | 2022-08-28 | 2022-09-10 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
Fire Proofing of POD |  | 53 | 2022-08-06 | 2022-10-06
C-PW-035570 | Fire Proofing works on POD Steel Structure (Except Leave out area) | 37 | 2022-08-06 | 2022-09-18 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
C-PW-035580 | Fire Proofing works on POD Steel Structure for Leave out area | 8 | 2022-09-28 | 2022-10-06 | 01 | 01 | 01 | 03 | 010 | 30 |  | Building | Civil | Museum | Zone 01C | Pod | Civil SubZones
Cladding Works |  | 222 | 2022-03-19 | 2022-12-12
C-PW-035590 | Install access Platform at ring beam level & Inclined MonoRails | 18 | 2022-03-19 | 2022-04-07 | 01 | 05 | 01 | 03 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Pod | Architectural SubZones
C-PW-035600 | Install POD Facade Phase 1 (Belly & mid panels) | 38 | 2022-04-09 | 2022-05-25 | 01 | 05 | 01 | 03 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Pod | Architectural SubZones
C-PW-035620 | Install POD Facade Phase 2 (Belly & mid panels) | 23 | 2022-05-26 | 2022-06-21 | 01 | 05 | 01 | 03 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Pod | Architectural SubZones
C-PW-035630 | Remove Access Platform at ring beam level & Inclined Monorails | 12 | 2022-06-22 | 2022-07-05 | 01 | 05 | 01 | 03 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Pod | Architectural SubZones
C-PW-035610 | Install POD Facade Phase 3 (Soffit) | 79 | 2022-04-27 | 2022-08-06 | 01 | 05 | 01 | 03 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Pod | Architectural SubZones
C-PW-035640 | Install POD Facade Phase 4 (Upper panels) | 13 | 2022-09-11 | 2022-09-25 | 01 | 05 | 01 | 03 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Pod | Architectural SubZones
C-PW-035650 | Install POD Skylight - Phase 1 | 18 | 2022-09-11 | 2022-10-01 | 01 | 05 | 01 | 03 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Pod | Architectural SubZones
C-PW-035660 | Install POD Facade Phase 5 (Leaveouts) | 39 | 2022-09-26 | 2022-11-10 | 01 | 05 | 01 | 03 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Pod | Architectural SubZones
C-PW-035670 | Install POD BMU | 18 | 2022-11-12 | 2022-12-03 | 01 | 05 | 01 | 03 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Pod | Architectural SubZones
C-PW-035680 | Install POD Skylight - Phase 2 (including metal works and cladding) | 60 | 2022-10-02 | 2022-12-12 | 01 | 05 | 01 | 03 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Pod | Architectural SubZones
Architectural |  | 59 | 2022-11-30 | 2023-02-20
FLOOR |  | 23 | 2023-01-19 | 2023-02-20
C-MS-P-FN-P4-70815 | Secondary Steel / Metal Decking / Screed | 7 | 2023-01-19 | 2023-01-27 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-70825 | Void Former | 6 | 2023-01-30 | 2023-02-06 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-70830 | Polished concrete Floor | 5 | 2023-02-07 | 2023-02-13 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-70835 | Bronze Grill/Skirting | 5 | 2023-02-14 | 2023-02-20 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
WALLS |  | 52 | 2022-11-30 | 2023-02-09
STAGE 1 (BELLY) |  | 40 | 2022-12-16 | 2023-02-09
Pod Internal |  | 40 | 2022-12-16 | 2023-02-09
C-MS-P-FN-P4-70965 | Secondary Steel A - wall void | 7 | 2022-12-16 | 2022-12-26 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-70970 | Ladders A including Platforms etc - wall void | 5 | 2022-12-27 | 2023-01-02 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-70935 | Secondary Steel A | 9 | 2022-12-26 | 2023-01-05 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-70945 | Pod Internal Cladding | 18 | 2023-01-17 | 2023-02-09 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
STAGE 2 (MID) |  | 30 | 2022-12-08 | 2023-01-18
Pod Internal |  | 30 | 2022-12-08 | 2023-01-18
C-MS-P-FN-P4-71045 | Secondary Steel B - wall void | 6 | 2022-12-08 | 2022-12-15 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-71050 | Ladders B including Platforms etc - wall void | 5 | 2022-12-16 | 2022-12-22 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-71015 | Secondary Steel B | 7 | 2022-12-15 | 2022-12-23 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-71025 | Pod Internal Cladding | 18 | 2022-12-26 | 2023-01-18 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
STAGE 3 (UPPER) |  | 46 | 2022-11-30 | 2023-02-01
Pod Internal |  | 46 | 2022-11-30 | 2023-02-01
C-MS-P-FN-P4-71130 | Secondary Steel C - wall void | 6 | 2022-11-30 | 2022-12-07 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-71095 | Secondary Steel C | 6 | 2022-12-07 | 2022-12-14 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-71135 | Ladders C including Platforms etc - wall void | 5 | 2022-12-08 | 2022-12-14 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-71105 | Pod Internal Cladding | 18 | 2022-12-15 | 2023-01-09 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-71120 | Internal Finishes in leave out areas | 17 | 2023-01-10 | 2023-02-01 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
STAGE 4(SOFFIT) |  | 12 | 2022-12-27 | 2023-01-11
WALL VOID |  | 12 | 2022-12-27 | 2023-01-11
C-MS-P-FN-P4-70885 | Secondary Steel D | 7 | 2022-12-27 | 2023-01-04 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
C-MS-P-FN-P4-70890 | Ladders D including Platforms etc | 5 | 2023-01-05 | 2023-01-11 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
MEP |  | 117 | 2022-09-19 | 2023-02-28
C-MS-P-MP-MA-73480 | MEP Access for POD Soffit Structure ( New Activity ) | 0 | 2022-09-19 |  | 01 | 14 | 01 | 03 | 010 | 70 |  | Building | General MEP | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-MA-73490 | MEP Access for Phase 2 (BELLY) ( New Activity ) | 0 | 2022-09-19 |  | 01 | 14 | 01 | 03 | 010 | 70 |  | Building | General MEP | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-MA-73510 | MEP Access for Phase 1 (MID & UPPER) ( New Activity ) | 0 | 2022-09-19 |  | 01 | 14 | 01 | 03 | 010 | 70 |  | Building | General MEP | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-MA-73500 | MEP Access for Finishes ( New Activity ) | 0 | 2023-02-10 |  | 01 | 14 | 01 | 03 | 010 | 70 |  | Building | General MEP | Museum | Zone 01C | Pod | MEP SubZones
MECHANICAL |  | 114 | 2022-09-19 | 2023-02-23
HVAC SYSTEM WORKS |  | 114 | 2022-09-19 | 2023-02-23
C-MS-P-MP-AC-71210 | 1st & 2nd Fix HVAC (Supports, Ducts & Insulation at Stage 1 Steel Frame) | 21 | 2022-09-19 | 2022-10-17 | 01 | 06 | 01 | 03 | 010 | 70 |  | Building | HVAC | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-AC-71205 | 1st Fix HVAC (Supports, Ducts & Insulation at Bottom Steel Trusses) | 26 | 2022-09-19 | 2022-10-24 | 01 | 06 | 01 | 03 | 010 | 70 |  | Building | HVAC | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-AC-71220 | Completion of Bottom Ducting & insulation after removal of Temp. tower | 14 | 2022-10-25 | 2022-11-11 | 01 | 06 | 01 | 03 | 010 | 70 |  | Building | HVAC | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-AC-71215 | 1st & 2nd Fix HVAC (Supports, Ducts & Insulation at Stage 2 Steel Frame) | 21 | 2022-10-25 | 2022-11-22 | 01 | 06 | 01 | 03 | 010 | 70 |  | Building | HVAC | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-AC-71225 | Final Fix HVAC (Grills, Diffusers) | 10 | 2023-02-10 | 2023-02-23 | 01 | 06 | 01 | 03 | 010 | 70 |  | Building | HVAC | Museum | Zone 01C | Pod | MEP SubZones
ELECTRICAL WORKS |  | 114 | 2022-09-19 | 2023-02-23
C-MS-P-MP-EL-71235 | 1st Fix Electrical (Conduiting & Boxes at Bottom Steel Trusses) | 12 | 2022-09-19 | 2022-10-04 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-73625 | 1st Fix Electrical (Conduiting & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-19 | 2022-10-04 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-73605 | 1st Fix Electrical (Supports and Cable trays at Stage 1 Steel Structure) | 18 | 2022-09-19 | 2022-10-12 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-71240 | 1st Fix Electrical (Supports and Cable trays at Bottom Steel Trusses) | 24 | 2022-09-19 | 2022-10-20 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-73635 | 1st Fix Electrical (Conduiting & Boxes at Stage 2 Steel Structure) | 12 | 2022-10-13 | 2022-10-28 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-73615 | 1st Fix Electrical (Supports and Cable trays at Stage 2 Steel Structure) | 18 | 2022-10-13 | 2022-11-07 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-71245 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-11-08 | 2022-12-01 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-71265 | 2nd Fix Electrical (Installation of Lighting Control Panels) | 6 | 2022-12-02 | 2022-12-09 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-71250 | Cable/Wire Termination & Dressing | 10 | 2022-12-12 | 2022-12-23 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-73895 | Final Fix Electrical (Light Fixtures-Strip Light below Sky light) | 4 | 2022-12-26 | 2022-12-29 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-71255 | Final Fix Electrical (Power Sockets/ Isolators) | 10 | 2023-02-10 | 2023-02-23 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-71260 | Final Fix Electrical (Light Fixtures) | 10 | 2023-02-10 | 2023-02-23 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-EL-71270 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2023-02-10 | 2023-02-23 | 01 | 07 | 01 | 03 | 010 | 70 |  | Building | Electrical | Museum | Zone 01C | Pod | MEP SubZones
ELV |  | 112 | 2022-09-19 | 2023-02-21
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 108 | 2022-09-19 | 2023-02-15
C-MS-P-MP-ELV-71285 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-19 | 2022-10-04 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71290 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 12 | 2022-10-05 | 2022-10-20 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71295 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 4 | 2023-02-10 | 2023-02-15 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
INTRUDER & HOLD-UPS ALARMS |  | 108 | 2022-09-19 | 2023-02-15
C-MS-P-MP-ELV-71305 | 1st Fix Intruder & Hold-Ups Alarms (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-19 | 2022-10-04 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-74110 | 1st Fix Intruder & Hold-Ups Alarms (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-09-19 | 2022-10-04 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71310 | 2nd Fix Intruder & Hold-Ups Alarms Works (Cable Wiring) | 12 | 2022-10-05 | 2022-10-20 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71315 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 4 | 2023-02-10 | 2023-02-15 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
VIDEO SURVEILLANCE SYSTEM |  | 108 | 2022-09-19 | 2023-02-15
C-MS-P-MP-ELV-71365 | 1st Fix Video Surveillance System Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-19 | 2022-10-04 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-74120 | 1st Fix Video Surveillance System Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-09-19 | 2022-10-04 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71370 | 2nd Fix Video Surveillance System Works (Cable Wiring) | 12 | 2022-10-05 | 2022-10-20 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71375 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 4 | 2023-02-10 | 2023-02-15 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
DATA AND TELECOMMUNICATION |  | 108 | 2022-09-19 | 2023-02-15
C-MS-P-MP-ELV-71385 | 1st Fix Data & Telecommunication Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-19 | 2022-10-04 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-74130 | 1st Fix Data & Telecommunication Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-10-05 | 2022-10-20 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71390 | 2nd Fix Data & Telecommunication Works (Cables Wiring) | 12 | 2022-10-21 | 2022-11-07 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71395 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 4 | 2023-02-10 | 2023-02-15 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
BMS AND AUTOMATIC CONTROLS |  | 108 | 2022-09-19 | 2023-02-15
C-MS-P-MP-ELV-71405 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-19 | 2022-10-04 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-74140 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-10-05 | 2022-10-20 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71410 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 12 | 2022-10-21 | 2022-11-07 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71415 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 4 | 2023-02-10 | 2023-02-15 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
EMERGENCY LIGHTING |  | 108 | 2022-09-19 | 2023-02-15
C-MS-P-MP-ELV-71455 | 1st Fix Emergency Lighting (Conduits & Boxes at Stage 1 Steel Structure | 12 | 2022-09-19 | 2022-10-04 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-74150 | 1st Fix Emergency Lighting (Conduits & Boxes at Stage 2 Steel Structure | 12 | 2022-10-05 | 2022-10-20 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71460 | 2nd Fix Emergency Lighting (Cable & Wiring) | 12 | 2022-10-21 | 2022-11-07 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71465 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 4 | 2023-02-10 | 2023-02-15 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
FIRE ALARM & PUBLIC ADDRESS |  | 112 | 2022-09-19 | 2023-02-21
C-MS-P-MP-ELV-71475 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes)along Bottom Steel Trusses | 12 | 2022-09-19 | 2022-10-04 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-74160 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes at Stage 1 Steel Structure | 12 | 2022-10-05 | 2022-10-20 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-74170 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes at Stage 2 Steel Structure | 12 | 2022-10-21 | 2022-11-07 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71480 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 12 | 2022-11-08 | 2022-11-23 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-ELV-71485 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 4 | 2023-02-16 | 2023-02-21 | 01 | 10 | 01 | 03 | 010 | 70 |  | Building | CCTV | Museum | Zone 01C | Pod | MEP SubZones
LIFE AND SAFETY SYSTEMS |  | 117 | 2022-09-19 | 2023-02-28
FIRE FIGHTING WORKS |  | 117 | 2022-09-19 | 2023-02-28
C-MS-P-MP-FF-71500 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Bottom Steel Trusses | 18 | 2022-09-19 | 2022-10-12 | 01 | 09 | 01 | 03 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-FF-73705 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Stage 1 Steel Structure) | 18 | 2022-10-05 | 2022-10-28 | 01 | 09 | 01 | 03 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-FF-73855 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Bottom Steel Trusses 2nd Layer | 18 | 2022-10-25 | 2022-11-17 | 01 | 09 | 01 | 03 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-FF-73725 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Stage 2 Steel Structure) | 18 | 2022-10-31 | 2022-11-23 | 01 | 09 | 01 | 03 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-FF-71505 | Fire fighting Pipes Pressure Testing | 3 | 2022-11-24 | 2022-11-28 | 01 | 09 | 01 | 03 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-FF-73895 | Final Fix Piping System (Sprinkler Heads below Sky Light) | 4 | 2022-12-13 | 2022-12-16 | 01 | 09 | 01 | 03 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01C | Pod | MEP SubZones
C-MS-P-MP-FF-71510 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 10 | 2023-02-15 | 2023-02-28 | 01 | 09 | 01 | 03 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01C | Pod | MEP SubZones
Close Out Works |  | 34 | 2023-03-01 | 2023-04-17
C-MS-W-CL-W4-71665 | Testing & Commissioning Works - Wing 4 & Pod 4 | 20 | 2023-03-01 | 2023-03-28 | 01 | 14 | 01 | 03 | 010 | 70 |  | Building | General MEP | Museum | Zone 01C | Pod | MEP SubZones
C-MS-W-CL-W4-71670 | Snagging & De-snagging Works - Wing 4 & Pod 4 | 28 | 2023-03-09 | 2023-04-17 | 01 | 04 | 01 | 03 | 010 | 50 |  | Building | Architecture | Museum | Zone 01C | Pod | Architectural SubZones
Zone 1C - Wing 4 |  | 502 | 2021-10-07 | 2023-06-03
Civil works |  | 343 | 2021-10-07 | 2022-11-24
Steel Structure |  | 343 | 2021-10-07 | 2022-11-24
Temporary Access / Steel Support |  | 253 | 2021-10-28 | 2022-08-30
C-PW-035750 | Temporary Steel Platform - Tier - 1 - Pre-assembly | 18 | 2021-10-28 | 2021-11-17 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035760 | Lifting and Installation of Preassembled Temporary Steel Platform - Tier - 1 | 3 | 2021-12-25 | 2021-12-27 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035770 | Erection of Temporary Steel for Tier - 2 | 17 | 2022-02-13 | 2022-03-03 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035780 | Erection of Temporary Steel for Tier - 3 | 16 | 2022-05-05 | 2022-05-23 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035790 | Erection of Temporary Steel for Cantilever | 4 | 2022-07-23 | 2022-07-26 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035800 | Dismantling of temporary Steel - bracing | 10 | 2022-07-23 | 2022-08-03 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035810 | De-Propping of Permanent steel | 2 | 2022-08-04 | 2022-08-06 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035820 | Erection , alignment , welding and inspection of Verticals,Mullions & Arches Cantilever | 17 | 2022-08-07 | 2022-08-25 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035830 | Dismantling of temporary steel - Tier 3,Tier 2 & Tier 1 | 18 | 2022-08-07 | 2022-08-27 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035840 | Dismantling of Temporary Steel for Cantilever | 4 | 2022-08-27 | 2022-08-30 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
Erection of Wing |  | 343 | 2021-10-07 | 2022-11-24
C-PW-035850 | Wing 4- Tier 1 A-Frames Pre-assembly | 18 | 2021-10-07 | 2021-10-28 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035860 | Lifting & Installation of Pre-assembled Wing 4 A-Frame | 6 | 2021-12-21 | 2021-12-27 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035870 | Wing 4- Tier 1 Erection (Front & Back) | 56 | 2021-12-28 | 2022-03-03 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035880 | Wing 4- Tier 2 Erection (Front & Back) | 62 | 2022-03-05 | 2022-05-18 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035890 | Wing 4- Tier 3 Erection (Front & Back) | 48 | 2022-05-24 | 2022-07-21 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035900 | Installation of Wing Leaveout Steel Structure - Tier 2 | 12 | 2022-10-03 | 2022-10-17 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
C-PW-035910 | Installation of Wing Leaveout Steel Structure - Tier 3 | 12 | 2022-11-12 | 2022-11-24 | 01 | 02 | 01 | 03 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01C | Wing | Civil SubZones
Architectural works |  | 192 | 2022-10-18 | 2023-06-03
Facade Works |  | 192 | 2022-10-18 | 2023-06-03
C-OW-035920 | Facade/ MEP/ BMU installation works for Wing 4 (Middle Area - 7 levels) | 124 | 2022-10-18 | 2023-03-13 | 01 | 05 | 01 | 03 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Wing | Architectural SubZones
C-OW-035930 | Facade/ MEP/ BMU installation works for Wing 4 (Bottom Area - 6 levels) | 162 | 2022-10-18 | 2023-04-29 | 01 | 05 | 01 | 03 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Wing | Architectural SubZones
C-OW-035940 | Facade/ MEP/ BMU installation works for Wing 4 (Top Area - 7 levels) | 126 | 2023-01-05 | 2023-06-03 | 01 | 05 | 01 | 03 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01C | Wing | Architectural SubZones
Zone 1A - Drum 5 |  | 572 | 2021-05-06 | 2023-03-28
Civil Works |  | 412 | 2021-05-06 | 2022-09-19
White Concrete |  | 151 | 2021-05-06 | 2021-11-07
Ring Beam 5 |  | 151 | 2021-05-06 | 2021-11-07
POD Support/Heavy Reinforcement Areas |  | 40 | 2021-05-20 | 2021-07-05
C-PW-035950 | Reinforcement Shifting/Removal/Cleaning | 18 | 2021-05-20 | 2021-06-09 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-035960 | Formwork QA/QC Insp., Joint Insp., Repairs Clean. & Approval | 12 | 2021-06-03 | 2021-06-16 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-035970 | Reinforcement Reshifting/Installation/Approval and Access Control -RB5 | 24 | 2021-06-08 | 2021-07-05 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-035980 | MEP and Other Embedments (If any) | 15 | 2021-06-19 | 2021-07-05 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
Other Areas |  | 39 | 2021-05-20 | 2021-07-04
C-PW-035990 | Reinforcement Shifting/Removal/Cleaning | 18 | 2021-05-20 | 2021-06-09 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036000 | Formwork QA/QC Insp., Joint Insp., Repairs Clean. & Approval | 18 | 2021-06-03 | 2021-06-23 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036010 | Reinforcement Reshifting/Installation/Approval and Access Control -RB5 | 18 | 2021-06-14 | 2021-07-04 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
General |  | 151 | 2021-05-06 | 2021-11-07
C-PW-036020 | Initial Formwork Survey/Report - Stage 1 | 4 | 2021-05-06 | 2021-05-10 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036030 | Final Fromwork Survey/Report and Final Inspection - Stage 1 | 3 | 2021-07-06 | 2021-07-08 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036040 | Casting of White Concrete - Stage 1 | 1 | 2021-07-10 | 2021-07-10 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036050 | Installation of Plywood - Stage 2 | 12 | 2021-07-18 | 2021-08-03 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036060 | Installation of Reinforcement - Stage 2 | 44 | 2021-07-28 | 2021-09-18 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036070 | Installation of Structural Steel Embed. | 7 | 2021-09-09 | 2021-09-18 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036080 | QA/QC/Work Inspections - Stage 2 | 5 | 2021-09-19 | 2021-09-23 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036090 | Casting of White Concrete - Stage 2 | 1 | 2021-09-25 | 2021-09-25 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036100 | Curing, Removal Formwork & Access for Honing | 18 | 2021-09-26 | 2021-10-16 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036110 | Preparation, Honing, and Protection - RB Vertical | 18 | 2021-10-06 | 2021-10-27 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036120 | Remove Scaffolding and Doka Shoring | 18 | 2021-10-17 | 2021-11-07 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
Grey Concrete |  | 48 | 2022-07-24 | 2022-09-19
C-PW-036150 | Ground Level Slab (leave out area) | 12 | 2022-08-03 | 2022-08-16 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036130 | Composite slab SSL +19.95 | 21 | 2022-07-24 | 2022-08-18 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036140 | Composite slab SSL +19.95 (Leaveout) | 6 | 2022-08-18 | 2022-08-25 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036160 | Construction of Verticals to Raised Floor Slab | 8 | 2022-08-17 | 2022-08-25 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036170 | Filling of EPS Void Former | 6 | 2022-08-27 | 2022-09-01 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036180 | Stairs to POD | 26 | 2022-08-18 | 2022-09-18 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
C-PW-036190 | Construction of Raised Floor Slab | 15 | 2022-09-03 | 2022-09-19 | 01 | 01 | 01 | 01 | 009 | 30 |  | Building | Civil | Museum | Zone 01A | Drum / Ring Beam | Civil SubZones
Architectural |  | 136 | 2022-09-20 | 2023-03-28
C-MS-G-FN-MLB-36735 | Void Former & Floor Screed Works | 12 | 2022-09-20 | 2022-10-05 | 01 | 04 | 01 | 01 | 009 | 50 |  | Building | Architecture | Museum | Zone 01A | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36740 | Specialist Fixtures (Framing for Precast Panels/Seating arrangements) | 28 | 2022-10-06 | 2022-11-14 | 01 | 04 | 01 | 01 | 009 | 50 |  | Building | Architecture | Museum | Zone 01A | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36745 | Wall Finishes (in-situ White Conc Finish) | 24 | 2022-10-28 | 2022-11-30 | 01 | 04 | 01 | 01 | 009 | 50 |  | Building | Architecture | Museum | Zone 01A | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36750 | Floor Finishes (Polished Conc floor finish) | 14 | 2022-12-01 | 2022-12-20 | 01 | 04 | 01 | 01 | 009 | 50 |  | Building | Architecture | Museum | Zone 01A | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36760 | Balustrades and Handrails | 6 | 2022-12-21 | 2022-12-28 | 01 | 04 | 01 | 01 | 009 | 50 |  | Building | Architecture | Museum | Zone 01A | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36755 | Specialist Fixtures (Precast Panels/Glazing elements) | 28 | 2022-12-21 | 2023-01-27 | 01 | 04 | 01 | 01 | 009 | 50 |  | Building | Architecture | Museum | Zone 01A | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36765 | Fitout & Step Finishes | 24 | 2023-01-30 | 2023-03-02 | 01 | 04 | 01 | 01 | 009 | 50 |  | Building | Architecture | Museum | Zone 01A | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36770 | Installation of Signage | 10 | 2023-03-03 | 2023-03-16 | 01 | 04 | 01 | 01 | 009 | 50 |  | Building | Architecture | Museum | Zone 01A | Drum / Ring Beam | Architectural SubZones
C-MS-G-FN-MLB-36775 | Final Finishes & Fittings | 8 | 2023-03-17 | 2023-03-28 | 01 | 04 | 01 | 01 | 009 | 50 |  | Building | Architecture | Museum | Zone 01A | Drum / Ring Beam | Architectural SubZones
MEP |  | 98 | 2022-10-06 | 2023-02-20
C-MS-G-MP-46555 | Wall & Floor MEP works 1st & 2nd Fix | 20 | 2022-10-06 | 2022-11-02 | 01 | 14 | 01 | 01 | 009 | 70 |  | Building | General MEP | Museum | Zone 01A | Drum / Ring Beam | MEP SubZones
C-MS-G-MP-46560 | Final Fix MEP works | 10 | 2023-02-07 | 2023-02-20 | 01 | 14 | 01 | 01 | 009 | 70 |  | Building | General MEP | Museum | Zone 01A | Drum / Ring Beam | MEP SubZones
Zone 1A - POD 5 |  | 577 | 2021-05-25 | 2023-04-20
Civil works |  | 388 | 2021-05-25 | 2022-09-06
Steel Structure |  | 388 | 2021-05-25 | 2022-09-06
Temporary Access / Steel Support |  | 138 | 2021-05-25 | 2021-11-07
C-PW-036270 | Erection of Temporary Steel - Preassembly Area | 17 | 2021-05-25 | 2021-06-13 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
C-PW-036280 | Installation of temporary towers / Struts / to support wing & POD - Stage 02 | 20 | 2021-07-04 | 2021-07-29 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
C-PW-036290 | De-Propping and dismantling of temporary towers | 6 | 2021-09-30 | 2021-10-06 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
C-PW-036300 | Erection of Temporary Steel - Stage 01 within Drum | 5 | 2021-11-02 | 2021-11-07 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
Erection of POD |  | 336 | 2021-07-04 | 2022-08-16
C-PW-036310 | POD 5 - Stage 01 assembly | 42 | 2021-07-04 | 2021-08-25 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
C-PW-036320 | POD 5 - Stage 02 assembly | 36 | 2021-08-26 | 2021-10-06 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
C-PW-036330 | Pre-Inspection works at Ring beam for POD erection | 5 | 2021-11-02 | 2021-11-07 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
C-PW-036340 | Lifting & Installation of Pre-assembled POD 5 steel frame | 12 | 2021-11-08 | 2021-11-21 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
C-PW-036350 | Installation of POD Leaveout Steel Structure | 12 | 2022-08-03 | 2022-08-16 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
Fire Proofing of POD |  | 37 | 2022-07-24 | 2022-09-06
C-PW-036360 | Fire Proofing works on POD Steel Structure (Except Leave out area) | 37 | 2022-07-24 | 2022-09-06 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
C-PW-036370 | Fire Proofing works on POD Steel Structure for Leave out area | 8 | 2022-08-28 | 2022-09-06 | 01 | 02 | 01 | 01 | 010 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Pod | Civil SubZones
Cladding Works |  | 238 | 2022-02-24 | 2022-12-08
C-PW-036380 | Install access platform at ring beam level & Inclined MonoRails | 24 | 2022-02-24 | 2022-03-23 | 01 | 05 | 01 | 01 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Pod | Architectural SubZones
C-PW-036390 | Install POD Facade Phase 1 (Belly & mid panels) | 24 | 2022-04-04 | 2022-05-05 | 01 | 05 | 01 | 01 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Pod | Architectural SubZones
C-PW-036410 | Install POD Facade Phase 2 (Belly & mid panels) | 31 | 2022-05-05 | 2022-06-11 | 01 | 05 | 01 | 01 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Pod | Architectural SubZones
C-PW-036420 | Remove access platform at ring beam level & Inclined MonoRails | 12 | 2022-06-11 | 2022-06-25 | 01 | 05 | 01 | 01 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Pod | Architectural SubZones
C-PW-036400 | Install POD Facade Phase 3 (Soffit) | 69 | 2022-04-27 | 2022-07-24 | 01 | 05 | 01 | 01 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Pod | Architectural SubZones
C-PW-036430 | Install POD Facade Phase 4 (Upper panels) | 10 | 2022-08-17 | 2022-08-28 | 01 | 05 | 01 | 01 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Pod | Architectural SubZones
C-PW-036440 | Install POD Skylight - Phase 1 | 24 | 2022-08-17 | 2022-09-13 | 01 | 05 | 01 | 01 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Pod | Architectural SubZones
C-PW-036450 | Install POD Facade Phase 5 (Leaveouts) | 42 | 2022-08-29 | 2022-10-17 | 01 | 05 | 01 | 01 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Pod | Architectural SubZones
C-PW-036460 | Install POD BMU | 18 | 2022-10-18 | 2022-11-07 | 01 | 05 | 01 | 01 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Pod | Architectural SubZones
C-PW-036470 | Install POD Skylight - Phase 2 (including metal works and cladding) | 72 | 2022-09-14 | 2022-12-08 | 01 | 05 | 01 | 01 | 010 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Pod | Architectural SubZones
Architectural |  | 64 | 2022-11-28 | 2023-02-23
FLOOR |  | 26 | 2023-01-19 | 2023-02-23
C-MS-P-FN-P5-69750 | Secondary Steel / Metal Decking / Screed | 7 | 2023-01-19 | 2023-01-27 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-69760 | Void Former | 6 | 2023-02-02 | 2023-02-09 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-69765 | Polished concrete Floor | 5 | 2023-02-10 | 2023-02-16 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-69770 | Bronze Grill/Skirting | 5 | 2023-02-17 | 2023-02-23 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
WALLS |  | 54 | 2022-11-28 | 2023-02-09
STAGE 1 (BELLY) |  | 41 | 2022-12-15 | 2023-02-09
Pod Internal |  | 41 | 2022-12-15 | 2023-02-09
C-MS-P-FN-P5-69900 | Secondary Steel A - wall void | 7 | 2022-12-15 | 2022-12-23 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-69905 | Ladders A including Platforms etc - wall void | 5 | 2022-12-26 | 2022-12-30 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-69870 | Secondary Steel A | 9 | 2022-12-26 | 2023-01-05 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-69880 | Pod Internal Cladding | 18 | 2023-01-17 | 2023-02-09 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
STAGE 2 (MID) |  | 32 | 2022-12-06 | 2023-01-18
Pod Internal |  | 32 | 2022-12-06 | 2023-01-18
C-MS-P-FN-P5-69980 | Secondary Steel B - wall void | 7 | 2022-12-06 | 2022-12-14 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-69985 | Ladders B including Platforms etc - wall void | 5 | 2022-12-15 | 2022-12-21 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-69950 | Secondary Steel B | 7 | 2022-12-15 | 2022-12-23 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-69960 | Pod Internal Cladding | 18 | 2022-12-26 | 2023-01-18 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
STAGE 3 (UPPER) |  | 48 | 2022-11-28 | 2023-02-01
Pod Internal |  | 48 | 2022-11-28 | 2023-02-01
C-MS-P-FN-P5-70065 | Secondary Steel C - wall void | 6 | 2022-11-28 | 2022-12-05 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-70070 | Ladders C including Platforms etc - wall void | 5 | 2022-12-06 | 2022-12-12 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-70030 | Secondary Steel C | 7 | 2022-12-06 | 2022-12-14 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-70040 | Pod Internal Cladding | 18 | 2022-12-15 | 2023-01-09 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-70055 | Internal finishes in leave out areas C | 17 | 2023-01-10 | 2023-02-01 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
STAGE 4(SOFFIT) |  | 12 | 2022-12-26 | 2023-01-10
WALL VOID |  | 12 | 2022-12-26 | 2023-01-10
C-MS-P-FN-P5-69820 | Secondary Steel D | 7 | 2022-12-26 | 2023-01-03 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
C-MS-P-FN-P5-69825 | Ladders D including Platforms etc | 5 | 2023-01-04 | 2023-01-10 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
MEP |  | 127 | 2022-09-06 | 2023-03-02
C-MS-P-MP-MA-70170 | MEP Access for POD Soffit Structure ( New Activity ) | 0 | 2022-09-06 |  | 01 | 14 | 01 | 01 | 010 | 70 |  | Building | General MEP | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-MA-73360 | MEP Access for Phase 2 (BELLY) ( New Activity ) | 0 | 2022-09-06 |  | 01 | 14 | 01 | 01 | 010 | 70 |  | Building | General MEP | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-MA-73470 | MEP Access for Phase 1 (MID & UPPER) ( New Activity ) | 0 | 2022-09-06 |  | 01 | 14 | 01 | 01 | 010 | 70 |  | Building | General MEP | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-MA-73370 | MEP Access for Finishes ( New Activity ) | 0 | 2023-02-10 |  | 01 | 14 | 01 | 01 | 010 | 70 |  | Building | General MEP | Museum | Zone 01A | Pod | MEP SubZones
MECHANICAL |  | 122 | 2022-09-06 | 2023-02-23
HVAC SYSTEM WORKS |  | 122 | 2022-09-06 | 2023-02-23
C-MS-P-MP-AC-70145 | 1st & 2nd Fix HVAC (Supports, Ducts & Insulation at Stage 1 Steel Frame) | 21 | 2022-09-06 | 2022-10-05 | 01 | 06 | 01 | 01 | 010 | 70 |  | Building | HVAC | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-AC-70140 | 1st Fix HVAC (Supports, Ducts & Insulation at Bottom Steel Trusses) | 26 | 2022-09-06 | 2022-10-12 | 01 | 06 | 01 | 01 | 010 | 70 |  | Building | HVAC | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-AC-70150 | 1st & 2nd Fix HVAC (Supports, Ducts & Insulation at Stage 2 Steel Frame) | 21 | 2022-10-12 | 2022-11-10 | 01 | 06 | 01 | 01 | 010 | 70 |  | Building | HVAC | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-AC-70155 | Completion of Bottom Ducting & insulation after removal of Temp. tower | 14 | 2022-10-28 | 2022-11-17 | 01 | 06 | 01 | 01 | 010 | 70 |  | Building | HVAC | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-AC-70160 | Final Fix HVAC (Grills, Diffusers) | 10 | 2023-02-10 | 2023-02-23 | 01 | 06 | 01 | 01 | 010 | 70 |  | Building | HVAC | Museum | Zone 01A | Pod | MEP SubZones
ELECTRICAL WORKS |  | 125 | 2022-09-08 | 2023-03-02
C-MS-P-MP-EL-73485 | 1st Fix Electrical (Supports and Cable trays at Stage 1 Steel Structure) | 18 | 2022-09-08 | 2022-10-04 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-73505 | 1st Fix Electrical (Conduiting & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-16 | 2022-10-04 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-70175 | 1st Fix Electrical (Conduiting & Boxes at Bottom Steel Trusses) | 12 | 2022-09-26 | 2022-10-12 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-70170 | 1st Fix Electrical (Supports and Cable trays at Bottom Steel Trusses) | 24 | 2022-09-08 | 2022-10-12 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-70205 | 1st Fix Electrical (Supports and Cable trays at Stage 2 Steel Structure) | 18 | 2022-10-04 | 2022-10-28 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-73515 | 1st Fix Electrical (Conduiting & Boxes at Stage 2 Steel Structure) | 12 | 2022-10-12 | 2022-10-28 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-70180 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-10-28 | 2022-11-23 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-73465 | 2nd Fix Electrical (Installation of Lighting Control Panels) | 6 | 2022-11-23 | 2022-12-01 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-70185 | Cable/Wire Termination & Dressing | 10 | 2022-12-01 | 2022-12-15 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-73885 | Final Fix Electrical (Light Fixtures-Strip Light below Sky light) | 3 | 2022-12-15 | 2022-12-20 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-70190 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2023-02-10 | 2023-02-23 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-70195 | Final Fix Electrical (Power Sockets/ Isolators) | 10 | 2023-02-15 | 2023-02-28 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-EL-70200 | Final Fix Electrical (Light Fixtures) | 10 | 2023-02-17 | 2023-03-02 | 01 | 07 | 01 | 01 | 010 | 70 |  | Building | Electrical | Museum | Zone 01A | Pod | MEP SubZones
ELV |  | 120 | 2022-09-08 | 2023-02-23
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 114 | 2022-09-08 | 2023-02-15
C-MS-P-MP-ELV-70220 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-08 | 2022-09-26 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70225 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 12 | 2022-09-26 | 2022-10-12 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70230 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 4 | 2023-02-10 | 2023-02-15 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
INTRUDER & HOLD-UPS ALARMS |  | 108 | 2022-09-20 | 2023-02-17
C-MS-P-MP-ELV-70240 | 1st Fix Intruder & Hold-Ups Alarms (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-20 | 2022-10-06 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-73830 | 1st Fix Intruder & Hold-Ups Alarms (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-09-20 | 2022-10-06 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70245 | 2nd Fix Intruder & Hold-Ups Alarms Works (Cable Wiring) | 12 | 2022-10-06 | 2022-10-24 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70250 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 4 | 2023-02-14 | 2023-02-17 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
VIDEO SURVEILLANCE SYSTEM |  | 104 | 2022-09-22 | 2023-02-15
C-MS-P-MP-ELV-70300 | 1st Fix Video Surveillance System Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-22 | 2022-10-10 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-73840 | 1st Fix Video Surveillance System Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-09-22 | 2022-10-10 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70305 | 2nd Fix Video Surveillance System Works (Cable Wiring) | 12 | 2022-10-10 | 2022-10-26 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70310 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 4 | 2023-02-10 | 2023-02-15 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
DATA AND TELECOMMUNICATION |  | 104 | 2022-09-26 | 2023-02-17
C-MS-P-MP-ELV-70320 | 1st Fix Data & Telecommunication Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-26 | 2022-10-12 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-73850 | 1st Fix Data & Telecommunication Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-10-12 | 2022-10-28 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70325 | 2nd Fix Data & Telecommunication Works (Cables Wiring) | 12 | 2022-10-28 | 2022-11-15 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70330 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 4 | 2023-02-14 | 2023-02-17 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
BMS AND AUTOMATIC CONTROLS |  | 102 | 2022-09-28 | 2023-02-17
C-MS-P-MP-ELV-70340 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes at Stage 1 Steel Structure) | 12 | 2022-09-28 | 2022-10-14 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-73860 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes at Stage 2 Steel Structure) | 12 | 2022-10-14 | 2022-11-01 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70345 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 12 | 2022-11-01 | 2022-11-17 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70350 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 4 | 2023-02-14 | 2023-02-17 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
EMERGENCY LIGHTING |  | 100 | 2022-09-30 | 2023-02-17
C-MS-P-MP-ELV-70390 | 1st Fix Emergency Lighting (Conduits & Boxes at Stage 1 Steel Structure | 12 | 2022-09-30 | 2022-10-18 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-73870 | 1st Fix Emergency Lighting (Conduits & Boxes at Stage 2 Steel Structure | 12 | 2022-10-18 | 2022-11-03 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70395 | 2nd Fix Emergency Lighting (Cable & Wiring) | 12 | 2022-11-03 | 2022-11-21 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70400 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 4 | 2023-02-14 | 2023-02-17 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
FIRE ALARM & PUBLIC ADDRESS |  | 108 | 2022-09-26 | 2023-02-23
C-MS-P-MP-ELV-70410 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes)along Bottom Steel Trusses | 12 | 2022-09-26 | 2022-10-12 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-73880 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes at Stage 1 Steel Structure | 12 | 2022-10-12 | 2022-10-28 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-73890 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes at Stage 2 Steel Structure | 12 | 2022-10-28 | 2022-11-15 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70415 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 12 | 2022-11-15 | 2022-12-01 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-ELV-70420 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 4 | 2023-02-20 | 2023-02-23 | 01 | 10 | 01 | 01 | 010 | 70 |  | Building | CCTV | Museum | Zone 01A | Pod | MEP SubZones
LIFE AND SAFETY SYSTEMS |  | 125 | 2022-09-06 | 2023-02-28
FIRE FIGHTING WORKS |  | 125 | 2022-09-06 | 2023-02-28
C-MS-P-MP-FF-70435 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Bottom Steel Trusses | 18 | 2022-09-06 | 2022-09-30 | 01 | 09 | 01 | 01 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-FF-70440 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Stage 1 Steel Structure) | 18 | 2022-09-22 | 2022-10-18 | 01 | 09 | 01 | 01 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-FF-73845 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Bottom Steel Trusses 2nd Layer | 18 | 2022-10-12 | 2022-11-07 | 01 | 09 | 01 | 01 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-FF-73675 | 1st Fix (Piping Support and Installation of Fire fighting pipes & Fittings at Stage 2 Steel Structure) | 18 | 2022-10-18 | 2022-11-11 | 01 | 09 | 01 | 01 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-FF-73685 | Fire fighting Pipes Pressure Testing | 3 | 2022-11-11 | 2022-11-16 | 01 | 09 | 01 | 01 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-FF-73885 | Final Fix Piping System (Sprinkler Heads below Sky Light) | 4 | 2022-12-09 | 2022-12-14 | 01 | 09 | 01 | 01 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01A | Pod | MEP SubZones
C-MS-P-MP-FF-70445 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 10 | 2023-02-15 | 2023-02-28 | 01 | 09 | 01 | 01 | 010 | 70 |  | Building | Firefighting | Museum | Zone 01A | Pod | MEP SubZones
Close Out Works |  | 35 | 2023-03-03 | 2023-04-20
C-MS-W-CL-W5-70600 | Testing & Commissioning Works - Wing 5 & Pod 5 | 15 | 2023-03-03 | 2023-03-23 | 01 | 14 | 01 | 01 | 010 | 70 |  | Building | General MEP | Museum | Zone 01A | Pod | MEP SubZones
C-MS-W-CL-W5-70605 | Snagging & De-snagging Works - Wing 5 & Pod 5 | 20 | 2023-03-24 | 2023-04-20 | 01 | 04 | 01 | 01 | 010 | 50 |  | Building | Architecture | Museum | Zone 01A | Pod | Architectural SubZones
Zone 1A - Wing 5 |  | 518 | 2021-09-23 | 2023-06-07
Civil works |  | 334 | 2021-09-23 | 2022-10-31
Steel Structure |  | 334 | 2021-09-23 | 2022-10-31
Temporary Access / Steel Support |  | 265 | 2021-09-23 | 2022-08-10
C-PW-036540 | Temporary Steel Platform - Tier - 1 - Pre-assembly | 15 | 2021-09-23 | 2021-10-10 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036550 | Lifting and Installation of Preassembled Temporary Steel Platform - Tier - 1 | 3 | 2021-11-18 | 2021-11-21 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036560 | Erection of Temporary Steel for Tier - 2 | 17 | 2022-01-22 | 2022-02-09 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036570 | Erection of Temporary Steel for Tier - 3 | 16 | 2022-04-12 | 2022-04-30 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036580 | Erection of Temporary Steel for Cantilever | 4 | 2022-06-25 | 2022-06-28 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036590 | Dismantling of temporary steel - bracing | 10 | 2022-06-25 | 2022-07-05 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036600 | De-Propping of Permanent steel | 2 | 2022-07-06 | 2022-07-07 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036610 | Dismantling of temporary steel - Tier 3, Tier 2 & Tier 1 | 18 | 2022-07-09 | 2022-08-02 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036620 | Erection , alignment , welding and inspection of Verticals,Mullions & Arches Cantilever | 21 | 2022-07-09 | 2022-08-06 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036630 | Dismantling of temporary steel for Cantilever | 4 | 2022-08-07 | 2022-08-10 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
Erection of Wing |  | 334 | 2021-09-23 | 2022-10-31
C-PW-036640 | Wing 5- Tier 1 A-Frames Pre-assembly | 18 | 2021-09-23 | 2021-10-13 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036650 | Lifting & Installation of Pre-assembled Wing 5 A-Frame | 6 | 2021-11-15 | 2021-11-21 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036660 | Wing 5- Tier 1 Erection (Front & Back) | 66 | 2021-11-22 | 2022-02-09 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036670 | Wing 5- Tier 2 Erection (Front & Back) | 64 | 2022-02-10 | 2022-04-25 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036680 | Wing 5- Tier 3 Erection (Front & Back) | 44 | 2022-05-04 | 2022-06-23 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036690 | Installation of Wing Leaveout Steel Structure - Tier 2 | 13 | 2022-09-22 | 2022-10-06 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
C-PW-036700 | Installation of Wing Leaveout Steel Structure - Tier 3 | 12 | 2022-10-18 | 2022-10-31 | 01 | 02 | 01 | 01 | 011 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01A | Wing | Civil SubZones
Architectural works |  | 204 | 2022-10-08 | 2023-06-07
Facade Works |  | 204 | 2022-10-08 | 2023-06-07
C-OW-036710 | Facade/ MEP/ BMU installation works for Wing 5 (Middle Area - 5 levels) | 114 | 2022-10-08 | 2023-02-20 | 01 | 05 | 01 | 01 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Wing | Architectural SubZones
C-OW-036720 | Façade/ MEP/ BMU installation works for Wing 5 (Bottom Area - 8 levels) | 145 | 2022-10-08 | 2023-03-28 | 01 | 05 | 01 | 01 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Wing | Architectural SubZones
C-OW-036730 | Façade/ MEP/ BMU installation works for Wing 05 (Top Area - 8 levels) | 130 | 2023-01-05 | 2023-06-07 | 01 | 05 | 01 | 01 | 011 | 50 |  | Building | Façade/Envelope | Museum | Zone 01A | Wing | Architectural SubZones
Zone 1F - Central Lobby |  | 495 | 2021-09-09 | 2023-04-27
Civil Works |  | 384 | 2021-09-09 | 2022-12-15
C-PW-036740 | Construction of WC Central Lift Core - Stage 02, 03 & Roof Slab | 36 | 2021-09-09 | 2021-10-21 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036750 | Level 02 Slab - Phase 01 | 24 | 2022-02-09 | 2022-03-08 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036760 | Level 03 Slab - Phase 01 | 28 | 2022-02-26 | 2022-03-29 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036770 | Level 02 Slab - Phase 02 | 24 | 2022-03-09 | 2022-04-05 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036780 | Steel Feature Stair Installation | 28 | 2022-03-14 | 2022-04-16 | 01 | 02 | 01 | 06 | 008 | 30 |  | Building | Primary Steel Structure | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036790 | Level 02 Slab - Phase 03 | 24 | 2022-04-06 | 2022-05-07 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036800 | Level 03 Slab - Phase 02 | 36 | 2022-04-06 | 2022-05-21 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036810 | Curing / Dismantling Scaffolding | 18 | 2022-05-22 | 2022-06-11 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036820 | Level 03 WC Suspended Slab | 36 | 2022-06-12 | 2022-07-26 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036830 | Curing time | 18 | 2022-07-27 | 2022-08-17 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036840 | Conical Wall - Phase 1 | 18 | 2022-08-18 | 2022-09-07 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036850 | Construction of Verticals up to Level 04 Slab | 18 | 2022-08-18 | 2022-09-07 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036860 | Remaining Level 03 Slab | 18 | 2022-09-08 | 2022-09-28 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036870 | Conical Wall - Phase 2 | 18 | 2022-09-29 | 2022-10-20 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036880 | Level 04 Slab - Stage 1 | 24 | 2022-10-22 | 2022-11-17 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036890 | Level 04 Slab - Stage 2 | 24 | 2022-10-22 | 2022-11-17 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036900 | Level 04 Slab - Stage 3 | 24 | 2022-10-22 | 2022-11-17 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
Raised Slab |  | 47 | 2022-10-22 | 2022-12-15
C-PW-036910 | Ground Level Slab (leave out area) | 18 | 2022-10-22 | 2022-11-10 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036920 | Construction of Verticals to Raised Floor Slab | 6 | 2022-11-12 | 2022-11-17 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036930 | Filling of EPS Void Former | 8 | 2022-11-19 | 2022-11-27 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
C-PW-036940 | Construction of Raised Floor Slab | 15 | 2022-11-28 | 2022-12-15 | 01 | 01 | 01 | 06 | 008 | 30 |  | Building | Civil | Museum | Zone 01F | Central Lobby | Civil SubZones
Architectural Works |  | 459 | 2021-10-23 | 2023-04-27
L-BM Basement Mezzanine Level |  | 72 | 2021-10-23 | 2022-01-17
C-PW-036950 | Architectural Works | 72 | 2021-10-23 | 2022-01-17 | 01 | 04 | 01 | 06 | 008 | 50 |  | Building | Architecture | Museum | Zone 01F | Central Lobby | Architectural SubZones
L00 Ground Level |  | 131 | 2022-06-12 | 2022-11-16
CIRCULATIONS & CORRIDORS- NORTH |  | 131 | 2022-06-12 | 2022-11-16
C-PW-057900 | Plastering Works - Walls | 10 | 2022-06-12 | 2022-06-22 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057910 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-07-14 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057920 | Wall Finishes (Rendered Flooring,Wall Paints) | 17 | 2022-07-16 | 2022-08-04 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057930 | Ceiling Grid / Support Works | 14 | 2022-08-04 | 2022-08-22 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057940 | Ceiling Finishes (Plaster board ceiling) | 14 | 2022-08-22 | 2022-09-07 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057950 | Roller Shutter Installation | 2 | 2022-09-15 | 2022-09-18 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057960 | Floor Finishes (Polished Concrete,Epoxy Resin Flooring) | 17 | 2022-09-07 | 2022-09-27 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057970 | Door Frames & Architrave Fixing | 10 | 2022-09-27 | 2022-10-08 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057980 | Door Shuttering & Ironmongery | 10 | 2022-10-16 | 2022-10-26 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057990 | Final Finishes & Fittings | 10 | 2022-11-06 | 2022-11-16 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
L02 Gallery level |  | 199 | 2022-09-03 | 2023-04-27
CENTRAL GALLERY WALKWAY & MEMBERS LOUNGE |  | 199 | 2022-09-03 | 2023-04-27
C-PW-087830 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-09-03 | 01 | 14 | 01 | 45 | 005 | 01 |  | Building | General MEP | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-087840 | Wall Finishes (Balustrade Lining, Balustrade capping, & Metal wall system) | 22 | 2022-10-22 | 2022-11-16 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-087850 | Ceiling Grid / Support Works | 19 | 2022-11-05 | 2022-11-27 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-087860 | Ceiling Finishes (Suspended Plaster board ceiling) | 19 | 2022-11-28 | 2022-12-21 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-087870 | Floor Finishes (Timber board flooring) | 9 | 2022-12-21 | 2022-12-31 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-087880 | Floor Finishes (Polished Conc floor finish,Resin board flooring) | 11 | 2022-12-21 | 2023-01-04 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-087890 | Door Frames & Architrave Fixing | 11 | 2023-01-04 | 2023-01-17 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-087900 | Door Shuttering & Ironmongery | 8 | 2023-01-16 | 2023-01-24 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-087910 | Joinery Fixing & Fitout works | 11 | 2023-04-08 | 2023-04-23 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-087920 | Final Finishes | 13 | 2023-04-11 | 2023-04-27 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
L03 Plenum |  | 161 | 2022-04-27 | 2022-11-10
SERVICE ACCESS AREAS & MEWP GARAGE |  | 161 | 2022-04-27 | 2022-11-10
C-PW-102120 | General Block Works | 14 | 2022-04-27 | 2022-05-17 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102130 | Marking & Chasing Walls for MEP Services | 14 | 2022-05-10 | 2022-05-26 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102140 | First Coat Paint in Ceiling | 14 | 2022-05-28 | 2022-06-13 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102150 | Wall Waterproofing works | 14 | 2022-06-28 | 2022-07-18 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102160 | Wall Finishes Works | 14 | 2022-07-18 | 2022-08-04 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102170 | Equipment Foundation/ Platform | 14 | 2022-08-04 | 2022-08-22 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102180 | Floor Surface Preparation for Epoxy Coating | 14 | 2022-08-22 | 2022-09-07 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102190 | Floor Finishes (Epoxy Coating) | 17 | 2022-08-30 | 2022-09-19 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102200 | Cleaning Equipment Installation | 16 | 2022-09-07 | 2022-09-26 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102210 | Access hatch works | 14 | 2022-09-19 | 2022-10-05 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102220 | Door Frames Fixing | 6 | 2022-10-05 | 2022-10-13 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102230 | Door Shuttering / Louvre's & Ironmongery | 10 | 2022-10-15 | 2022-10-25 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-102240 | Final Coat Ceiling Paint | 14 | 2022-10-25 | 2022-11-10 | 01 | 04 | 01 | 49 | 006 | 02 |  | Building | Architecture | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
L04 |  | 105 | 2022-10-22 | 2023-02-22
C-PW-037050 | Architectural Works -1st Fix | 6 | 2022-10-22 | 2022-10-27 | 01 | 04 | 01 | 06 | 008 | 50 |  | Building | Architecture | Museum | Zone 01F | Central Lobby | Architectural SubZones
C-PW-037060 | Architectural Works - 2nd Fix | 6 | 2023-01-19 | 2023-01-25 | 01 | 04 | 01 | 06 | 008 | 50 |  | Building | Architecture | Museum | Zone 01F | Central Lobby | Architectural SubZones
C-PW-037070 | Architectural Works - Final Fix | 12 | 2023-02-09 | 2023-02-22 | 01 | 04 | 01 | 06 | 008 | 50 |  | Building | Architecture | Museum | Zone 01F | Central Lobby | Architectural SubZones
MEP Works |  | 425 | 2021-11-20 | 2023-04-13
L-BM Basement Mezzanine Level |  | 56 | 2022-05-23 | 2022-08-01
C-PW-037080 | MEP works inside service tunnel - Bs.MZ Level | 56 | 2022-05-23 | 2022-08-01 | 01 | 14 | 01 | 06 | 008 | 70 |  | Building | General MEP | Museum | Zone 01F | Central Lobby | MEP SubZones
L00 Ground Level |  | 182 | 2022-03-28 | 2022-11-05
CIRCULATIONS & CORRIDORS- NORTH |  | 182 | 2022-03-28 | 2022-11-05
MECHANICAL |  | 157 | 2022-04-27 | 2022-11-05
HVAC SYSTEM WORKS |  | 149 | 2022-05-10 | 2022-11-05
C-PW-063090 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 18 | 2022-05-10 | 2022-05-31 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063100 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 18 | 2022-05-10 | 2022-05-31 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063110 | 2nd Fix HVAC (FCUs, Valves Package, Duct Heaters & Humidifiers) | 10 | 2022-05-31 | 2022-06-13 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063120 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-27 | 2022-11-05 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-04-27 | 2022-06-04
C-PW-063130 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-27 | 2022-05-22 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063140 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-22 | 2022-06-04 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-05-07 | 2022-06-08
C-PW-063150 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-07 | 2022-05-28 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063160 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-28 | 2022-06-08 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 181 | 2022-03-28 | 2022-11-05
C-PW-063170 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-28 | 2022-04-13 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063180 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-05-04 | 2022-05-23 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063190 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-23 | 2022-06-08 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063200 | LV Switchgears (DB's) | 5 | 2022-06-08 | 2022-06-13 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063210 | Cable/Wire Termination & Dressing | 7 | 2022-06-14 | 2022-06-22 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063220 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-22 | 2022-10-31 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063230 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-23 | 2022-10-31 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063240 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-10-25 | 2022-11-02 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063250 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-27 | 2022-11-05 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELV |  | 168 | 2022-04-04 | 2022-10-26
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 162 | 2022-04-04 | 2022-10-18
C-PW-063260 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063270 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-16 | 2022-04-27 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063280 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-16 | 2022-10-18 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 160 | 2022-04-05 | 2022-10-18
C-PW-063290 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063300 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063310 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-16 | 2022-10-18 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 159 | 2022-04-07 | 2022-10-18
C-PW-063320 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063330 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063340 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-16 | 2022-10-18 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 159 | 2022-04-09 | 2022-10-20
C-PW-063350 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-21 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063360 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-21 | 2022-05-07 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063370 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-18 | 2022-10-20 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 157 | 2022-04-11 | 2022-10-20
C-PW-063380 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-11 | 2022-04-23 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063390 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-23 | 2022-05-09 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063400 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-18 | 2022-10-20 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 157 | 2022-04-13 | 2022-10-22
C-PW-063410 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-13 | 2022-04-25 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063420 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-25 | 2022-05-10 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063430 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-19 | 2022-10-22 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 155 | 2022-04-14 | 2022-10-22
C-PW-063440 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063450 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063460 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-19 | 2022-10-22 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-19 | 2022-10-26
C-PW-063470 | Active Component System Works | 6 | 2022-10-19 | 2022-10-26 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 116 | 2022-04-27 | 2022-09-17
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 110 | 2022-04-27 | 2022-09-10
C-PW-063480 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063490 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-12 | 2022-05-24 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063500 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-07 | 2022-09-10 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 108 | 2022-04-28 | 2022-09-10
C-PW-063510 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-28 | 2022-05-14 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063520 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063530 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-07 | 2022-09-10 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 78 | 2022-06-14 | 2022-09-17
C-PW-063540 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-14 | 2022-07-02 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063550 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-07-03 | 2022-07-14 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063560 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 8 | 2022-09-07 | 2022-09-17 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
L02 Gallery level |  | 174 | 2022-07-05 | 2023-02-02
CENTRAL GALLERY WALKWAY & MEMBERS LOUNGE |  | 174 | 2022-07-05 | 2023-02-02
MECHANICAL |  | 168 | 2022-07-05 | 2023-01-25
HVAC SYSTEM WORKS |  | 160 | 2022-07-18 | 2023-01-25
C-PW-100980 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 14 | 2022-07-18 | 2022-08-04 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100990 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 14 | 2022-07-20 | 2022-08-06 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101000 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-08-07 | 2022-08-18 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101010 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2023-01-17 | 2023-01-25 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-07-05 | 2022-08-13
C-PW-101020 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-05 | 2022-08-01 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101030 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-01 | 2022-08-13 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-07-14 | 2022-08-18
C-PW-101040 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-14 | 2022-08-06 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101050 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-07 | 2022-08-18 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 160 | 2022-07-26 | 2023-02-02
C-PW-101060 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-07-26 | 2022-08-08 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101070 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-07-27 | 2022-08-14 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101080 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-08-14 | 2022-08-29 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101090 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2023-01-19 | 2023-01-28 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101100 | Final Fix Electrical (Light Fixtures) | 10 | 2023-01-21 | 2023-02-02 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101110 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2023-01-21 | 2023-02-02 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELV |  | 156 | 2022-07-27 | 2023-01-30
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 147 | 2022-07-27 | 2023-01-19
C-PW-101120 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-07-27 | 2022-08-10 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101130 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-08-10 | 2022-08-22 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101140 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2023-01-17 | 2023-01-19 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 146 | 2022-07-31 | 2023-01-19
C-PW-101150 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-07-31 | 2022-08-11 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101160 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-08-11 | 2022-08-24 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101170 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2023-01-17 | 2023-01-19 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 144 | 2022-08-02 | 2023-01-19
C-PW-101180 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-08-02 | 2022-08-14 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101190 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-08-14 | 2022-08-25 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101200 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2023-01-17 | 2023-01-19 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 144 | 2022-08-03 | 2023-01-22
C-PW-101210 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-08-03 | 2022-08-15 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101220 | 2nd Fix AV System Works (Wiring) | 10 | 2022-08-16 | 2022-08-28 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101230 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2023-01-19 | 2023-01-22 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 142 | 2022-08-06 | 2023-01-22
C-PW-101240 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-08-06 | 2022-08-17 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101250 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-08-17 | 2022-08-29 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101260 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2023-01-19 | 2023-01-22 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 142 | 2022-08-07 | 2023-01-24
C-PW-101270 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-08-07 | 2022-08-20 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101280 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-20 | 2022-08-31 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101290 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2023-01-21 | 2023-01-24 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 141 | 2022-08-09 | 2023-01-24
C-PW-101300 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-08-09 | 2022-08-21 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101310 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-21 | 2022-09-03 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101320 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2023-01-21 | 2023-01-24 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2023-01-24 | 2023-01-30
C-PW-101330 | Active Component System Works | 6 | 2023-01-24 | 2023-01-30 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 150 | 2022-07-24 | 2023-01-19
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 147 | 2022-07-27 | 2023-01-19
C-PW-101340 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-27 | 2022-08-10 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101350 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-08-10 | 2022-08-22 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101360 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2023-01-17 | 2023-01-19 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 146 | 2022-07-31 | 2023-01-19
C-PW-101370 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-31 | 2022-08-11 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101380 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-11 | 2022-08-24 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101390 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2023-01-17 | 2023-01-19 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 133 | 2022-07-24 | 2022-12-29
C-PW-101400 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-07-24 | 2022-08-10 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101410 | 2nd Fix Piping System - (Fittings) | 8 | 2022-08-10 | 2022-08-20 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-101420 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-12-21 | 2022-12-29 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
LIFTS |  | 251 | 2022-06-18 | 2023-04-13
C-PW-037150 | Machine , BM Installation for lift | 208 | 2022-06-18 | 2023-02-22 | 01 | 13 | 01 | 06 | 008 | 70 |  | Building | Vertical Transportation | Museum | Zone 01F | Central Lobby | MEP SubZones
C-PW-037160 | Lift Cabine, door , Finishes and tests for Lift | 234 | 2022-07-07 | 2023-04-13 | 01 | 13 | 01 | 06 | 008 | 70 |  | Building | Vertical Transportation | Museum | Zone 01F | Central Lobby | MEP SubZones
L03 Plenum |  | 284 | 2021-11-20 | 2022-10-29
SERVICE ACCESS AREAS & MEWP GARAGE |  | 284 | 2021-11-20 | 2022-10-29
MECHANICAL |  | 72 | 2022-05-19 | 2022-08-16
DRAINAGE WORKS |  | 28 | 2022-05-19 | 2022-06-21
C-PW-103850 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-05-19 | 2022-06-07 | 01 | 08 | 01 | 49 | 006 | 02 |  | Building | Plumbing | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103860 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 12 | 2022-06-07 | 2022-06-21 | 01 | 08 | 01 | 49 | 006 | 02 |  | Building | Plumbing | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 28 | 2022-06-13 | 2022-07-19
C-PW-103870 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-06-13 | 2022-07-02 | 01 | 08 | 01 | 49 | 006 | 02 |  | Building | Plumbing | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103880 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 12 | 2022-07-02 | 2022-07-19 | 01 | 08 | 01 | 49 | 006 | 02 |  | Building | Plumbing | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
HVAC SYSTEM WORKS |  | 48 | 2022-06-16 | 2022-08-16
C-PW-103890 | 1st Fix HVAC (Supports, Ducts ,Dampers - VCD,NRD,MDs) | 16 | 2022-06-16 | 2022-07-05 | 01 | 06 | 01 | 49 | 006 | 02 |  | Building | HVAC | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103900 | 2nd Fix HVAC (Duct Plenums & Flex.Connector) | 16 | 2022-07-05 | 2022-07-27 | 01 | 06 | 01 | 49 | 006 | 02 |  | Building | HVAC | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103910 | Final Fix HVAC (Grills, Diffusers) | 10 | 2022-08-04 | 2022-08-16 | 01 | 06 | 01 | 49 | 006 | 02 |  | Building | HVAC | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 80 | 2022-05-16 | 2022-08-22
C-PW-103920 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 12 | 2022-05-16 | 2022-05-30 | 01 | 07 | 01 | 49 | 006 | 02 |  | Building | Electrical | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103930 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-06-13 | 2022-07-02 | 01 | 07 | 01 | 49 | 006 | 02 |  | Building | Electrical | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103940 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 16 | 2022-07-02 | 2022-07-24 | 01 | 07 | 01 | 49 | 006 | 02 |  | Building | Electrical | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103950 | LV Switchgears (DB's) | 5 | 2022-07-24 | 2022-07-31 | 01 | 07 | 01 | 49 | 006 | 02 |  | Building | Electrical | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103960 | Cable/Wire Termination & Dressing | 7 | 2022-07-31 | 2022-08-08 | 01 | 07 | 01 | 49 | 006 | 02 |  | Building | Electrical | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103970 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-08-08 | 2022-08-16 | 01 | 07 | 01 | 49 | 006 | 02 |  | Building | Electrical | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103980 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-10 | 2022-08-18 | 01 | 07 | 01 | 49 | 006 | 02 |  | Building | Electrical | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-103990 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-11 | 2022-08-20 | 01 | 07 | 01 | 49 | 006 | 02 |  | Building | Electrical | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104000 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-14 | 2022-08-22 | 01 | 07 | 01 | 49 | 006 | 02 |  | Building | Electrical | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
ELV |  | 30 | 2022-05-28 | 2022-06-30
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-05-28 | 2022-06-23
C-PW-104010 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-28 | 2022-06-08 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104020 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104030 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-06-20 | 2022-06-23 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
AV SYSTEM |  | 23 | 2022-05-29 | 2022-06-25
C-PW-104040 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-29 | 2022-06-09 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104050 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104060 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-06-22 | 2022-06-25 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-05-31 | 2022-06-27
C-PW-104070 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-31 | 2022-06-12 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104080 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-12 | 2022-06-23 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104090 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-06-25 | 2022-06-27 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 23 | 2022-06-01 | 2022-06-28
C-PW-104100 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-01 | 2022-06-14 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104110 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104120 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-06-26 | 2022-06-28 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-06-04 | 2022-06-30
C-PW-104130 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-04 | 2022-06-15 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104140 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-15 | 2022-06-28 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104150 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-06-28 | 2022-06-30 | 01 | 10 | 01 | 49 | 006 | 02 |  | Building | CCTV | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 284 | 2021-11-20 | 2022-10-29
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 23 | 2021-11-20 | 2021-12-19
C-PW-104160 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2021-11-20 | 2021-12-04 | 01 | 09 | 01 | 49 | 006 | 02 |  | Building | Firefighting | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104170 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2021-12-04 | 2021-12-15 | 01 | 09 | 01 | 49 | 006 | 02 |  | Building | Firefighting | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104180 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2021-12-15 | 2021-12-19 | 01 | 09 | 01 | 49 | 006 | 02 |  | Building | Firefighting | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 76 | 2021-11-21 | 2022-02-21
C-PW-104190 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2021-11-21 | 2021-12-05 | 01 | 09 | 01 | 49 | 006 | 02 |  | Building | Firefighting | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104200 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2021-12-06 | 2021-12-18 | 01 | 09 | 01 | 49 | 006 | 02 |  | Building | Firefighting | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104210 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-02-19 | 2022-02-21 | 01 | 09 | 01 | 49 | 006 | 02 |  | Building | Firefighting | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 113 | 2022-06-13 | 2022-10-29
C-PW-104220 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-13 | 2022-07-02 | 01 | 09 | 01 | 49 | 006 | 02 |  | Building | Firefighting | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104230 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 12 | 2022-07-02 | 2022-07-19 | 01 | 09 | 01 | 49 | 006 | 02 |  | Building | Firefighting | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
C-PW-104240 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 10 | 2022-10-17 | 2022-10-29 | 01 | 09 | 01 | 49 | 006 | 02 |  | Building | Firefighting | Museum | L03 Z02 & Z03 Service Area | L03 Plenum Level | MEP / Service Rooms
L04 |  | 32 | 2022-11-19 | 2022-12-26
C-PW-037200 | MEP works 1st Fix | 6 | 2022-11-19 | 2022-11-24 | 01 | 14 | 01 | 06 | 008 | 70 |  | Building | General MEP | Museum | Zone 01F | Central Lobby | MEP SubZones
C-PW-037210 | MEP works 2nd Fix | 6 | 2022-12-01 | 2022-12-07 | 01 | 14 | 01 | 06 | 008 | 70 |  | Building | General MEP | Museum | Zone 01F | Central Lobby | MEP SubZones
C-PW-037220 | MEP Final Fix | 12 | 2022-12-13 | 2022-12-26 | 01 | 14 | 01 | 06 | 008 | 70 |  | Building | General MEP | Museum | Zone 01F | Central Lobby | MEP SubZones
Zone 2 and Zone 3 |  | 624 | 2021-04-21 | 2023-05-16
LEVEL BASEMENT |  | 492 | 2021-09-30 | 2023-05-16
CIVIL WORKS |  | 64 | 2022-01-24 | 2022-04-07
ZONE 03C |  | 64 | 2022-01-24 | 2022-04-07
C-PW-037230 | Excavation till Formation Level of Pilecaps - Zone 3C | 8 | 2022-01-24 | 2022-02-01 | 01 | 01 | 01 | 17 | 001 | 30 |  | Building | Civil | Museum | Zone 03C | L-B1 Basement Level | Civil SubZones
C-PW-037240 | Pile Breaking Head & Profiling - Zone 3C | 8 | 2022-02-02 | 2022-02-10 | 01 | 01 | 01 | 17 | 001 | 30 |  | Building | Civil | Museum | Zone 03C | L-B1 Basement Level | Civil SubZones
C-PW-037250 | Pile Testing - Zone 3C | 8 | 2022-02-12 | 2022-02-20 | 01 | 01 | 01 | 17 | 001 | 30 |  | Building | Civil | Museum | Zone 03C | L-B1 Basement Level | Civil SubZones
C-PW-037260 | Construction of Pilecaps & Tie beams - Zone 3C | 8 | 2022-02-21 | 2022-03-01 | 01 | 01 | 01 | 17 | 001 | 30 |  | Building | Civil | Museum | Zone 03C | L-B1 Basement Level | Civil SubZones
C-PW-037270 | Construction of basement Slab - Zone 3C | 8 | 2022-03-02 | 2022-03-10 | 01 | 01 | 01 | 17 | 001 | 30 |  | Building | Civil | Museum | Zone 03C | L-B1 Basement Level | Civil SubZones
C-PW-037280 | Soil Compaction , Anti-termite & Blinding - Zone 3C | 8 | 2022-03-12 | 2022-03-20 | 01 | 01 | 01 | 17 | 001 | 30 |  | Building | Civil | Museum | Zone 03C | L-B1 Basement Level | Civil SubZones
C-PW-037290 | Waterproofing & Screed Works - Zone 3C | 8 | 2022-03-21 | 2022-03-29 | 01 | 01 | 01 | 17 | 001 | 30 |  | Building | Civil | Museum | Zone 03C | L-B1 Basement Level | Civil SubZones
C-PW-037300 | Construction of walls up to Basement Mezzanine Slab - Zone 3C | 8 | 2022-03-30 | 2022-04-07 | 01 | 01 | 01 | 17 | 001 | 30 |  | Building | Civil | Museum | Zone 03C | L-B1 Basement Level | Civil SubZones
ARCHITECTURAL WORKS |  | 477 | 2021-10-07 | 2023-05-06
NORTH WEST |  | 477 | 2021-10-07 | 2023-05-06
COMMON FLOOR WORKS- NORTH |  | 29 | 2022-01-03 | 2022-02-05
C-PW-037310 | General Block Work - MEP Rooms | 14 | 2022-01-03 | 2022-01-19 | 01 | 04 | 01 | 46 | 001 | 01 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-037320 | Marking & Chasing Walls for MEP Services | 14 | 2022-01-19 | 2022-02-05 | 01 | 04 | 01 | 46 | 001 | 01 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
MECHANICAL PLANT ROOM A & B - NORTH |  | 206 | 2022-01-08 | 2022-09-13
C-PW-037330 | Equipment Foundation Works | 14 | 2022-01-08 | 2022-01-24 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037340 | Paint 1st Coat - Ceiling and Wall (Primer, Paint Base Coat) | 10 | 2022-01-24 | 2022-02-05 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037350 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-04-14 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037360 | Floor Finishes (Epoxy Resin Flooring) | 14 | 2022-05-24 | 2022-06-11 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037370 | Door Frame, Shutter & Ironmongery | 10 | 2022-08-08 | 2022-08-18 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037380 | Final Finishes | 22 | 2022-08-18 | 2022-09-13 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL PLANT & UPS 1 - NORTH |  | 148 | 2022-01-19 | 2022-07-17
C-PW-037390 | Equipment Foundation Works | 14 | 2022-01-19 | 2022-02-05 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037400 | Floor Trench Works | 14 | 2022-02-05 | 2022-02-21 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037410 | Paint 1st Coat - Ceiling and Wall (Primer, Paint Base Coat) | 6 | 2022-02-21 | 2022-03-01 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037420 | Grating Works | 10 | 2022-03-21 | 2022-03-31 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037430 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-05-18 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037440 | Floor Finishes (Epoxy Resin Flooring) | 14 | 2022-04-28 | 2022-05-18 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037450 | Door Frame, Shutter & Ironmongery | 10 | 2022-05-19 | 2022-05-30 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037460 | Final Finishes | 22 | 2022-06-18 | 2022-07-17 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
MAIN TEL. ROOM 1, CCU1 & 2, ETISALAT METER 1 - NORTH |  | 122 | 2022-03-01 | 2022-07-28
C-PW-037470 | Paint 1st Coat - Ceiling (Primer, Paint Base Coat) | 6 | 2022-03-01 | 2022-03-08 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037480 | Wall Finishes | 11 | 2022-05-18 | 2022-05-31 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037490 | Ceiling Finishes (Dust Sealer) | 13 | 2022-05-31 | 2022-06-15 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037500 | Floor Finishes | 14 | 2022-06-15 | 2022-07-02 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037510 | Door Frame, Shutter & Ironmongery | 13 | 2022-06-21 | 2022-07-05 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037520 | Final Finishes | 17 | 2022-07-05 | 2022-07-28 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
GREASE TRAP ROOM - NORTH |  | 122 | 2022-03-01 | 2022-07-28
C-PW-037530 | Paint 1st Coat - Ceiling (Primer, Paint Base Coat) | 6 | 2022-03-01 | 2022-03-08 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037540 | Wall Finishes | 11 | 2022-05-18 | 2022-05-31 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037550 | Ceiling Finishes (Dust Sealer) | 13 | 2022-05-31 | 2022-06-15 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037560 | Floor Finishes | 14 | 2022-06-15 | 2022-07-02 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037570 | Door Frame, Shutter & Ironmongery | 13 | 2022-06-21 | 2022-07-05 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-037580 | Final Finishes | 17 | 2022-07-05 | 2022-07-28 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ADMIN CANTEEN & LOBBY - NORTH |  | 390 | 2022-01-19 | 2023-05-03
C-PW-037590 | General Block Work | 11 | 2022-01-19 | 2022-02-01 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037600 | Marking & Chasing Walls for MEP Services | 11 | 2022-02-01 | 2022-02-14 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037610 | Plastering Works - Walls | 14 | 2022-02-14 | 2022-03-03 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037620 | Ceiling Grid / Support Works | 11 | 2022-06-25 | 2022-07-07 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037630 | Wall Finishes (Plaster Board Lining & Interior Paint) | 22 | 2022-06-14 | 2022-07-13 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037640 | Ceiling Finishes (Suspended Gypsum Tiles & Dust Sealer) | 14 | 2022-07-07 | 2022-07-28 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037650 | Floor Finishes (Epoxy Resin Flooring) | 11 | 2022-07-28 | 2022-08-11 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037660 | Door Frames & Architrave Fixing | 6 | 2022-08-11 | 2022-08-18 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037670 | Door Shuttering & Ironmongery | 10 | 2022-08-18 | 2022-08-30 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037680 | Joinery Fixing | 11 | 2023-04-08 | 2023-04-23 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037690 | Final Finishes | 10 | 2023-04-23 | 2023-05-03 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
STAFF CANTEEN, WASTE STORAGE 1 & SPECIAL EVENT STORAGE- NORTH |  | 368 | 2022-02-14 | 2023-05-03
C-PW-037700 | Plastering Works - Walls | 14 | 2022-02-14 | 2022-03-03 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037710 | General Block Work | 13 | 2022-03-15 | 2022-03-29 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037720 | Marking & Chasing Walls for MEP Services | 11 | 2022-03-29 | 2022-04-11 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037730 | Ceiling Grid / Support Works | 11 | 2022-06-25 | 2022-07-07 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037740 | Wall Finishes (Plaster Board Lining & Interior Paint) | 22 | 2022-06-14 | 2022-07-13 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037750 | Ceiling Finishes | 14 | 2022-07-07 | 2022-07-28 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037760 | Floor Finishes (Epoxy Resin Flooring) | 11 | 2022-07-28 | 2022-08-11 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037770 | Door Frames & Architrave Fixing | 6 | 2022-08-11 | 2022-08-18 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037780 | Door Shuttering & Ironmongery | 10 | 2022-08-18 | 2022-08-30 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037790 | Joinery Fixing | 11 | 2023-04-08 | 2023-04-23 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-037800 | Final Finishes | 10 | 2023-04-23 | 2023-05-03 | 01 | 04 | 01 | 46 | 001 | 05 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
KITCHEN AREAS (FIT OUT BY TENANT)- NORTH |  | 86 | 2022-05-15 | 2022-08-27
C-PW-037810 | Shell and Core Scope (Block works) | 22 | 2022-05-15 | 2022-06-09 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037820 | Access for Kitchen Fitout Works | 0 | 2022-08-27 |  | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
CIRCULATIONS & CORRIDORS- NORTH |  | 70 | 2022-02-27 | 2022-05-22
C-PW-037830 | Wall Finishes | 22 | 2022-02-27 | 2022-03-24 | 01 | 04 | 01 | 46 | 001 | 01 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-037840 | Ceiling Finishes | 22 | 2022-03-31 | 2022-04-26 | 01 | 04 | 01 | 46 | 001 | 01 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-037850 | Floor Finishes | 22 | 2022-04-23 | 2022-05-22 | 01 | 04 | 01 | 46 | 001 | 01 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
STAFF TOILETS - EAST |  | 477 | 2021-10-07 | 2023-05-06
C-PW-037860 | General Block Work | 11 | 2021-10-07 | 2021-10-21 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037870 | Marking & Chasing Walls for MEP Services | 11 | 2022-01-12 | 2022-01-25 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037880 | Plastering Works - Walls | 14 | 2022-06-18 | 2022-07-04 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037890 | Floor Waterproofing Works | 8 | 2022-07-23 | 2022-08-01 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037900 | Floor Screed Works | 5 | 2022-08-02 | 2022-08-07 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037910 | Paint 1st Coat - Walls (Primer, Paint Base Coat) | 10 | 2022-08-07 | 2022-08-18 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037920 | Wall Finishes | 11 | 2022-08-07 | 2022-08-20 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037930 | Ceiling Grid / Support Works | 14 | 2022-08-18 | 2022-09-04 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037940 | Ceiling Finishes (Gypsum Tiles) | 14 | 2022-09-04 | 2022-09-21 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037950 | Floor Finishes (Ceramic Tiles) | 11 | 2022-09-21 | 2022-10-04 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037960 | Door Frames & Architrave Fixing | 6 | 2022-10-04 | 2022-10-12 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037970 | Door Shuttering & Ironmongery | 10 | 2022-10-12 | 2022-10-24 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037980 | Joinery Fixing | 10 | 2023-04-08 | 2023-04-18 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-037990 | Installation of Lockers | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038000 | Final Finishes | 6 | 2023-04-29 | 2023-05-06 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
CHILLED WATER PUMP ROOM - ETS ROOM - WEST |  | 252 | 2022-01-19 | 2022-11-19
C-PW-038010 | Equipment Foundation Works | 11 | 2022-01-19 | 2022-02-01 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038020 | Paint 1st Coat - Ceiling & Wall (Primer, Paint Base Coat) | 8 | 2022-02-01 | 2022-02-10 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038030 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-03-09 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038040 | Floor Finishes (Epoxy Resin Flooring) | 14 | 2022-09-11 | 2022-09-27 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038050 | Door Frame, Shutter & Ironmongery | 10 | 2022-09-27 | 2022-10-10 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038060 | Final Finishes | 22 | 2022-10-24 | 2022-11-19 | 01 | 04 | 01 | 46 | 001 | 02 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
MALE & FEMALE PRAYER ROOM, LOBBY, ABLUTION AND TOILET - WEST |  | 390 | 2022-01-19 | 2023-05-03
C-PW-038070 | General Block Work | 13 | 2022-01-19 | 2022-02-03 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038080 | Marking & Chasing Walls for MEP Services | 11 | 2022-02-05 | 2022-02-17 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038090 | Plastering Works - Walls | 11 | 2022-03-06 | 2022-03-19 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038100 | Floor Waterproofing Works | 8 | 2022-06-11 | 2022-06-19 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038110 | Floor Screed Works | 5 | 2022-06-20 | 2022-06-25 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038120 | Wall Finishes (Plaster Board and Ceramic Wall Tiling) | 19 | 2022-06-25 | 2022-07-20 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038130 | Paint 1st Coat - Walls (Primer, Paint Base Coat) | 10 | 2022-07-21 | 2022-08-02 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038140 | Ceiling Grid / Support Works | 14 | 2022-08-02 | 2022-08-18 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038150 | Ceiling Finishes (Gypsum Tiles) | 14 | 2022-08-20 | 2022-09-05 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038160 | Floor Finishes | 11 | 2022-09-05 | 2022-09-18 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038170 | Door Frames & Architrave Fixing | 6 | 2022-09-18 | 2022-09-25 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038180 | Door Shuttering & Ironmongery | 6 | 2022-10-22 | 2022-10-29 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038190 | Joinery Fixing | 10 | 2023-04-08 | 2023-04-18 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038200 | Installation of Lockers | 5 | 2023-04-18 | 2023-04-26 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-038210 | Final Finishes | 6 | 2023-04-26 | 2023-05-03 | 01 | 04 | 01 | 46 | 001 | 03 |  | Building | Architecture | Museum | North West | L-B1 Basement Level | Wet Areas
NORTH EAST |  | 268 | 2021-12-09 | 2022-10-29
COMMON FLOOR WORKS - EAST |  | 29 | 2021-12-09 | 2022-01-12
C-PW-038220 | General Block Work - MEP Rooms | 14 | 2021-12-09 | 2021-12-26 | 01 | 04 | 01 | 44 | 001 | 01 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-038230 | Marking & Chasing Walls for MEP Services | 14 | 2021-12-26 | 2022-01-12 | 01 | 04 | 01 | 44 | 001 | 01 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
MECHANICAL PLANT - EAST |  | 248 | 2022-01-03 | 2022-10-29
C-PW-038240 | Equipment Foundation Works | 14 | 2022-01-03 | 2022-01-18 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038250 | Paint 1st Coat - Wall & Ceiling (Primer, Paint Base Coat) | 10 | 2022-01-19 | 2022-01-30 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038260 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-06-25 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038270 | Floor Finishes (Epoxy Resin Flooring) | 22 | 2022-08-01 | 2022-08-27 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038280 | Door Frame, Shutter & Ironmongery | 10 | 2022-08-27 | 2022-09-07 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038290 | Final Finishes | 22 | 2022-10-02 | 2022-10-29 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL PLANT & UPS ROOM 2 - EAST |  | 210 | 2022-01-03 | 2022-09-12
C-PW-038300 | Equipment Foundation Works | 14 | 2022-01-03 | 2022-01-18 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038310 | Floor Trench Works | 14 | 2022-01-19 | 2022-02-05 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038320 | Paint 1st Coat - Ceiling and Wall (Primer, Paint Base Coat) | 10 | 2022-02-05 | 2022-02-15 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038330 | Grating Works | 10 | 2022-05-15 | 2022-05-26 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038340 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-05-31 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038350 | Floor Finishes (Epoxy Resin Flooring) | 19 | 2022-06-16 | 2022-07-09 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038360 | Door Frame, Shutter & Ironmongery | 10 | 2022-07-13 | 2022-07-24 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038370 | Final Finishes | 22 | 2022-08-17 | 2022-09-12 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
STANDBY CHILLER 1- EAST |  | 225 | 2022-01-03 | 2022-09-29
C-PW-038380 | Equipment Foundation Works | 14 | 2022-01-03 | 2022-01-18 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038390 | Paint 1st Coat - Ceiling and Wall (Primer, Paint Base Coat) | 10 | 2022-01-19 | 2022-01-30 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038400 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-06-07 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038410 | Floor Finishes (Epoxy Flooring and Raised Floor) | 14 | 2022-07-06 | 2022-07-26 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038420 | Door Frame, Shutter & Ironmongery | 6 | 2022-07-26 | 2022-08-03 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038430 | Final Finishes | 22 | 2022-09-04 | 2022-09-29 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
STANDY BY ICE STORAGE TANKS - EAST |  | 214 | 2022-01-03 | 2022-09-17
C-PW-038440 | Equipment Foundation Works | 14 | 2022-01-03 | 2022-01-18 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038450 | Paint 1st Coat - Ceiling and Wall (Primer, Paint Base Coat) | 10 | 2022-01-19 | 2022-01-30 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038460 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-06-07 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038470 | Floor Finishes (Epoxy Flooring and Raised Floor) | 14 | 2022-07-19 | 2022-08-06 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038480 | Door Frame, Shutter & Ironmongery | 6 | 2022-08-07 | 2022-08-14 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-038490 | Final Finishes | 22 | 2022-08-22 | 2022-09-17 | 01 | 04 | 01 | 44 | 001 | 02 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
CIRCULATIONS & CORRIDORS - EAST |  | 182 | 2022-02-15 | 2022-09-24
C-PW-038500 | Wall Finishes | 22 | 2022-02-15 | 2022-03-13 | 01 | 04 | 01 | 44 | 001 | 01 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-038510 | Ceiling Finishes | 22 | 2022-03-09 | 2022-04-05 | 01 | 04 | 01 | 44 | 001 | 01 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-038520 | Floor Finishes | 22 | 2022-04-05 | 2022-05-04 | 01 | 04 | 01 | 44 | 001 | 01 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-038530 | Roller Shutter Installation | 7 | 2022-09-15 | 2022-09-24 | 01 | 04 | 01 | 44 | 001 | 01 |  | Building | Architecture | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
SOUTH WEST |  | 405 | 2022-01-03 | 2023-05-03
COMMON FLOOR WORKS - WEST |  | 29 | 2022-01-03 | 2022-02-05
C-PW-038540 | General Block Work - MEP Rooms | 14 | 2022-01-03 | 2022-01-19 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-038550 | Marking & Chasing Walls for MEP Services | 14 | 2022-01-19 | 2022-02-05 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
MECHANICAL PLANT ROOM - WEST |  | 197 | 2022-01-08 | 2022-09-01
C-PW-038560 | Equipment Foundation Works | 11 | 2022-01-08 | 2022-01-19 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038570 | Paint 1st Coat - Ceiling & Wall (Primer, Paint Base Coat) | 11 | 2022-01-20 | 2022-02-02 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038580 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-04-26 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038590 | Floor Finishes (Epoxy Resin Flooring) | 14 | 2022-06-21 | 2022-07-07 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038600 | Door Frame, Shutter & Ironmongery | 10 | 2022-07-07 | 2022-07-23 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038610 | Final Finishes | 22 | 2022-08-07 | 2022-09-01 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
CANADIAN DUCT AHU - WEST |  | 192 | 2022-01-08 | 2022-08-27
C-PW-038620 | Equipment Foundation Works | 11 | 2022-01-08 | 2022-01-19 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038630 | Paint 1st Coat - Ceiling & Wall (Primer, Paint Base Coat) | 10 | 2022-01-20 | 2022-01-31 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038640 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-04-13 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038650 | Floor Finishes (Epoxy Resin Flooring) | 14 | 2022-05-19 | 2022-06-05 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038660 | Door Frame, Shutter & Ironmongery | 10 | 2022-06-05 | 2022-06-16 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038670 | Final Finishes | 22 | 2022-08-01 | 2022-08-27 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
MAIN LV SWITCH ROOM 1 - WEST |  | 255 | 2022-01-19 | 2022-11-22
C-PW-038680 | Equipment Foundation | 17 | 2022-01-19 | 2022-02-08 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038690 | Floor Trench Works | 14 | 2022-02-08 | 2022-02-24 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038700 | Paint 1st Coat - Ceiling and Wall (Primer, Paint Base Coat) | 10 | 2022-02-24 | 2022-03-08 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038710 | Grating Works | 5 | 2022-04-25 | 2022-04-30 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038720 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-04-30 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038730 | Floor Finishes (Epoxy Flooring and Raised Floor) | 14 | 2022-06-11 | 2022-06-28 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038740 | Door Frame, Shutter & Ironmongery | 6 | 2022-06-28 | 2022-07-05 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038750 | Final Finishes | 22 | 2022-10-26 | 2022-11-22 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL PLANT ROOM - WEST |  | 255 | 2022-01-19 | 2022-11-22
C-PW-038760 | Equipment Foundation | 11 | 2022-01-19 | 2022-02-01 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038770 | Floor Trench Works | 14 | 2022-02-01 | 2022-02-17 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038780 | Paint 1st Coat - Ceiling and Wall (Primer, Paint Base Coat) | 10 | 2022-02-17 | 2022-03-01 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038790 | Grating Works | 5 | 2022-03-27 | 2022-03-31 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038800 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-04-25 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038810 | Floor Finishes (Epoxy Flooring and Raised Floor) | 14 | 2022-04-17 | 2022-05-08 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038820 | Door Frame, Shutter & Ironmongery | 6 | 2022-05-08 | 2022-05-15 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038830 | Final Finishes | 22 | 2022-10-26 | 2022-11-22 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
TSE INTAKE / CONDENSATE TANK - WEST |  | 96 | 2022-01-19 | 2022-05-15
C-PW-038840 | Equipment Foundation Works | 14 | 2022-01-19 | 2022-02-05 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038850 | Installation of Metal Access Ladders | 5 | 2022-03-09 | 2022-03-14 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038860 | Water Tanks Leakage Testing | 2 | 2022-03-14 | 2022-03-16 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038870 | Final Finishes & Fittings | 14 | 2022-04-25 | 2022-05-15 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
IT/AV STORE & MOTOR ROOM 2 - WEST |  | 72 | 2022-05-30 | 2022-08-27
C-PW-038880 | Plaster Works | 11 | 2022-05-30 | 2022-06-12 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038890 | Wall Finishes (Paint) | 11 | 2022-06-12 | 2022-06-25 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038900 | Ceiling Finishes | 13 | 2022-06-25 | 2022-07-13 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038910 | Door Frame, Shutter & Ironmongery | 13 | 2022-07-14 | 2022-07-28 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038920 | Floor Finishes | 19 | 2022-07-13 | 2022-08-06 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-038930 | Final Finishes | 16 | 2022-08-08 | 2022-08-27 | 01 | 04 | 01 | 47 | 001 | 02 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DOCUMENT CENTER, STORAGE, ISOLATION, ARTIFACT, SECURE STORAGE AND MUSEUM LOADING DOCK - WEST |  | 379 | 2022-02-02 | 2023-05-03
C-PW-038940 | General Block Work | 16 | 2022-02-02 | 2022-02-20 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-038950 | Marking & Chasing Walls for MEP Services | 11 | 2022-02-19 | 2022-03-03 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-038960 | Plastering Works - Walls | 11 | 2022-03-22 | 2022-04-04 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-038970 | Wall Finishes (Interior Paint) | 11 | 2022-04-20 | 2022-05-07 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-038980 | Ceiling Finishes (Dust Sealer) | 14 | 2022-04-20 | 2022-05-11 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-038990 | Floor Finishes (Epoxy Resin Flooring) | 11 | 2022-07-21 | 2022-08-04 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039000 | Door Frames & Architrave Fixing | 6 | 2022-08-04 | 2022-08-11 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039010 | Roller Shutter Installation | 26 | 2022-09-15 | 2022-10-16 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039020 | Door Shuttering & Ironmongery | 6 | 2022-10-26 | 2022-11-02 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039030 | Joinery Fixing | 11 | 2023-04-08 | 2023-04-23 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039040 | Final Finishes | 10 | 2023-04-23 | 2023-05-03 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
DOCK MASTER, SECURITY ROOM & EQUIPMENT, MAINTENANCE WORSHOP & STORAGE AND FALCON S/R ROOM - WEST |  | 363 | 2022-02-21 | 2023-05-03
C-PW-039050 | General Block Work | 16 | 2022-02-21 | 2022-03-10 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039060 | Marking & Chasing Walls for MEP Services | 11 | 2022-03-03 | 2022-03-16 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039070 | Plastering Works - Walls | 11 | 2022-04-06 | 2022-04-19 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039080 | Wall Finishes (Plaster Board Lining & Interior Paint) | 24 | 2022-06-14 | 2022-07-14 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039090 | Ceiling Grid / Support Works | 11 | 2022-08-04 | 2022-08-17 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039100 | Ceiling Finishes (Suspended Gypsum Tiles & Dust Sealer) | 14 | 2022-08-17 | 2022-09-03 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039110 | Floor Finishes (Epoxy Resin Flooring & Raised Flooring) | 11 | 2022-09-03 | 2022-09-15 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039120 | Roller Shutter Installation | 7 | 2022-09-15 | 2022-09-24 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039130 | Door Frames & Architrave Fixing | 6 | 2022-09-17 | 2022-09-24 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039140 | Door Shuttering & Ironmongery | 6 | 2022-10-31 | 2022-11-08 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039150 | Joinery Fixing | 11 | 2023-04-08 | 2023-04-23 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039160 | Final Finishes | 10 | 2023-04-23 | 2023-05-03 | 01 | 04 | 01 | 47 | 001 | 05 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
PARKING, ARRIVALS, DRIVEWAYS AND LOADING BAYS |  | 203 | 2022-02-02 | 2022-10-04
C-PW-039170 | General Block Work | 13 | 2022-02-02 | 2022-02-16 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039180 | Plastering Works - Walls | 10 | 2022-02-23 | 2022-03-06 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039190 | Ceiling Finishes | 14 | 2022-03-23 | 2022-04-09 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039200 | Wall Finishes (Exterior Paints) | 13 | 2022-04-09 | 2022-04-24 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039210 | Floor Surface preparation | 11 | 2022-04-24 | 2022-05-10 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039220 | Installation of Wheel Stopper, Speed Breaker,dock blocker and Wall Guard | 6 | 2022-05-10 | 2022-05-17 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039230 | Doors & Ironmongery | 10 | 2022-05-10 | 2022-05-22 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039240 | Installation of Barriers | 6 | 2022-05-17 | 2022-05-23 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039250 | Final Coat Paint | 10 | 2022-05-24 | 2022-06-04 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039260 | Parking Area & Road Marking | 8 | 2022-06-04 | 2022-06-13 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039270 | Installation of Balustrades, Bollards, Mirrors, Signages | 5 | 2022-06-13 | 2022-06-19 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039280 | Roller Shutter Installation | 12 | 2022-09-15 | 2022-09-28 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039290 | Final Finishes | 5 | 2022-09-29 | 2022-10-04 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
CIRCULATIONS & CORRIDORS - WEST |  | 58 | 2022-10-02 | 2022-12-12
C-PW-039300 | Wall Finishes | 22 | 2022-10-02 | 2022-10-30 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039310 | Ceiling Finishes | 22 | 2022-10-23 | 2022-11-17 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039320 | Roller Shutter Installation | 2 | 2022-11-19 | 2022-11-21 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-039330 | Floor Finishes | 22 | 2022-11-14 | 2022-12-12 | 01 | 04 | 01 | 47 | 001 | 01 |  | Building | Architecture | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
SOUTH EAST |  | 381 | 2022-01-31 | 2023-05-03
COMMON FLOOR WORKS - SOUTH |  | 29 | 2022-01-31 | 2022-03-05
C-PW-039340 | General Block Work - MEP Rooms | 14 | 2022-01-31 | 2022-02-16 | 01 | 04 | 01 | 45 | 001 | 01 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-039350 | Marking & Chasing Walls for MEP Services | 14 | 2022-02-16 | 2022-03-05 | 01 | 04 | 01 | 45 | 001 | 01 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
MECHANICAL PLANT 1 & 2 - SOUTH |  | 194 | 2022-02-16 | 2022-10-10
C-PW-039360 | Equipment Foundation Works | 0 | 2022-02-16 | 2022-02-16 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039370 | Paint 1st Coat - Wall & Ceiling (Primer, Paint Base Coat) | 10 | 2022-02-16 | 2022-02-27 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039380 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-05-25 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039390 | Floor Finishes (Epoxy Resin Flooring) | 14 | 2022-07-16 | 2022-08-02 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039400 | Door Frame, Shutter & Ironmongery | 10 | 2022-08-02 | 2022-08-14 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039410 | Final Finishes | 22 | 2022-09-13 | 2022-10-10 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
HEATING & CALORIFIER ROOMS - SOUTH |  | 176 | 2022-02-16 | 2022-09-17
C-PW-039420 | Equipment Foundation Works | 14 | 2022-02-16 | 2022-03-05 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039430 | Paint 1st Coat - Wall & Ceiling (Primer, Paint Base Coat) | 10 | 2022-03-05 | 2022-03-15 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039440 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-05-19 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039450 | Floor Finishes (Epoxy Resin Flooring) | 14 | 2022-06-30 | 2022-07-20 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039460 | Door Frame, Shutter & Ironmongery | 10 | 2022-07-20 | 2022-08-01 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039470 | Final Finishes | 22 | 2022-08-22 | 2022-09-17 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
UPS ROOM 3 & ELECTRICAL PLANT ROOM - SOUTH |  | 159 | 2022-02-16 | 2022-08-29
C-PW-039480 | Equipment Foundation Works | 17 | 2022-02-16 | 2022-03-08 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039490 | Floor Trench Works | 14 | 2022-03-08 | 2022-03-24 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039500 | Paint 1st Coat - Ceiling and Wall (Primer, Paint Base Coat) | 10 | 2022-03-24 | 2022-04-05 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039510 | Grating Works | 10 | 2022-05-29 | 2022-06-09 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039520 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-06-15 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039530 | Floor Finishes (Epoxy Resin Flooring & Raised Floorings | 14 | 2022-07-02 | 2022-07-21 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039540 | Door Frame, Shutter & Ironmongery | 10 | 2022-07-23 | 2022-08-03 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039550 | Final Finishes | 14 | 2022-08-11 | 2022-08-29 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
MAIN LV SWITCH ROOM 2 - SOUTH |  | 228 | 2022-02-16 | 2022-11-19
C-PW-039560 | Equipment Foundation Works | 17 | 2022-02-16 | 2022-03-08 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039570 | Floor Trench Works | 14 | 2022-03-08 | 2022-03-24 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039580 | Paint 1st Coat - Ceiling and Wall (Primer, Paint Base Coat) | 10 | 2022-03-24 | 2022-04-05 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039590 | Grating Works | 10 | 2022-06-15 | 2022-06-26 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039600 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-06-26 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039610 | Floor Finishes (Epoxy Resin Flooring & Raised Floorings | 14 | 2022-09-15 | 2022-10-02 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039620 | Door Frame, Shutter & Ironmongery | 10 | 2022-10-02 | 2022-10-15 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039630 | Final Finishes | 17 | 2022-10-31 | 2022-11-19 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
PHOTOGRAPHIC STUDIO & STORE ROOMS - SOUTH |  | 373 | 2022-02-09 | 2023-05-03
C-PW-039640 | General Block Work | 10 | 2022-02-09 | 2022-02-20 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039650 | Marking & Chasing Walls for MEP Services | 11 | 2022-03-05 | 2022-03-17 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039660 | Wall Finishes | 11 | 2022-04-11 | 2022-04-24 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039670 | Ceiling Finishes (Dust Sealer) | 14 | 2022-08-25 | 2022-09-12 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039680 | Floor Finishes (Epoxy Resin Flooring) | 11 | 2022-09-12 | 2022-09-25 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039690 | Door Frames & Architrave Fixing | 6 | 2022-09-25 | 2022-10-02 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039700 | Door Shuttering & Ironmongery | 6 | 2022-10-02 | 2022-10-11 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039710 | Joinery Fixing | 11 | 2023-04-08 | 2023-04-23 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039720 | Final Finishes | 10 | 2023-04-23 | 2023-05-03 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
MOTOR ROOM 1, BMS ROOM, MAIN TELECOM ROOM 2, CC3 & 4 AND ETISALAT METER 2 - SOUTH |  | 159 | 2022-04-05 | 2022-10-16
C-PW-039730 | Paint 1st Coat - Ceiling and Wall (Primer, Paint Base Coat) | 6 | 2022-04-05 | 2022-04-12 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039740 | Wall Finishes | 11 | 2022-07-04 | 2022-07-20 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039750 | Ceiling Finishes (Dust Sealer) | 13 | 2022-07-20 | 2022-08-06 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039760 | Floor Finishes (Epoxy Flooring and Raised Floors) | 14 | 2022-08-06 | 2022-08-22 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039770 | Door Frame, Shutter & Ironmongery | 13 | 2022-08-22 | 2022-09-06 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-039780 | Final Finishes | 16 | 2022-09-27 | 2022-10-16 | 01 | 04 | 01 | 45 | 001 | 02 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
COLLECTION STORAGE 1 & 2 - SOUTH |  | 381 | 2022-01-31 | 2023-05-03
C-PW-039790 | General Block Work | 10 | 2022-01-31 | 2022-02-10 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039800 | Marking & Chasing Walls for MEP Services | 11 | 2022-03-05 | 2022-03-17 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039810 | Wall Finishes | 11 | 2022-04-14 | 2022-04-27 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039820 | Ceiling Finishes (Dust Sealer) | 14 | 2022-08-28 | 2022-09-13 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039830 | Roller Shutter Installation | 10 | 2022-09-15 | 2022-09-26 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039840 | Floor Finishes (Epoxy Resin Flooring) | 11 | 2022-09-13 | 2022-09-26 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039850 | Door Frames & Architrave Fixing | 6 | 2022-09-27 | 2022-10-04 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039860 | Door Shuttering & Ironmongery | 6 | 2022-10-04 | 2022-10-12 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039870 | Joinery Fixing | 11 | 2023-04-08 | 2023-04-23 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-039880 | Final Finishes | 10 | 2023-04-23 | 2023-05-03 | 01 | 04 | 01 | 45 | 001 | 05 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
CIRCULATIONS & CORRIDORS - SOUTH |  | 68 | 2022-09-27 | 2022-12-17
C-PW-039890 | Wall Finishes | 22 | 2022-09-27 | 2022-10-24 | 01 | 04 | 01 | 45 | 001 | 01 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-039900 | Ceiling Finishes | 22 | 2022-10-15 | 2022-11-09 | 01 | 04 | 01 | 45 | 001 | 01 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-039910 | Floor Finishes | 22 | 2022-11-20 | 2022-12-17 | 01 | 04 | 01 | 45 | 001 | 01 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
WC'S, STAFF CHANGING ROOMS AND VIP PANTRY - WEST |  | 347 | 2022-03-12 | 2023-05-03
C-PW-039920 | General Block Work | 13 | 2022-03-12 | 2022-03-26 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-039930 | Marking & Chasing Walls for MEP Services | 11 | 2022-03-16 | 2022-03-29 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-039940 | Plastering Works - Walls | 11 | 2022-04-25 | 2022-05-11 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-039950 | Floor Waterproofing Works | 8 | 2022-06-04 | 2022-06-13 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-039960 | Floor Screed Works | 5 | 2022-06-13 | 2022-06-18 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-039970 | Wall Finishes (Ceramic Wall Tiling) | 19 | 2022-07-16 | 2022-08-08 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-039980 | Paint 1st Coat - Walls (Primer, Paint Base Coat) | 10 | 2022-08-04 | 2022-08-16 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-039990 | Ceiling Grid / Support Works | 14 | 2022-08-16 | 2022-09-01 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-040000 | Ceiling Finishes (Gypsum Tiles) | 14 | 2022-09-01 | 2022-09-19 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-040010 | Floor Finishes (Ceramic Tiles) | 11 | 2022-09-19 | 2022-10-02 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-040020 | Door Frames & Architrave Fixing | 6 | 2022-10-02 | 2022-10-10 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-040030 | Door Shuttering & Ironmongery | 6 | 2022-10-10 | 2022-10-18 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-040040 | Joinery Fixing | 10 | 2023-04-08 | 2023-04-18 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-040050 | Installation of Lockers | 5 | 2023-04-18 | 2023-04-26 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
C-PW-040060 | Final Finishes | 6 | 2023-04-26 | 2023-05-03 | 01 | 04 | 01 | 45 | 001 | 03 |  | Building | Architecture | Museum | South East | L-B1 Basement Level | Wet Areas
MEP WORKS |  | 492 | 2021-09-30 | 2023-05-16
NORTH WEST |  | 492 | 2021-09-30 | 2023-05-16
MECHANICAL PLANT ROOM A & B - NORTH |  | 190 | 2022-02-05 | 2022-09-22
MECHANICAL |  | 167 | 2022-02-05 | 2022-08-27
HVAC |  | 167 | 2022-02-05 | 2022-08-27
C-PW-040070 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs & Leakage Test) | 57 | 2022-02-05 | 2022-04-12 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040080 | 1st Fix HVAC (CHW Piping, LTHW & Pressure Testing) | 57 | 2022-02-07 | 2022-04-14 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040090 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 14 | 2022-04-14 | 2022-05-04 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040100 | AHU Installation incl valve packages | 31 | 2022-04-20 | 2022-05-30 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040110 | Duct Connection incl. S.Attenuator ,CHW Connection, joint Insulation & Electrical Connection | 42 | 2022-04-20 | 2022-06-12 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040120 | Cladding Works incl Labels | 23 | 2022-06-12 | 2022-07-09 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040130 | Final Fix HVAC (Louvers/Wire Mesh, Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-08-18 | 2022-08-27 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 71 | 2022-02-05 | 2022-04-28
C-PW-040140 | 1st Fix Piping System (Supports, Piping) | 47 | 2022-02-05 | 2022-03-31 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040150 | 2nd Fix Piping System (Fittings & Insulation) | 20 | 2022-03-31 | 2022-04-24 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040160 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 4 | 2022-04-24 | 2022-04-28 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 70 | 2022-03-31 | 2022-06-25
C-PW-040170 | 1st Fix Piping System (Supports, Piping) | 47 | 2022-03-31 | 2022-05-29 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040180 | 2nd Fix Piping System (Fittings & Insulation) | 21 | 2022-05-29 | 2022-06-22 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040190 | Final Fix Installation (Bip Tap) | 2 | 2022-06-22 | 2022-06-25 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 172 | 2022-02-05 | 2022-09-01
C-PW-040200 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-02-05 | 2022-02-20 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040210 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 47 | 2022-02-07 | 2022-04-03 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040220 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 38 | 2022-04-04 | 2022-05-21 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040230 | LV Switchgears (SMDB's, MCC's & DB's) | 16 | 2022-05-21 | 2022-06-08 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040240 | Cable/Wire Termination & Dressing | 16 | 2022-06-08 | 2022-06-27 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040250 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-08-18 | 2022-08-27 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040260 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-21 | 2022-08-29 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040270 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-22 | 2022-08-30 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040280 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-24 | 2022-09-01 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 188 | 2022-02-07 | 2022-09-22
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 188 | 2022-02-07 | 2022-09-22
C-PW-040290 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 28 | 2022-02-07 | 2022-03-10 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040300 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 16 | 2022-04-04 | 2022-04-21 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040310 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 7 | 2022-09-14 | 2022-09-22 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 187 | 2022-02-08 | 2022-09-22
C-PW-040320 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 28 | 2022-02-08 | 2022-03-13 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040330 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 16 | 2022-04-04 | 2022-04-21 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040340 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 7 | 2022-09-14 | 2022-09-22 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 185 | 2022-02-10 | 2022-09-22
C-PW-040350 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 28 | 2022-02-10 | 2022-03-15 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040360 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 16 | 2022-04-05 | 2022-04-24 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040370 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 7 | 2022-09-14 | 2022-09-22 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 187 | 2022-02-08 | 2022-09-22
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 187 | 2022-02-08 | 2022-09-22
C-PW-040380 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 28 | 2022-02-08 | 2022-03-13 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040390 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 16 | 2022-04-04 | 2022-04-21 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040400 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 7 | 2022-09-14 | 2022-09-22 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 185 | 2022-02-10 | 2022-09-22
C-PW-040410 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 28 | 2022-02-10 | 2022-03-15 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040420 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 16 | 2022-04-05 | 2022-04-24 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040430 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 7 | 2022-09-14 | 2022-09-22 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 163 | 2022-02-10 | 2022-08-27
C-PW-040440 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 47 | 2022-02-10 | 2022-04-06 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040450 | 2nd Fix Piping System - (Fittings) | 35 | 2022-04-06 | 2022-05-21 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040460 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-08-18 | 2022-08-27 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
MAIN TEL. ROOM 1, CCU1 & 2, ETISALAT METER 1 NORTH |  | 114 | 2022-03-08 | 2022-07-26
MECHANICAL |  | 114 | 2022-03-08 | 2022-07-26
HVAC |  | 82 | 2022-04-14 | 2022-07-26
C-PW-040470 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 14 | 2022-04-14 | 2022-05-04 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040480 | 1st Fix HVAC (CHW Piping) | 14 | 2022-04-18 | 2022-05-07 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040490 | 2nd Fix HVAC (CRAC Units) | 10 | 2022-05-07 | 2022-05-18 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040500 | Final Fix HVAC (Grills, Diffusers) | 7 | 2022-07-18 | 2022-07-26 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 24 | 2022-03-08 | 2022-04-05
C-PW-040510 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-08 | 2022-03-24 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040520 | 2nd Fix Piping System (Fittings & Insulation) | 10 | 2022-03-24 | 2022-04-05 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 111 | 2022-03-08 | 2022-07-23
C-PW-040530 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-03-08 | 2022-03-20 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040540 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-04-18 | 2022-05-08 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040550 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-08 | 2022-05-23 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040560 | LV Switchgears (DB's) | 5 | 2022-05-24 | 2022-05-29 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040570 | Cable/Wire Termination & Dressing | 16 | 2022-05-29 | 2022-06-16 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040580 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-07-05 | 2022-07-17 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040590 | Final Fix Electrical (Light Fixtures) | 7 | 2022-07-07 | 2022-07-19 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040600 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-07-13 | 2022-07-21 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040610 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-07-14 | 2022-07-23 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 102 | 2022-03-21 | 2022-07-24
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 91 | 2022-03-21 | 2022-07-09
C-PW-040620 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-21 | 2022-04-02 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040630 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-08 | 2022-05-19 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040640 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-07-05 | 2022-07-09 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 90 | 2022-03-22 | 2022-07-09
C-PW-040650 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-22 | 2022-04-03 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040660 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-10 | 2022-05-23 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040670 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-07-05 | 2022-07-09 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 90 | 2022-03-24 | 2022-07-14
C-PW-040680 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-24 | 2022-04-05 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040690 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-12 | 2022-05-24 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040700 | Server panels Installation & Connections | 16 | 2022-05-24 | 2022-06-12 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040710 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-07-09 | 2022-07-14 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 91 | 2022-03-26 | 2022-07-17
C-PW-040720 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-07 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040730 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040740 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-07-14 | 2022-07-17 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-07-18 | 2022-07-24
C-PW-040750 | Active Component System Works | 6 | 2022-07-18 | 2022-07-24 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 85 | 2022-04-05 | 2022-07-20
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 82 | 2022-04-05 | 2022-07-17
C-PW-040760 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-05 | 2022-04-17 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040770 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-08 | 2022-05-19 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040780 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-14 | 2022-07-17 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 83 | 2022-04-07 | 2022-07-20
C-PW-040790 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-07 | 2022-04-19 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040800 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-10 | 2022-05-22 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040810 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-07-18 | 2022-07-20 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 76 | 2022-04-13 | 2022-07-17
C-PW-040820 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-04-13 | 2022-04-28 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040830 | 2nd Fix Piping System - (Fittings) | 10 | 2022-05-22 | 2022-06-02 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040840 | Final Fix- (Installation FM200, Sprinkler Heads for Gas Fire Suppression System) | 7 | 2022-07-05 | 2022-07-17 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
GREASE TRAP ROOM- NORTH |  | 108 | 2022-03-08 | 2022-07-19
MECHANICAL |  | 102 | 2022-03-08 | 2022-07-09
HVAC |  | 70 | 2022-04-14 | 2022-07-09
C-PW-040850 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 7 | 2022-04-14 | 2022-04-23 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040860 | 1st Fix HVAC (CHW Piping) | 7 | 2022-04-18 | 2022-04-26 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040870 | 2nd Fix HVAC (FCUs, Droppers, Dampers) | 3 | 2022-04-26 | 2022-04-30 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040880 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 3 | 2022-07-05 | 2022-07-09 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 17 | 2022-03-08 | 2022-03-28
C-PW-040890 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-03-08 | 2022-03-19 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040900 | 2nd Fix Piping System & Grease Interceptor (Fittings, accessories & Insulation) | 7 | 2022-03-19 | 2022-03-27 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040910 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 1 | 2022-03-27 | 2022-03-28 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 108 | 2022-03-08 | 2022-07-19
C-PW-040920 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 6 | 2022-03-08 | 2022-03-15 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040930 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 7 | 2022-04-18 | 2022-04-26 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040940 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 7 | 2022-04-27 | 2022-05-09 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040950 | LV Switchgears (DB's) | 2 | 2022-05-09 | 2022-05-11 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040960 | Cable/Wire Termination & Dressing | 7 | 2022-05-11 | 2022-05-19 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040970 | Final Fix Electrical (Power Socket / Isolators) | 3 | 2022-07-05 | 2022-07-09 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040980 | Final Fix Electrical (Installation of Lighting Control Panels) | 3 | 2022-07-13 | 2022-07-17 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-040990 | Final Fix Electrical (Installation of Lighting Control Devices) | 3 | 2022-07-14 | 2022-07-18 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041000 | Final Fix Electrical (Light Fixtures) | 7 | 2022-07-07 | 2022-07-19 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 96 | 2022-03-15 | 2022-07-09
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 96 | 2022-03-15 | 2022-07-09
C-PW-041010 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 6 | 2022-03-15 | 2022-03-21 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041020 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 6 | 2022-04-27 | 2022-05-07 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041030 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-07-05 | 2022-07-09 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 94 | 2022-03-16 | 2022-07-09
C-PW-041040 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 6 | 2022-03-16 | 2022-03-23 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041050 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 6 | 2022-04-27 | 2022-05-07 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041060 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-07-05 | 2022-07-09 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 95 | 2022-03-19 | 2022-07-14
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 93 | 2022-03-19 | 2022-07-09
C-PW-041070 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 6 | 2022-03-19 | 2022-03-24 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041080 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 6 | 2022-04-27 | 2022-05-07 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041090 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-05 | 2022-07-09 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 94 | 2022-03-21 | 2022-07-14
C-PW-041100 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 6 | 2022-03-21 | 2022-03-27 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041110 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 6 | 2022-04-28 | 2022-05-09 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041120 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-07-09 | 2022-07-14 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 71 | 2022-04-13 | 2022-07-09
C-PW-041130 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 7 | 2022-04-13 | 2022-04-21 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041140 | 2nd Fix Piping System - (Fittings) | 6 | 2022-05-09 | 2022-05-15 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041150 | Final Fix- (Installation of Sprinkler Heads) | 2 | 2022-07-05 | 2022-07-09 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL PLANT & UPS 1 - NORTH |  | 110 | 2022-02-21 | 2022-07-03
MECHANICAL |  | 82 | 2022-03-01 | 2022-06-07
HVAC |  | 82 | 2022-03-01 | 2022-06-07
C-PW-041160 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-03-01 | 2022-03-22 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041170 | 1st Fix HVAC (CHW Piping) | 18 | 2022-03-03 | 2022-03-24 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041180 | 2nd Fix HVAC (CRAC Unit) | 14 | 2022-03-26 | 2022-04-10 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041190 | Final Fix HVAC (Grills, Diffusers) | 7 | 2022-05-30 | 2022-06-07 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 32 | 2022-03-01 | 2022-04-07
C-PW-041200 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-01 | 2022-03-22 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041210 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-03-22 | 2022-04-07 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 110 | 2022-02-21 | 2022-07-03
C-PW-041220 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-02-21 | 2022-03-08 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041230 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-02-23 | 2022-03-16 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041240 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-03-16 | 2022-04-07 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041250 | LV Switchgears (SMDB's, Cap. Bank, MCC's & DB's) | 10 | 2022-05-19 | 2022-05-31 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041260 | Busduct Installation & Connections | 10 | 2022-05-31 | 2022-06-12 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041270 | Cable/Wire Termination & Dressing | 16 | 2022-05-31 | 2022-06-19 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041280 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-06-19 | 2022-06-27 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041290 | Final Fix Electrical (Light Fixtures) | 7 | 2022-06-21 | 2022-06-29 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041300 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-06-22 | 2022-06-30 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041310 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-06-25 | 2022-07-03 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 82 | 2022-02-22 | 2022-06-01
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 82 | 2022-02-22 | 2022-06-01
C-PW-041320 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-22 | 2022-03-06 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041330 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-16 | 2022-03-29 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041340 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-05-30 | 2022-06-01 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 81 | 2022-02-24 | 2022-06-01
C-PW-041350 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-24 | 2022-03-08 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041360 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-20 | 2022-03-31 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041370 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-05-30 | 2022-06-01 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 79 | 2022-02-26 | 2022-06-01
C-PW-041380 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-26 | 2022-03-10 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041390 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-22 | 2022-04-03 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041400 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-05-30 | 2022-06-01 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 77 | 2022-03-08 | 2022-06-09
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 70 | 2022-03-08 | 2022-06-01
C-PW-041410 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-08 | 2022-03-20 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041420 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-21 | 2022-04-02 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041430 | UPS & Battery Panels Installation & Connections | 10 | 2022-04-02 | 2022-04-13 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041440 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-05-30 | 2022-06-01 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 70 | 2022-03-08 | 2022-06-01
C-PW-041450 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-08 | 2022-03-20 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041460 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-22 | 2022-04-03 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041470 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-05-30 | 2022-06-01 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 65 | 2022-03-22 | 2022-06-09
C-PW-041480 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 18 | 2022-03-22 | 2022-04-12 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041490 | 2nd Fix Piping System - (Fittings) | 14 | 2022-04-13 | 2022-04-28 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-041500 | Final Fix- (Installation FM200, Sprinkler Heads for Gas Fire Suppression System) | 9 | 2022-05-30 | 2022-06-09 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ADMIN CANTEEN, LOBBY - NORTH |  | 170 | 2022-02-14 | 2022-09-08
MECHANICAL |  | 142 | 2022-02-14 | 2022-08-08
HVAC SYSTEM WORKS |  | 80 | 2022-04-28 | 2022-08-08
C-PW-041510 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-04-28 | 2022-05-23 | 01 | 06 | 01 | 46 | 001 | 05 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041520 | 1st Fix HVAC (CHW Piping & Drain Pipes) | 18 | 2022-05-04 | 2022-05-26 | 01 | 06 | 01 | 46 | 001 | 05 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041530 | 2nd Fix HVAC (FCUs, Droppers, Dampers & Fans) | 14 | 2022-05-26 | 2022-06-11 | 01 | 06 | 01 | 46 | 001 | 05 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041540 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-07-28 | 2022-08-08 | 01 | 06 | 01 | 46 | 001 | 05 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 32 | 2022-02-14 | 2022-03-23
C-PW-041550 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-02-14 | 2022-03-08 | 01 | 08 | 01 | 46 | 001 | 05 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041560 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-03-08 | 2022-03-23 | 01 | 08 | 01 | 46 | 001 | 05 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 32 | 2022-04-12 | 2022-05-22
C-PW-041570 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-12 | 2022-05-07 | 01 | 08 | 01 | 46 | 001 | 05 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041580 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-05-07 | 2022-05-22 | 01 | 08 | 01 | 46 | 001 | 05 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 146 | 2022-02-16 | 2022-08-14
C-PW-041590 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-02-16 | 2022-03-05 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041600 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-05-05 | 2022-05-26 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041610 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-28 | 2022-06-12 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041620 | Final Fix Electrical (Power Sockets/ Isolators) | 8 | 2022-07-28 | 2022-08-08 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041630 | Final Fix Electrical (Light Fixtures) | 7 | 2022-07-31 | 2022-08-08 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041640 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-06 | 2022-08-14 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
ELV |  | 160 | 2022-02-19 | 2022-09-01
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 101 | 2022-02-19 | 2022-06-19
C-PW-041650 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-19 | 2022-03-02 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041660 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041670 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-06-16 | 2022-06-19 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 99 | 2022-02-21 | 2022-06-19
C-PW-041680 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-02-21 | 2022-03-05 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041690 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-30 | 2022-06-11 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041700 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-06-16 | 2022-06-19 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 157 | 2022-02-22 | 2022-09-01
C-PW-041710 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-22 | 2022-03-06 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041720 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-01 | 2022-06-14 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041730 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 156 | 2022-02-24 | 2022-09-01
C-PW-041740 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-24 | 2022-03-08 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041750 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-05 | 2022-06-16 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041760 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEMS |  | 160 | 2022-02-26 | 2022-09-08
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 156 | 2022-02-26 | 2022-09-05
C-PW-041770 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-26 | 2022-03-10 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041780 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-07 | 2022-06-19 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041790 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-01 | 2022-09-05 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 155 | 2022-02-28 | 2022-09-05
C-PW-041800 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-02-28 | 2022-03-12 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041810 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-11 | 2022-06-22 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041820 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-01 | 2022-09-05 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 101 | 2022-05-09 | 2022-09-08
C-PW-041830 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-05-09 | 2022-05-26 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041840 | 2nd Fix Piping System - (Fittings) | 12 | 2022-06-11 | 2022-06-23 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-041850 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-30 | 2022-09-08 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
KITCHEN AREAS - NORTH |  | 63 | 2022-06-09 | 2022-08-27
MECHANICAL |  | 22 | 2022-06-09 | 2022-07-04
DRAINAGE WORKS |  | 22 | 2022-06-09 | 2022-07-04
C-PW-041860 | Shell and Core Scope | 22 | 2022-06-09 | 2022-07-04 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
HOT & COLD WATER SYSTEM |  | 22 | 2022-06-09 | 2022-07-04
C-PW-041870 | Shell and Core Scope | 22 | 2022-06-09 | 2022-07-04 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
LIFE AND SAFETY SYSTEMS |  | 42 | 2022-07-05 | 2022-08-27
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 16 | 2022-07-05 | 2022-07-26
C-PW-041880 | Shell and Core Scope | 16 | 2022-07-05 | 2022-07-26 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 16 | 2022-07-23 | 2022-08-11
C-PW-041890 | Shell and Core Scope | 16 | 2022-07-23 | 2022-08-11 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
FIRE FIGHTING |  | 16 | 2022-08-08 | 2022-08-27
C-PW-041900 | Shell and Core Scope | 16 | 2022-08-08 | 2022-08-27 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
CIRCULATIONS & CORRIDORS- NORTH |  | 204 | 2021-09-30 | 2022-06-04
MECHANICAL |  | 201 | 2021-09-30 | 2022-05-30
HVAC |  | 90 | 2022-02-12 | 2022-05-30
C-PW-041910 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-02-12 | 2022-03-05 | 01 | 06 | 01 | 46 | 001 | 01 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-041920 | 1st Fix HVAC (CHW Piping) | 18 | 2022-02-19 | 2022-03-12 | 01 | 06 | 01 | 46 | 001 | 01 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-041930 | 2nd Fix HVAC (FCUs, Droppers & Dampers) | 14 | 2022-03-12 | 2022-03-27 | 01 | 06 | 01 | 46 | 001 | 01 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-041940 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-05-22 | 2022-05-30 | 01 | 06 | 01 | 46 | 001 | 01 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
DRAINAGE WORKS |  | 42 | 2021-09-30 | 2021-11-18
C-PW-041950 | 1st Fix Piping System (Supports, Piping) | 18 | 2021-09-30 | 2021-10-23 | 01 | 06 | 01 | 46 | 001 | 01 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-041960 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2021-10-23 | 2021-11-07 | 01 | 06 | 01 | 46 | 001 | 01 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-041970 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 4 | 2021-11-08 | 2021-11-11 | 01 | 06 | 01 | 46 | 001 | 01 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-041980 | Installation & connections of Condensate Sump Pump & Foul Pumps | 6 | 2021-11-13 | 2021-11-18 | 01 | 06 | 01 | 46 | 001 | 01 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 27 | 2021-10-04 | 2021-11-06
C-PW-041990 | 1st Fix Piping System (Supports, Piping) | 14 | 2021-10-04 | 2021-10-21 | 01 | 06 | 01 | 46 | 001 | 01 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042000 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2021-10-21 | 2021-11-06 | 01 | 06 | 01 | 46 | 001 | 01 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 98 | 2022-02-05 | 2022-06-04
C-PW-042010 | 1st Fix Electrical (Conduits & boxes) - Power and Ligthing System | 14 | 2022-02-05 | 2022-02-21 | 01 | 07 | 01 | 46 | 001 | 01 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042020 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 22 | 2022-02-09 | 2022-03-06 | 01 | 07 | 01 | 46 | 001 | 01 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042030 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 22 | 2022-03-06 | 2022-03-31 | 01 | 07 | 01 | 46 | 001 | 01 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042040 | LV Switchgears (DB's) | 6 | 2022-03-31 | 2022-04-06 | 01 | 07 | 01 | 46 | 001 | 01 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042050 | Busduct Installation | 12 | 2022-03-31 | 2022-04-14 | 01 | 07 | 01 | 46 | 001 | 01 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042060 | Cable/Wire Termination & Dressing | 7 | 2022-04-06 | 2022-04-14 | 01 | 07 | 01 | 46 | 001 | 01 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042070 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-04-16 | 2022-04-24 | 01 | 07 | 01 | 46 | 001 | 01 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042080 | Final Fix Electrical (Light Fixtures) | 7 | 2022-05-22 | 2022-05-30 | 01 | 07 | 01 | 46 | 001 | 01 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042090 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-05-24 | 2022-06-01 | 01 | 07 | 01 | 46 | 001 | 01 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042100 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-05-26 | 2022-06-04 | 01 | 07 | 01 | 46 | 001 | 01 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
ELV |  | 90 | 2022-02-07 | 2022-05-26
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 89 | 2022-02-07 | 2022-05-25
C-PW-042110 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-07 | 2022-02-19 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042120 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-06 | 2022-03-17 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042130 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-05-22 | 2022-05-25 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 87 | 2022-02-09 | 2022-05-25
C-PW-042140 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-02-09 | 2022-02-21 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042150 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-03-09 | 2022-03-21 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042160 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-05-22 | 2022-05-25 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 87 | 2022-02-10 | 2022-05-26
C-PW-042170 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-10 | 2022-02-22 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042180 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-12 | 2022-03-23 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042190 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-05-24 | 2022-05-26 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 86 | 2022-02-13 | 2022-05-26
C-PW-042200 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-13 | 2022-02-24 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042210 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-14 | 2022-03-27 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042220 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-05-24 | 2022-05-26 | 01 | 10 | 01 | 46 | 001 | 01 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEMS |  | 97 | 2022-02-05 | 2022-06-01
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 86 | 2022-02-14 | 2022-05-30
C-PW-042230 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-14 | 2022-02-27 | 01 | 09 | 01 | 46 | 001 | 01 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042240 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-17 | 2022-03-29 | 01 | 09 | 01 | 46 | 001 | 01 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042250 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-05-26 | 2022-05-30 | 01 | 09 | 01 | 46 | 001 | 01 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 86 | 2022-02-14 | 2022-05-30
C-PW-042260 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-02-14 | 2022-02-27 | 01 | 09 | 01 | 46 | 001 | 01 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042270 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-19 | 2022-03-31 | 01 | 09 | 01 | 46 | 001 | 01 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042280 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-05-26 | 2022-05-30 | 01 | 09 | 01 | 46 | 001 | 01 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
FIRE FIGHTING |  | 97 | 2022-02-05 | 2022-06-01
C-PW-042290 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 18 | 2022-02-05 | 2022-02-27 | 01 | 09 | 01 | 46 | 001 | 01 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042300 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 14 | 2022-02-27 | 2022-03-14 | 01 | 09 | 01 | 46 | 001 | 01 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
C-PW-042310 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 9 | 2022-05-22 | 2022-06-01 | 01 | 09 | 01 | 46 | 001 | 01 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Circulation / Common Areas
STAFF CANTEEN, WASTE STORAGE 1 & SPECIAL EVENT STORAGE- NORTH |  | 125 | 2022-04-12 | 2022-09-13
MECHANICAL |  | 121 | 2022-04-12 | 2022-09-08
HVAC SYSTEM WORKS |  | 109 | 2022-04-26 | 2022-09-08
C-PW-042320 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-04-26 | 2022-05-22 | 01 | 06 | 01 | 46 | 001 | 05 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042330 | 1st Fix HVAC (CHW Piping & Drain Pipes) | 18 | 2022-04-30 | 2022-05-24 | 01 | 06 | 01 | 46 | 001 | 05 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042340 | 2nd Fix HVAC (FCUs, Droppers, Dampers & Fans) | 14 | 2022-05-24 | 2022-06-09 | 01 | 06 | 01 | 46 | 001 | 05 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042350 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-08-30 | 2022-09-08 | 01 | 06 | 01 | 46 | 001 | 05 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 36 | 2022-04-12 | 2022-05-26
C-PW-042360 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-12 | 2022-05-07 | 01 | 08 | 01 | 46 | 001 | 05 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042370 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-05-07 | 2022-05-22 | 01 | 08 | 01 | 46 | 001 | 05 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042380 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 4 | 2022-05-23 | 2022-05-26 | 01 | 08 | 01 | 46 | 001 | 05 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 32 | 2022-04-17 | 2022-05-28
C-PW-042390 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-17 | 2022-05-12 | 01 | 08 | 01 | 46 | 001 | 05 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042400 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-05-12 | 2022-05-28 | 01 | 08 | 01 | 46 | 001 | 05 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 123 | 2022-04-14 | 2022-09-13
C-PW-042410 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-14 | 2022-04-30 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042420 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-05-04 | 2022-05-25 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042430 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-25 | 2022-06-09 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042440 | LV Switchgears (DB's) | 5 | 2022-06-11 | 2022-06-15 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042450 | Cable/Wire Termination & Dressing | 7 | 2022-06-15 | 2022-06-23 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042460 | Final Fix Electrical (Power Sockets/ Isolators) | 8 | 2022-08-30 | 2022-09-08 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042470 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-01 | 2022-09-10 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042480 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-03 | 2022-09-11 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042490 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-05 | 2022-09-13 | 01 | 07 | 01 | 46 | 001 | 05 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
ELV |  | 113 | 2022-04-17 | 2022-09-04
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 112 | 2022-04-17 | 2022-09-01
C-PW-042500 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-17 | 2022-04-28 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042510 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042520 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 110 | 2022-04-18 | 2022-09-01
C-PW-042530 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042540 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-09 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042550 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 110 | 2022-04-20 | 2022-09-04
C-PW-042560 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-20 | 2022-05-05 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042570 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-31 | 2022-06-12 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042580 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-01 | 2022-09-04 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 109 | 2022-04-21 | 2022-09-04
C-PW-042590 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-21 | 2022-05-08 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042600 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-02 | 2022-06-14 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042610 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-01 | 2022-09-04 | 01 | 10 | 01 | 46 | 001 | 05 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEMS |  | 109 | 2022-04-24 | 2022-09-06
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 109 | 2022-04-24 | 2022-09-06
C-PW-042620 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-24 | 2022-05-09 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042630 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-06 | 2022-06-18 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042640 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-04 | 2022-09-06 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 108 | 2022-04-26 | 2022-09-06
C-PW-042650 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042660 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-07 | 2022-06-19 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042670 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-04 | 2022-09-06 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 76 | 2022-05-07 | 2022-08-08
C-PW-042680 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-05-07 | 2022-05-25 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042690 | 2nd Fix Piping System - (Fittings) | 12 | 2022-06-07 | 2022-06-21 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-042700 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-07-28 | 2022-08-08 | 01 | 09 | 01 | 46 | 001 | 05 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Storage / Offices / Admin Areas
STAFF TOILETS - EAST |  | 395 | 2022-01-26 | 2023-05-16
MECHANICAL |  | 394 | 2022-01-26 | 2023-05-15
HVAC SYSTEM WORKS |  | 390 | 2022-01-31 | 2023-05-15
C-PW-042710 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-01-31 | 2022-02-22 | 01 | 06 | 01 | 46 | 001 | 03 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042720 | 1st Fix HVAC (CHW Piping & Drain Pipes) | 18 | 2022-02-03 | 2022-02-24 | 01 | 06 | 01 | 46 | 001 | 03 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042730 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 10 | 2022-02-24 | 2022-03-08 | 01 | 06 | 01 | 46 | 001 | 03 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042740 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2023-05-06 | 2023-05-15 | 01 | 06 | 01 | 46 | 001 | 03 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Wet Areas
DRAINAGE WORKS |  | 230 | 2022-01-26 | 2022-10-30
C-PW-042750 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-01-26 | 2022-02-16 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042760 | 2nd Fix Piping System (Fittings & Insulation) | 10 | 2022-02-16 | 2022-02-28 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042770 | Final Fix (Installation of Sanitaryware & Accessories) | 6 | 2022-10-24 | 2022-10-30 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
HOT & COLD WATER SYSTEM |  | 378 | 2022-01-26 | 2023-04-26
C-PW-042780 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-01-26 | 2022-02-16 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042790 | 2nd Fix Piping System (Fittings & Insulation) | 10 | 2022-02-16 | 2022-02-28 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042800 | Electric Water Heater Installation | 2 | 2022-02-28 | 2022-03-02 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042810 | Final Fix Installation | 5 | 2023-04-18 | 2023-04-26 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
ELECTRICAL WORKS |  | 289 | 2022-06-02 | 2023-05-16
C-PW-042820 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-06-02 | 2022-06-18 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042830 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-06-12 | 2022-07-03 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042840 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-03 | 2022-07-21 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042850 | Final Fix Electrical (Power Sockets/ Isolators) | 8 | 2023-05-06 | 2023-05-15 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042860 | Final Fix Electrical (Light Fixtures) | 7 | 2023-05-08 | 2023-05-16 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042870 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2023-05-08 | 2023-05-16 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
ELV |  | 121 | 2022-06-02 | 2022-10-26
BMS AND AUTOMATIC CONTROLS |  | 121 | 2022-06-02 | 2022-10-26
C-PW-042880 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 10 | 01 | 46 | 001 | 03 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042890 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-03 | 2022-07-18 | 01 | 10 | 01 | 46 | 001 | 03 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042900 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-24 | 2022-10-26 | 01 | 10 | 01 | 46 | 001 | 03 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Wet Areas
LIFE AND SAFETY SYSTEMS |  | 228 | 2022-01-27 | 2022-10-30
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 225 | 2022-01-27 | 2022-10-26
C-PW-042910 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-27 | 2022-02-08 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042920 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-05 | 2022-07-21 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042930 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-24 | 2022-10-26 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 226 | 2022-01-30 | 2022-10-30
C-PW-042940 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-01-30 | 2022-02-10 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042950 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-09 | 2022-07-24 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042960 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-26 | 2022-10-30 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
FIRE FIGHTING WORKS |  | 188 | 2022-02-09 | 2022-09-25
C-PW-042970 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-02-09 | 2022-02-27 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042980 | 2nd Fix Piping System - (Fittings) | 8 | 2022-02-28 | 2022-03-08 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-042990 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-15 | 2022-09-25 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
CHILLED WATER PUMP ROOM - ETS ROOM - WEST |  | 228 | 2022-02-10 | 2022-11-12
MECHANICAL |  | 228 | 2022-02-10 | 2022-11-12
HVAC |  | 228 | 2022-02-10 | 2022-11-12
C-PW-043000 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs & Leakage Test) | 14 | 2022-02-10 | 2022-02-27 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043010 | 1st Fix HVAC (CHW Piping, LTHW & Pressure Testing) | 22 | 2022-02-13 | 2022-03-09 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043020 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 7 | 2022-03-09 | 2022-03-17 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043030 | Installation & Connection of CHW Pumps | 26 | 2022-07-31 | 2022-08-30 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043040 | Installation of CHW Pipes from Pumps to HEX secondary flanges and flushing | 39 | 2022-08-30 | 2022-10-16 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043050 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection and Testing) | 7 | 2022-10-10 | 2022-10-18 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043060 | Installation of Control System | 18 | 2022-10-16 | 2022-11-06 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043070 | Cladding Works incl Labels | 23 | 2022-10-16 | 2022-11-12 | 01 | 06 | 01 | 46 | 001 | 02 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 35 | 2022-02-10 | 2022-03-23
C-PW-043080 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-02-10 | 2022-03-03 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043090 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-03-03 | 2022-03-20 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043100 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 3 | 2022-03-20 | 2022-03-23 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 32 | 2022-02-16 | 2022-03-26
C-PW-043110 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-02-16 | 2022-03-09 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043120 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-03-09 | 2022-03-26 | 01 | 08 | 01 | 46 | 001 | 02 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 211 | 2022-02-10 | 2022-10-24
C-PW-043130 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-02-10 | 2022-02-26 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043140 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-02-14 | 2022-03-07 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043150 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-03-08 | 2022-03-29 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043160 | LV Switchgears (SMDB's, MCC's & DB's) | 7 | 2022-03-29 | 2022-04-06 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043170 | Cable/Wire Termination & Dressing | 10 | 2022-04-06 | 2022-04-18 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043180 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-10-10 | 2022-10-18 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043190 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-11 | 2022-10-19 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043200 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-10-13 | 2022-10-22 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043210 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-15 | 2022-10-24 | 01 | 07 | 01 | 46 | 001 | 02 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 202 | 2022-02-13 | 2022-10-15
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 200 | 2022-02-13 | 2022-10-12
C-PW-043220 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-13 | 2022-02-24 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043230 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-08 | 2022-03-20 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043240 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-10 | 2022-10-12 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 198 | 2022-02-14 | 2022-10-12
C-PW-043250 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-14 | 2022-02-26 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043260 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-02-27 | 2022-03-10 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043270 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-10 | 2022-10-12 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 199 | 2022-02-16 | 2022-10-15
C-PW-043280 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-16 | 2022-02-28 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043290 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-02-28 | 2022-03-12 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043300 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-12 | 2022-10-15 | 01 | 10 | 01 | 46 | 001 | 02 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 201 | 2022-02-16 | 2022-10-18
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 197 | 2022-02-17 | 2022-10-15
C-PW-043310 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-17 | 2022-03-02 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043320 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-02 | 2022-03-14 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043330 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-12 | 2022-10-15 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 198 | 2022-02-20 | 2022-10-18
C-PW-043340 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-02-20 | 2022-03-03 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043350 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-03 | 2022-03-16 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043360 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-15 | 2022-10-18 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 201 | 2022-02-16 | 2022-10-18
C-PW-043370 | 2nd Fix Piping System - (Fittings) | 14 | 2022-02-22 | 2022-03-09 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043380 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 18 | 2022-02-16 | 2022-03-09 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
C-PW-043390 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-10-10 | 2022-10-18 | 01 | 09 | 01 | 46 | 001 | 02 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | MEP / Service Rooms
MALE & FEMALE PRAYER ROOM, LOBBY, ABLUTION AND TOILET - WEST |  | 217 | 2022-02-19 | 2022-11-08
MECHANICAL |  | 182 | 2022-03-30 | 2022-11-07
HVAC SYSTEM WORKS |  | 174 | 2022-04-09 | 2022-11-07
C-PW-043400 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-04-09 | 2022-04-30 | 01 | 06 | 01 | 46 | 001 | 03 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043410 | 1st Fix HVAC (CHW Piping & Drain Pipes) | 18 | 2022-04-12 | 2022-05-07 | 01 | 06 | 01 | 46 | 001 | 03 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043420 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 10 | 2022-05-07 | 2022-05-18 | 01 | 06 | 01 | 46 | 001 | 03 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043430 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-29 | 2022-11-07 | 01 | 06 | 01 | 46 | 001 | 03 |  | Building | HVAC | Museum | North West | L-B1 Basement Level | Wet Areas
DRAINAGE WORKS |  | 179 | 2022-03-30 | 2022-11-03
C-PW-043440 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-30 | 2022-04-20 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043450 | 2nd Fix Piping System (Fittings & Insulation) | 10 | 2022-04-21 | 2022-05-07 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043460 | Final Fix (Installation of Sanitaryware & Accessories) | 5 | 2022-10-29 | 2022-11-03 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
HOT & COLD WATER SYSTEM |  | 175 | 2022-04-05 | 2022-11-03
C-PW-043470 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-05 | 2022-04-26 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043480 | 2nd Fix Piping System (Fittings & Insulation) | 10 | 2022-04-26 | 2022-05-12 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043490 | Electric Water Heater Installation | 2 | 2022-05-12 | 2022-05-14 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043500 | Final Fix Installation | 6 | 2022-10-29 | 2022-11-03 | 01 | 08 | 01 | 46 | 001 | 03 |  | Building | Plumbing | Museum | North West | L-B1 Basement Level | Wet Areas
ELECTRICAL WORKS |  | 217 | 2022-02-19 | 2022-11-08
C-PW-043510 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-02-19 | 2022-03-06 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043520 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-05-04 | 2022-05-25 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043530 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-25 | 2022-06-09 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043540 | Final Fix Electrical (Power Sockets/ Isolators) | 8 | 2022-10-29 | 2022-11-07 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043550 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-31 | 2022-11-08 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043560 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-31 | 2022-11-08 | 01 | 07 | 01 | 46 | 001 | 03 |  | Building | Electrical | Museum | North West | L-B1 Basement Level | Wet Areas
ELV |  | 150 | 2022-05-05 | 2022-11-02
BMS AND AUTOMATIC CONTROLS |  | 150 | 2022-05-05 | 2022-11-02
C-PW-043570 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 46 | 001 | 03 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043580 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 46 | 001 | 03 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043590 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-02 | 01 | 10 | 01 | 46 | 001 | 03 |  | Building | CCTV | Museum | North West | L-B1 Basement Level | Wet Areas
LIFE AND SAFETY SYSTEMS |  | 163 | 2022-04-17 | 2022-11-02
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 150 | 2022-05-05 | 2022-11-02
C-PW-043600 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043610 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-18 | 2022-05-30 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043620 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-02 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 148 | 2022-05-08 | 2022-11-02
C-PW-043630 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-08 | 2022-05-19 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043640 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-19 | 2022-05-31 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043650 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-02 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
FIRE FIGHTING WORKS |  | 117 | 2022-04-17 | 2022-09-08
C-PW-043660 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-17 | 2022-05-09 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043670 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-09 | 2022-05-18 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
C-PW-043680 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-30 | 2022-09-08 | 01 | 09 | 01 | 46 | 001 | 03 |  | Building | Firefighting | Museum | North West | L-B1 Basement Level | Wet Areas
NORTH EAST |  | 243 | 2022-01-12 | 2022-11-01
ELECTRICAL PLANT & UPS ROOM 2 - EAST |  | 142 | 2022-02-16 | 2022-08-08
MECHANICAL |  | 137 | 2022-02-16 | 2022-08-02
HVAC |  | 137 | 2022-02-16 | 2022-08-02
C-PW-043690 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-02-16 | 2022-03-09 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043700 | 1st Fix HVAC (CHW Piping) | 18 | 2022-02-19 | 2022-03-12 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043710 | 2nd Fix HVAC (CRAC Units) | 14 | 2022-03-12 | 2022-03-28 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043720 | Final Fix HVAC (Grills, Diffusers) | 7 | 2022-07-24 | 2022-08-02 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 81 | 2022-04-27 | 2022-08-08
C-PW-043730 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-27 | 2022-05-17 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043740 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-05-04 | 2022-05-25 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043750 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-05-25 | 2022-06-15 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043760 | LV Switchgears (SMDB's, Cap. Bank, MCC's & DB's) | 10 | 2022-06-16 | 2022-06-28 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043770 | Busduct Installation & Connections | 10 | 2022-06-28 | 2022-07-13 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043780 | Cable/Wire Termination & Dressing | 16 | 2022-06-28 | 2022-07-20 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043790 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-07-24 | 2022-08-02 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043800 | Final Fix Electrical (Light Fixtures) | 7 | 2022-07-26 | 2022-08-04 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043810 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-07-27 | 2022-08-06 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043820 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-07-31 | 2022-08-08 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 72 | 2022-04-30 | 2022-07-31
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 70 | 2022-04-30 | 2022-07-26
C-PW-043830 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043840 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043850 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-07-24 | 2022-07-26 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 68 | 2022-05-05 | 2022-07-26
C-PW-043860 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043870 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-29 | 2022-06-09 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043880 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-07-24 | 2022-07-26 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 69 | 2022-05-07 | 2022-07-31
C-PW-043890 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-07 | 2022-05-18 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043900 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-31 | 2022-06-12 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043910 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-07-27 | 2022-07-31 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 137 | 2022-02-16 | 2022-08-02
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 58 | 2022-05-17 | 2022-07-26
C-PW-043920 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-17 | 2022-05-29 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043930 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-29 | 2022-06-11 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043940 | UPS & Battery Panels Installation & Connections | 10 | 2022-06-11 | 2022-06-22 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043950 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-24 | 2022-07-26 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 58 | 2022-05-19 | 2022-07-31
C-PW-043960 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-19 | 2022-05-31 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043970 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-31 | 2022-06-12 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-043980 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-07-27 | 2022-07-31 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 137 | 2022-02-16 | 2022-08-02
C-PW-043990 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 18 | 2022-02-16 | 2022-03-09 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044000 | 2nd Fix Piping System - (Fittings) | 14 | 2022-03-09 | 2022-03-24 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044010 | Final Fix- (Installation FM200, Sprinkler Heads for Gas Fire Suppression System) | 7 | 2022-07-24 | 2022-08-02 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
MECHANICAL PLANT - EAST |  | 176 | 2022-03-31 | 2022-11-01
MECHANICAL |  | 176 | 2022-03-31 | 2022-11-01
HVAC |  | 166 | 2022-04-12 | 2022-11-01
C-PW-044020 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs & Leakage Test) | 58 | 2022-04-12 | 2022-06-21 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044030 | 1st Fix HVAC (CHW Piping, LTHW & Pressure Testing) | 58 | 2022-04-14 | 2022-06-25 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044040 | 2nd Fix HVAC (FCUs, Droppers, Dampers,Fans) | 14 | 2022-06-25 | 2022-07-13 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044050 | AHU Installation incl valve packages | 31 | 2022-07-05 | 2022-08-15 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044060 | Duct Connection incl. S.Attenuator ,CHW Connection, joint Insulation & Electrical Connection | 42 | 2022-08-16 | 2022-10-04 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044070 | Final Fix HVAC (Louvers/Wire Mesh, Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-10-04 | 2022-10-13 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044080 | Cladding Works incl Labels | 23 | 2022-10-04 | 2022-11-01 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 75 | 2022-03-31 | 2022-06-30
C-PW-044090 | 1st Fix Piping System (Supports, Piping) | 47 | 2022-03-31 | 2022-05-29 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044100 | 2nd Fix Piping System (Fittings & Insulation) | 21 | 2022-05-29 | 2022-06-22 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044110 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 3 | 2022-06-22 | 2022-06-26 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044120 | Installation & connections of Condensate Sump Pump & Foul Pumps | 7 | 2022-06-22 | 2022-06-30 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 70 | 2022-04-06 | 2022-06-29
C-PW-044130 | 1st Fix Piping System (Supports, Piping) | 47 | 2022-04-06 | 2022-06-04 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044140 | 2nd Fix Piping System (Fittings & Insulation) | 21 | 2022-06-04 | 2022-06-28 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044150 | Final Fix Installation (Bip Tap) | 2 | 2022-06-28 | 2022-06-29 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 138 | 2022-04-05 | 2022-09-21
C-PW-044160 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 19 | 2022-04-05 | 2022-04-27 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044170 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 47 | 2022-04-16 | 2022-06-13 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044180 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 38 | 2022-06-13 | 2022-08-01 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044190 | LV Switchgears (SMDB's, MCC's & DB's) | 16 | 2022-08-01 | 2022-08-20 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044200 | Cable/Wire Termination & Dressing | 16 | 2022-08-20 | 2022-09-07 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044210 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-09-07 | 2022-09-15 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044220 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-08 | 2022-09-17 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044230 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-11 | 2022-09-19 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044240 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-13 | 2022-09-21 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 138 | 2022-04-07 | 2022-09-24
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 131 | 2022-04-07 | 2022-09-15
C-PW-044250 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 38 | 2022-04-07 | 2022-05-25 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044260 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 16 | 2022-06-13 | 2022-07-02 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044270 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 7 | 2022-09-07 | 2022-09-15 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 130 | 2022-04-09 | 2022-09-15
C-PW-044280 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 38 | 2022-04-09 | 2022-05-28 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044290 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 16 | 2022-06-16 | 2022-07-04 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044300 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 7 | 2022-09-07 | 2022-09-15 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 135 | 2022-04-11 | 2022-09-24
C-PW-044310 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 28 | 2022-04-11 | 2022-05-17 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044320 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 16 | 2022-06-19 | 2022-07-07 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044330 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 7 | 2022-09-15 | 2022-09-24 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 152 | 2022-04-09 | 2022-10-11
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 141 | 2022-04-13 | 2022-10-02
C-PW-044340 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 28 | 2022-04-13 | 2022-05-18 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044350 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 16 | 2022-06-21 | 2022-07-13 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044360 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 7 | 2022-09-24 | 2022-10-02 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 146 | 2022-04-14 | 2022-10-11
C-PW-044370 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 38 | 2022-04-14 | 2022-06-01 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044380 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 16 | 2022-06-23 | 2022-07-16 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044390 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 7 | 2022-10-02 | 2022-10-11 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 130 | 2022-04-09 | 2022-09-15
C-PW-044400 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 48 | 2022-04-09 | 2022-06-06 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044410 | 2nd Fix Piping System - (Fittings) | 35 | 2022-06-07 | 2022-07-21 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044420 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-09-07 | 2022-09-15 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
STANDBY CHILLER 1 - EAST |  | 179 | 2022-01-12 | 2022-08-17
MECHANICAL |  | 173 | 2022-01-12 | 2022-08-10
HVAC |  | 70 | 2022-05-17 | 2022-08-10
C-PW-044430 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 14 | 2022-05-17 | 2022-06-01 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044440 | 1st Fix HVAC (CHW Piping, LTHW & Drain) | 18 | 2022-05-21 | 2022-06-11 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044450 | 2nd Fix HVAC (FCUs, Droppers, Dampers) | 14 | 2022-06-12 | 2022-06-27 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044460 | Installation of Chillers,Pumps,Air Separator, Heat Exchangers incl. valve packages | 25 | 2022-06-22 | 2022-07-25 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044470 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 5 | 2022-08-04 | 2022-08-09 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044480 | Cladding Works incl Labels | 14 | 2022-07-25 | 2022-08-10 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 32 | 2022-01-12 | 2022-02-19
C-PW-044490 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-01-12 | 2022-02-03 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044500 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-02-03 | 2022-02-19 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 32 | 2022-01-30 | 2022-03-08
C-PW-044510 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-01-30 | 2022-02-20 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044520 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-02-21 | 2022-03-08 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 76 | 2022-05-17 | 2022-08-17
C-PW-044530 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-05-17 | 2022-06-01 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044540 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-05-21 | 2022-06-11 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044550 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-06-12 | 2022-07-03 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044560 | LV Switchgears (SMDB's, MCC's & DB's) | 7 | 2022-07-03 | 2022-07-14 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044570 | Cable/Wire Termination & Dressing | 10 | 2022-07-14 | 2022-07-26 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044580 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-08-04 | 2022-08-13 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044590 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-06 | 2022-08-14 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044600 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-08 | 2022-08-16 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044610 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-09 | 2022-08-17 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 67 | 2022-05-19 | 2022-08-09
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 64 | 2022-05-19 | 2022-08-07
C-PW-044620 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-19 | 2022-05-31 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044630 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-12 | 2022-06-23 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044640 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 63 | 2022-05-21 | 2022-08-07
C-PW-044650 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-21 | 2022-06-01 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044660 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044670 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 64 | 2022-05-23 | 2022-08-09
C-PW-044680 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-23 | 2022-06-04 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044690 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-16 | 2022-06-29 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044700 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-07 | 2022-08-09 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 155 | 2022-02-05 | 2022-08-13
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 62 | 2022-05-24 | 2022-08-09
C-PW-044710 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-24 | 2022-06-06 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044720 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-20 | 2022-07-02 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044730 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-07 | 2022-08-09 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 63 | 2022-05-26 | 2022-08-13
C-PW-044740 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-26 | 2022-06-07 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044750 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-22 | 2022-07-04 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044760 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-09 | 2022-08-13 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 152 | 2022-02-05 | 2022-08-09
C-PW-044770 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 19 | 2022-02-05 | 2022-02-27 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044780 | 2nd Fix Piping System - (Fittings) | 14 | 2022-02-27 | 2022-03-15 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044790 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-08-04 | 2022-08-09 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
STANDY BY ICE STORAGE TANKS - EAST |  | 173 | 2022-01-30 | 2022-08-28
MECHANICAL |  | 166 | 2022-01-30 | 2022-08-20
HVAC |  | 77 | 2022-05-17 | 2022-08-20
C-PW-044800 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 14 | 2022-05-17 | 2022-06-01 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044810 | 1st Fix HVAC (CHW Piping, LTHW & Drain) | 14 | 2022-05-21 | 2022-06-06 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044820 | 2nd Fix HVAC (FCUs, Droppers, Dampers) | 14 | 2022-06-06 | 2022-06-21 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044830 | Installation of Chillers,Pumps,Air Separator etc. | 25 | 2022-06-16 | 2022-07-19 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044840 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 5 | 2022-08-14 | 2022-08-20 | 01 | 06 | 01 | 44 | 001 | 02 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 32 | 2022-01-30 | 2022-03-08
C-PW-044850 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-01-30 | 2022-02-20 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044860 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-02-21 | 2022-03-08 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 32 | 2022-02-05 | 2022-03-14
C-PW-044870 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-02-05 | 2022-02-26 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044880 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-02-26 | 2022-03-14 | 01 | 08 | 01 | 44 | 001 | 02 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 84 | 2022-05-17 | 2022-08-28
C-PW-044890 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-05-17 | 2022-06-01 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044900 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-05-21 | 2022-06-06 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044910 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-06-06 | 2022-06-27 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044920 | LV Switchgears (SMDB's, MCC's & DB's) | 7 | 2022-06-27 | 2022-07-05 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044930 | Cable/Wire Termination & Dressing | 10 | 2022-07-05 | 2022-07-21 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044940 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-08-14 | 2022-08-22 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044950 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-16 | 2022-08-24 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044960 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-17 | 2022-08-25 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044970 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-20 | 2022-08-28 | 01 | 07 | 01 | 44 | 001 | 02 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 75 | 2022-05-19 | 2022-08-20
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 73 | 2022-05-19 | 2022-08-16
C-PW-044980 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-19 | 2022-05-31 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-044990 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-06 | 2022-06-18 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045000 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-14 | 2022-08-16 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 71 | 2022-05-21 | 2022-08-16
C-PW-045010 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-21 | 2022-06-01 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045020 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045030 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-14 | 2022-08-16 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 72 | 2022-05-23 | 2022-08-20
C-PW-045040 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-23 | 2022-06-04 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045050 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045060 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-16 | 2022-08-20 | 01 | 10 | 01 | 44 | 001 | 02 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 158 | 2022-02-10 | 2022-08-22
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 70 | 2022-05-24 | 2022-08-20
C-PW-045070 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-24 | 2022-06-06 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045080 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-12 | 2022-06-23 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045090 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-16 | 2022-08-20 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 71 | 2022-05-26 | 2022-08-22
C-PW-045100 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-26 | 2022-06-07 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045110 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-14 | 2022-06-26 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045120 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-20 | 2022-08-22 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 156 | 2022-02-10 | 2022-08-20
C-PW-045130 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-02-10 | 2022-02-26 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045140 | 2nd Fix Piping System - (Fittings) | 14 | 2022-02-26 | 2022-03-14 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
C-PW-045150 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-08-14 | 2022-08-20 | 01 | 09 | 01 | 44 | 001 | 02 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | MEP / Service Rooms
CIRCULATIONS & CORRIDORS- EAST |  | 217 | 2022-01-12 | 2022-10-01
MECHANICAL |  | 78 | 2022-01-12 | 2022-04-13
HVAC |  | 67 | 2022-01-25 | 2022-04-13
C-PW-045160 | 1st Fix HVAC (CHW Piping) | 14 | 2022-01-31 | 2022-02-16 | 01 | 06 | 01 | 44 | 001 | 01 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045170 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 19 | 2022-01-25 | 2022-02-16 | 01 | 06 | 01 | 44 | 001 | 01 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045180 | 2nd Fix HVAC (FCUs, Droppers & Dampers) | 14 | 2022-02-16 | 2022-03-03 | 01 | 06 | 01 | 44 | 001 | 01 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045190 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-04-05 | 2022-04-13 | 01 | 06 | 01 | 44 | 001 | 01 |  | Building | HVAC | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
DRAINAGE WORKS |  | 27 | 2022-01-12 | 2022-02-13
C-PW-045200 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-01-12 | 2022-01-29 | 01 | 08 | 01 | 44 | 001 | 01 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045210 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-01-29 | 2022-02-13 | 01 | 08 | 01 | 44 | 001 | 01 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 27 | 2022-01-17 | 2022-02-17
C-PW-045220 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-01-17 | 2022-02-01 | 01 | 08 | 01 | 44 | 001 | 01 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045230 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-02-02 | 2022-02-17 | 01 | 08 | 01 | 44 | 001 | 01 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 93 | 2022-01-24 | 2022-05-16
C-PW-045240 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-01-26 | 2022-02-14 | 01 | 07 | 01 | 44 | 001 | 01 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045250 | 1st Fix Electrical (Conduits & boxes) - Power and Ligthing System | 19 | 2022-01-24 | 2022-02-15 | 01 | 07 | 01 | 44 | 001 | 01 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045260 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 22 | 2022-02-15 | 2022-03-13 | 01 | 07 | 01 | 44 | 001 | 01 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045270 | LV Switchgears (DB's) | 6 | 2022-04-06 | 2022-04-13 | 01 | 07 | 01 | 44 | 001 | 01 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045280 | Cable/Wire Termination & Dressing | 7 | 2022-04-13 | 2022-04-21 | 01 | 07 | 01 | 44 | 001 | 01 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045290 | Busduct Installation | 12 | 2022-04-14 | 2022-04-28 | 01 | 07 | 01 | 44 | 001 | 01 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045300 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-04-21 | 2022-04-30 | 01 | 07 | 01 | 44 | 001 | 01 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045310 | Final Fix Electrical (Light Fixtures) | 7 | 2022-04-30 | 2022-05-11 | 01 | 07 | 01 | 44 | 001 | 01 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045320 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-05-05 | 2022-05-14 | 01 | 07 | 01 | 44 | 001 | 01 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045330 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-05-08 | 2022-05-16 | 01 | 07 | 01 | 44 | 001 | 01 |  | Building | Electrical | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
ELV |  | 206 | 2022-01-26 | 2022-10-01
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 202 | 2022-01-26 | 2022-09-26
C-PW-045340 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-01-26 | 2022-02-07 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045350 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-02-14 | 2022-02-27 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045360 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 200 | 2022-01-27 | 2022-09-26
C-PW-045370 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-01-27 | 2022-02-08 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045380 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-02-17 | 2022-03-01 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045390 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 200 | 2022-01-30 | 2022-09-28
C-PW-045400 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-01-30 | 2022-02-10 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045410 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-02-20 | 2022-03-03 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045420 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-28 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 201 | 2022-01-31 | 2022-10-01
C-PW-045430 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-01-31 | 2022-02-13 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045440 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-02-23 | 2022-03-07 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045450 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-01 | 01 | 10 | 01 | 44 | 001 | 01 |  | Building | CCTV | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEMS |  | 212 | 2022-01-18 | 2022-10-01
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 199 | 2022-02-02 | 2022-10-01
C-PW-045460 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-02 | 2022-02-14 | 01 | 09 | 01 | 44 | 001 | 01 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045470 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-02-26 | 2022-03-09 | 01 | 09 | 01 | 44 | 001 | 01 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045480 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-01 | 01 | 09 | 01 | 44 | 001 | 01 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 198 | 2022-02-05 | 2022-10-01
C-PW-045490 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-02-05 | 2022-02-16 | 01 | 09 | 01 | 44 | 001 | 01 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045500 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-02-28 | 2022-03-13 | 01 | 09 | 01 | 44 | 001 | 01 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045510 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-01 | 01 | 09 | 01 | 44 | 001 | 01 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
FIRE FIGHTING |  | 74 | 2022-01-18 | 2022-04-14
C-PW-045520 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 19 | 2022-01-18 | 2022-02-09 | 01 | 09 | 01 | 44 | 001 | 01 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045530 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 14 | 2022-02-09 | 2022-02-26 | 01 | 08 | 01 | 44 | 001 | 01 |  | Building | Plumbing | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
C-PW-045540 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 9 | 2022-04-05 | 2022-04-14 | 01 | 09 | 01 | 44 | 001 | 01 |  | Building | Firefighting | Museum | North East | L-B1 Basement Level | Circulation / Common Areas
SOUTH WEST |  | 268 | 2022-01-31 | 2022-12-20
CIRCULATIONS & CORRIDORS- WEST |  | 226 | 2022-03-21 | 2022-12-20
MECHANICAL |  | 226 | 2022-03-21 | 2022-12-20
HVAC |  | 216 | 2022-04-02 | 2022-12-20
C-PW-045550 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 14 | 2022-04-02 | 2022-04-18 | 01 | 06 | 01 | 47 | 001 | 01 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045560 | 1st Fix HVAC (CHW Piping) | 18 | 2022-04-09 | 2022-04-30 | 01 | 06 | 01 | 47 | 001 | 01 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045570 | 2nd Fix HVAC (FCUs, Droppers & Dampers) | 14 | 2022-04-30 | 2022-05-19 | 01 | 06 | 01 | 47 | 001 | 01 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045580 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-12-12 | 2022-12-20 | 01 | 06 | 01 | 47 | 001 | 01 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
DRAINAGE WORKS |  | 36 | 2022-03-21 | 2022-05-05
C-PW-045590 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-21 | 2022-04-11 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045600 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-04-11 | 2022-04-27 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045610 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 4 | 2022-04-27 | 2022-05-05 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 27 | 2022-03-26 | 2022-04-26
C-PW-045620 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-26 | 2022-04-10 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045630 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-04-10 | 2022-04-26 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 76 | 2022-03-30 | 2022-06-30
C-PW-045640 | 1st Fix Electrical (Conduits & boxes) - Power and Ligthing System | 14 | 2022-03-30 | 2022-04-14 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045650 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 22 | 2022-04-02 | 2022-04-27 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045660 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 22 | 2022-04-27 | 2022-05-25 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045670 | LV Switchgears (DB's) | 6 | 2022-05-26 | 2022-06-01 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045680 | Cable/Wire Termination & Dressing | 7 | 2022-06-01 | 2022-06-09 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045690 | Busduct Installation | 12 | 2022-06-01 | 2022-06-15 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045700 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-06-09 | 2022-06-18 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045710 | Final Fix Electrical (Light Fixtures) | 7 | 2022-06-19 | 2022-06-27 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045720 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-06-20 | 2022-06-28 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045730 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-06-22 | 2022-06-30 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
ELV |  | 207 | 2022-04-02 | 2022-12-08
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 195 | 2022-04-02 | 2022-11-23
C-PW-045740 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-02 | 2022-04-13 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045750 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045760 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-21 | 2022-11-23 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 196 | 2022-04-03 | 2022-11-27
C-PW-045770 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-03 | 2022-04-14 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045780 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-30 | 2022-05-15 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045790 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-23 | 2022-11-27 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 198 | 2022-04-03 | 2022-11-29
C-PW-045800 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-03 | 2022-04-14 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045810 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-04 | 2022-05-16 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045820 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-27 | 2022-11-29 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 199 | 2022-04-05 | 2022-12-03
C-PW-045830 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045840 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-07 | 2022-05-18 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045850 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-29 | 2022-12-03 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 200 | 2022-04-06 | 2022-12-06
C-PW-045860 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-06 | 2022-04-19 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045870 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-08 | 2022-05-21 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045880 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-12-04 | 2022-12-06 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 200 | 2022-04-09 | 2022-12-08
C-PW-045890 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-20 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045900 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-10 | 2022-05-22 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045910 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-12-06 | 2022-12-08 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEMS |  | 204 | 2022-03-27 | 2022-11-28
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 192 | 2022-04-06 | 2022-11-27
C-PW-045920 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-06 | 2022-04-19 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045930 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045940 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-23 | 2022-11-27 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 191 | 2022-04-09 | 2022-11-27
C-PW-045950 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-20 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045960 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-20 | 2022-05-07 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045970 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-23 | 2022-11-27 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
FIRE FIGHTING |  | 204 | 2022-03-27 | 2022-11-28
C-PW-045980 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-03-27 | 2022-04-11 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-045990 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 14 | 2022-04-11 | 2022-04-27 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-046000 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 9 | 2022-11-19 | 2022-11-28 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
MECHANICAL PLANT ROOM - WEST |  | 155 | 2022-02-02 | 2022-08-09
MECHANICAL |  | 151 | 2022-02-02 | 2022-08-04
HVAC |  | 148 | 2022-02-05 | 2022-08-04
C-PW-046010 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs & Leakage Test) | 58 | 2022-02-05 | 2022-04-13 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046020 | 1st Fix HVAC (CHW Piping, LTHW & Pressure Testing) | 58 | 2022-02-19 | 2022-04-26 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046030 | 2nd Fix HVAC (FCUs, Droppers, Fans) | 14 | 2022-04-26 | 2022-05-16 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046040 | Installation of Air Handling Units, Pumps & Valve Package | 31 | 2022-05-16 | 2022-06-21 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046050 | Duct Connection incl. S.Attenuator ,CHW Connection, joint Insulation & Electrical Connection | 42 | 2022-05-16 | 2022-07-04 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046060 | Final Fix HVAC (Louvers/Wire Mesh, Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-07-23 | 2022-08-01 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046070 | Cladding Works incl Labels | 23 | 2022-07-04 | 2022-08-04 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 60 | 2022-02-02 | 2022-04-13
C-PW-046080 | 1st Fix Piping System (Supports, Piping) | 35 | 2022-02-02 | 2022-03-15 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046090 | 2nd Fix Piping System (Fittings & Insulation) | 21 | 2022-03-15 | 2022-04-09 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046100 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 4 | 2022-04-09 | 2022-04-13 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 151 | 2022-02-03 | 2022-08-07
C-PW-046110 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-02-09 | 2022-02-24 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046120 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 19 | 2022-02-03 | 2022-02-26 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046130 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-02-27 | 2022-03-20 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046140 | LV Switchgears (SMDB's, MCC's & DB's) | 7 | 2022-03-20 | 2022-03-28 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046150 | Cable/Wire Termination & Dressing | 10 | 2022-03-28 | 2022-04-09 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046160 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-07-23 | 2022-08-01 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046170 | Final Fix Electrical (Light Fixtures) | 7 | 2022-07-25 | 2022-08-03 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046180 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-07-26 | 2022-08-04 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046190 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-07-28 | 2022-08-07 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 151 | 2022-02-06 | 2022-08-09
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 144 | 2022-02-06 | 2022-08-01
C-PW-046200 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 28 | 2022-02-06 | 2022-03-10 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046210 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 16 | 2022-03-10 | 2022-03-29 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046220 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 7 | 2022-07-23 | 2022-08-01 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 143 | 2022-02-08 | 2022-08-01
C-PW-046230 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 28 | 2022-02-08 | 2022-03-12 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046240 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 16 | 2022-03-13 | 2022-03-30 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046250 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 7 | 2022-07-23 | 2022-08-01 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 148 | 2022-02-09 | 2022-08-09
C-PW-046260 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 28 | 2022-02-09 | 2022-03-14 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046270 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 16 | 2022-03-14 | 2022-04-02 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046280 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 7 | 2022-08-01 | 2022-08-09 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 150 | 2022-02-08 | 2022-08-09
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 139 | 2022-02-12 | 2022-08-01
C-PW-046290 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 28 | 2022-02-12 | 2022-03-16 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046300 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 16 | 2022-03-16 | 2022-04-04 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046310 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 7 | 2022-07-23 | 2022-08-01 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 146 | 2022-02-13 | 2022-08-09
C-PW-046320 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 38 | 2022-02-13 | 2022-03-29 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046330 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 16 | 2022-03-29 | 2022-04-17 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046340 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 7 | 2022-08-01 | 2022-08-09 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 143 | 2022-02-08 | 2022-08-01
C-PW-046350 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 48 | 2022-02-08 | 2022-04-04 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046360 | 2nd Fix Piping System - (Fittings) | 35 | 2022-04-05 | 2022-05-19 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046370 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-07-23 | 2022-08-01 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
CANADIAN DUCT AHU - WEST |  | 126 | 2022-01-31 | 2022-06-30
MECHANICAL |  | 121 | 2022-01-31 | 2022-06-25
HVAC |  | 117 | 2022-02-05 | 2022-06-25
C-PW-046380 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs & Leakage Test) | 18 | 2022-02-05 | 2022-02-27 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046390 | 1st Fix HVAC (CHW Piping, LTHW & Pressure Testing) | 18 | 2022-02-19 | 2022-03-12 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046400 | 2nd Fix HVAC (FCUs, Droppers, Fans) | 14 | 2022-03-12 | 2022-03-27 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046410 | AHU Installation incl valve packages | 12 | 2022-04-13 | 2022-04-27 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046420 | Duct Connection incl. S.Attenuator ,CHW Connection, joint Insulation & Electrical Connection | 11 | 2022-04-27 | 2022-05-14 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046430 | Cladding Works incl Labels | 14 | 2022-05-14 | 2022-05-30 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046440 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-06-16 | 2022-06-25 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 35 | 2022-01-31 | 2022-03-13
C-PW-046450 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-01-31 | 2022-02-21 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046460 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-02-22 | 2022-03-09 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046470 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 3 | 2022-03-09 | 2022-03-13 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 117 | 2022-02-10 | 2022-06-30
C-PW-046480 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-02-10 | 2022-02-26 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046490 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-02-13 | 2022-03-07 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046500 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-03-07 | 2022-03-28 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046510 | LV Switchgears (SMDB's, MCC's & DB's) | 7 | 2022-03-28 | 2022-04-05 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046520 | Cable/Wire Termination & Dressing | 10 | 2022-04-05 | 2022-04-18 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046530 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-06-16 | 2022-06-25 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046540 | Final Fix Electrical (Light Fixtures) | 7 | 2022-06-18 | 2022-06-26 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046550 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-06-20 | 2022-06-28 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046560 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-06-22 | 2022-06-30 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 108 | 2022-02-13 | 2022-06-21
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 106 | 2022-02-13 | 2022-06-19
C-PW-046570 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-13 | 2022-02-24 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046580 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-02-24 | 2022-03-08 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046590 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-06-16 | 2022-06-19 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 103 | 2022-02-15 | 2022-06-19
C-PW-046600 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-15 | 2022-02-27 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046610 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-02-27 | 2022-03-12 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046620 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-06-16 | 2022-06-19 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 104 | 2022-02-17 | 2022-06-21
C-PW-046630 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-17 | 2022-03-01 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046640 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-01 | 2022-03-13 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046650 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-06-19 | 2022-06-21 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 116 | 2022-02-06 | 2022-06-25
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 100 | 2022-02-19 | 2022-06-19
C-PW-046660 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-19 | 2022-03-02 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046670 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-03 | 2022-03-15 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046680 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-06-16 | 2022-06-19 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 101 | 2022-02-21 | 2022-06-21
C-PW-046690 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-02-21 | 2022-03-05 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046700 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-05 | 2022-03-16 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046710 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-06-19 | 2022-06-21 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 116 | 2022-02-06 | 2022-06-25
C-PW-046720 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 18 | 2022-02-06 | 2022-02-27 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046730 | 2nd Fix Piping System - (Fittings) | 14 | 2022-02-27 | 2022-03-15 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046740 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-06-16 | 2022-06-25 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL PLANT ROOM - WEST |  | 204 | 2022-02-22 | 2022-10-26
MECHANICAL |  | 204 | 2022-02-22 | 2022-10-26
HVAC |  | 197 | 2022-03-01 | 2022-10-26
C-PW-046750 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-03-01 | 2022-03-22 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046760 | 1st Fix HVAC (CHW Piping and Drain pipes) | 14 | 2022-03-08 | 2022-03-23 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046770 | 2nd Fix HVAC (CRAC Unit) | 14 | 2022-03-24 | 2022-04-09 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046780 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection and Testing) | 5 | 2022-10-22 | 2022-10-26 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 32 | 2022-02-22 | 2022-03-30
C-PW-046790 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-02-22 | 2022-03-15 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046800 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-03-15 | 2022-03-30 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 84 | 2022-03-01 | 2022-06-11
C-PW-046810 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-01 | 2022-03-16 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046820 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-03-08 | 2022-03-26 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046830 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-03-27 | 2022-04-17 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046840 | Busduct Installation & Connections | 10 | 2022-04-17 | 2022-04-28 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046850 | Installation of Electrical EquipmentsLV Switchgears (SMDB's, MCP's & DB's) | 12 | 2022-04-25 | 2022-05-12 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046860 | Cable/Wire Termination & Dressing | 16 | 2022-05-09 | 2022-05-28 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046870 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-05-28 | 2022-06-05 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046880 | Final Fix Electrical (Light Fixtures) | 7 | 2022-05-30 | 2022-06-07 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046890 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-06-01 | 2022-06-09 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046900 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-06-02 | 2022-06-11 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 64 | 2022-03-06 | 2022-05-22
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 61 | 2022-03-06 | 2022-05-19
C-PW-046910 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-06 | 2022-03-17 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046920 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-27 | 2022-04-07 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046930 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-05-17 | 2022-05-19 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 60 | 2022-03-08 | 2022-05-19
C-PW-046940 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-08 | 2022-03-20 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046950 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-20 | 2022-03-31 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046960 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-05-17 | 2022-05-19 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 60 | 2022-03-09 | 2022-05-22
C-PW-046970 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-09 | 2022-03-21 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046980 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-22 | 2022-04-03 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-046990 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-05-19 | 2022-05-22 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 198 | 2022-02-28 | 2022-10-26
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 49 | 2022-03-20 | 2022-05-19
C-PW-047000 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-20 | 2022-03-31 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047010 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-31 | 2022-04-13 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047020 | UPS & Battery Panels Installation & Connections | 10 | 2022-04-13 | 2022-04-25 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047030 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-05-17 | 2022-05-19 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 50 | 2022-03-22 | 2022-05-22
C-PW-047040 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-22 | 2022-04-03 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047050 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-03 | 2022-04-14 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047060 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-05-19 | 2022-05-22 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 198 | 2022-02-28 | 2022-10-26
C-PW-047070 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-02-28 | 2022-03-16 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047080 | 2nd Fix Piping System - (Fittings) | 14 | 2022-03-16 | 2022-03-31 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047090 | Final Fix- (Installation FM200, Sprinkler Heads for Gas Fire Suppression System) | 5 | 2022-10-22 | 2022-10-26 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
MAIN LV SWITCH ROOM 1 - WEST |  | 198 | 2022-03-01 | 2022-10-26
MECHANICAL |  | 198 | 2022-03-01 | 2022-10-26
HVAC |  | 191 | 2022-03-08 | 2022-10-26
C-PW-047100 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-03-08 | 2022-03-29 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047110 | 1st Fix HVAC (CHW Piping and Drain pipes) | 18 | 2022-03-10 | 2022-04-02 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047120 | 2nd Fix HVAC (CRAC Unit) | 14 | 2022-04-02 | 2022-04-17 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047130 | Final Fix HVAC (Grills, Diffusers) | 5 | 2022-10-22 | 2022-10-26 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 32 | 2022-03-01 | 2022-04-06
C-PW-047140 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-01 | 2022-03-22 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047150 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-03-22 | 2022-04-06 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 110 | 2022-03-08 | 2022-07-20
C-PW-047160 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-08 | 2022-03-23 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047170 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 38 | 2022-03-12 | 2022-04-25 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047180 | Installation of Electrical Equipments LV Switchgears (MDB incl. Harmonic filter) | 12 | 2022-05-09 | 2022-05-23 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047190 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 38 | 2022-04-25 | 2022-06-11 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047200 | Installation of Electrical EquipmentsLV Switchgears (SMDB's, Cap. Bank, MCC's & DB's) | 28 | 2022-05-09 | 2022-06-11 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047210 | Busduct Installation & Connections | 21 | 2022-06-11 | 2022-07-05 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047220 | Cable/Wire Termination & Dressing | 28 | 2022-06-11 | 2022-07-17 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047230 | Final Fix Electrical (Power Socket / Isolators) | 3 | 2022-07-14 | 2022-07-18 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047240 | Final Fix Electrical (Light Fixtures) | 3 | 2022-07-17 | 2022-07-20 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047250 | Final Fix Electrical (Installation of Lighting Control Panels) | 3 | 2022-07-17 | 2022-07-20 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047260 | Final Fix Electrical (Installation of Lighting Control Devices) | 3 | 2022-07-17 | 2022-07-20 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 102 | 2022-03-13 | 2022-07-16
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 99 | 2022-03-13 | 2022-07-13
C-PW-047270 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-13 | 2022-03-24 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047280 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-24 | 2022-04-06 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047290 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-07-07 | 2022-07-13 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 98 | 2022-03-15 | 2022-07-13
C-PW-047300 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-15 | 2022-03-27 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047310 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-27 | 2022-04-07 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047320 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-07-07 | 2022-07-13 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 98 | 2022-03-16 | 2022-07-16
C-PW-047330 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-16 | 2022-03-28 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047340 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-29 | 2022-04-10 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047350 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-07-13 | 2022-07-16 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 193 | 2022-03-06 | 2022-10-26
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 87 | 2022-03-27 | 2022-07-13
C-PW-047360 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-27 | 2022-04-07 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047370 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-07 | 2022-04-20 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047380 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-07 | 2022-07-13 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 88 | 2022-03-29 | 2022-07-16
C-PW-047390 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-29 | 2022-04-10 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047400 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-10 | 2022-04-21 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047410 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-07-13 | 2022-07-16 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 193 | 2022-03-06 | 2022-10-26
C-PW-047420 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 18 | 2022-03-06 | 2022-03-28 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047430 | 2nd Fix Piping System - (Fittings) | 14 | 2022-03-28 | 2022-04-12 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047440 | Final Fix- (Installation FM200, Sprinkler Heads for Gas Fire Suppression System) | 5 | 2022-10-22 | 2022-10-26 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
TSE INTAKE / CONDENSATE TANK - WEST |  | 68 | 2022-02-05 | 2022-04-25
MECHANICAL |  | 41 | 2022-02-05 | 2022-03-24
HVAC |  | 23 | 2022-02-15 | 2022-03-14
C-PW-047450 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-02-15 | 2022-03-08 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047460 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection and Testing) | 5 | 2022-03-09 | 2022-03-14 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 41 | 2022-02-05 | 2022-03-24
C-PW-047470 | 1st Fix Piping System (Piping) | 9 | 2022-02-05 | 2022-02-15 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047480 | 2nd Fix Piping System (Fittings | 6 | 2022-03-16 | 2022-03-22 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047490 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 2 | 2022-03-23 | 2022-03-24 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 34 | 2022-02-05 | 2022-03-16
C-PW-047500 | 1st Fix Piping System (Piping) | 9 | 2022-02-05 | 2022-02-15 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047510 | 1st Fix Installation of TSE/Condensate Tank | 9 | 2022-02-27 | 2022-03-08 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047520 | 2nd Fix Installation of Condensate Transfer Pump | 2 | 2022-03-09 | 2022-03-10 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047530 | 2nd Fix Piping System (Fittings, Level Indicator) | 3 | 2022-03-09 | 2022-03-13 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047540 | 2nd Fix Installation valves & accessories & piping connections | 3 | 2022-03-13 | 2022-03-16 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 49 | 2022-02-27 | 2022-04-25
C-PW-047550 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-02-27 | 2022-03-07 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047560 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-03-08 | 2022-03-17 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047570 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 7 | 2022-03-17 | 2022-03-26 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047580 | Installation of Electrical EquipmentsLV Switchgears (DB's) | 3 | 2022-03-29 | 2022-04-02 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047590 | Cable/Wire Termination & Dressing | 6 | 2022-04-02 | 2022-04-09 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047600 | Final Fix Electrical (Power Socket / Isolators) | 3 | 2022-04-09 | 2022-04-12 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047610 | Final Fix Electrical (Light Fixtures) | 3 | 2022-04-18 | 2022-04-21 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047620 | Final Fix Electrical (Installation of Lighting Control Panels) | 3 | 2022-04-19 | 2022-04-23 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047630 | Final Fix Electrical (Installation of Lighting Control Devices) | 3 | 2022-04-21 | 2022-04-25 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
IT/AV STORE & MOTOR ROOM 2 - WEST |  | 115 | 2022-03-22 | 2022-08-11
MECHANICAL |  | 108 | 2022-03-22 | 2022-08-03
HVAC |  | 101 | 2022-03-29 | 2022-08-03
C-PW-047640 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 7 | 2022-03-29 | 2022-04-06 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047650 | 1st Fix HVAC (CHW Piping and Drain pipes) | 7 | 2022-04-02 | 2022-04-10 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047660 | 2nd Fix HVAC (FCUs, Droppers) | 6 | 2022-04-10 | 2022-04-16 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047670 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 3 | 2022-07-31 | 2022-08-03 | 01 | 06 | 01 | 47 | 001 | 02 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 13 | 2022-03-22 | 2022-04-06
C-PW-047680 | 1st Fix Piping System (Supports, Piping) | 7 | 2022-03-22 | 2022-03-30 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047690 | 2nd Fix Piping System (Fittings & Insulation) | 6 | 2022-03-30 | 2022-04-06 | 01 | 08 | 01 | 47 | 001 | 02 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 82 | 2022-04-30 | 2022-08-11
C-PW-047700 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 6 | 2022-04-30 | 2022-05-09 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047710 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-05-05 | 2022-05-17 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047720 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-05-17 | 2022-05-30 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047730 | LV Switchgears (DB's) | 5 | 2022-05-30 | 2022-06-04 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047740 | Cable/Wire Termination & Dressing | 8 | 2022-06-05 | 2022-06-13 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047750 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-07-31 | 2022-08-06 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047760 | Final Fix Electrical (Light Fixtures) | 6 | 2022-08-01 | 2022-08-08 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047770 | Final Fix Electrical (Installation of Lighting Control Panels) | 6 | 2022-08-03 | 2022-08-09 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047780 | Final Fix Electrical (Installation of Lighting Control Devices) | 6 | 2022-08-04 | 2022-08-11 | 01 | 07 | 01 | 47 | 001 | 02 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 76 | 2022-05-08 | 2022-08-08
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 70 | 2022-05-08 | 2022-08-02
C-PW-047790 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 6 | 2022-05-08 | 2022-05-14 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047800 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 7 | 2022-05-14 | 2022-05-22 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047810 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-07-31 | 2022-08-02 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 69 | 2022-05-09 | 2022-08-02
C-PW-047820 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 6 | 2022-05-09 | 2022-05-16 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047830 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 7 | 2022-05-16 | 2022-05-24 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047840 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-07-31 | 2022-08-02 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 67 | 2022-05-11 | 2022-08-02
C-PW-047850 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 6 | 2022-05-11 | 2022-05-17 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047860 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 7 | 2022-05-17 | 2022-05-25 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047870 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-07-31 | 2022-08-02 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-08-02 | 2022-08-08
C-PW-047880 | Active Component System Works | 6 | 2022-08-02 | 2022-08-08 | 01 | 10 | 01 | 47 | 001 | 02 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 107 | 2022-03-28 | 2022-08-08
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 63 | 2022-05-16 | 2022-08-02
C-PW-047890 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 6 | 2022-05-16 | 2022-05-22 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047900 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 6 | 2022-05-22 | 2022-05-29 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047910 | UPS & Battery Panels Installation & Connections | 6 | 2022-05-29 | 2022-06-04 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047920 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-31 | 2022-08-02 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 62 | 2022-05-17 | 2022-08-02
C-PW-047930 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 6 | 2022-05-17 | 2022-05-24 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047940 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 6 | 2022-05-24 | 2022-05-30 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047950 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-07-31 | 2022-08-02 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 107 | 2022-03-28 | 2022-08-08
C-PW-047960 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 10 | 2022-03-28 | 2022-04-09 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047970 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-09 | 2022-04-18 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
C-PW-047980 | Final Fix- (Installation FM200, Sprinkler Heads for Gas Fire Suppression System) | 7 | 2022-07-31 | 2022-08-08 | 01 | 09 | 01 | 47 | 001 | 02 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | MEP / Service Rooms
DOCUMENT CENTER, STORAGE, ISOLATION, ARTIFACT, SECURE STORAGE AND MUSEUM LOADING DOCK - WEST |  | 213 | 2022-03-03 | 2022-11-16
MECHANICAL |  | 209 | 2022-03-03 | 2022-11-12
HVAC SYSTEM WORKS |  | 201 | 2022-03-13 | 2022-11-12
C-PW-047990 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-03-13 | 2022-04-03 | 01 | 06 | 01 | 47 | 001 | 05 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048000 | 1st Fix HVAC (CHW Piping & Drain Pipes) | 18 | 2022-03-15 | 2022-04-05 | 01 | 06 | 01 | 47 | 001 | 05 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048010 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 14 | 2022-04-06 | 2022-04-21 | 01 | 06 | 01 | 47 | 001 | 05 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048020 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-02 | 2022-11-12 | 01 | 06 | 01 | 47 | 001 | 05 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 32 | 2022-03-03 | 2022-04-10
C-PW-048030 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-03 | 2022-03-24 | 01 | 08 | 01 | 47 | 001 | 05 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048040 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-03-24 | 2022-04-10 | 01 | 08 | 01 | 47 | 001 | 05 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 32 | 2022-03-09 | 2022-04-14
C-PW-048050 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-09 | 2022-03-30 | 01 | 08 | 01 | 47 | 001 | 05 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048060 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-03-30 | 2022-04-14 | 01 | 08 | 01 | 47 | 001 | 05 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 211 | 2022-03-06 | 2022-11-16
C-PW-048070 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-06 | 2022-03-22 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048080 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-05-25 | 2022-06-15 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048090 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-15 | 2022-07-02 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048100 | LV Switchgears (DB's) | 5 | 2022-07-02 | 2022-07-07 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048110 | Cable/Wire Termination & Dressing | 7 | 2022-07-07 | 2022-07-19 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048120 | Final Fix Electrical (Power Sockets/ Isolators) | 8 | 2022-11-02 | 2022-11-12 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048130 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-05 | 2022-11-13 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048140 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-06 | 2022-11-14 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048150 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-08 | 2022-11-16 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
ELV |  | 201 | 2022-03-08 | 2022-11-07
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 200 | 2022-03-08 | 2022-11-05
C-PW-048160 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-08 | 2022-03-20 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048170 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-15 | 2022-06-28 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048180 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-02 | 2022-11-05 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 198 | 2022-03-09 | 2022-11-05
C-PW-048190 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-09 | 2022-03-22 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048200 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048210 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-02 | 2022-11-05 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 198 | 2022-03-09 | 2022-11-05
C-PW-048220 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-03-09 | 2022-03-22 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048230 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-21 | 2022-07-03 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048240 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-02 | 2022-11-05 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 196 | 2022-03-12 | 2022-11-05
C-PW-048250 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-12 | 2022-03-23 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048260 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-25 | 2022-07-06 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048270 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-02 | 2022-11-05 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 196 | 2022-03-14 | 2022-11-07
C-PW-048280 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-14 | 2022-03-26 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048290 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048300 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-05 | 2022-11-07 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 195 | 2022-03-15 | 2022-11-07
C-PW-048310 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-15 | 2022-03-27 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048320 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-29 | 2022-07-16 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048330 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-05 | 2022-11-07 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEMS |  | 193 | 2022-03-17 | 2022-11-07
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 193 | 2022-03-17 | 2022-11-07
C-PW-048340 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-17 | 2022-03-29 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048350 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-03 | 2022-07-18 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048360 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-05 | 2022-11-07 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 192 | 2022-03-19 | 2022-11-07
C-PW-048370 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-19 | 2022-03-31 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048380 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-05 | 2022-07-20 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048390 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-05 | 2022-11-07 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 46 | 2022-03-19 | 2022-05-15
C-PW-048400 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-03-19 | 2022-04-06 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048410 | 2nd Fix Piping System - (Fittings) | 12 | 2022-04-06 | 2022-04-20 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048420 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-05-05 | 2022-05-15 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
DOCK MASTER, SECURITY ROOM & EQUIPMENT, MAINTENANCE WORSHOP & STORAGE AND FALCON S/R ROOM - WEST |  | 204 | 2022-03-16 | 2022-11-17
MECHANICAL |  | 203 | 2022-03-16 | 2022-11-17
HVAC SYSTEM WORKS |  | 195 | 2022-03-26 | 2022-11-17
C-PW-048430 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-03-26 | 2022-04-16 | 01 | 06 | 01 | 47 | 001 | 05 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048440 | 1st Fix HVAC (CHW Piping & Drain Pipes) | 18 | 2022-03-28 | 2022-04-19 | 01 | 06 | 01 | 47 | 001 | 05 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048450 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 14 | 2022-04-19 | 2022-05-08 | 01 | 06 | 01 | 47 | 001 | 05 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048460 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection & Testing) | 8 | 2022-11-08 | 2022-11-17 | 01 | 06 | 01 | 47 | 001 | 05 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 32 | 2022-03-16 | 2022-04-23
C-PW-048470 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-16 | 2022-04-06 | 01 | 08 | 01 | 47 | 001 | 05 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048480 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-04-06 | 2022-04-23 | 01 | 08 | 01 | 47 | 001 | 05 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 32 | 2022-03-22 | 2022-04-28
C-PW-048490 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-22 | 2022-04-12 | 01 | 08 | 01 | 47 | 001 | 05 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048500 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-04-12 | 2022-04-28 | 01 | 08 | 01 | 47 | 001 | 05 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 199 | 2022-03-22 | 2022-11-17
C-PW-048510 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-22 | 2022-04-06 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048520 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-06-15 | 2022-07-07 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048530 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-07 | 2022-07-26 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048540 | Final Fix Electrical (Power Sockets/ Isolators) | 8 | 2022-11-08 | 2022-11-17 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048550 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-09 | 2022-11-17 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048560 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-09 | 2022-11-17 | 01 | 07 | 01 | 47 | 001 | 05 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
ELV |  | 186 | 2022-03-23 | 2022-11-05
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 184 | 2022-03-23 | 2022-11-03
C-PW-048570 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-23 | 2022-04-05 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048580 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-07 | 2022-07-23 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048590 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 183 | 2022-03-26 | 2022-11-03
C-PW-048600 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-06 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048610 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-13 | 2022-07-25 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048620 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 181 | 2022-03-28 | 2022-11-03
C-PW-048630 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-28 | 2022-04-09 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048640 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-17 | 2022-07-28 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048650 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 181 | 2022-03-29 | 2022-11-05
C-PW-048660 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-29 | 2022-04-10 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048670 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-17 | 2022-07-28 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048680 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-02 | 2022-11-05 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 180 | 2022-03-31 | 2022-11-05
C-PW-048690 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048700 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-19 | 2022-08-01 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048710 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-02 | 2022-11-05 | 01 | 10 | 01 | 47 | 001 | 05 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEMS |  | 178 | 2022-03-31 | 2022-11-03
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 178 | 2022-03-31 | 2022-11-03
C-PW-048720 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-31 | 2022-04-12 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048730 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-19 | 2022-08-01 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048740 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 176 | 2022-04-02 | 2022-11-03
C-PW-048750 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-02 | 2022-04-14 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048760 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-21 | 2022-08-04 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048770 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 134 | 2022-04-02 | 2022-09-12
C-PW-048780 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-02 | 2022-04-19 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048790 | 2nd Fix Piping System - (Fittings) | 12 | 2022-04-20 | 2022-05-07 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-048800 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-03 | 2022-09-12 | 01 | 09 | 01 | 47 | 001 | 05 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Storage / Offices / Admin Areas
PARKING, ARRIVALS, DRIVEWAYS AND LOADING BAYS |  | 129 | 2022-02-16 | 2022-07-24
MECHANICAL |  | 129 | 2022-02-16 | 2022-07-24
HVAC SYSTEM WORKS |  | 77 | 2022-02-26 | 2022-05-30
C-PW-048810 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 10 | 2022-02-26 | 2022-03-10 | 01 | 06 | 01 | 47 | 001 | 01 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048820 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 10 | 2022-03-10 | 2022-03-22 | 01 | 06 | 01 | 47 | 001 | 01 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048830 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-05-24 | 2022-05-30 | 01 | 06 | 01 | 47 | 001 | 01 |  | Building | HVAC | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
DRAINAGE WORKS |  | 129 | 2022-02-16 | 2022-07-24
C-PW-048840 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-02-16 | 2022-03-05 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048850 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 10 | 2022-03-05 | 2022-03-15 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048860 | Installation & connections of Condensate Sump Pump & Foul Pumps | 6 | 2022-07-13 | 2022-07-19 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048870 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 4 | 2022-07-19 | 2022-07-24 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 25 | 2022-02-22 | 2022-03-23
C-PW-048880 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-02-22 | 2022-03-10 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048890 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 10 | 2022-03-10 | 2022-03-21 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048900 | Final Fix Installation (Bip Tap) | 2 | 2022-03-21 | 2022-03-23 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 77 | 2022-03-02 | 2022-06-02
C-PW-048910 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-03-02 | 2022-03-14 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048920 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-03-14 | 2022-03-29 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048930 | Final Fix Electrical (Power Sockets/ Isolators) | 6 | 2022-05-24 | 2022-05-30 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048940 | Final Fix Electrical (Light Fixtures) | 7 | 2022-05-25 | 2022-06-02 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048950 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-05-25 | 2022-06-02 | 01 | 07 | 01 | 47 | 001 | 01 |  | Building | Electrical | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
ELV |  | 78 | 2022-03-03 | 2022-06-06
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 74 | 2022-03-03 | 2022-06-01
C-PW-048960 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-03 | 2022-03-15 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048970 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-16 | 2022-03-28 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-048980 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-05-30 | 2022-06-01 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 75 | 2022-03-06 | 2022-06-05
C-PW-048990 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-06 | 2022-03-17 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049000 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-03-17 | 2022-03-29 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049010 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-06-02 | 2022-06-05 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 75 | 2022-03-07 | 2022-06-06
C-PW-049020 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-07 | 2022-03-20 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049030 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-20 | 2022-03-31 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049040 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-06-04 | 2022-06-06 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 74 | 2022-03-09 | 2022-06-06
C-PW-049050 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-09 | 2022-03-21 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049060 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-21 | 2022-04-03 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049070 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-06-04 | 2022-06-06 | 01 | 10 | 01 | 47 | 001 | 01 |  | Building | CCTV | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEMS |  | 74 | 2022-03-09 | 2022-06-06
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 74 | 2022-03-09 | 2022-06-06
C-PW-049080 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-09 | 2022-03-21 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049090 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-21 | 2022-04-03 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049100 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-06-04 | 2022-06-06 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 72 | 2022-03-12 | 2022-06-06
C-PW-049110 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-12 | 2022-03-23 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049120 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-23 | 2022-04-04 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049130 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-06-04 | 2022-06-06 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 63 | 2022-03-14 | 2022-05-30
C-PW-049140 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 10 | 2022-03-14 | 2022-03-26 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049150 | 2nd Fix Piping System - (Fittings, Connections & Testing) | 8 | 2022-03-26 | 2022-04-04 | 01 | 08 | 01 | 47 | 001 | 01 |  | Building | Plumbing | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
C-PW-049160 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-05-24 | 2022-05-30 | 01 | 09 | 01 | 47 | 001 | 01 |  | Building | Firefighting | Museum | South West | L-B1 Basement Level | Circulation / Common Areas
SOUTH EAST |  | 249 | 2022-02-28 | 2022-12-26
MECHANICAL PLANT 1 & 2 - SOUTH |  | 178 | 2022-02-28 | 2022-10-01
MECHANICAL |  | 178 | 2022-02-28 | 2022-10-01
HVAC |  | 178 | 2022-02-28 | 2022-10-01
C-PW-049170 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs & Leakage Test) | 58 | 2022-02-28 | 2022-05-09 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049180 | 1st Fix HVAC (CHW Piping, LTHW & Pressure Testing) | 58 | 2022-03-16 | 2022-05-25 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049190 | 2nd Fix HVAC (FCUs, Droppers, Dampers & Fans) | 14 | 2022-05-25 | 2022-06-11 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049200 | AHU Installation incl valve packages | 31 | 2022-06-06 | 2022-07-16 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049210 | Duct Connection incl. S.Attenuator ,CHW Connection, joint Insulation & Electrical Connection | 42 | 2022-07-16 | 2022-09-04 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049220 | Final Fix HVAC (Louvers/Wire Mesh, Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-09-04 | 2022-09-12 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049230 | Cladding Works incl Labels | 23 | 2022-09-04 | 2022-10-01 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 110 | 2022-02-28 | 2022-07-09
C-PW-049240 | 1st Fix Piping System (Supports, Piping) | 35 | 2022-02-28 | 2022-04-10 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049250 | 2nd Fix Piping System (Fittings & Insulation) | 21 | 2022-04-10 | 2022-05-07 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049260 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 3 | 2022-05-08 | 2022-05-11 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049270 | Installation & connections of Condensate Sump Pump & Foul Pumps | 7 | 2022-06-30 | 2022-07-09 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 58 | 2022-03-16 | 2022-05-25
C-PW-049280 | 1st Fix Piping System (Supports, Piping) | 35 | 2022-03-16 | 2022-04-26 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049290 | 2nd Fix Piping System (Fittings & Insulation) | 21 | 2022-04-26 | 2022-05-23 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049300 | Final Fix Installation (Bip Tap) | 2 | 2022-05-24 | 2022-05-25 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 148 | 2022-02-28 | 2022-08-28
C-PW-049310 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 19 | 2022-02-28 | 2022-03-22 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049320 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 35 | 2022-03-03 | 2022-04-13 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049330 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 38 | 2022-04-13 | 2022-05-31 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049340 | LV Switchgears (SMDB's, MCC's & DB's) | 16 | 2022-05-31 | 2022-06-19 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049350 | Cable/Wire Termination & Dressing | 16 | 2022-06-19 | 2022-07-07 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049360 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-08-14 | 2022-08-22 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049370 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-16 | 2022-08-24 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049380 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-17 | 2022-08-25 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049390 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-20 | 2022-08-28 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 146 | 2022-03-05 | 2022-08-30
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 139 | 2022-03-05 | 2022-08-22
C-PW-049400 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 38 | 2022-03-05 | 2022-04-19 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049410 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 16 | 2022-04-19 | 2022-05-11 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049420 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 7 | 2022-08-14 | 2022-08-22 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 139 | 2022-03-05 | 2022-08-22
C-PW-049430 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 28 | 2022-03-05 | 2022-04-06 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049440 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 16 | 2022-04-21 | 2022-05-14 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049450 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 7 | 2022-08-14 | 2022-08-22 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 144 | 2022-03-07 | 2022-08-30
C-PW-049460 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 28 | 2022-03-07 | 2022-04-09 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049470 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 16 | 2022-04-25 | 2022-05-16 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049480 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 7 | 2022-08-22 | 2022-08-30 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 144 | 2022-03-07 | 2022-08-30
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 137 | 2022-03-07 | 2022-08-22
C-PW-049490 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 28 | 2022-03-07 | 2022-04-09 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049500 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 16 | 2022-04-27 | 2022-05-19 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049510 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 7 | 2022-08-14 | 2022-08-22 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 143 | 2022-03-09 | 2022-08-30
C-PW-049520 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 38 | 2022-03-09 | 2022-04-23 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049530 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 16 | 2022-04-30 | 2022-05-22 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049540 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 7 | 2022-08-22 | 2022-08-30 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 125 | 2022-03-21 | 2022-08-22
C-PW-049550 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 48 | 2022-03-21 | 2022-05-19 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049560 | 2nd Fix Piping System - (Fittings) | 35 | 2022-05-19 | 2022-06-29 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049570 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-08-14 | 2022-08-22 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
HEATING & CALORIFIER ROOMS - SOUTH |  | 124 | 2022-03-16 | 2022-08-15
MECHANICAL |  | 117 | 2022-03-16 | 2022-08-07
HVAC |  | 109 | 2022-03-26 | 2022-08-07
C-PW-049580 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs & Leakage Test) | 22 | 2022-03-26 | 2022-04-19 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049590 | 1st Fix HVAC (CHW Piping, LTHW & Pressure Testing) | 22 | 2022-03-28 | 2022-04-21 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049600 | 2nd Fix HVAC (FCUs, Droppers, Dampers & Fans) | 14 | 2022-04-23 | 2022-05-11 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049610 | Installation of Heat pump | 3 | 2022-05-19 | 2022-05-23 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049620 | Installation of Boilers | 7 | 2022-05-25 | 2022-06-02 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049630 | Duct Connection,CHW Connection & Electrical Connection | 22 | 2022-06-02 | 2022-06-28 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049640 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 5 | 2022-08-02 | 2022-08-07 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 34 | 2022-03-16 | 2022-04-24
C-PW-049650 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-16 | 2022-04-06 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049660 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-04-06 | 2022-04-21 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049670 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 2 | 2022-04-23 | 2022-04-24 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 70 | 2022-03-21 | 2022-06-14
C-PW-049680 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-21 | 2022-04-06 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049690 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-04-06 | 2022-04-21 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049700 | 2nd Fix Installation of Precool Tank & EM Cooler | 3 | 2022-05-19 | 2022-05-23 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049710 | 2nd Fix Installation of Calorifiers incl. Heat Exchanger | 3 | 2022-05-25 | 2022-05-29 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049720 | 2nd Fix Installation of Expansion Vessels & Dosingng Unit | 3 | 2022-05-29 | 2022-06-01 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049730 | 2nd Fix Installation of Solar Water Circulation Pumpset | 3 | 2022-06-02 | 2022-06-06 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049740 | 2nd Fix Installation of Valves & Equipments Connections | 7 | 2022-06-06 | 2022-06-14 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 124 | 2022-03-16 | 2022-08-15
C-PW-049750 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 19 | 2022-03-16 | 2022-04-07 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049760 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-03-29 | 2022-04-19 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049770 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-04-19 | 2022-05-14 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049780 | LV Switchgears (SMDB's, MCC's & DB's) | 7 | 2022-05-15 | 2022-05-23 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049790 | Cable/Wire Termination & Dressing | 10 | 2022-06-14 | 2022-06-26 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049800 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-08-02 | 2022-08-10 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049810 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-03 | 2022-08-11 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049820 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-06 | 2022-08-14 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049830 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-07 | 2022-08-15 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 115 | 2022-03-17 | 2022-08-07
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 113 | 2022-03-17 | 2022-08-04
C-PW-049840 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-17 | 2022-03-29 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049850 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049860 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-02 | 2022-08-04 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 111 | 2022-03-20 | 2022-08-04
C-PW-049870 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-20 | 2022-03-31 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049880 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-23 | 2022-05-08 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049890 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-02 | 2022-08-04 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 112 | 2022-03-21 | 2022-08-07
C-PW-049900 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-21 | 2022-04-03 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049910 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-25 | 2022-05-10 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049920 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 113 | 2022-03-23 | 2022-08-10
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 110 | 2022-03-23 | 2022-08-07
C-PW-049930 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-23 | 2022-04-04 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049940 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-27 | 2022-05-14 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049950 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 111 | 2022-03-26 | 2022-08-10
C-PW-049960 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-06 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049970 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-30 | 2022-05-15 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-049980 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-07 | 2022-08-10 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 107 | 2022-03-27 | 2022-08-07
C-PW-049990 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 18 | 2022-03-27 | 2022-04-17 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050000 | 2nd Fix Piping System - (Fittings) | 14 | 2022-04-18 | 2022-05-07 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050010 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-08-02 | 2022-08-07 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
UPS ROOM 3 & ELECTRICAL PLANT ROOM - SOUTH |  | 106 | 2022-04-07 | 2022-08-17
MECHANICAL |  | 86 | 2022-04-26 | 2022-08-11
HVAC |  | 77 | 2022-05-10 | 2022-08-11
C-PW-050020 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 14 | 2022-05-10 | 2022-05-25 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050030 | 1st Fix HVAC (CHW Piping and Drain pipes) | 18 | 2022-05-25 | 2022-06-15 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050040 | 2nd Fix HVAC (CRAC Unit) | 14 | 2022-06-16 | 2022-07-02 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050050 | Final Fix HVAC (Grills, Diffusers) | 7 | 2022-08-03 | 2022-08-11 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 32 | 2022-04-26 | 2022-06-06
C-PW-050060 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-26 | 2022-05-21 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050070 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-05-21 | 2022-06-06 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 106 | 2022-04-07 | 2022-08-17
C-PW-050080 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-07 | 2022-04-23 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050090 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-05-14 | 2022-05-29 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050100 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-05-29 | 2022-06-20 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050110 | Installation of Electrical Equipments LV Switchgears (SMDB's, MCP's & DB's) | 10 | 2022-06-20 | 2022-07-02 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050120 | Busduct Installation & Connections | 10 | 2022-07-02 | 2022-07-17 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050130 | Cable/Wire Termination & Dressing | 16 | 2022-07-02 | 2022-07-24 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050140 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-08-03 | 2022-08-11 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050150 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-06 | 2022-08-14 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050160 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-07 | 2022-08-15 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050170 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-09 | 2022-08-17 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 98 | 2022-04-09 | 2022-08-09
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 95 | 2022-04-09 | 2022-08-06
C-PW-050180 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-21 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050190 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-29 | 2022-06-11 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050200 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-03 | 2022-08-06 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 94 | 2022-04-11 | 2022-08-06
C-PW-050210 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-11 | 2022-04-23 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050220 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-01 | 2022-06-13 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050230 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-03 | 2022-08-06 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 94 | 2022-04-13 | 2022-08-09
C-PW-050240 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-13 | 2022-04-25 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050250 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-04 | 2022-06-15 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050260 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-07 | 2022-08-09 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 88 | 2022-04-23 | 2022-08-11
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 83 | 2022-04-23 | 2022-08-06
C-PW-050270 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-23 | 2022-05-09 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050280 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-09 | 2022-05-21 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050290 | UPS & Battery Panels Installation & Connections | 10 | 2022-05-21 | 2022-06-01 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050300 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-03 | 2022-08-06 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 82 | 2022-04-25 | 2022-08-06
C-PW-050310 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-25 | 2022-05-10 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050320 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050330 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-03 | 2022-08-06 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 81 | 2022-05-05 | 2022-08-11
C-PW-050340 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-05-05 | 2022-05-21 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050350 | 2nd Fix Piping System - (Fittings) | 14 | 2022-05-21 | 2022-06-06 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050360 | Final Fix- (Installation FM200, Sprinkler Heads for Gas Fire Suppression System) | 7 | 2022-08-03 | 2022-08-11 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
MAIN LV SWITCH ROOM 2 - SOUTH |  | 162 | 2022-04-07 | 2022-10-23
MECHANICAL |  | 146 | 2022-04-26 | 2022-10-23
HVAC |  | 138 | 2022-05-10 | 2022-10-23
C-PW-050370 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 14 | 2022-05-10 | 2022-05-25 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050380 | 1st Fix HVAC (CHW Piping and Drain pipes) | 18 | 2022-05-25 | 2022-06-15 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050390 | 2nd Fix HVAC (CRAC Unit) | 14 | 2022-06-16 | 2022-07-02 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050400 | Final Fix HVAC (Grills, Diffusers) | 7 | 2022-10-15 | 2022-10-23 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 32 | 2022-04-26 | 2022-06-06
C-PW-050410 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-26 | 2022-05-21 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050420 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-05-21 | 2022-06-06 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 134 | 2022-04-07 | 2022-09-19
C-PW-050430 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-07 | 2022-04-23 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050440 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 28 | 2022-05-14 | 2022-06-15 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050450 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 38 | 2022-06-15 | 2022-08-02 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050460 | Installation of Electrical Equipments LV Switchgears (MDB incl. Harmonic filter) | 12 | 2022-08-02 | 2022-08-16 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050470 | Installation of Electrical EquipmentsLV Switchgears (SMDB's, Cap. Bank, MCC's & DB's) | 28 | 2022-08-02 | 2022-09-04 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050480 | Busduct Installation & Connections | 21 | 2022-08-20 | 2022-09-12 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050490 | Cable/Wire Termination & Dressing | 28 | 2022-08-14 | 2022-09-15 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050500 | Final Fix Electrical (Power Socket / Isolators) | 3 | 2022-09-13 | 2022-09-17 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050510 | Final Fix Electrical (Light Fixtures) | 3 | 2022-09-15 | 2022-09-19 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050520 | Final Fix Electrical (Installation of Lighting Control Panels) | 3 | 2022-09-15 | 2022-09-19 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050530 | Final Fix Electrical (Installation of Lighting Control Devices) | 3 | 2022-09-15 | 2022-09-19 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 158 | 2022-04-09 | 2022-10-20
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 156 | 2022-04-09 | 2022-10-17
C-PW-050540 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-21 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050550 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-15 | 2022-06-27 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050560 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-15 | 2022-10-17 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 154 | 2022-04-11 | 2022-10-17
C-PW-050570 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-11 | 2022-04-23 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050580 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-23 | 2022-05-09 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050590 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-15 | 2022-10-17 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 155 | 2022-04-13 | 2022-10-20
C-PW-050600 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-13 | 2022-04-25 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050610 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-25 | 2022-05-10 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050620 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-20 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 149 | 2022-04-23 | 2022-10-23
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 144 | 2022-04-23 | 2022-10-17
C-PW-050630 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-23 | 2022-05-09 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050640 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-09 | 2022-05-21 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050650 | UPS & Battery Panels Installation & Connections | 10 | 2022-05-21 | 2022-06-01 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050660 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-15 | 2022-10-17 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 142 | 2022-04-25 | 2022-10-17
C-PW-050670 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-25 | 2022-05-10 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050680 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-10 | 2022-05-23 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050690 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-15 | 2022-10-17 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 142 | 2022-05-05 | 2022-10-23
C-PW-050700 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-05-05 | 2022-05-21 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050710 | 2nd Fix Piping System - (Fittings) | 14 | 2022-05-21 | 2022-06-06 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050720 | Final Fix- (Installation FM200, Sprinkler Heads for Gas Fire Suppression System) | 7 | 2022-10-15 | 2022-10-23 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
MOTOR ROOM 1, BMS ROOM, MAIN TELECOM ROOM 2, CC3 & 4 AND ETISALAT METER 2 - SOUTH |  | 136 | 2022-04-12 | 2022-09-26
MECHANICAL |  | 96 | 2022-05-21 | 2022-09-14
HVAC |  | 90 | 2022-05-29 | 2022-09-14
C-PW-050730 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 10 | 2022-05-29 | 2022-06-09 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050740 | 1st Fix HVAC (CHW Piping and Drain pipes) | 14 | 2022-06-16 | 2022-07-02 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050750 | 2nd Fix HVAC (CRAC UNITS) | 10 | 2022-07-02 | 2022-07-17 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050760 | Final Fix HVAC (Grills, Diffusers) | 7 | 2022-09-06 | 2022-09-14 | 01 | 06 | 01 | 45 | 001 | 02 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
DRAINAGE WORKS |  | 24 | 2022-05-21 | 2022-06-18
C-PW-050770 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-05-21 | 2022-06-06 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050780 | 2nd Fix Piping System (Fittings & Insulation) | 10 | 2022-06-06 | 2022-06-18 | 01 | 08 | 01 | 45 | 001 | 02 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ELECTRICAL |  | 136 | 2022-04-12 | 2022-09-26
C-PW-050790 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-12 | 2022-04-28 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050800 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-06-01 | 2022-06-18 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050810 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-18 | 2022-07-04 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050820 | LV Switchgears (DB's) | 5 | 2022-07-04 | 2022-07-09 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050830 | Installation of Electrical Equipments | 10 | 2022-07-13 | 2022-07-25 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050840 | Cable/Wire Termination & Dressing | 16 | 2022-07-25 | 2022-08-14 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050850 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-09-06 | 2022-09-14 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050860 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-14 | 2022-09-22 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050870 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-17 | 2022-09-25 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050880 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-18 | 2022-09-26 | 01 | 07 | 01 | 45 | 001 | 02 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ELV |  | 132 | 2022-04-17 | 2022-09-26
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 119 | 2022-04-17 | 2022-09-11
C-PW-050890 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-17 | 2022-04-28 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050900 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-18 | 2022-06-29 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050910 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 117 | 2022-04-19 | 2022-09-11
C-PW-050920 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-19 | 2022-05-04 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050930 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-04 | 2022-05-16 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050940 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 117 | 2022-04-20 | 2022-09-12
C-PW-050950 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 14 | 2022-04-20 | 2022-05-11 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050960 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050970 | Server panels Installation & Connections | 16 | 2022-05-23 | 2022-06-11 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-050980 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-12 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 121 | 2022-04-23 | 2022-09-19
C-PW-050990 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-23 | 2022-05-08 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-051000 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-08 | 2022-05-21 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-051010 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 6 | 2022-09-13 | 2022-09-19 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-19 | 2022-09-26
C-PW-051020 | Active Component System Works | 6 | 2022-09-19 | 2022-09-26 | 01 | 10 | 01 | 45 | 001 | 02 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 104 | 2022-05-11 | 2022-09-14
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 101 | 2022-05-11 | 2022-09-11
C-PW-051030 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-11 | 2022-05-23 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-051040 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-23 | 2022-06-04 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-051050 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 100 | 2022-05-12 | 2022-09-11
C-PW-051060 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 14 | 2022-05-12 | 2022-05-30 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-051070 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-30 | 2022-06-11 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-051080 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
FIRE FIGHTING |  | 91 | 2022-05-26 | 2022-09-14
C-PW-051090 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-05-26 | 2022-06-12 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-051100 | 2nd Fix Piping System - (Fittings) | 10 | 2022-06-12 | 2022-06-25 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
C-PW-051110 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-09-06 | 2022-09-14 | 01 | 09 | 01 | 45 | 001 | 02 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | MEP / Service Rooms
COLLECTION STORAGE 1 & 2 - SOUTH |  | 183 | 2022-03-19 | 2022-10-26
MECHANICAL |  | 127 | 2022-05-21 | 2022-10-22
HVAC SYSTEM WORKS |  | 90 | 2022-07-03 | 2022-10-22
C-PW-051120 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 19 | 2022-07-03 | 2022-07-28 | 01 | 06 | 01 | 45 | 001 | 05 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051130 | 1st Fix HVAC (CHW Piping & Drain Pipes) | 18 | 2022-07-05 | 2022-08-01 | 01 | 06 | 01 | 45 | 001 | 05 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051140 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 14 | 2022-08-01 | 2022-08-16 | 01 | 06 | 01 | 45 | 001 | 05 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051150 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-12 | 2022-10-22 | 01 | 06 | 01 | 45 | 001 | 05 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 23 | 2022-05-21 | 2022-06-16
C-PW-051160 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-21 | 2022-06-11 | 01 | 08 | 01 | 45 | 001 | 05 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051170 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-06-01 | 2022-06-16 | 01 | 08 | 01 | 45 | 001 | 05 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 23 | 2022-06-12 | 2022-07-09
C-PW-051180 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-12 | 2022-07-03 | 01 | 08 | 01 | 45 | 001 | 05 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051190 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-06-22 | 2022-07-09 | 01 | 08 | 01 | 45 | 001 | 05 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 183 | 2022-03-19 | 2022-10-26
C-PW-051200 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 19 | 2022-03-19 | 2022-04-10 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051210 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-07-06 | 2022-08-01 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051220 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-08-02 | 2022-08-17 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051230 | LV Switchgears (DB's) | 5 | 2022-08-17 | 2022-08-23 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051240 | Cable/Wire Termination & Dressing | 7 | 2022-08-23 | 2022-08-31 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051250 | Final Fix Electrical (Power Sockets/ Isolators) | 8 | 2022-10-12 | 2022-10-22 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051260 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-15 | 2022-10-23 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051270 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-10-17 | 2022-10-25 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051280 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-18 | 2022-10-26 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
ELV |  | 179 | 2022-03-20 | 2022-10-24
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 172 | 2022-03-20 | 2022-10-16
C-PW-051290 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 14 | 2022-03-20 | 2022-04-05 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051300 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-08-02 | 2022-08-14 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051310 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-12 | 2022-10-16 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 170 | 2022-03-22 | 2022-10-16
C-PW-051320 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-22 | 2022-04-03 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051330 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-08-03 | 2022-08-15 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051340 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-12 | 2022-10-16 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 168 | 2022-03-23 | 2022-10-16
C-PW-051350 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-03-23 | 2022-04-05 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051360 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-08-06 | 2022-08-17 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051370 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-12 | 2022-10-16 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 169 | 2022-03-26 | 2022-10-18
C-PW-051380 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-06 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051390 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-08-07 | 2022-08-20 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051400 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-16 | 2022-10-18 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 170 | 2022-03-28 | 2022-10-20
C-PW-051410 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 14 | 2022-03-28 | 2022-04-13 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051420 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-09 | 2022-08-21 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051430 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-18 | 2022-10-20 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 171 | 2022-03-29 | 2022-10-24
C-PW-051440 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-29 | 2022-04-10 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051450 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-11 | 2022-08-23 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051460 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-24 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEMS |  | 169 | 2022-03-31 | 2022-10-24
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 169 | 2022-03-31 | 2022-10-24
C-PW-051470 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-31 | 2022-04-12 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051480 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-08-14 | 2022-08-25 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051490 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-24 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 168 | 2022-04-02 | 2022-10-24
C-PW-051500 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-02 | 2022-04-14 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051510 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-16 | 2022-08-28 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051520 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-24 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 56 | 2022-07-13 | 2022-09-17
C-PW-051530 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-07-13 | 2022-08-01 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051540 | 2nd Fix Piping System - (Fittings) | 12 | 2022-07-24 | 2022-08-08 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051550 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-08 | 2022-09-17 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
PHOTOGRAPHIC STUDIO & STORE ROOMS - SOUTH |  | 178 | 2022-03-19 | 2022-10-20
MECHANICAL |  | 126 | 2022-05-21 | 2022-10-20
HVAC SYSTEM WORKS |  | 99 | 2022-06-21 | 2022-10-20
C-PW-051560 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-06-21 | 2022-07-16 | 01 | 06 | 01 | 45 | 001 | 05 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051570 | 1st Fix HVAC (CHW Piping & Drain Pipes) | 18 | 2022-06-23 | 2022-07-18 | 01 | 06 | 01 | 45 | 001 | 05 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051580 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 14 | 2022-07-18 | 2022-08-04 | 01 | 06 | 01 | 45 | 001 | 05 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051590 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-11 | 2022-10-20 | 01 | 06 | 01 | 45 | 001 | 05 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 23 | 2022-05-21 | 2022-06-16
C-PW-051600 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-21 | 2022-06-11 | 01 | 08 | 01 | 45 | 001 | 05 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051610 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-06-01 | 2022-06-16 | 01 | 08 | 01 | 45 | 001 | 05 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 23 | 2022-05-26 | 2022-06-22
C-PW-051620 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-26 | 2022-06-16 | 01 | 08 | 01 | 45 | 001 | 05 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051630 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-06-07 | 2022-06-22 | 01 | 08 | 01 | 45 | 001 | 05 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 178 | 2022-03-19 | 2022-10-20
C-PW-051640 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-19 | 2022-04-03 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051650 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-06-25 | 2022-07-19 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051660 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-19 | 2022-08-06 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051670 | Final Fix Electrical (Power Sockets/ Isolators) | 8 | 2022-10-11 | 2022-10-20 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051680 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-12 | 2022-10-20 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051690 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-12 | 2022-10-20 | 01 | 07 | 01 | 45 | 001 | 05 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
ELV |  | 172 | 2022-03-20 | 2022-10-16
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 170 | 2022-03-20 | 2022-10-13
C-PW-051700 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-20 | 2022-03-31 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051710 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-19 | 2022-08-01 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051720 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-11 | 2022-10-13 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 168 | 2022-03-22 | 2022-10-13
C-PW-051730 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-22 | 2022-04-03 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051740 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-23 | 2022-08-04 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051750 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-11 | 2022-10-13 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 167 | 2022-03-23 | 2022-10-13
C-PW-051760 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-23 | 2022-04-05 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051770 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-25 | 2022-08-07 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051780 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-11 | 2022-10-13 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 168 | 2022-03-26 | 2022-10-16
C-PW-051790 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-06 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051800 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-27 | 2022-08-10 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051810 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-13 | 2022-10-16 | 01 | 10 | 01 | 45 | 001 | 05 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEMS |  | 166 | 2022-03-28 | 2022-10-16
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 166 | 2022-03-28 | 2022-10-16
C-PW-051820 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-28 | 2022-04-09 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051830 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-08-01 | 2022-08-13 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051840 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-13 | 2022-10-16 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 164 | 2022-03-29 | 2022-10-16
C-PW-051850 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-29 | 2022-04-10 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051860 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-02 | 2022-08-15 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051870 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-13 | 2022-10-16 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 65 | 2022-06-27 | 2022-09-15
C-PW-051880 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-27 | 2022-07-19 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051890 | 2nd Fix Piping System - (Fittings) | 12 | 2022-07-09 | 2022-07-26 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
C-PW-051900 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-06 | 2022-09-15 | 01 | 09 | 01 | 45 | 001 | 05 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Storage / Offices / Admin Areas
CIRCULATIONS & CORRIDORS- SOUTH |  | 244 | 2022-03-05 | 2022-12-26
MECHANICAL |  | 244 | 2022-03-05 | 2022-12-26
HVAC |  | 234 | 2022-03-17 | 2022-12-26
C-PW-051910 | 1st Fix HVAC (CHW Piping) | 14 | 2022-03-23 | 2022-04-09 | 01 | 06 | 01 | 45 | 001 | 01 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-051920 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 19 | 2022-03-17 | 2022-04-09 | 01 | 06 | 01 | 45 | 001 | 01 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-051930 | 2nd Fix HVAC (FCUs, Droppers & Dampers) | 14 | 2022-04-09 | 2022-04-24 | 01 | 06 | 01 | 45 | 001 | 01 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-051940 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-12-18 | 2022-12-26 | 01 | 06 | 01 | 45 | 001 | 01 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
DRAINAGE WORKS |  | 31 | 2022-03-05 | 2022-04-10
C-PW-051950 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-05 | 2022-03-21 | 01 | 08 | 01 | 45 | 001 | 01 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-051960 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-03-21 | 2022-04-05 | 01 | 08 | 01 | 45 | 001 | 01 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-051970 | Final Fix Installation (Drain Ancillaries-Floor Drains, Rodding eye, etc.) | 4 | 2022-04-06 | 2022-04-10 | 01 | 08 | 01 | 45 | 001 | 01 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 27 | 2022-03-09 | 2022-04-10
C-PW-051980 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-09 | 2022-03-24 | 01 | 08 | 01 | 45 | 001 | 01 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-051990 | 2nd Fix Piping System (Fittings & Insulation) | 14 | 2022-03-26 | 2022-04-10 | 01 | 08 | 01 | 45 | 001 | 01 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 71 | 2022-03-14 | 2022-06-08
C-PW-052000 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-03-17 | 2022-04-05 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052010 | 1st Fix Electrical (Conduits & boxes) - Power and Ligthing System | 19 | 2022-03-14 | 2022-04-05 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052020 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 22 | 2022-04-06 | 2022-05-04 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052030 | LV Switchgears (DB's) | 6 | 2022-05-04 | 2022-05-11 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052040 | Cable/Wire Termination & Dressing | 7 | 2022-05-11 | 2022-05-19 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052050 | Busduct Installation | 12 | 2022-05-11 | 2022-05-25 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052060 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-05-19 | 2022-05-28 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052070 | Final Fix Electrical (Light Fixtures) | 7 | 2022-05-28 | 2022-06-05 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052080 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-05-30 | 2022-06-07 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052090 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-05-31 | 2022-06-08 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
ELV |  | 37 | 2022-03-16 | 2022-04-28
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 30 | 2022-03-16 | 2022-04-19
C-PW-052100 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-16 | 2022-03-28 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052110 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052120 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-04-17 | 2022-04-19 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 28 | 2022-03-19 | 2022-04-19
C-PW-052130 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-03-19 | 2022-03-30 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052140 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-03-30 | 2022-04-11 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052150 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-04-17 | 2022-04-19 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 29 | 2022-03-20 | 2022-04-23
C-PW-052160 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-20 | 2022-03-31 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052170 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-02 | 2022-04-13 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052180 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-04-20 | 2022-04-23 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 30 | 2022-03-22 | 2022-04-25
C-PW-052190 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-22 | 2022-04-03 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052200 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-03 | 2022-04-14 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052210 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-04-23 | 2022-04-25 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 30 | 2022-03-23 | 2022-04-28
C-PW-052220 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-23 | 2022-04-05 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052230 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052240 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-28 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEMS |  | 210 | 2022-03-10 | 2022-11-20
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 191 | 2022-03-26 | 2022-11-13
C-PW-052250 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-06 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052260 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-06 | 2022-04-19 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052270 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-09 | 2022-11-13 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 189 | 2022-03-28 | 2022-11-13
C-PW-052280 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-28 | 2022-04-09 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052290 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-09 | 2022-04-20 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052300 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-09 | 2022-11-13 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
FIRE FIGHTING |  | 210 | 2022-03-10 | 2022-11-20
C-PW-052310 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-03-10 | 2022-03-27 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052320 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 14 | 2022-03-27 | 2022-04-11 | 01 | 08 | 01 | 45 | 001 | 01 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052330 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 9 | 2022-11-09 | 2022-11-20 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
WC'S, STAFF CHANGING ROOMS AND VIP PANTRY - WEST |  | 174 | 2022-03-29 | 2022-10-27
MECHANICAL |  | 174 | 2022-03-29 | 2022-10-27
HVAC SYSTEM WORKS |  | 166 | 2022-04-07 | 2022-10-27
C-PW-052350 | 1st Fix HVAC (CHW Piping & Drain Pipes) | 14 | 2022-04-11 | 2022-04-26 | 01 | 06 | 01 | 45 | 001 | 01 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052340 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 18 | 2022-04-07 | 2022-04-28 | 01 | 06 | 01 | 45 | 001 | 01 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052360 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 10 | 2022-04-30 | 2022-05-15 | 01 | 06 | 01 | 45 | 001 | 01 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052370 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-18 | 2022-10-27 | 01 | 06 | 01 | 45 | 001 | 01 |  | Building | HVAC | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-03-29 | 2022-05-05
C-PW-052380 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-29 | 2022-04-19 | 01 | 08 | 01 | 45 | 001 | 01 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052390 | 2nd Fix Piping System (Fittings & Insulation) | 10 | 2022-04-20 | 2022-05-05 | 01 | 08 | 01 | 45 | 001 | 01 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-04-04 | 2022-05-11
C-PW-052400 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-04 | 2022-04-25 | 01 | 08 | 01 | 45 | 001 | 01 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052410 | 2nd Fix Piping System (Fittings & Insulation) | 10 | 2022-04-25 | 2022-05-11 | 01 | 08 | 01 | 45 | 001 | 01 |  | Building | Plumbing | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 167 | 2022-04-06 | 2022-10-27
C-PW-052420 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-06 | 2022-04-23 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052430 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-04-30 | 2022-05-18 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052440 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-18 | 2022-06-04 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052450 | Final Fix Electrical (Power Sockets/ Isolators) | 8 | 2022-10-18 | 2022-10-27 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052460 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-19 | 2022-10-27 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052470 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-19 | 2022-10-27 | 01 | 07 | 01 | 45 | 001 | 01 |  | Building | Electrical | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
ELV |  | 155 | 2022-04-09 | 2022-10-16
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 153 | 2022-04-09 | 2022-10-13
C-PW-052480 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-20 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052490 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-18 | 2022-05-30 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052500 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-10 | 2022-10-13 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 145 | 2022-04-20 | 2022-10-16
C-PW-052510 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-20 | 2022-05-07 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052520 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-07 | 2022-05-18 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052530 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-13 | 2022-10-16 | 01 | 10 | 01 | 45 | 001 | 01 |  | Building | CCTV | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEMS |  | 154 | 2022-04-11 | 2022-10-16
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 154 | 2022-04-11 | 2022-10-16
C-PW-052540 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-11 | 2022-04-23 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052550 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-23 | 2022-05-08 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052560 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-13 | 2022-10-16 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 152 | 2022-04-12 | 2022-10-16
C-PW-052570 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-12 | 2022-04-24 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052580 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-25 | 2022-05-11 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052590 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-13 | 2022-10-16 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 134 | 2022-04-16 | 2022-09-28
C-PW-052600 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-16 | 2022-05-08 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052610 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-08 | 2022-05-17 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
C-PW-052620 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-19 | 2022-09-28 | 01 | 09 | 01 | 45 | 001 | 01 |  | Building | Firefighting | Museum | South East | L-B1 Basement Level | Circulation / Common Areas
LEVEL BM BASEMENT MEZZANINE |  | 315 | 2021-11-11 | 2022-11-27
CIVIL WORKS |  | 97 | 2021-12-28 | 2022-04-20
ZONE 02D |  | 26 | 2021-12-28 | 2022-01-27
C-PW-052630 | Construction of Verticals up to Ground Floor Slab - Zone 2D | 26 | 2021-12-28 | 2022-01-27 | 01 | 01 | 01 | 10 | 002 | 30 |  | Building | Civil | Museum | Zone 02D | L-BM Basement Mezzanine Level | Civil SubZones
ZONE 03C |  | 15 | 2022-04-04 | 2022-04-20
C-PW-052640 | Construction of Verticals up to Ground Floor Slab - Zone 3C | 15 | 2022-04-04 | 2022-04-20 | 01 | 01 | 01 | 17 | 002 | 30 |  | Building | Civil | Museum | Zone 03C | L-BM Basement Mezzanine Level | Civil SubZones
ARCHITECTURAL WORKS |  | 315 | 2021-11-11 | 2022-11-27
NORTH WEST |  | 315 | 2021-11-11 | 2022-11-27
SERVICE SLAB 1&2 AND AIR PLENUM - NORTH |  | 269 | 2021-11-11 | 2022-10-02
C-PW-052650 | General Block Works | 10 | 2021-11-11 | 2021-11-22 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052660 | Marking & Chasing Walls for MEP Services | 10 | 2021-11-22 | 2021-12-06 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052670 | Equipment Foundation Works | 5 | 2021-12-06 | 2021-12-11 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052680 | Floor Trench Works | 3 | 2021-12-12 | 2021-12-15 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052690 | First Coat Paint in Ceiling & Wall | 14 | 2021-12-15 | 2022-01-02 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052700 | Grating Works | 3 | 2022-01-02 | 2022-01-05 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052710 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-06-25 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052720 | Wall Finishes Works | 11 | 2022-07-19 | 2022-08-02 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052730 | Floor Surface Preparation for Epoxy Coating | 10 | 2022-08-03 | 2022-08-14 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052740 | Floor Finishes (Epoxy Coating) | 10 | 2022-08-14 | 2022-08-25 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052750 | Installation of Balustrades | 5 | 2022-08-25 | 2022-08-30 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052760 | Door Frames Fixing | 6 | 2022-08-31 | 2022-09-07 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052770 | Door Shuttering & Ironmongery | 6 | 2022-09-07 | 2022-09-14 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052780 | Final Finishes | 10 | 2022-09-21 | 2022-10-02 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
SERVICE SLAB 3 - NORTH |  | 268 | 2021-11-22 | 2022-10-13
C-PW-052790 | General Block Works | 10 | 2021-11-22 | 2021-12-06 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052800 | Marking & Chasing Walls for MEP Services | 10 | 2021-12-06 | 2021-12-16 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052810 | Equipment Foundation Works | 5 | 2021-12-16 | 2021-12-22 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052820 | Floor Trench Works | 3 | 2021-12-22 | 2021-12-26 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052830 | First Coat Paint in Ceiling & Wall | 14 | 2021-12-26 | 2022-01-13 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052840 | Grating Works | 3 | 2022-01-13 | 2022-01-17 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052850 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-02-01 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052860 | Wall Finishes Works | 11 | 2022-07-31 | 2022-08-13 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052870 | Floor Surface Preparation for Epoxy Coating | 10 | 2022-08-13 | 2022-08-24 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052880 | Floor Finishes (Epoxy Coating) | 10 | 2022-08-24 | 2022-09-04 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052890 | Installation of Balustrades | 5 | 2022-09-05 | 2022-09-10 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052900 | Door Frames Fixing | 6 | 2022-09-10 | 2022-09-18 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052910 | Door Shuttering & Ironmongery | 6 | 2022-09-18 | 2022-09-25 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052920 | Final Finishes | 10 | 2022-10-02 | 2022-10-13 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
KITCHEN PLANT ROOM- NORTH |  | 296 | 2021-12-06 | 2022-11-27
C-PW-052930 | General Block Works | 10 | 2021-12-06 | 2021-12-16 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052940 | Equipment Foundation Works | 11 | 2021-12-06 | 2021-12-19 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052950 | Floor Trench Works | 8 | 2021-12-19 | 2021-12-28 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052960 | Marking & Chasing Walls for MEP Services | 10 | 2021-12-16 | 2021-12-28 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052970 | First Coat Paint | 14 | 2021-12-28 | 2022-01-15 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052980 | Grating Works | 8 | 2022-01-15 | 2022-01-24 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-052990 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-02-26 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053000 | Wall Finishes Works | 11 | 2022-09-24 | 2022-10-06 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053010 | Floor Finishes (Epoxy Coating) | 10 | 2022-10-08 | 2022-10-19 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053020 | Installation of Balustrades | 5 | 2022-10-19 | 2022-10-25 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053030 | Door Frames Fixing | 6 | 2022-10-25 | 2022-11-01 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053040 | Door Shuttering & Ironmongery | 6 | 2022-11-01 | 2022-11-09 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053050 | Final Finishes | 10 | 2022-11-15 | 2022-11-27 | 01 | 04 | 01 | 46 | 002 | 02 |  | Building | Architecture | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
NORTH EAST |  | 251 | 2021-12-07 | 2022-10-04
SERVICE SLAB 4&5 - EAST |  | 251 | 2021-12-07 | 2022-10-04
C-PW-053060 | General Block Works | 11 | 2021-12-07 | 2021-12-20 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053070 | Marking & Chasing Walls for MEP Services | 11 | 2021-12-20 | 2022-01-03 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053080 | Equipment Foundation Works | 5 | 2022-01-11 | 2022-01-16 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053090 | Floor Trench Works | 3 | 2022-01-16 | 2022-01-19 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053100 | First Coat Paint in Ceiling & Wall | 10 | 2022-01-20 | 2022-01-31 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053110 | Grating Works | 3 | 2022-01-31 | 2022-02-03 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053120 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-06-26 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053130 | Wall Finishes Works | 11 | 2022-08-01 | 2022-08-14 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053140 | Floor Surface Preparation for Epoxy Coating | 10 | 2022-08-14 | 2022-08-25 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053150 | Floor Finishes (Epoxy Coating) | 10 | 2022-08-25 | 2022-09-05 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053160 | Installation of Balustrades | 5 | 2022-09-05 | 2022-09-11 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053170 | Door Frames Fixing | 5 | 2022-09-11 | 2022-09-17 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053180 | Door Shuttering & Ironmongery | 5 | 2022-09-17 | 2022-09-22 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053190 | Final Finishes | 10 | 2022-09-24 | 2022-10-04 | 01 | 04 | 01 | 44 | 002 | 02 |  | Building | Architecture | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
SOUTH WEST |  | 179 | 2022-01-19 | 2022-08-24
SERVICE BRIDGE AND SERVICE SLAB 12 - WEST |  | 179 | 2022-01-19 | 2022-08-24
C-PW-053200 | Equipment Foundation Works | 10 | 2022-01-22 | 2022-02-01 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053210 | General Block Works | 19 | 2022-01-19 | 2022-02-10 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053220 | Marking & Chasing Walls for MEP Services | 17 | 2022-02-10 | 2022-03-02 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053230 | Floor Trench Works | 6 | 2022-03-02 | 2022-03-09 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053240 | Grating Works | 6 | 2022-03-09 | 2022-03-17 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053250 | First Coat Paint in Ceiling & Wall | 17 | 2022-03-09 | 2022-03-29 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053260 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-04-18 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053270 | Wall Finishes Works | 11 | 2022-06-07 | 2022-06-20 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053280 | Floor Surface Preparation for Epoxy Coating | 10 | 2022-06-20 | 2022-07-02 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053290 | Floor Finishes (Epoxy Coating) | 10 | 2022-07-02 | 2022-07-16 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053300 | Installation of Balustrades | 5 | 2022-07-16 | 2022-07-21 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053310 | Door Frames Fixing | 6 | 2022-07-21 | 2022-07-28 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053320 | Door Shuttering & Ironmongery | 6 | 2022-07-31 | 2022-08-07 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053330 | Final Finishes | 10 | 2022-08-14 | 2022-08-24 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
WATER TREATMENT PLANT - WEST |  | 138 | 2022-02-10 | 2022-07-28
C-PW-053340 | General Block Works | 10 | 2022-02-10 | 2022-02-22 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053350 | Marking & Chasing Walls for MEP Services | 10 | 2022-02-22 | 2022-03-05 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053360 | Equipment Foundation Works | 5 | 2022-03-05 | 2022-03-10 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053370 | Floor Trench Works | 3 | 2022-03-10 | 2022-03-14 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053380 | Grating Works | 3 | 2022-03-14 | 2022-03-17 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053390 | First Coat Paint | 10 | 2022-03-14 | 2022-03-26 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053400 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-04-26 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053410 | Wall Finishes Works | 11 | 2022-05-25 | 2022-06-07 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053420 | Floor Finishes (Epoxy Coating) | 10 | 2022-06-07 | 2022-06-18 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053430 | Installation of Balustrades | 5 | 2022-06-19 | 2022-06-23 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053440 | Door Frames Fixing | 6 | 2022-06-23 | 2022-07-02 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053450 | Door Shuttering & Ironmongery | 6 | 2022-07-02 | 2022-07-09 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053460 | Final Finishes | 10 | 2022-07-17 | 2022-07-28 | 01 | 04 | 01 | 47 | 002 | 02 |  | Building | Architecture | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
SOUTH EAST |  | 129 | 2022-01-26 | 2022-06-28
SERVICE SLAB 6 - SOUTH |  | 129 | 2022-01-26 | 2022-06-28
C-PW-053470 | General Block Works | 10 | 2022-01-26 | 2022-02-06 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053480 | Marking & Chasing Walls for MEP Services | 10 | 2022-02-06 | 2022-02-17 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053490 | Equipment Foundation Works | 6 | 2022-02-17 | 2022-02-24 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053500 | Floor Trench Works | 5 | 2022-02-24 | 2022-03-01 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053510 | First Coat Paint in Ceiling & Wall | 10 | 2022-03-02 | 2022-03-13 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053520 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-03-19 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053530 | Grating Works | 5 | 2022-03-13 | 2022-03-19 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053540 | Wall Finishes Works | 11 | 2022-04-13 | 2022-04-26 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053550 | Floor Surface Preparation for Epoxy Coating | 10 | 2022-05-05 | 2022-05-16 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053560 | Floor Finishes (Epoxy Coating) | 10 | 2022-05-16 | 2022-05-28 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053570 | Installation of Balustrades | 5 | 2022-05-28 | 2022-06-01 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053580 | Door Frames Fixing | 6 | 2022-06-02 | 2022-06-09 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053590 | Door Shuttering & Ironmongery | 6 | 2022-06-09 | 2022-06-16 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053600 | Final Finishes | 10 | 2022-06-18 | 2022-06-28 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
SERVICE SLAB 7&8 - SOUTH |  | 113 | 2022-02-06 | 2022-06-21
C-PW-053610 | General Block Works | 10 | 2022-02-06 | 2022-02-17 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053620 | Equipment Foundation Works | 6 | 2022-02-17 | 2022-02-24 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053630 | Marking & Chasing Walls for MEP Services | 10 | 2022-02-17 | 2022-02-28 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053640 | Floor Trench Works | 5 | 2022-02-24 | 2022-03-02 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053650 | Plant Rooms Ready to Receive Equipment | 0 |  | 2022-03-08 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053660 | Grating Works | 5 | 2022-03-02 | 2022-03-08 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053670 | First Coat Paint in Ceiling & Wall | 10 | 2022-03-02 | 2022-03-13 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053680 | Wall Finishes Works | 11 | 2022-04-11 | 2022-04-24 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053690 | Floor Surface Preparation for Epoxy Coating | 10 | 2022-04-25 | 2022-05-09 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053700 | Floor Finishes (Epoxy Coating) | 10 | 2022-05-09 | 2022-05-21 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053710 | Installation of Balustrades | 5 | 2022-05-21 | 2022-05-25 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053720 | Door Frames Fixing | 6 | 2022-05-26 | 2022-06-02 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053730 | Door Shuttering & Ironmongery | 6 | 2022-06-02 | 2022-06-09 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053740 | Final Finishes | 10 | 2022-06-11 | 2022-06-21 | 01 | 04 | 01 | 45 | 002 | 02 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
SERVICE BRIDGE & TUNNEL |  | 101 | 2022-02-10 | 2022-06-12
C-PW-053750 | General Block Works | 6 | 2022-02-10 | 2022-02-17 | 01 | 04 | 01 | 45 | 002 | 04 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | ZNM Specific Areas
C-PW-053760 | Marking & Chasing Walls for MEP Services | 3 | 2022-02-17 | 2022-02-21 | 01 | 04 | 01 | 45 | 002 | 04 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | ZNM Specific Areas
C-PW-053770 | First Coat Paint in Ceiling & Wall | 11 | 2022-02-21 | 2022-03-06 | 01 | 04 | 01 | 45 | 002 | 04 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | ZNM Specific Areas
C-PW-053780 | Wall Finishes Works | 11 | 2022-03-29 | 2022-04-11 | 01 | 04 | 01 | 45 | 002 | 04 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | ZNM Specific Areas
C-PW-053790 | Floor Surface Preparation for Epoxy Coating | 10 | 2022-04-11 | 2022-04-21 | 01 | 04 | 01 | 45 | 002 | 04 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | ZNM Specific Areas
C-PW-053800 | Floor Finishes (Epoxy Coating) | 10 | 2022-04-21 | 2022-05-07 | 01 | 04 | 01 | 45 | 002 | 04 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | ZNM Specific Areas
C-PW-053810 | Installation of Balustrades | 5 | 2022-05-07 | 2022-05-12 | 01 | 04 | 01 | 45 | 002 | 04 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | ZNM Specific Areas
C-PW-053820 | Door Frames Fixing | 5 | 2022-05-12 | 2022-05-17 | 01 | 04 | 01 | 45 | 002 | 04 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | ZNM Specific Areas
C-PW-053830 | Door Shuttering & Ironmongery | 5 | 2022-05-18 | 2022-05-23 | 01 | 04 | 01 | 45 | 002 | 04 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | ZNM Specific Areas
C-PW-053840 | Final Finishes | 10 | 2022-05-31 | 2022-06-12 | 01 | 04 | 01 | 45 | 002 | 04 |  | Building | Architecture | Museum | South East | L-BM Basement Mezzanine Level | ZNM Specific Areas
MEP WORKS |  | 289 | 2021-12-09 | 2022-11-21
NORTH WEST |  | 264 | 2022-01-08 | 2022-11-21
SERVICE SLAB 1&2 AND AIR PLENUM - NORTH |  | 94 | 2022-06-05 | 2022-09-27
ELECTRICAL WORKS |  | 94 | 2022-06-05 | 2022-09-27
C-PW-053850 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-06-05 | 2022-06-14 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053860 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-06-18 | 2022-06-30 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053870 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-06-30 | 2022-07-16 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053880 | LV Switchgears (DB's) | 5 | 2022-07-16 | 2022-07-21 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053890 | Cable/Wire Termination & Dressing | 7 | 2022-07-21 | 2022-07-31 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053900 | Final Fix Electrical (Power Sockets/ Isolators) | 6 | 2022-09-13 | 2022-09-19 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053910 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-14 | 2022-09-22 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053920 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-17 | 2022-09-25 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053930 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-19 | 2022-09-27 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
MECHANICAL |  | 87 | 2022-06-05 | 2022-09-19
HVAC SYSTEM WORKS |  | 79 | 2022-06-14 | 2022-09-19
C-PW-053940 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs incl Testing) | 10 | 2022-06-14 | 2022-06-26 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053950 | 1st Fix HVAC (CHW Piping and Drain pipes incl Testing) | 10 | 2022-06-18 | 2022-06-30 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053960 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 10 | 2022-06-30 | 2022-07-16 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053970 | AHU Installation,Duct Connection,CHW Connection,Electrical Connection | 4 | 2022-07-14 | 2022-07-19 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-053980 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-09-13 | 2022-09-19 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 18 | 2022-06-05 | 2022-06-26
C-PW-053990 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-06-05 | 2022-06-16 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054000 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-06-18 | 2022-06-26 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 18 | 2022-06-11 | 2022-07-02
C-PW-054010 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-06-11 | 2022-06-22 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054020 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-06-22 | 2022-07-02 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELV |  | 84 | 2022-06-05 | 2022-09-15
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 84 | 2022-06-05 | 2022-09-15
C-PW-054030 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-05 | 2022-06-16 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054040 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-18 | 2022-06-29 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054050 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-13 | 2022-09-15 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 82 | 2022-06-07 | 2022-09-15
C-PW-054060 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054070 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054080 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-13 | 2022-09-15 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 81 | 2022-06-08 | 2022-09-15
C-PW-054090 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-08 | 2022-06-21 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054100 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-21 | 2022-07-03 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054110 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-13 | 2022-09-15 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 81 | 2022-06-11 | 2022-09-18
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 79 | 2022-06-11 | 2022-09-15
C-PW-054120 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-11 | 2022-06-22 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054130 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-22 | 2022-07-05 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054140 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-13 | 2022-09-15 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 78 | 2022-06-13 | 2022-09-15
C-PW-054150 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-13 | 2022-06-25 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054160 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-25 | 2022-07-06 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054170 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-13 | 2022-09-15 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 81 | 2022-06-11 | 2022-09-18
C-PW-054180 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 10 | 2022-06-11 | 2022-06-22 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054190 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-06-22 | 2022-07-02 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054200 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 6 | 2022-09-11 | 2022-09-18 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
SERVICE SLAB 3 - NORTH |  | 222 | 2022-01-13 | 2022-10-06
MECHANICAL |  | 215 | 2022-01-13 | 2022-09-29
HVAC SYSTEM WORKS |  | 207 | 2022-01-23 | 2022-09-29
C-PW-054210 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs incl Testing) | 10 | 2022-01-23 | 2022-02-03 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054220 | 1st Fix HVAC (CHW Piping and Drain pipes incl Testing) | 10 | 2022-01-26 | 2022-02-07 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054230 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 10 | 2022-02-07 | 2022-02-20 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054240 | AHU Installation,Duct Connection,CHW Connection,Electrical Connection | 9 | 2022-07-19 | 2022-07-31 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054250 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-09-24 | 2022-09-29 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 18 | 2022-01-13 | 2022-02-03
C-PW-054260 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-01-13 | 2022-01-25 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054270 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-01-25 | 2022-02-03 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 18 | 2022-01-19 | 2022-02-09
C-PW-054280 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-01-19 | 2022-01-31 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054290 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-01-31 | 2022-02-09 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 222 | 2022-01-13 | 2022-10-06
C-PW-054300 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-01-13 | 2022-01-23 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054310 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-02-03 | 2022-02-15 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054320 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-02-16 | 2022-02-28 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054330 | LV Switchgears (DB's) | 5 | 2022-02-28 | 2022-03-06 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054340 | Cable/Wire Termination & Dressing | 7 | 2022-03-06 | 2022-03-14 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054350 | Final Fix Electrical (Power Sockets/ Isolators) | 6 | 2022-09-24 | 2022-09-29 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054360 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-25 | 2022-10-03 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054370 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-27 | 2022-10-05 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054380 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-28 | 2022-10-06 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELV |  | 212 | 2022-01-13 | 2022-09-26
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 212 | 2022-01-13 | 2022-09-26
C-PW-054390 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-01-13 | 2022-01-25 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054400 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-01-25 | 2022-02-06 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054410 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 211 | 2022-01-15 | 2022-09-26
C-PW-054420 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-01-15 | 2022-01-27 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054430 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-01-27 | 2022-02-08 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054440 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 209 | 2022-01-17 | 2022-09-26
C-PW-054450 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-01-17 | 2022-01-29 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054460 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-01-29 | 2022-02-10 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054470 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 209 | 2022-01-19 | 2022-09-27
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 207 | 2022-01-19 | 2022-09-26
C-PW-054480 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-19 | 2022-01-31 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054490 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-01-31 | 2022-02-12 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054500 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 206 | 2022-01-20 | 2022-09-26
C-PW-054510 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-01-20 | 2022-02-01 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054520 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-02-02 | 2022-02-14 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054530 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 207 | 2022-01-20 | 2022-09-27
C-PW-054540 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 10 | 2022-01-20 | 2022-02-01 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054550 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-02-02 | 2022-02-10 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054560 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 6 | 2022-09-21 | 2022-09-27 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
KITCHEN PLANT ROOM- NORTH |  | 264 | 2022-01-08 | 2022-11-21
MECHANICAL |  | 260 | 2022-01-08 | 2022-11-15
HVAC SYSTEM WORKS |  | 236 | 2022-02-03 | 2022-11-15
C-PW-054570 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs incl. Testing) | 57 | 2022-02-03 | 2022-04-11 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054580 | 1st Fix HVAC (CHW Piping and Drain pipes incl. Testing) | 57 | 2022-02-07 | 2022-04-14 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054590 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 10 | 2022-04-14 | 2022-04-26 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054600 | AHU's & Ecology Unit Installation,Duct Connection,CHW Connection,Electrical Connection | 47 | 2022-07-31 | 2022-09-24 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054610 | Final Fix HVAC (Louvers/Wire mesh, Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-11-07 | 2022-11-15 | 01 | 06 | 01 | 46 | 002 | 02 |  | Building | HVAC | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 68 | 2022-01-08 | 2022-03-28
C-PW-054620 | 1st Fix Piping System (Supports, Piping) | 47 | 2022-01-08 | 2022-03-03 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054630 | 2nd Fix Piping System (Fittings & Insulation) | 21 | 2022-03-03 | 2022-03-28 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 47 | 2022-01-13 | 2022-03-09
C-PW-054640 | 2nd Fix Piping System (Fittings & Insulation) | 21 | 2022-01-24 | 2022-02-17 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054650 | Final Fix Installation (Bip Tap) | 2 | 2022-02-17 | 2022-02-19 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054660 | 1st Fix Piping System (Supports, Piping) | 47 | 2022-01-13 | 2022-03-09 | 01 | 08 | 01 | 46 | 002 | 02 |  | Building | Plumbing | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 258 | 2022-01-15 | 2022-11-21
C-PW-054670 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-01-15 | 2022-01-24 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054680 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 47 | 2022-02-07 | 2022-04-03 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054690 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 38 | 2022-04-04 | 2022-05-21 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054700 | LV Switchgears (DB's) | 16 | 2022-05-21 | 2022-06-08 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054710 | Cable/Wire Termination & Dressing | 16 | 2022-06-08 | 2022-06-27 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054720 | Final Fix Electrical (Power Sockets/ Isolators) | 7 | 2022-11-07 | 2022-11-15 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054730 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-09 | 2022-11-17 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054740 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-10 | 2022-11-19 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054750 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-13 | 2022-11-21 | 01 | 07 | 01 | 46 | 002 | 02 |  | Building | Electrical | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELV |  | 252 | 2022-01-17 | 2022-11-15
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 252 | 2022-01-17 | 2022-11-15
C-PW-054760 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 28 | 2022-01-17 | 2022-02-19 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054770 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 16 | 2022-04-04 | 2022-04-21 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054780 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 7 | 2022-11-07 | 2022-11-15 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 250 | 2022-01-18 | 2022-11-15
C-PW-054790 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 28 | 2022-01-18 | 2022-02-20 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054800 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 16 | 2022-02-20 | 2022-03-10 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054810 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 7 | 2022-11-07 | 2022-11-15 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 248 | 2022-01-20 | 2022-11-15
C-PW-054820 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 28 | 2022-01-20 | 2022-02-22 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054830 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 16 | 2022-02-22 | 2022-03-13 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054840 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 7 | 2022-11-07 | 2022-11-15 | 01 | 10 | 01 | 46 | 002 | 02 |  | Building | CCTV | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 253 | 2022-01-15 | 2022-11-15
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 247 | 2022-01-23 | 2022-11-15
C-PW-054850 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 28 | 2022-01-23 | 2022-02-23 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054860 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 16 | 2022-02-24 | 2022-03-14 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054870 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 7 | 2022-11-07 | 2022-11-15 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 245 | 2022-01-24 | 2022-11-15
C-PW-054880 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 28 | 2022-01-24 | 2022-02-26 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054890 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 16 | 2022-02-26 | 2022-03-16 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054900 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 7 | 2022-11-07 | 2022-11-15 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 252 | 2022-01-15 | 2022-11-14
C-PW-054910 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 35 | 2022-01-26 | 2022-03-08 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054920 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 47 | 2022-01-15 | 2022-03-10 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054930 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 7 | 2022-11-06 | 2022-11-14 | 01 | 09 | 01 | 46 | 002 | 02 |  | Building | Firefighting | Museum | North West | L-BM Basement Mezzanine Level | MEP / Service Rooms
NORTH EAST |  | 106 | 2022-06-05 | 2022-10-12
SERVICE SLAB 4&5 - EAST |  | 106 | 2022-06-05 | 2022-10-12
MECHANICAL |  | 95 | 2022-06-05 | 2022-09-28
HVAC SYSTEM WORKS |  | 87 | 2022-06-14 | 2022-09-28
C-PW-054940 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs incl .Testing) | 10 | 2022-06-14 | 2022-06-26 | 01 | 06 | 01 | 44 | 002 | 02 |  | Building | HVAC | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054950 | 1st Fix HVAC (CHW Piping and Drain pipes incl .Testing) | 10 | 2022-06-18 | 2022-06-30 | 01 | 06 | 01 | 44 | 002 | 02 |  | Building | HVAC | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054960 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 10 | 2022-06-30 | 2022-07-16 | 01 | 06 | 01 | 44 | 002 | 02 |  | Building | HVAC | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054970 | AHU Installation,Duct Connection,CHW Connection,Electrical Connection | 14 | 2022-07-14 | 2022-08-01 | 01 | 06 | 01 | 44 | 002 | 02 |  | Building | HVAC | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-054980 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-09-22 | 2022-09-28 | 01 | 06 | 01 | 44 | 002 | 02 |  | Building | HVAC | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 18 | 2022-06-05 | 2022-06-26
C-PW-054990 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-06-05 | 2022-06-16 | 01 | 08 | 01 | 44 | 002 | 02 |  | Building | Plumbing | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055000 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-06-18 | 2022-06-26 | 01 | 08 | 01 | 44 | 002 | 02 |  | Building | Plumbing | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 18 | 2022-06-11 | 2022-07-02
C-PW-055010 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-06-11 | 2022-06-22 | 01 | 08 | 01 | 44 | 002 | 02 |  | Building | Plumbing | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055020 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-06-22 | 2022-07-02 | 01 | 08 | 01 | 44 | 002 | 02 |  | Building | Plumbing | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 106 | 2022-06-05 | 2022-10-12
C-PW-055030 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-06-05 | 2022-06-14 | 01 | 07 | 01 | 44 | 002 | 02 |  | Building | Electrical | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055040 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-06-18 | 2022-06-30 | 01 | 07 | 01 | 44 | 002 | 02 |  | Building | Electrical | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055050 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-06-30 | 2022-07-16 | 01 | 07 | 01 | 44 | 002 | 02 |  | Building | Electrical | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055060 | LV Switchgears (DB's) | 5 | 2022-07-16 | 2022-07-21 | 01 | 07 | 01 | 44 | 002 | 02 |  | Building | Electrical | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055070 | Cable/Wire Termination & Dressing | 7 | 2022-07-21 | 2022-07-31 | 01 | 07 | 01 | 44 | 002 | 02 |  | Building | Electrical | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055080 | Final Fix Electrical (Power Sockets/ Isolators) | 6 | 2022-09-22 | 2022-09-28 | 01 | 07 | 01 | 44 | 002 | 02 |  | Building | Electrical | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055090 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-28 | 2022-10-06 | 01 | 07 | 01 | 44 | 002 | 02 |  | Building | Electrical | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055100 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-10-01 | 2022-10-10 | 01 | 07 | 01 | 44 | 002 | 02 |  | Building | Electrical | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055110 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-03 | 2022-10-12 | 01 | 07 | 01 | 44 | 002 | 02 |  | Building | Electrical | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELV |  | 96 | 2022-06-07 | 2022-10-02
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 96 | 2022-06-07 | 2022-10-02
C-PW-055120 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 44 | 002 | 02 |  | Building | CCTV | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055130 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 10 | 01 | 44 | 002 | 02 |  | Building | CCTV | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055140 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 10 | 01 | 44 | 002 | 02 |  | Building | CCTV | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 94 | 2022-06-08 | 2022-10-02
C-PW-055150 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-08 | 2022-06-21 | 01 | 10 | 01 | 44 | 002 | 02 |  | Building | CCTV | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055160 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-21 | 2022-07-03 | 01 | 10 | 01 | 44 | 002 | 02 |  | Building | CCTV | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055170 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 10 | 01 | 44 | 002 | 02 |  | Building | CCTV | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 93 | 2022-06-11 | 2022-10-02
C-PW-055180 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 44 | 002 | 02 |  | Building | CCTV | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055190 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-22 | 2022-07-05 | 01 | 10 | 01 | 44 | 002 | 02 |  | Building | CCTV | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055200 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 10 | 01 | 44 | 002 | 02 |  | Building | CCTV | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 93 | 2022-06-11 | 2022-10-02
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 91 | 2022-06-13 | 2022-10-02
C-PW-055210 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-13 | 2022-06-25 | 01 | 09 | 01 | 44 | 002 | 02 |  | Building | Firefighting | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055220 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-25 | 2022-07-06 | 01 | 09 | 01 | 44 | 002 | 02 |  | Building | Firefighting | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055230 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 09 | 01 | 44 | 002 | 02 |  | Building | Firefighting | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 90 | 2022-06-14 | 2022-10-02
C-PW-055240 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-26 | 01 | 09 | 01 | 44 | 002 | 02 |  | Building | Firefighting | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055250 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-27 | 2022-07-09 | 01 | 09 | 01 | 44 | 002 | 02 |  | Building | Firefighting | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055260 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 09 | 01 | 44 | 002 | 02 |  | Building | Firefighting | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 89 | 2022-06-11 | 2022-09-27
C-PW-055270 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 10 | 2022-06-11 | 2022-06-22 | 01 | 09 | 01 | 44 | 002 | 02 |  | Building | Firefighting | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055280 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-06-22 | 2022-07-02 | 01 | 09 | 01 | 44 | 002 | 02 |  | Building | Firefighting | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055290 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 6 | 2022-09-20 | 2022-09-27 | 01 | 09 | 01 | 44 | 002 | 02 |  | Building | Firefighting | Museum | North East | L-BM Basement Mezzanine Level | MEP / Service Rooms
SOUTH WEST |  | 123 | 2022-03-20 | 2022-08-18
SERVICE BRIDGE AND SERVICE SLAB 12 - WEST |  | 115 | 2022-03-29 | 2022-08-18
MECHANICAL |  | 109 | 2022-03-29 | 2022-08-11
HVAC SYSTEM WORKS |  | 101 | 2022-04-07 | 2022-08-11
C-PW-055300 | 1st Fix HVAC (Supports, Ducts, Insulation, Dampers - VCD,NRD,MDs incl . Testing) | 8 | 2022-04-07 | 2022-04-17 | 01 | 06 | 01 | 47 | 002 | 02 |  | Building | HVAC | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055310 | 1st Fix HVAC (CHW Piping and Drain pipes incl. Testing) | 8 | 2022-04-11 | 2022-04-20 | 01 | 06 | 01 | 47 | 002 | 02 |  | Building | HVAC | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055320 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 10 | 2022-04-20 | 2022-05-07 | 01 | 06 | 01 | 47 | 002 | 02 |  | Building | HVAC | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055330 | AHU Installation,Duct Connection,CHW Connection,Electrical Connection & Canadian Duct Connection | 28 | 2022-05-05 | 2022-06-07 | 01 | 06 | 01 | 47 | 002 | 02 |  | Building | HVAC | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055340 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-08-04 | 2022-08-11 | 01 | 06 | 01 | 47 | 002 | 02 |  | Building | HVAC | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 18 | 2022-03-29 | 2022-04-19
C-PW-055350 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-03-29 | 2022-04-10 | 01 | 08 | 01 | 47 | 002 | 02 |  | Building | Plumbing | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055360 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-04-11 | 2022-04-19 | 01 | 08 | 01 | 47 | 002 | 02 |  | Building | Plumbing | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 18 | 2022-04-04 | 2022-04-25
C-PW-055370 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-04-04 | 2022-04-16 | 01 | 08 | 01 | 47 | 002 | 02 |  | Building | Plumbing | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055380 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-04-16 | 2022-04-25 | 01 | 08 | 01 | 47 | 002 | 02 |  | Building | Plumbing | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 115 | 2022-03-29 | 2022-08-18
C-PW-055390 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-03-29 | 2022-04-07 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055400 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 8 | 2022-04-11 | 2022-04-20 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055410 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-04-20 | 2022-05-07 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055420 | LV Switchgears (DB's) | 5 | 2022-05-07 | 2022-05-11 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055430 | Cable/Wire Termination & Dressing | 7 | 2022-05-12 | 2022-05-21 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055440 | Final Fix Electrical (Power Sockets/ Isolators) | 6 | 2022-08-04 | 2022-08-11 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055450 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-07 | 2022-08-15 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055460 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-09 | 2022-08-17 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055470 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-10 | 2022-08-18 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELV |  | 104 | 2022-03-31 | 2022-08-08
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 104 | 2022-03-31 | 2022-08-08
C-PW-055480 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055490 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-20 | 2022-05-07 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055500 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-08 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 102 | 2022-04-02 | 2022-08-08
C-PW-055510 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-02 | 2022-04-14 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055520 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055530 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-08 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 101 | 2022-04-04 | 2022-08-08
C-PW-055540 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055550 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-16 | 2022-04-28 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055560 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-08 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 102 | 2022-04-04 | 2022-08-09
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 101 | 2022-04-04 | 2022-08-08
C-PW-055570 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055580 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-16 | 2022-04-28 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055590 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-08 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 99 | 2022-04-06 | 2022-08-08
C-PW-055600 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-06 | 2022-04-18 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055610 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-18 | 2022-04-30 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055620 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-08 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 102 | 2022-04-04 | 2022-08-09
C-PW-055630 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 8 | 2022-04-04 | 2022-04-13 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055640 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-04-13 | 2022-04-23 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055650 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 6 | 2022-08-03 | 2022-08-09 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
WATER TREATMENT PLANT - WEST |  | 96 | 2022-03-20 | 2022-07-17
MECHANICAL |  | 91 | 2022-03-26 | 2022-07-17
HVAC SYSTEM WORKS |  | 88 | 2022-03-29 | 2022-07-17
C-PW-055660 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 7 | 2022-03-29 | 2022-04-06 | 01 | 06 | 01 | 47 | 002 | 02 |  | Building | HVAC | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055670 | 1st Fix HVAC (CHW Piping and Drain pipes) | 7 | 2022-04-06 | 2022-04-14 | 01 | 06 | 01 | 47 | 002 | 02 |  | Building | HVAC | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055680 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 8 | 2022-04-16 | 2022-04-24 | 01 | 06 | 01 | 47 | 002 | 02 |  | Building | HVAC | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055690 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-07-07 | 2022-07-17 | 01 | 06 | 01 | 47 | 002 | 02 |  | Building | HVAC | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 49 | 2022-03-26 | 2022-05-25
C-PW-055700 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-03-26 | 2022-04-05 | 01 | 08 | 01 | 47 | 002 | 02 |  | Building | Plumbing | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055710 | 2nd Fix Piping System (Fittings & Insulation) | 7 | 2022-04-05 | 2022-04-13 | 01 | 08 | 01 | 47 | 002 | 02 |  | Building | Plumbing | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055720 | Install Equipment and piping works | 22 | 2022-04-26 | 2022-05-25 | 01 | 08 | 01 | 47 | 002 | 02 |  | Building | Plumbing | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 90 | 2022-03-26 | 2022-07-16
C-PW-055730 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-03-26 | 2022-04-03 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055740 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-04-03 | 2022-04-13 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055750 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 9 | 2022-04-13 | 2022-04-24 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055760 | LV Switchgears (DB's) | 5 | 2022-04-24 | 2022-04-28 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055770 | Cable/Wire Termination & Dressing | 7 | 2022-04-30 | 2022-05-11 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055780 | Final Fix Electrical (Final Fixture) | 5 | 2022-07-07 | 2022-07-16 | 01 | 07 | 01 | 47 | 002 | 02 |  | Building | Electrical | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELV |  | 86 | 2022-03-28 | 2022-07-13
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 86 | 2022-03-28 | 2022-07-13
C-PW-055790 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-28 | 2022-04-09 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055800 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-09 | 2022-04-20 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055810 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-07-07 | 2022-07-13 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 76 | 2022-04-09 | 2022-07-13
C-PW-055820 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-20 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055830 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-20 | 2022-05-07 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055840 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-07-07 | 2022-07-13 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 74 | 2022-04-11 | 2022-07-13
C-PW-055850 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-11 | 2022-04-23 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055860 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-23 | 2022-05-08 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055870 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-07-07 | 2022-07-13 | 01 | 10 | 01 | 47 | 002 | 02 |  | Building | CCTV | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 94 | 2022-03-20 | 2022-07-14
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 73 | 2022-04-12 | 2022-07-13
C-PW-055880 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-12 | 2022-04-24 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055890 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-25 | 2022-05-10 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055900 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-07 | 2022-07-13 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 71 | 2022-04-14 | 2022-07-13
C-PW-055910 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055920 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 10 | 2022-04-26 | 2022-05-11 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055930 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 2 | 2022-07-07 | 2022-07-13 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 94 | 2022-03-20 | 2022-07-14
C-PW-055940 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 7 | 2022-03-20 | 2022-03-28 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055950 | 2nd Fix Piping System - (Fittings) | 6 | 2022-03-28 | 2022-04-04 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055960 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-07-05 | 2022-07-14 | 01 | 09 | 01 | 47 | 002 | 02 |  | Building | Firefighting | Museum | South West | L-BM Basement Mezzanine Level | MEP / Service Rooms
SOUTH EAST |  | 109 | 2022-02-12 | 2022-06-22
SERVICE SLAB 6 - SOUTH MEP |  | 109 | 2022-02-12 | 2022-06-22
MECHANICAL |  | 70 | 2022-02-15 | 2022-05-11
HVAC SYSTEM WORKS |  | 45 | 2022-03-16 | 2022-05-11
C-PW-055970 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs incl .Testing) | 8 | 2022-03-16 | 2022-03-26 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055980 | 1st Fix HVAC (CHW Piping and Drain pipes incl .Testing) | 8 | 2022-03-26 | 2022-04-04 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-055990 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 7 | 2022-04-04 | 2022-04-12 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056000 | AHU Installation,Duct Connection,CHW Connection,Electrical Connection | 14 | 2022-04-16 | 2022-05-04 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056010 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-05-05 | 2022-05-11 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 18 | 2022-02-15 | 2022-03-08
C-PW-056020 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-02-15 | 2022-02-27 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056030 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-02-28 | 2022-03-08 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 16 | 2022-03-13 | 2022-03-31
C-PW-056040 | 1st Fix Piping System (Supports, Piping) | 8 | 2022-03-13 | 2022-03-22 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056050 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-03-22 | 2022-03-31 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 74 | 2022-02-12 | 2022-05-12
C-PW-056060 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 11 | 2022-02-12 | 2022-02-24 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056070 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 8 | 2022-03-21 | 2022-03-29 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056080 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-03-30 | 2022-04-11 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056090 | LV Switchgears (DB's) | 5 | 2022-04-11 | 2022-04-17 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056100 | Cable/Wire Termination & Dressing | 7 | 2022-04-17 | 2022-04-25 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056110 | Final Fix Electrical (Power Sockets/ Isolators) | 6 | 2022-04-25 | 2022-05-04 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056120 | Final Fix Electrical (Light Fixtures) | 7 | 2022-04-27 | 2022-05-09 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056130 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-04-28 | 2022-05-10 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056140 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-05-04 | 2022-05-12 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELV |  | 60 | 2022-02-17 | 2022-04-27
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 60 | 2022-02-17 | 2022-04-27
C-PW-056150 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-17 | 2022-03-01 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056160 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-01 | 2022-03-13 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056170 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-27 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 58 | 2022-02-19 | 2022-04-27
C-PW-056180 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-19 | 2022-03-03 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056190 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-03 | 2022-03-15 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056200 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-27 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 56 | 2022-02-21 | 2022-04-27
C-PW-056210 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-21 | 2022-03-05 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056220 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-05 | 2022-03-17 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056230 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-27 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 102 | 2022-02-21 | 2022-06-22
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 56 | 2022-02-21 | 2022-04-27
C-PW-056240 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-21 | 2022-03-05 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056250 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-05 | 2022-03-17 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056260 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-27 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 55 | 2022-02-23 | 2022-04-27
C-PW-056270 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-02-23 | 2022-03-07 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056280 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-07 | 2022-03-19 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056290 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-27 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 88 | 2022-03-09 | 2022-06-22
C-PW-056300 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 11 | 2022-03-09 | 2022-03-22 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056310 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-03-22 | 2022-03-31 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056320 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 6 | 2022-06-16 | 2022-06-22 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
SERVICE SLAB 7&8 - SOUTH MEP |  | 94 | 2022-02-23 | 2022-06-15
MECHANICAL |  | 51 | 2022-02-27 | 2022-04-27
HVAC SYSTEM WORKS |  | 35 | 2022-03-17 | 2022-04-27
C-PW-056330 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs incl. Testing) | 8 | 2022-03-17 | 2022-03-27 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056340 | 1st Fix HVAC (CHW Piping and Drain pipes incl. Testing) | 8 | 2022-03-21 | 2022-03-30 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056350 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 3 | 2022-03-30 | 2022-04-03 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056360 | AHU Installation,Duct Connection,CHW Connection,Electrical Connection | 9 | 2022-04-11 | 2022-04-20 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056370 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-04-20 | 2022-04-27 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 18 | 2022-02-27 | 2022-03-20
C-PW-056380 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-02-27 | 2022-03-10 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056390 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-03-10 | 2022-03-20 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 18 | 2022-03-14 | 2022-04-04
C-PW-056400 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-03-14 | 2022-03-26 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056410 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-03-26 | 2022-04-04 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 63 | 2022-02-23 | 2022-05-11
C-PW-056420 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-02-23 | 2022-03-05 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056430 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 8 | 2022-03-21 | 2022-03-30 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056440 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-03-30 | 2022-04-11 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056450 | LV Switchgears (DB's) | 5 | 2022-04-11 | 2022-04-17 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056460 | Cable/Wire Termination & Dressing | 7 | 2022-04-17 | 2022-04-25 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056470 | Final Fix Electrical (Power Sockets/ Isolators) | 6 | 2022-04-25 | 2022-05-05 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056480 | Final Fix Electrical (Light Fixtures) | 7 | 2022-04-27 | 2022-05-09 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056490 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-04-30 | 2022-05-11 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELV |  | 50 | 2022-02-28 | 2022-04-28
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 50 | 2022-02-28 | 2022-04-28
C-PW-056500 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-28 | 2022-03-13 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056510 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-30 | 2022-04-11 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056520 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-28 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 49 | 2022-03-02 | 2022-04-28
C-PW-056530 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-02 | 2022-03-14 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056540 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-14 | 2022-03-27 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056550 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-28 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 47 | 2022-03-05 | 2022-04-28
C-PW-056560 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-05 | 2022-03-16 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056570 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-16 | 2022-03-28 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056580 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-28 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 84 | 2022-03-06 | 2022-06-15
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 46 | 2022-03-06 | 2022-04-28
C-PW-056590 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-06 | 2022-03-17 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056600 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-19 | 2022-03-30 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056610 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-28 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 44 | 2022-03-08 | 2022-04-28
C-PW-056620 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-08 | 2022-03-20 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056630 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-20 | 2022-03-31 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056640 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-04-25 | 2022-04-28 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 78 | 2022-03-14 | 2022-06-15
C-PW-056650 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 8 | 2022-03-14 | 2022-03-22 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056660 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-03-23 | 2022-03-31 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056670 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 6 | 2022-06-09 | 2022-06-15 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
SERVICE BRIDGE & TUNNEL |  | 145 | 2021-12-09 | 2022-05-31
MECHANICAL |  | 48 | 2022-02-27 | 2022-04-24
HVAC SYSTEM WORKS |  | 38 | 2022-03-09 | 2022-04-24
C-PW-056680 | 1st Fix HVAC (Supports, Ducts, Insulation & Dampers - VCD,NRD,MDs) | 10 | 2022-03-09 | 2022-03-22 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056690 | 1st Fix HVAC (CHW Piping and Drain pipes) | 10 | 2022-03-22 | 2022-04-03 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056700 | 2nd Fix HVAC (FCUs, Droppers, Dampers, Fans) | 12 | 2022-04-03 | 2022-04-17 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056710 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-04-17 | 2022-04-24 | 01 | 06 | 01 | 45 | 002 | 02 |  | Building | HVAC | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 18 | 2022-02-27 | 2022-03-20
C-PW-056720 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-02-27 | 2022-03-10 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056730 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-03-10 | 2022-03-20 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 18 | 2022-03-06 | 2022-03-27
C-PW-056740 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-03-06 | 2022-03-17 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056750 | 2nd Fix Piping System (Fittings & Insulation) | 8 | 2022-03-19 | 2022-03-27 | 01 | 08 | 01 | 45 | 002 | 02 |  | Building | Plumbing | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 57 | 2022-02-23 | 2022-04-30
C-PW-056760 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-02-23 | 2022-03-05 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056770 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-03-05 | 2022-03-16 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056780 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-03-16 | 2022-03-28 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056790 | LV Switchgears (DB's) | 5 | 2022-03-29 | 2022-04-03 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056800 | Cable/Wire Termination & Dressing | 7 | 2022-04-03 | 2022-04-11 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056810 | Final Fix Electrical (Power Sockets/ Isolators) | 6 | 2022-04-12 | 2022-04-18 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056820 | Final Fix Electrical (Light Fixtures) | 7 | 2022-04-18 | 2022-04-26 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056830 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-04-20 | 2022-04-28 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056840 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-04-21 | 2022-04-30 | 01 | 07 | 01 | 45 | 002 | 02 |  | Building | Electrical | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
ELV |  | 26 | 2022-02-21 | 2022-03-23
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-02-21 | 2022-03-20
C-PW-056850 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-21 | 2022-03-05 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056860 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-05 | 2022-03-17 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056870 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-03-17 | 2022-03-20 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 23 | 2022-02-23 | 2022-03-22
C-PW-056880 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-23 | 2022-03-07 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056890 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-07 | 2022-03-19 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056900 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-03-19 | 2022-03-22 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-02-24 | 2022-03-23
C-PW-056910 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-24 | 2022-03-08 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056920 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-09 | 2022-03-21 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056930 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-03-21 | 2022-03-23 | 01 | 10 | 01 | 45 | 002 | 02 |  | Building | CCTV | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 145 | 2021-12-09 | 2022-05-31
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 23 | 2021-12-09 | 2022-01-06
C-PW-056940 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2021-12-09 | 2021-12-21 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056950 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2021-12-21 | 2022-01-03 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056960 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-01-03 | 2022-01-06 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 61 | 2021-12-11 | 2022-02-21
C-PW-056970 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2021-12-11 | 2021-12-22 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056980 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2021-12-23 | 2022-01-05 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-056990 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-02-19 | 2022-02-21 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 77 | 2022-02-27 | 2022-05-31
C-PW-057000 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 10 | 2022-02-27 | 2022-03-10 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-057010 | 2nd Fix Piping System - (Fittings) | 8 | 2022-03-10 | 2022-03-20 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
C-PW-057020 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-05-25 | 2022-05-31 | 01 | 09 | 01 | 45 | 002 | 02 |  | Building | Firefighting | Museum | South East | L-BM Basement Mezzanine Level | MEP / Service Rooms
LEVEL 00 GROUND |  | 620 | 2021-04-21 | 2023-05-11
CIVIL WORKS |  | 331 | 2021-04-21 | 2022-05-28
ZONE 02C |  | 32 | 2021-11-25 | 2022-01-04
C-PW-057030 | Construction of Verticals & Zone 02 Ceiling Slab at Level +13.475m - Zone 2C | 32 | 2021-11-25 | 2022-01-04 | 01 | 01 | 01 | 09 | 003 | 30 |  | Building | Civil | Museum | Zone 02C | L00 Ground Level | Civil SubZones
ZONE 02D |  | 286 | 2021-05-09 | 2022-04-19
C-PW-057040 | Site Survey for Action (Item 21 - Immediate) | 1 | 2021-05-09 | 2021-05-09 | 01 | 01 | 01 | 10 | 003 | 30 |  | Building | Civil | Museum | Zone 02D | L00 Ground Level | Civil SubZones
C-PW-057050 | Construction of Verticals up to Level 01 Slab - Zone 2D (Item 21 - Immediate) | 12 | 2021-08-17 | 2021-08-30 | 01 | 01 | 01 | 10 | 003 | 30 |  | Building | Civil | Museum | Zone 02D | L00 Ground Level | Civil SubZones
C-PW-057060 | Construction of Ground Floor Slab - Zone 2D | 26 | 2022-01-29 | 2022-02-27 | 01 | 01 | 01 | 10 | 003 | 30 |  | Building | Civil | Museum | Zone 02D | L00 Ground Level | Civil SubZones
C-PW-057070 | Construction of Verticals up to Level 01 Slab - Zone 2D | 26 | 2022-02-05 | 2022-03-06 | 01 | 01 | 01 | 10 | 003 | 30 |  | Building | Civil | Museum | Zone 02D | L00 Ground Level | Civil SubZones
C-PW-057080 | Hollow Core Slab installation - Zone 2D | 24 | 2022-03-23 | 2022-04-19 | 01 | 01 | 01 | 10 | 003 | 30 |  | Building | Civil | Museum | Zone 02D | L00 Ground Level | Civil SubZones
ZONE 02E |  | 153 | 2021-04-21 | 2021-10-25
C-PW-057090 | Site Survey for Action (Item 16 - Immediate) | 1 | 2021-04-21 | 2021-04-21 | 01 | 01 | 01 | 11 | 003 | 30 |  | Building | Civil | Museum | Zone 02E | L00 Ground Level | Civil SubZones
C-PW-057100 | Construction of Ground Floor Slab - Zone 2E - Tunnel Slab - (Item 16 - Immediate) | 12 | 2021-06-26 | 2021-07-08 | 01 | 01 | 01 | 11 | 003 | 30 |  | Building | Civil | Museum | Zone 02E | L00 Ground Level | Civil SubZones
C-PW-057110 | Construction of Ground Floor Slab - Zone 2E | 24 | 2021-09-20 | 2021-10-17 | 01 | 01 | 01 | 11 | 003 | 30 |  | Building | Civil | Museum | Zone 02E | L00 Ground Level | Civil SubZones
C-PW-057120 | Construction of Verticals up to Level 01 Slab - Zone 2E | 24 | 2021-09-27 | 2021-10-25 | 01 | 01 | 01 | 11 | 003 | 30 |  | Building | Civil | Museum | Zone 02E | L00 Ground Level | Civil SubZones
ZONE 02F |  | 24 | 2021-10-26 | 2021-11-22
C-PW-057130 | Hollow Core Installation - Zone 2F | 24 | 2021-10-26 | 2021-11-22 | 01 | 01 | 01 | 12 | 003 | 30 |  | Building | Civil | Museum | Zone 02F | L00 Ground Level | Civil SubZones
ZONE 02G |  | 24 | 2021-11-02 | 2021-11-29
C-PW-057140 | Construction of Verticals from GF to Level 01Stage 01 - Zone 2G | 24 | 2021-11-02 | 2021-11-29 | 01 | 01 | 01 | 13 | 003 | 30 |  | Building | Civil | Museum | Zone 02G | L00 Ground Level | Civil SubZones
ZONE 03B |  | 233 | 2021-04-24 | 2022-02-01
C-PW-057150 | Site Survey for Action (Item 11 - Immediate) | 1 | 2021-04-24 | 2021-04-24 | 01 | 01 | 01 | 16 | 003 | 30 |  | Building | Civil | Museum | Zone 03B | L00 Ground Level | Civil SubZones
C-PW-057160 | Site Survey for Action (Item 13 - Immediate) | 1 | 2021-04-25 | 2021-04-25 | 01 | 01 | 01 | 16 | 003 | 30 |  | Building | Civil | Museum | Zone 03B | L00 Ground Level | Civil SubZones
C-PW-057170 | Site Survey for Action (Item 12 - Immediate) | 1 | 2021-05-02 | 2021-05-02 | 01 | 01 | 01 | 16 | 003 | 30 |  | Building | Civil | Museum | Zone 03B | L00 Ground Level | Civil SubZones
C-PW-057180 | Construction of Gr-Mz 01 Slab - Zone 3B (Item 11 - Immediate) | 10 | 2021-07-10 | 2021-07-24 | 01 | 01 | 01 | 16 | 003 | 30 |  | Building | Civil | Museum | Zone 03B | L00 Ground Level | Civil SubZones
C-PW-057190 | Construction of Gr-Mz 01 Wall - Zone 3B (Item 13 - Immediate) | 12 | 2021-07-25 | 2021-08-07 | 01 | 01 | 01 | 16 | 003 | 30 |  | Building | Civil | Museum | Zone 03B | L00 Ground Level | Civil SubZones
C-PW-057200 | Construction of Ground Level Slab - Zone 3B (Item 12 - Immediate) | 10 | 2021-08-08 | 2021-08-19 | 01 | 01 | 01 | 16 | 003 | 30 |  | Building | Civil | Museum | Zone 03B | L00 Ground Level | Civil SubZones
C-PW-057210 | Construction of Ground Level Slab - Zone 3B | 24 | 2021-12-26 | 2022-01-23 | 01 | 01 | 01 | 16 | 003 | 30 |  | Building | Civil | Museum | Zone 03B | L00 Ground Level | Civil SubZones
C-PW-057220 | Construction of Verticals up to Level 01 Slab - Zone 3B | 26 | 2022-01-03 | 2022-02-01 | 01 | 01 | 01 | 16 | 003 | 30 |  | Building | Civil | Museum | Zone 03B | L00 Ground Level | Civil SubZones
ZONE 03C |  | 32 | 2022-04-18 | 2022-05-28
C-PW-057230 | Construction of Ground Floor Slab - Zone 3C | 15 | 2022-04-18 | 2022-05-08 | 01 | 01 | 01 | 17 | 003 | 30 |  | Building | Civil | Museum | Zone 03C | L00 Ground Level | Civil SubZones
C-PW-057240 | Construction of Verticals up to Level 01 Slab - Zone 3C | 26 | 2022-04-25 | 2022-05-28 | 01 | 01 | 01 | 17 | 003 | 30 |  | Building | Civil | Museum | Zone 03C | L00 Ground Level | Civil SubZones
ZONE 03A |  | 32 | 2021-12-05 | 2022-01-11
C-PW-057250 | Construction of Ground Floor Slab - Zone 3A | 26 | 2021-12-05 | 2022-01-04 | 01 | 01 | 01 | 15 | 003 | 30 |  | Building | Civil | Museum | Zone 03A | L00 Ground Level | Civil SubZones
C-PW-057260 | Construction of Verticals up to Level 01 Slab - Zone 3A | 26 | 2021-12-12 | 2022-01-11 | 01 | 01 | 01 | 15 | 003 | 30 |  | Building | Civil | Museum | Zone 03A | L00 Ground Level | Civil SubZones
ARCHITECTURAL WORKS |  | 482 | 2021-10-07 | 2023-05-11
NORTH WEST |  | 383 | 2022-02-05 | 2023-05-11
COMMON WORKS- NORTH |  | 35 | 2022-02-05 | 2022-03-17
C-PW-057270 | General Block Work | 19 | 2022-02-05 | 2022-02-27 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057280 | Marking & Chasing Walls for MEP Services | 16 | 2022-02-27 | 2022-03-17 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
RESTAURANT GALLERIES,PANTRY,PUBLIC TOILETS,GRAB&GO- NORTH |  | 130 | 2022-04-04 | 2022-09-11
C-PW-057290 | Floor Waterproofing Works in wet areas | 8 | 2022-04-04 | 2022-04-12 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057300 | Floor Screed Works | 8 | 2022-04-13 | 2022-04-21 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057310 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-05-09 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057320 | Floor Finishes (Polished Conc floor finish) | 14 | 2022-05-09 | 2022-05-25 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057330 | Wall Finishes (Plate render,PVC,Stone Wall Linings) | 19 | 2022-05-25 | 2022-06-16 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057340 | Ceiling Grid / Support Works | 14 | 2022-06-06 | 2022-06-22 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057350 | Wall Finishes - Balcony (Wall Cladding) | 14 | 2022-06-16 | 2022-07-04 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057360 | Ceiling Finishes (Suspended Plaster board ceiling) | 14 | 2022-06-22 | 2022-07-09 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057370 | Floor Finishes - Balcony (Flexible Terrazzo) | 10 | 2022-07-04 | 2022-07-18 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057380 | Floor Finishes (Resin & Timber board flooring) | 14 | 2022-07-13 | 2022-07-31 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057390 | Door Frames & Architrave Fixing | 6 | 2022-07-31 | 2022-08-07 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057400 | Door Shuttering & Ironmongery | 6 | 2022-08-07 | 2022-08-15 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057410 | Final Finishes & Fittings | 14 | 2022-08-25 | 2022-09-11 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
GRAB&GO - TENANT FITOUT |  | 0 | 2022-09-11 | 2022-09-11
C-PW-057420 | Access for Tenant Fit-out Works | 0 |  | 2022-09-11 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
AUDITORIUM,CONFERENCE ROOM,LOBBY AND ASSOCIATED ROOMS- NORTH |  | 176 | 2022-04-18 | 2022-11-17
C-PW-057440 | Plastering Works - Walls | 11 | 2022-04-18 | 2022-05-04 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057450 | Void Former & Floor Screed | 11 | 2022-04-25 | 2022-05-11 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057460 | Wall Finishes | 22 | 2022-05-11 | 2022-06-06 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057430 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-22 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057470 | Ceiling Grid / Support Works | 19 | 2022-06-22 | 2022-07-18 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057480 | Ceiling Finishes (Plasterboard Ceilings & Fabric Lining Ceiling) | 19 | 2022-07-18 | 2022-08-10 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057490 | Floor Finishes (Carpet boardloom & Timber floor) | 19 | 2022-08-11 | 2022-09-03 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057500 | Door Frames Fixing | 11 | 2022-09-03 | 2022-09-15 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057510 | Door Shuttering & Ironmongery | 11 | 2022-09-15 | 2022-09-28 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057520 | Final Finishes & Fittings | 10 | 2022-10-10 | 2022-10-20 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057530 | Auditorium Fit-out Works | 24 | 2022-10-22 | 2022-11-17 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
KITCHEN AREA,TOILETS & JANITOR ROOMS- NORTH |  | 145 | 2022-05-08 | 2022-10-30
C-PW-057540 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-05-17 | 01 | 14 | 01 | 46 | 003 | 03 |  | Building | General MEP | Museum | North West | L00 Ground Level | Wet Areas
C-PW-057550 | Floor Waterproofing Works | 16 | 2022-05-08 | 2022-05-25 | 01 | 04 | 01 | 46 | 003 | 03 |  | Building | Architecture | Museum | North West | L00 Ground Level | Wet Areas
C-PW-057560 | Void former & Floor Screed Works | 10 | 2022-05-26 | 2022-06-06 | 01 | 04 | 01 | 46 | 003 | 03 |  | Building | Architecture | Museum | North West | L00 Ground Level | Wet Areas
C-PW-057570 | Wall Finishes (PVC wall lining,WC cubicles & wall tiles) | 18 | 2022-05-30 | 2022-06-19 | 01 | 04 | 01 | 46 | 003 | 03 |  | Building | Architecture | Museum | North West | L00 Ground Level | Wet Areas
C-PW-057580 | Ceiling Grid / Support Works | 18 | 2022-06-19 | 2022-07-13 | 01 | 04 | 01 | 46 | 003 | 03 |  | Building | Architecture | Museum | North West | L00 Ground Level | Wet Areas
C-PW-057590 | Ceiling Finishes (Metal tile ceiling & Plaster board ceiling) | 18 | 2022-07-13 | 2022-08-03 | 01 | 04 | 01 | 46 | 003 | 03 |  | Building | Architecture | Museum | North West | L00 Ground Level | Wet Areas
C-PW-057600 | Floor Finishes (Resin flooring system,Ceramic Tiles) | 18 | 2022-07-19 | 2022-08-09 | 01 | 04 | 01 | 46 | 003 | 03 |  | Building | Architecture | Museum | North West | L00 Ground Level | Wet Areas
C-PW-057610 | Door Frames Fixing | 13 | 2022-08-09 | 2022-08-24 | 01 | 04 | 01 | 46 | 003 | 03 |  | Building | Architecture | Museum | North West | L00 Ground Level | Wet Areas
C-PW-057620 | Door Shuttering & Ironmongery | 13 | 2022-09-19 | 2022-10-04 | 01 | 04 | 01 | 46 | 003 | 03 |  | Building | Architecture | Museum | North West | L00 Ground Level | Wet Areas
C-PW-057630 | Final Finishes & Fittings | 13 | 2022-10-15 | 2022-10-30 | 01 | 04 | 01 | 46 | 003 | 03 |  | Building | Architecture | Museum | North West | L00 Ground Level | Wet Areas
KITCHEN AREAS - TENANT FITOUT |  | 0 | 2022-05-17 | 2022-05-17
C-PW-057640 | Access for Tenant Fit-out Works | 0 |  | 2022-05-17 | 01 | 04 | 01 | 46 | 003 | 03 |  | Building | Architecture | Museum | North West | L00 Ground Level | Wet Areas
RESTAURANT,VIP VIEWING LOUNGE- NORTH |  | 158 | 2022-05-22 | 2022-11-28
C-PW-057650 | Floor Screed Works | 5 | 2022-05-22 | 2022-05-26 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057660 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-14 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057670 | Ceiling Grid / Support Works | 14 | 2022-06-14 | 2022-06-30 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057680 | Ceiling Finishes (Suspended plasterboard ceiling & Stretch Fabric Ceiling) | 14 | 2022-07-02 | 2022-07-21 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057690 | Floor Finishes (Polished Conc floor finish incl. screed) | 17 | 2022-07-21 | 2022-08-11 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057700 | Wall Finishes (Plate Render & Bespoke Stone wall system) | 19 | 2022-07-31 | 2022-08-22 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057710 | Wall Finishes - Balcony (Wall Cladding) | 17 | 2022-08-22 | 2022-09-11 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057720 | Floor Finishes - Balcony (Flexible Terrazzo) | 14 | 2022-09-11 | 2022-09-27 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057730 | Balustrades in Balcony | 10 | 2022-09-28 | 2022-10-10 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057740 | Door Frames Fixing | 10 | 2022-09-28 | 2022-10-10 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057750 | Door Shuttering & Ironmongery | 10 | 2022-10-10 | 2022-10-22 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057760 | Final Finishes & Fittings | 8 | 2022-10-31 | 2022-11-09 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-057770 | VIP Viewing Lounge Fit-out Works | 16 | 2022-11-09 | 2022-11-28 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
STAFF OFFICE,VIP VIEWING LOBBY,SECURITY & SCAN AREAS- NORTH |  | 114 | 2022-06-22 | 2022-11-09
C-PW-057780 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-22 | 01 | 14 | 01 | 46 | 003 | 05 |  | Building | General MEP | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057790 | Wall Finishes (Painting & Rendered Finish) | 19 | 2022-06-23 | 2022-07-19 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057800 | Ceiling Grid / Support Works | 5 | 2022-07-19 | 2022-07-24 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057810 | Wall Finishes - Balcony (Wall Cladding) | 10 | 2022-07-19 | 2022-07-31 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057820 | Ceiling Finishes (Plaster board ceiling) | 5 | 2022-07-25 | 2022-07-31 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057830 | Floor Finishes (Polished Conc floor finish & RAF) | 14 | 2022-07-31 | 2022-08-17 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057840 | Floor Finishes - Balcony (Flexible Terrazzo) | 10 | 2022-08-17 | 2022-08-28 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057850 | Balustrades in Balcony | 6 | 2022-08-28 | 2022-09-05 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057860 | Door Frames & Architrave Fixing | 6 | 2022-08-28 | 2022-09-05 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057870 | Door Shuttering & Ironmongery | 6 | 2022-10-13 | 2022-10-22 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057880 | Installation of Lockers | 8 | 2022-10-20 | 2022-10-30 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-057890 | Final Finishes & Fittings | 6 | 2022-11-01 | 2022-11-09 | 01 | 04 | 01 | 46 | 003 | 05 |  | Building | Architecture | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
MAIN LOBBY |  | 295 | 2022-05-22 | 2023-05-11
MEETING SPACE |  | 100 | 2022-10-22 | 2023-02-18
C-PW-058000 | Void Former & Floor Screed Works | 6 | 2022-10-22 | 2022-10-30 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058010 | Specialist Fixtures (Framing for Precast Panels/Glass display cases) | 19 | 2022-10-30 | 2022-11-21 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058020 | Wall Finishes (in-situ White Conc Finish) | 17 | 2022-11-14 | 2022-12-05 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058030 | Floor Finishes (Polished Conc floor finish) | 11 | 2022-11-29 | 2022-12-13 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058040 | Specialist Fixtures (Precast Panels/Glass display cases) | 19 | 2022-12-13 | 2023-01-05 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058050 | Fitout & Step Finishes | 22 | 2023-01-07 | 2023-02-01 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058060 | Installation of Signage | 8 | 2023-02-01 | 2023-02-11 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058070 | Final Finishes & Fittings | 6 | 2023-02-11 | 2023-02-18 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
CAFE |  | 114 | 2022-10-18 | 2023-03-01
C-PW-058080 | Void Former & Floor Screed Works | 10 | 2022-10-18 | 2022-10-29 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058090 | Specialist Fixtures (Framing for Precast Panels/Precast Mould elements) | 17 | 2022-10-29 | 2022-11-17 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058100 | Wall Finishes (in-situ White Conc Finish) | 19 | 2022-11-13 | 2022-12-06 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058110 | Floor Finishes (Polished Conc floor finish) | 11 | 2022-12-06 | 2022-12-19 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058120 | Specialist Fixtures (Precast Panels/Precast Mould elements) | 19 | 2022-12-19 | 2023-01-11 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058130 | Specialist Fixtures (GRC inlay Panels) | 11 | 2023-01-04 | 2023-01-17 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058140 | Fitout & Step Finishes | 22 | 2023-01-17 | 2023-02-13 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058150 | Balustrades and Handrails | 5 | 2023-02-13 | 2023-02-18 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058160 | Installation of Signage | 8 | 2023-02-13 | 2023-02-22 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058170 | Final Finishes & Fittings | 6 | 2023-02-22 | 2023-03-01 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
TICKET/INFO POINT |  | 106 | 2022-06-22 | 2022-10-30
C-PW-058180 | Void Former & Floor Screed Works | 10 | 2022-06-22 | 2022-07-04 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058190 | Wall Finishes (in-situ White Conc Finish) | 19 | 2022-07-26 | 2022-08-18 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058200 | Floor Finishes (Polished Conc floor finish) | 11 | 2022-08-18 | 2022-08-31 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058210 | Specialist Fixtures (Precast Panels) | 22 | 2022-08-31 | 2022-09-26 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058220 | Fitout Works | 10 | 2022-09-27 | 2022-10-08 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058230 | Installation of Signage | 8 | 2022-10-12 | 2022-10-22 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058240 | Final Finishes & Fittings | 6 | 2022-10-22 | 2022-10-30 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
PERFORMANCE SPACE |  | 112 | 2022-08-06 | 2022-12-17
C-PW-058250 | Void Former & Floor Screed Works | 10 | 2022-08-06 | 2022-08-17 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058260 | Specialist Fixtures (Framing for Precast Panels/Seating arrangements) | 17 | 2022-08-17 | 2022-09-05 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058270 | Wall Finishes (in-situ White Conc Finish) | 19 | 2022-09-01 | 2022-09-24 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058280 | Floor Finishes (Polished Conc floor finish) | 11 | 2022-09-24 | 2022-10-06 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058290 | Balustrades and Handrails | 5 | 2022-10-06 | 2022-10-13 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058300 | Specialist Fixtures (Precast Panels/Precast Mould elements) | 22 | 2022-10-06 | 2022-11-02 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058310 | Fitout & Step Finishes | 22 | 2022-11-02 | 2022-11-29 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058320 | Installation of Signage | 8 | 2022-11-29 | 2022-12-10 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058330 | Final Finishes & Fittings | 6 | 2022-12-10 | 2022-12-17 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
RETAIL |  | 109 | 2022-07-24 | 2022-12-01
C-PW-058340 | Void Former & Floor Screed Works | 10 | 2022-07-24 | 2022-08-06 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058350 | Specialist Fixtures (Framing for Precast Panels/Seating arrangements) | 22 | 2022-08-06 | 2022-08-31 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058360 | Wall Finishes (in-situ White Conc Finish) | 19 | 2022-08-21 | 2022-09-12 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058370 | Floor Finishes (Polished Conc floor finish) | 11 | 2022-09-12 | 2022-09-25 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058380 | Balustrades and Handrails | 5 | 2022-09-25 | 2022-10-01 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058390 | Specialist Fixtures (Precast Panels/Glazing elements) | 22 | 2022-09-25 | 2022-10-22 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058400 | Fitout & Step Finishes | 19 | 2022-10-22 | 2022-11-13 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058410 | Installation of Signage | 8 | 2022-11-14 | 2022-11-22 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058420 | Final Finishes & Fittings | 6 | 2022-11-23 | 2022-12-01 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
CIRCULATIONS & CORRIDORS |  | 295 | 2022-05-22 | 2023-05-11
C-PW-058430 | Void Former & Floor Screed Works | 12 | 2022-05-22 | 2022-06-04 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058440 | Ceiling Finishes (Conc Finish) | 17 | 2022-06-05 | 2022-06-23 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058450 | Specialist Fixtures (Framing for Precast Panels) for Central Lift | 14 | 2022-06-20 | 2022-07-06 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058460 | Wall Finishes (in-situ White Conc Finish) | 19 | 2022-06-15 | 2022-07-07 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058470 | Floor Finishes (Polished Conc floor finish) | 14 | 2022-06-30 | 2022-07-20 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058480 | Central Staircase Finishes | 14 | 2022-07-07 | 2022-07-27 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058490 | Balustrades and Handrails | 10 | 2022-07-20 | 2022-08-02 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058500 | Central Staircase GRC Balustrade Cladding | 14 | 2022-07-27 | 2022-08-14 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058510 | Specialist Fixtures (Precast Panels/Glazing elements) | 14 | 2022-08-04 | 2022-08-21 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058520 | Joinery Works | 14 | 2023-04-08 | 2023-04-26 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058530 | Installation of Signage | 8 | 2023-04-26 | 2023-05-06 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058540 | Final Finishes & Fittings | 5 | 2023-05-06 | 2023-05-11 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
ENTRANCE LOBBY |  | 358 | 2022-02-27 | 2023-05-03
CITY ENTRANCE |  | 358 | 2022-02-27 | 2023-05-03
C-PW-058550 | General Block Work | 11 | 2022-02-27 | 2022-03-12 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058560 | Marking & Chasing Walls for MEP Services | 11 | 2022-03-12 | 2022-03-24 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058570 | Plastering Works - Walls | 10 | 2022-04-04 | 2022-04-14 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058580 | Void Former & Floor Screed Works | 17 | 2022-04-04 | 2022-04-23 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058600 | Floor Finishes (Polished Conc floor finish) | 11 | 2022-05-10 | 2022-05-23 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058590 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-05-26 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058610 | Wall Finishes (GRC/Metal Cladding) | 11 | 2022-05-23 | 2022-06-05 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058620 | Door Frames & Architrave Fixing | 13 | 2022-05-23 | 2022-06-07 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058630 | Ceiling Grid / Support Works | 5 | 2022-06-05 | 2022-06-11 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058640 | Ceiling Finishes (GRC ceiling) | 5 | 2022-06-11 | 2022-06-16 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058650 | Door Shuttering & Ironmongery | 13 | 2022-06-11 | 2022-06-26 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058660 | Installation of Signage | 11 | 2022-08-27 | 2022-09-08 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058670 | Joinery Fixing | 10 | 2023-04-08 | 2023-04-18 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058680 | Final Finishes & Fittings | 11 | 2023-04-18 | 2023-05-03 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
GARDEN ENTRANCE |  | 345 | 2022-03-12 | 2023-05-02
C-PW-058690 | General Block Work | 11 | 2022-03-12 | 2022-03-24 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058700 | Marking & Chasing Walls for MEP Services | 11 | 2022-03-24 | 2022-04-06 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058710 | Plastering Works - Walls | 10 | 2022-04-06 | 2022-04-18 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058720 | Void Former & Floor Screed Works | 22 | 2022-04-06 | 2022-05-07 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058730 | Floor Finishes (Polished Conc floor finish) | 6 | 2022-07-04 | 2022-07-14 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058740 | Wall Finishes (GRC/Metal Cladding) | 6 | 2022-07-13 | 2022-07-20 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058750 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-07-25 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058760 | Door Frames & Architrave Fixing | 10 | 2022-07-16 | 2022-07-26 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058770 | Ceiling Grid / Support Works | 5 | 2022-07-25 | 2022-08-01 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058780 | Ceiling Finishes (GRC Soffit, Fabric ceiling) | 5 | 2022-08-01 | 2022-08-07 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058790 | Door Shuttering & Ironmongery | 14 | 2022-08-07 | 2022-08-23 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058800 | Joinery Fixing | 10 | 2023-04-08 | 2023-04-18 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058810 | Installation of Signage | 11 | 2023-04-09 | 2023-04-24 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-058820 | Final Finishes & Fittings | 6 | 2023-04-24 | 2023-05-02 | 01 | 04 | 01 | 46 | 003 | 01 |  | Building | Architecture | Museum | North West | L00 Ground Level | Circulation / Common Areas
NORTH EAST |  | 428 | 2021-12-09 | 2023-05-07
COMMON WORKS - EAST |  | 26 | 2021-12-09 | 2022-01-09
C-PW-058830 | General Block Work | 17 | 2021-12-09 | 2021-12-28 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-058840 | Marking & Chasing Walls for MEP Services | 14 | 2021-12-22 | 2022-01-09 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
GALLERY C & FALCONRY AND CONSERVATION GALLERY - EAST |  | 129 | 2022-07-20 | 2022-12-21
C-PW-058850 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-04 | 01 | 14 | 01 | 44 | 003 | 01 |  | Building | General MEP | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-058860 | Internal Wall Partition & Plastering Works - Walls | 13 | 2022-07-20 | 2022-08-06 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-058870 | Floor Finishes (Polished Conc floor finish incl. screed) | 19 | 2022-08-06 | 2022-08-28 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-058880 | Wall Finishes | 22 | 2022-08-28 | 2022-09-22 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-058890 | Door Frames Fixing | 8 | 2022-09-24 | 2022-10-02 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-058930 | Roller Shutter Installation | 12 | 2022-09-24 | 2022-10-06 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-058900 | Ceiling Grid / Support Works | 13 | 2022-10-03 | 2022-10-18 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-058910 | Ceiling Finishes (Acoustic Plasterboard Ceiling) | 14 | 2022-10-18 | 2022-11-05 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-058920 | Door Shuttering & Ironmongery | 8 | 2022-11-05 | 2022-11-14 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-058940 | Final Finishes & Fittings | 19 | 2022-11-28 | 2022-12-21 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
WILDLIFE KITCHEN & STORAGE,PREPARATION RECEPTION & SHELTER AREAS - EAST |  | 380 | 2022-02-05 | 2023-05-07
C-PW-058950 | Ceiling Finishes (1st Coat Paints) | 7 | 2022-02-05 | 2022-02-13 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-058960 | Floor Waterproofing Works | 3 | 2022-02-13 | 2022-02-16 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-058970 | Void Former & Floor Screed Works | 2 | 2022-02-16 | 2022-02-17 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-058980 | Plastering Works - Walls | 13 | 2022-07-07 | 2022-07-26 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-058990 | Wall Finishes (PVC wall lining & Paints) | 19 | 2022-08-24 | 2022-09-15 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059000 | Floor Finishes (Resin flooring & Vinyl Sheeting) | 14 | 2022-09-15 | 2022-10-02 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059010 | Door Frames Fixing | 6 | 2022-10-03 | 2022-10-11 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059020 | Door Shuttering & Ironmongery | 6 | 2022-11-14 | 2022-11-21 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059030 | Joinery Work | 13 | 2023-04-08 | 2023-04-24 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059040 | Final Finishes & Fittings | 11 | 2023-04-24 | 2023-05-07 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
CIRCULATIONS & CORRIDORS - EAST |  | 110 | 2022-08-17 | 2022-12-26
C-PW-059050 | Plastering Works - Walls | 13 | 2022-08-17 | 2022-08-31 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-059070 | Floor Screed works | 4 | 2022-08-31 | 2022-09-05 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-059060 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-09-08 | 01 | 14 | 01 | 44 | 003 | 01 |  | Building | General MEP | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-059080 | Wall Finishes (Interior Paints) | 19 | 2022-09-10 | 2022-10-02 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-059090 | Ceiling Grid / Support Works | 14 | 2022-10-02 | 2022-10-19 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-059100 | Ceiling Finishes (Plaster board ceiling) | 14 | 2022-10-19 | 2022-11-05 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-059110 | Floor Finishes (Epoxy Resin flooring) | 11 | 2022-11-06 | 2022-11-19 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-059120 | Door Frames & Architrave Fixing | 6 | 2022-11-19 | 2022-11-26 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-059130 | Door Shuttering & Ironmongery | 6 | 2022-11-26 | 2022-12-04 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-059140 | Final Finishes & Fittings | 6 | 2022-12-19 | 2022-12-26 | 01 | 04 | 01 | 44 | 003 | 01 |  | Building | Architecture | Museum | North East | L00 Ground Level | Circulation / Common Areas
INTERVIEW,SECURITY SCAN, FIRST AID ROOMS AND OFFICE AREAS - EAST |  | 118 | 2022-07-05 | 2022-11-24
C-PW-059150 | General Block Work | 11 | 2022-07-05 | 2022-07-21 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059160 | Marking & Chasing Walls for MEP Services | 6 | 2022-07-21 | 2022-07-28 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059170 | Ceiling Finishes (V.E Rooms) | 8 | 2022-07-28 | 2022-08-08 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059180 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-09-21 | 01 | 14 | 01 | 44 | 003 | 05 |  | Building | General MEP | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059190 | Wall Finishes (Painting & Rendered Finish) | 14 | 2022-09-22 | 2022-10-10 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059200 | Ceiling Grid / Support Works | 3 | 2022-10-10 | 2022-10-13 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059210 | Ceiling Finishes (Plaster board ceiling) | 3 | 2022-10-13 | 2022-10-17 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059220 | Door Frames & Architrave Fixing | 6 | 2022-10-23 | 2022-10-30 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059230 | Floor Finishes (Polished Concrete,Resin flooring & Carpet Tiles) | 14 | 2022-10-17 | 2022-11-03 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059240 | Door Shuttering & Ironmongery | 6 | 2022-10-31 | 2022-11-07 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059250 | Installation of Lockers | 10 | 2022-11-06 | 2022-11-17 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059260 | Final Finishes & Fittings | 6 | 2022-11-17 | 2022-11-24 | 01 | 04 | 01 | 44 | 003 | 05 |  | Building | Architecture | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
SOUTH WEST |  | 471 | 2021-10-07 | 2023-04-27
COMMON WORKS - WEST |  | 34 | 2022-03-07 | 2022-04-14
C-PW-059270 | General Block Work | 14 | 2022-03-07 | 2022-03-23 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059280 | Scaffolds for BW till Lvl +19.650m | 10 | 2022-03-16 | 2022-03-27 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059290 | Block Work till Lvl +19.650m | 14 | 2022-03-22 | 2022-04-07 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059300 | Marking & Chasing Walls for MEP Services | 14 | 2022-03-29 | 2022-04-14 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
SECURITY, SCAN, INTERVIEW & CASH AREAS - WEST |  | 146 | 2022-04-14 | 2022-10-11
C-PW-059310 | Ceiling Finishes | 14 | 2022-04-14 | 2022-05-04 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059320 | Wall Finishes (Internal Paints, Render finish) | 13 | 2022-06-16 | 2022-07-02 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059330 | Floor Finishes (Epoxy Resin flooring) | 11 | 2022-07-07 | 2022-07-24 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059340 | Door Frames & Architrave Fixing | 11 | 2022-07-24 | 2022-08-07 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059350 | Door Shuttering & Ironmongery | 8 | 2022-08-07 | 2022-08-16 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059360 | Roller Shutter Installation | 7 | 2022-09-15 | 2022-09-24 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059370 | Final Finishes & Fittings | 14 | 2022-09-24 | 2022-10-11 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
ARTIFACT WORKSHOPS, SEP WORK & TOOL ROOMS - WEST |  | 137 | 2022-04-14 | 2022-09-29
C-PW-059380 | Ceiling Finishes | 14 | 2022-04-14 | 2022-05-04 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059390 | Wall Finishes (Internal Paints) | 13 | 2022-07-18 | 2022-08-02 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059400 | Floor Finishes (Epoxy Resin flooring) | 11 | 2022-08-02 | 2022-08-15 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059410 | Door Frames Fixing | 8 | 2022-08-16 | 2022-08-24 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059420 | Door Shuttering & Ironmongery | 8 | 2022-08-25 | 2022-09-03 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059430 | Roller Shutter Installation | 5 | 2022-09-15 | 2022-09-20 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059440 | Final Finishes & Fittings | 8 | 2022-09-20 | 2022-09-29 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
SEP TOILETS - WEST |  | 59 | 2022-07-19 | 2022-09-27
C-PW-059450 | Floor Waterproofing Works | 5 | 2022-07-19 | 2022-07-25 | 01 | 04 | 01 | 47 | 003 | 03 |  | Building | Architecture | Museum | South West | L00 Ground Level | Wet Areas
C-PW-059460 | Floor Screed Works | 2 | 2022-07-25 | 2022-07-27 | 01 | 04 | 01 | 47 | 003 | 03 |  | Building | Architecture | Museum | South West | L00 Ground Level | Wet Areas
C-PW-059470 | MEP Clearance for Suspended Ceiling in Toilets | 0 |  | 2022-08-03 | 01 | 14 | 01 | 47 | 003 | 03 |  | Building | General MEP | Museum | South West | L00 Ground Level | Wet Areas
C-PW-059480 | Wall Finishes (Plate render,Wall lining,WC cubicles & Paints) | 6 | 2022-08-03 | 2022-08-10 | 01 | 04 | 01 | 47 | 003 | 03 |  | Building | Architecture | Museum | South West | L00 Ground Level | Wet Areas
C-PW-059490 | Ceiling Grid / Support Works | 5 | 2022-08-11 | 2022-08-16 | 01 | 04 | 01 | 47 | 003 | 03 |  | Building | Architecture | Museum | South West | L00 Ground Level | Wet Areas
C-PW-059500 | Ceiling Finishes (Metal tile ceiling & Plaster board ceiling) | 5 | 2022-08-16 | 2022-08-22 | 01 | 04 | 01 | 47 | 003 | 03 |  | Building | Architecture | Museum | South West | L00 Ground Level | Wet Areas
C-PW-059510 | Floor Finishes (Terrazzo Resin flooring system) | 10 | 2022-08-22 | 2022-09-03 | 01 | 04 | 01 | 47 | 003 | 03 |  | Building | Architecture | Museum | South West | L00 Ground Level | Wet Areas
C-PW-059520 | Door Frames Fixing | 3 | 2022-09-03 | 2022-09-06 | 01 | 04 | 01 | 47 | 003 | 03 |  | Building | Architecture | Museum | South West | L00 Ground Level | Wet Areas
C-PW-059530 | Door Shuttering & Ironmongery | 3 | 2022-09-06 | 2022-09-10 | 01 | 04 | 01 | 47 | 003 | 03 |  | Building | Architecture | Museum | South West | L00 Ground Level | Wet Areas
C-PW-059540 | Final Finishes & Fittings | 6 | 2022-09-20 | 2022-09-27 | 01 | 04 | 01 | 47 | 003 | 03 |  | Building | Architecture | Museum | South West | L00 Ground Level | Wet Areas
SEP GALLERIES & LOBBY - WEST |  | 162 | 2022-04-14 | 2022-10-30
C-PW-059550 | Ceiling Finishes | 14 | 2022-04-14 | 2022-05-04 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059560 | Plastering Works - Walls | 14 | 2022-08-03 | 2022-08-20 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059570 | Wall Finishes (Plasterboard lining, paints & Rendered finish) | 17 | 2022-08-21 | 2022-09-08 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059580 | Roller Shutter Installation | 10 | 2022-09-15 | 2022-09-26 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059590 | Floor Finishes (Polished Conc floor incl screed) | 17 | 2022-09-08 | 2022-09-28 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059600 | Door Frames & Architrave Fixing | 8 | 2022-09-28 | 2022-10-08 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059610 | Door Shuttering & Ironmongery (Lobby) | 8 | 2022-10-08 | 2022-10-18 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059620 | Final Finishes & Fittings | 10 | 2022-10-18 | 2022-10-30 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
FUTURE EXPANSION ROOMS - WEST |  | 66 | 2022-07-19 | 2022-10-05
C-PW-059630 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-07-19 | 01 | 14 | 01 | 47 | 003 | 05 |  | Building | General MEP | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059640 | Wall Finishes (Render finish,Glazed cladding & Partions) | 14 | 2022-07-19 | 2022-08-06 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059650 | Ceiling Grid / Support Works | 10 | 2022-08-01 | 2022-08-11 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059660 | Ceiling Finishes | 14 | 2022-08-11 | 2022-08-29 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059670 | Floor Finishes | 11 | 2022-08-29 | 2022-09-11 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059680 | Door Frames & Architrave Fixing | 8 | 2022-09-11 | 2022-09-20 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059690 | Door Shuttering & Ironmongery | 6 | 2022-09-20 | 2022-09-27 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-059700 | Final Finishes & Fittings | 6 | 2022-09-27 | 2022-10-05 | 01 | 04 | 01 | 47 | 003 | 05 |  | Building | Architecture | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
CIRCULATIONS & CORRIDORS - WEST |  | 206 | 2022-08-25 | 2023-04-27
C-PW-059710 | Floor Screed | 4 | 2022-08-25 | 2022-08-29 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059720 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-09-03 | 01 | 14 | 01 | 47 | 003 | 01 |  | Building | General MEP | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059730 | Wall Finishes (Interior Paints & Platre render finish) | 19 | 2022-09-04 | 2022-09-26 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059740 | Ceiling Grid / Support Works | 14 | 2022-09-26 | 2022-10-13 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059750 | Ceiling Finishes (Plaster board ceiling) | 14 | 2022-10-13 | 2022-10-30 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059760 | Floor Finishes (Epoxy Resin flooring) | 11 | 2022-10-31 | 2022-11-13 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059770 | Door Frames & Architrave Fixing | 8 | 2022-11-13 | 2022-11-22 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059780 | Door Shuttering & Ironmongery | 6 | 2022-11-22 | 2022-11-29 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059790 | Joinery Fixing | 10 | 2023-04-08 | 2023-04-18 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059800 | Final Finishes & Fittings | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
COMMON WORKS - WEST-MEP ROOMS |  | 51 | 2022-01-03 | 2022-03-03
C-PW-059810 | General Block Work | 11 | 2022-01-03 | 2022-01-16 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059820 | Scaffolds for BW till Lvl +17.825m | 11 | 2022-02-05 | 2022-02-17 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059830 | Block Work till Lvl +17.825m | 11 | 2022-02-10 | 2022-02-23 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-059840 | Marking & Chasing Walls for MEP Services | 6 | 2022-02-23 | 2022-03-03 | 01 | 04 | 01 | 47 | 003 | 01 |  | Building | Architecture | Museum | South West | L00 Ground Level | Circulation / Common Areas
GENERATOR 1, SWITCH ROOM & OIL STORE |  | 94 | 2022-03-03 | 2022-06-25
C-PW-059850 | Equipment Foundation & Upstand Works (Incl. Acoustic Layers/ Insulators) | 5 | 2022-03-03 | 2022-03-09 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059860 | Paint 1st Coat - Ceiling (Dust Sealer) | 8 | 2022-03-09 | 2022-03-19 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059870 | Paint 1st Coat - Walls (Dust Sealer) | 17 | 2022-03-19 | 2022-04-07 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059880 | MEP Rooms Ready to Receive Equipment (Generator, Panels) | 0 |  | 2022-04-21 | 01 | 14 | 01 | 47 | 003 | 02 |  | Building | General MEP | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059890 | Floor Finishes (Dust Sealer) | 10 | 2022-05-21 | 2022-05-31 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059900 | Door Frame, Shutter & Ironmongery (Steel Doors) | 10 | 2022-05-31 | 2022-06-12 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059910 | Final Coat Paint | 10 | 2022-06-13 | 2022-06-25 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
SUBSTATION 1 |  | 113 | 2021-10-07 | 2022-02-21
C-PW-059920 | Block Work | 11 | 2021-10-07 | 2021-10-21 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059930 | Equipment Foundation & Upstand Works | 8 | 2021-10-21 | 2021-10-31 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059940 | Floor Trench Works | 10 | 2021-10-31 | 2021-11-10 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059950 | Paint 1st Coat - Ceiling (Dust Sealer) | 6 | 2021-11-10 | 2021-11-17 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059960 | Paint 1st Coat - Walls (Dust Sealer) | 6 | 2021-11-17 | 2021-11-24 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059970 | Grating Works | 5 | 2021-11-24 | 2021-12-01 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059980 | Floor Finishes (Dust Sealer) | 6 | 2022-01-24 | 2022-01-30 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-059990 | Doors & Ironmongery (Louvre Doors) | 5 | 2022-01-30 | 2022-02-05 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-060000 | Substation/Transformer Room Ready for Inspection | 0 |  | 2022-02-21 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-060010 | Final Coat Paint | 5 | 2022-02-15 | 2022-02-21 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
LOADING AREA FAN ROOM |  | 100 | 2022-03-03 | 2022-06-30
C-PW-060020 | Ceiling Finishes (Dust Sealer) | 6 | 2022-03-03 | 2022-03-09 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-060030 | Walls Finishes (Internal Paint) | 6 | 2022-03-09 | 2022-03-17 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-060040 | Floor Finishes (Dust Sealer) | 6 | 2022-05-30 | 2022-06-06 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-060050 | Doors & Ironmongery | 5 | 2022-06-06 | 2022-06-12 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-060060 | Final Coat Paint | 5 | 2022-06-26 | 2022-06-30 | 01 | 04 | 01 | 47 | 003 | 02 |  | Building | Architecture | Museum | South West | L00 Ground Level | MEP / Service Rooms
SOUTH EAST |  | 332 | 2021-10-07 | 2022-11-12
COMMON WORKS - SOUTH ZONE |  | 41 | 2022-01-31 | 2022-03-19
C-PW-060070 | General Block Work | 17 | 2022-01-31 | 2022-02-19 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060080 | Scaffolds for BW till Lvl +19.650m | 17 | 2022-02-13 | 2022-03-03 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060090 | Block Work till Lvl +19.650m | 19 | 2022-02-19 | 2022-03-13 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060100 | Marking & Chasing Walls for MEP Services | 19 | 2022-02-24 | 2022-03-19 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
LIBRARY, SHK.ZAYED LIFE & TIMES GALLERY AND LOBBY - SOUTH |  | 169 | 2022-03-19 | 2022-10-11
C-PW-060110 | Void Former for Floor finishes | 14 | 2022-03-19 | 2022-04-05 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060120 | Preparation for Floor finishes | 11 | 2022-04-05 | 2022-04-18 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060130 | Floor Finishes (Polished Conc floor finish incl. screed) | 19 | 2022-05-12 | 2022-06-04 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060140 | Wall Finishes (Plasterboard lining, paints & Rendered finish) | 19 | 2022-06-04 | 2022-06-26 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060150 | Door Frames & Architrave Fixing | 8 | 2022-06-26 | 2022-07-05 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060160 | Ceiling Grid / Support Works | 14 | 2022-07-05 | 2022-07-25 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060170 | Ceiling Finishes (Acoustic Plasterboard Ceiling) | 14 | 2022-07-25 | 2022-08-13 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060180 | Door Shuttering & Ironmongery | 8 | 2022-08-13 | 2022-08-22 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060190 | Roller Shutter Installation | 7 | 2022-09-15 | 2022-09-24 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060200 | Final Finishes & Fittings (Under ATC SoW) | 14 | 2022-09-24 | 2022-10-11 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
PANTY AREA, TOILETS & JANITOR ROOMS - SOUTH |  | 154 | 2022-03-19 | 2022-09-22
C-PW-060210 | Ceiling Finishes in Pantry Areas | 8 | 2022-03-19 | 2022-03-28 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060220 | Floor Waterproofing Works | 13 | 2022-03-28 | 2022-04-12 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060230 | Void Former & Floor Screed Works | 10 | 2022-04-12 | 2022-04-24 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060240 | MEP Clearance for Suspended Ceiling in Toilets | 0 |  | 2022-05-12 | 01 | 14 | 01 | 45 | 003 | 03 |  | Building | General MEP | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060250 | Wall Finishes (PVC wall lining,WC cubicles & wall tiles) | 14 | 2022-05-12 | 2022-05-30 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060260 | Ceiling Grid / Support Works in Toilets | 6 | 2022-05-30 | 2022-06-05 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060270 | Ceiling Finishes (Metal tile ceiling & Plaster board ceiling) in Toilets | 6 | 2022-06-05 | 2022-06-12 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060280 | Floor Finishes (Resin flooring system,Ceramic Tiles) | 14 | 2022-06-09 | 2022-06-26 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060290 | Door Frames Fixing | 10 | 2022-06-26 | 2022-07-06 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060300 | Door Shuttering & Ironmongery | 8 | 2022-08-22 | 2022-08-31 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060310 | Vanity counters , Cupboards etc, | 8 | 2022-08-31 | 2022-09-10 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
C-PW-060320 | Final Finishes & Fittings | 11 | 2022-09-10 | 2022-09-22 | 01 | 04 | 01 | 45 | 003 | 03 |  | Building | Architecture | Museum | South East | L00 Ground Level | Wet Areas
COLLECTION RESEARCH, WORKSHOPS & SECURITY/FIRE STAFF ROOMS - SOUTH |  | 151 | 2022-03-28 | 2022-09-28
C-PW-060330 | Ceiling Finishes | 14 | 2022-03-28 | 2022-04-14 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060340 | Wall Finishes (Internal Paints, Render finish & Wall tiles) | 13 | 2022-06-04 | 2022-06-18 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060350 | Floor Finishes (Resin flooring,RAF & Ceramic tiles) | 17 | 2022-06-19 | 2022-07-07 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060360 | Door Frames Fixing | 8 | 2022-07-07 | 2022-07-20 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060370 | Door Shuttering & Ironmongery | 8 | 2022-08-31 | 2022-09-10 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060380 | Final Finishes & Fittings | 6 | 2022-09-21 | 2022-09-28 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
FUTURE EXPANSION ROOMS - SOUTH |  | 104 | 2022-06-08 | 2022-10-13
C-PW-060390 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-08 | 01 | 14 | 01 | 45 | 003 | 05 |  | Building | General MEP | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060400 | Wall Finishes (Render finish,GRC/Glazed cladding & Partions) | 14 | 2022-06-08 | 2022-06-25 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060410 | Ceiling Grid / Support Works | 10 | 2022-06-15 | 2022-06-27 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060420 | Ceiling Finishes (Plasterboard/GRC Ceiling) | 14 | 2022-06-27 | 2022-07-17 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060430 | Floor Finishes | 13 | 2022-07-05 | 2022-07-24 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060440 | Door Frames Fixing | 8 | 2022-07-24 | 2022-08-03 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060450 | Door Shuttering & Ironmongery | 8 | 2022-09-10 | 2022-09-19 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-060460 | Final Finishes & Fittings | 8 | 2022-10-03 | 2022-10-13 | 01 | 04 | 01 | 45 | 003 | 05 |  | Building | Architecture | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
MAJLIS & VIP ARRIVAL LOBBY AREAS - SOUTH |  | 110 | 2022-06-22 | 2022-11-03
C-PW-060470 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-22 | 01 | 14 | 01 | 45 | 003 | 01 |  | Building | General MEP | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060480 | Wall Finishes (Plate Render,wall linings, Metal & Fin wall system) | 19 | 2022-06-23 | 2022-07-19 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060490 | Ceiling Grid / Support Works | 14 | 2022-07-19 | 2022-08-06 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060500 | Ceiling Finishes (Plasterboard & Acoustic timber Ceiling) | 14 | 2022-08-06 | 2022-08-22 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060510 | Floor Finishes (Resin & Stone flooring) | 14 | 2022-08-23 | 2022-09-08 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060520 | Door Frames & Architrave Fixing | 8 | 2022-09-08 | 2022-09-18 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060530 | Door Shuttering & Ironmongery | 8 | 2022-09-18 | 2022-09-27 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060540 | Final Finishes & Fittings | 22 | 2022-10-08 | 2022-11-03 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
CIRCULATIONS & CORRIDORS - SOUTH |  | 105 | 2022-07-07 | 2022-11-12
C-PW-060550 | Floor Screed works | 4 | 2022-07-07 | 2022-07-14 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060560 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-07-18 | 01 | 14 | 01 | 45 | 003 | 01 |  | Building | General MEP | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060570 | Wall Finishes (Interior Paints & Platre render finish) | 19 | 2022-07-18 | 2022-08-10 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060580 | Ceiling Grid / Support Works | 14 | 2022-08-10 | 2022-08-27 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060590 | Ceiling Finishes | 14 | 2022-08-28 | 2022-09-13 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060600 | Floor Finishes (Polished Concrete & Epoxy Resin flooring) | 16 | 2022-09-13 | 2022-10-02 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060610 | Door Frames & Architrave Fixing | 8 | 2022-10-02 | 2022-10-12 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060620 | Door Shuttering & Ironmongery | 8 | 2022-10-12 | 2022-10-22 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060630 | Final Finishes & Fittings | 6 | 2022-11-05 | 2022-11-12 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
COMMON WORKS - SOUTH ZONE-MEP ROOMS |  | 29 | 2021-10-07 | 2021-11-10
C-PW-060640 | General Block Work | 11 | 2021-10-07 | 2021-10-21 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060650 | Scaffolds for BW till Lvl +17.825m | 11 | 2021-10-13 | 2021-10-27 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060660 | Block Work till Lvl +17.825m | 11 | 2021-10-21 | 2021-11-03 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-060670 | Marking & Chasing Walls for MEP Services | 6 | 2021-11-03 | 2021-11-10 | 01 | 04 | 01 | 45 | 003 | 01 |  | Building | Architecture | Museum | South East | L00 Ground Level | Circulation / Common Areas
SUBSTATION 2 |  | 113 | 2021-10-07 | 2022-02-21
C-PW-060680 | Block Work | 17 | 2021-10-07 | 2021-10-27 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060690 | Block Work | 17 | 2021-10-07 | 2021-10-27 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060700 | Equipment Foundation & Upstand Works | 8 | 2021-11-03 | 2021-11-13 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060710 | Floor Trench Works | 10 | 2021-11-13 | 2021-11-23 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060720 | Paint 1st Coat - Ceiling (Dust Sealer) | 6 | 2021-11-24 | 2021-12-01 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060730 | Paint 1st Coat - Walls (Dust Sealer) | 6 | 2021-12-01 | 2021-12-09 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060740 | Grating Works | 5 | 2021-12-11 | 2021-12-15 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060750 | Floor Finishes (Dust Sealer) | 6 | 2022-01-18 | 2022-01-25 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060760 | Doors & Ironmongery (Louvre Doors) | 5 | 2022-02-02 | 2022-02-07 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060770 | Substation/Transformer Room Ready for Inspection | 0 |  | 2022-02-21 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060780 | Final Coat Paint | 5 | 2022-02-15 | 2022-02-21 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
GENERATOR 2, SWITCH ROOM & OIL STORE |  | 205 | 2022-02-05 | 2022-10-10
C-PW-060790 | Equipment Foundation & Upstand Works (Incl. Acoustic Layers/ Insulators) | 6 | 2022-02-05 | 2022-02-12 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060800 | Paint 1st Coat - Ceiling (Dust Sealer) | 8 | 2022-02-12 | 2022-02-21 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060810 | Paint 1st Coat - Walls (Dust Sealer) | 17 | 2022-02-12 | 2022-03-02 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060820 | MEP Rooms Ready to Receive Equipment (Generator, Panels) | 0 |  | 2022-07-17 | 01 | 14 | 01 | 45 | 003 | 02 |  | Building | General MEP | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060830 | Floor Finishes (Dust Sealer) | 10 | 2022-08-30 | 2022-09-10 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060840 | Door Frame, Shutter & Ironmongery (Steel Doors) | 5 | 2022-09-10 | 2022-09-15 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060850 | Final Coat Paint | 8 | 2022-09-29 | 2022-10-10 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
WATER TANKS, FIRE & DOMESTIC WATER PUMP ROOM |  | 194 | 2022-02-05 | 2022-09-27
C-PW-060860 | Equipment Foundation & Upstand Works | 8 | 2022-02-05 | 2022-02-13 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060870 | Installation of Metal Access Ladders | 14 | 2022-02-05 | 2022-02-21 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060880 | Floor Trench Works | 10 | 2022-02-14 | 2022-02-24 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060890 | Paint 1st Coat - Ceiling (Internal Paint) | 6 | 2022-02-24 | 2022-03-03 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060900 | Paint 1st Coat - Walls (Internal Paint) | 6 | 2022-03-03 | 2022-03-10 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060910 | Grating Works | 5 | 2022-03-09 | 2022-03-14 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060920 | GRP Lining / Waterproofing for Water Tanks Walls & Ceiling | 19 | 2022-02-21 | 2022-03-15 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060930 | Floor Finishes (Epoxy resin flooring) | 11 | 2022-09-03 | 2022-09-15 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060940 | Doors & Ironmongery | 5 | 2022-09-15 | 2022-09-21 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-060950 | Final Coat Paint | 5 | 2022-09-21 | 2022-09-27 | 01 | 04 | 01 | 45 | 003 | 02 |  | Building | Architecture | Museum | South East | L00 Ground Level | MEP / Service Rooms
MEP WORKS |  | 398 | 2022-01-02 | 2023-04-24
NORTH WEST |  | 349 | 2022-02-28 | 2023-04-24
RESTAURANT GALLERIES,PANTRY,PUBLIC TOILETS,GRAB&GO- NORTH |  | 148 | 2022-02-28 | 2022-08-28
MECHANICAL |  | 148 | 2022-02-28 | 2022-08-28
HVAC SYSTEM WORKS |  | 137 | 2022-03-09 | 2022-08-24
C-PW-060960 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 14 | 2022-03-09 | 2022-03-24 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-060970 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 14 | 2022-03-13 | 2022-03-28 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-060980 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-03-28 | 2022-04-10 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-060990 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-08-15 | 2022-08-24 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 143 | 2022-02-28 | 2022-08-21
C-PW-061000 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-02-28 | 2022-03-15 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061010 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-03-15 | 2022-03-27 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061020 | Final Fix (Installation of Sanitaryware & Accessories) | 6 | 2022-08-15 | 2022-08-21 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 144 | 2022-03-05 | 2022-08-28
C-PW-061030 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-05 | 2022-03-21 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061040 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-03-26 | 2022-04-06 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061050 | Final Fix - Water Meter Installation | 3 | 2022-08-24 | 2022-08-28 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 144 | 2022-03-02 | 2022-08-24
C-PW-061060 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-03-02 | 2022-03-14 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061070 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-03-06 | 2022-03-21 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061080 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-03-22 | 2022-04-06 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061090 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-08-15 | 2022-08-24 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061100 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-16 | 2022-08-24 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061110 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-16 | 2022-08-24 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELV |  | 136 | 2022-03-07 | 2022-08-20
AV SYSTEM |  | 133 | 2022-03-07 | 2022-08-17
C-PW-061120 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-03-07 | 2022-03-19 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061130 | 2nd Fix AV System Works (Wiring) | 10 | 2022-03-19 | 2022-03-30 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061140 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-15 | 2022-08-17 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 110 | 2022-04-04 | 2022-08-17
C-PW-061150 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061160 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-16 | 2022-04-27 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061170 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-15 | 2022-08-17 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 108 | 2022-04-05 | 2022-08-17
C-PW-061180 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061190 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061200 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-15 | 2022-08-17 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 109 | 2022-04-07 | 2022-08-20
C-PW-061210 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061220 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061230 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-17 | 2022-08-20 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 127 | 2022-03-14 | 2022-08-17
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 105 | 2022-04-09 | 2022-08-17
C-PW-061240 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-21 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061250 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-21 | 2022-05-07 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061260 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-15 | 2022-08-17 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 103 | 2022-04-11 | 2022-08-17
C-PW-061270 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-11 | 2022-04-23 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061280 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-23 | 2022-05-09 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061290 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-15 | 2022-08-17 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 105 | 2022-03-14 | 2022-07-21
C-PW-061300 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-03-14 | 2022-03-30 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061310 | 2nd Fix Piping System - (Fittings) | 8 | 2022-03-30 | 2022-04-09 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061320 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-07-13 | 2022-07-21 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
AUDITORIUM,CONFERENCE ROOM,LOBBY AND ASSOCIATED ROOMS- NORTH |  | 187 | 2022-03-05 | 2022-10-17
MECHANICAL |  | 176 | 2022-03-09 | 2022-10-10
HVAC SYSTEM WORKS |  | 176 | 2022-03-09 | 2022-10-10
C-PW-061330 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 16 | 2022-03-09 | 2022-03-27 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061340 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 16 | 2022-03-19 | 2022-04-05 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061350 | 2nd Fix HVAC (FCUs, Droppers, | 12 | 2022-04-06 | 2022-04-19 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061360 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 9 | 2022-09-28 | 2022-10-10 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 22 | 2022-03-13 | 2022-04-06
C-PW-061370 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-03-13 | 2022-03-31 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061380 | 2nd Fix Piping System (Fittings, Insulation) | 12 | 2022-03-23 | 2022-04-06 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 22 | 2022-03-19 | 2022-04-12
C-PW-061390 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-03-19 | 2022-04-05 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061400 | 2nd Fix Piping System (Fittings, Insulation) | 12 | 2022-03-29 | 2022-04-12 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 187 | 2022-03-05 | 2022-10-17
C-PW-061410 | 1st Fix Electrical Works (Conduits & Boxes) - Power and Lighting System | 10 | 2022-03-05 | 2022-03-16 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061420 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-03-22 | 2022-04-06 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061430 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-04-06 | 2022-04-23 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061440 | LV Switchgears (DB's) | 5 | 2022-04-23 | 2022-04-27 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061450 | Cable/Wire Termination & Dressing | 7 | 2022-04-28 | 2022-05-10 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061460 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-28 | 2022-10-08 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061470 | Final Fix Electrical (Light Fixtures) | 10 | 2022-10-01 | 2022-10-13 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061480 | Final Fix Electrical (Installation of Lighting Control Panels) | 10 | 2022-10-02 | 2022-10-16 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061490 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-10-04 | 2022-10-17 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELV |  | 155 | 2022-04-04 | 2022-10-11
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-04-04 | 2022-05-04
C-PW-061500 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061510 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-16 | 2022-04-27 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061520 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-04-27 | 2022-05-04 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-04-05 | 2022-05-05
C-PW-061530 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061540 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061550 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-04-30 | 2022-05-05 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 24 | 2022-04-07 | 2022-05-09
C-PW-061560 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061570 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061580 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-05-05 | 2022-05-09 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 120 | 2022-05-10 | 2022-10-01
C-PW-061590 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-10 | 2022-05-22 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061600 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061610 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-01 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 118 | 2022-05-11 | 2022-10-01
C-PW-061620 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061630 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-24 | 2022-06-05 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061640 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-28 | 2022-10-01 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 118 | 2022-05-14 | 2022-10-03
C-PW-061650 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061660 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061670 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-01 | 2022-10-03 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 117 | 2022-05-15 | 2022-10-03
C-PW-061680 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-28 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061690 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061700 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-01 | 2022-10-03 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-03 | 2022-10-11
C-PW-061710 | Active Component System Works | 6 | 2022-10-03 | 2022-10-11 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 116 | 2022-03-30 | 2022-08-20
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 63 | 2022-05-28 | 2022-08-14
C-PW-061720 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-28 | 2022-06-08 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061730 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061740 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-11 | 2022-08-14 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 62 | 2022-05-29 | 2022-08-14
C-PW-061750 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-29 | 2022-06-11 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061760 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061770 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-11 | 2022-08-14 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 116 | 2022-03-30 | 2022-08-20
C-PW-061780 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-03-30 | 2022-04-18 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061790 | 2nd Fix Piping System - (Fittings) | 12 | 2022-04-11 | 2022-04-24 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-061800 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-11 | 2022-08-20 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
KITCHEN AREA,TOILETS & JANITOR ROOMS- NORTH |  | 179 | 2022-03-10 | 2022-10-15
MECHANICAL |  | 161 | 2022-03-31 | 2022-10-15
HVAC SYSTEM WORKS |  | 154 | 2022-04-09 | 2022-10-15
C-PW-061810 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 14 | 2022-04-09 | 2022-04-24 | 01 | 06 | 01 | 46 | 003 | 03 |  | Building | HVAC | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061820 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 14 | 2022-04-12 | 2022-04-28 | 01 | 06 | 01 | 46 | 003 | 03 |  | Building | HVAC | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061830 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-04-28 | 2022-05-14 | 01 | 06 | 01 | 46 | 003 | 03 |  | Building | HVAC | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061840 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-04 | 2022-10-15 | 01 | 06 | 01 | 46 | 003 | 03 |  | Building | HVAC | Museum | North West | L00 Ground Level | Wet Areas
DRAINAGE WORKS |  | 159 | 2022-03-31 | 2022-10-11
C-PW-061850 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-31 | 2022-04-16 | 01 | 08 | 01 | 46 | 003 | 03 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061860 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-16 | 2022-04-28 | 01 | 08 | 01 | 46 | 003 | 03 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061870 | Final Fix (Installation of Sanitaryware & Accessories) | 10 | 2022-09-28 | 2022-10-11 | 01 | 08 | 01 | 46 | 003 | 03 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Wet Areas
HOT & COLD WATER SYSTEM |  | 148 | 2022-04-05 | 2022-10-02
C-PW-061880 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-04-05 | 2022-04-20 | 01 | 08 | 01 | 46 | 003 | 03 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061890 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-04-25 | 2022-05-11 | 01 | 08 | 01 | 46 | 003 | 03 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061900 | Final Fix - Water Meter Installation | 3 | 2022-09-28 | 2022-10-02 | 01 | 08 | 01 | 46 | 003 | 03 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Wet Areas
ELECTRICAL WORKS |  | 170 | 2022-03-10 | 2022-10-03
C-PW-061910 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-03-10 | 2022-03-22 | 01 | 07 | 01 | 46 | 003 | 03 |  | Building | Electrical | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061920 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-04-12 | 2022-04-28 | 01 | 07 | 01 | 46 | 003 | 03 |  | Building | Electrical | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061930 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-04-28 | 2022-05-17 | 01 | 07 | 01 | 46 | 003 | 03 |  | Building | Electrical | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061940 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-19 | 2022-09-28 | 01 | 07 | 01 | 46 | 003 | 03 |  | Building | Electrical | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061950 | Final Fix Electrical (Light Fixtures) | 10 | 2022-09-21 | 2022-10-03 | 01 | 07 | 01 | 46 | 003 | 03 |  | Building | Electrical | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061960 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-09-21 | 2022-10-03 | 01 | 07 | 01 | 46 | 003 | 03 |  | Building | Electrical | Museum | North West | L00 Ground Level | Wet Areas
ELV |  | 150 | 2022-03-22 | 2022-09-21
AV SYSTEM |  | 150 | 2022-03-22 | 2022-09-21
C-PW-061970 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-03-22 | 2022-04-03 | 01 | 10 | 01 | 46 | 003 | 03 |  | Building | CCTV | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061980 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 46 | 003 | 03 |  | Building | CCTV | Museum | North West | L00 Ground Level | Wet Areas
C-PW-061990 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-19 | 2022-09-21 | 01 | 10 | 01 | 46 | 003 | 03 |  | Building | CCTV | Museum | North West | L00 Ground Level | Wet Areas
DATA AND TELECOMMUNICATION |  | 150 | 2022-03-22 | 2022-09-21
C-PW-062000 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-22 | 2022-04-03 | 01 | 10 | 01 | 46 | 003 | 03 |  | Building | CCTV | Museum | North West | L00 Ground Level | Wet Areas
C-PW-062010 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 46 | 003 | 03 |  | Building | CCTV | Museum | North West | L00 Ground Level | Wet Areas
C-PW-062020 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-19 | 2022-09-21 | 01 | 10 | 01 | 46 | 003 | 03 |  | Building | CCTV | Museum | North West | L00 Ground Level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 149 | 2022-03-24 | 2022-09-21
C-PW-062030 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-24 | 2022-04-05 | 01 | 10 | 01 | 46 | 003 | 03 |  | Building | CCTV | Museum | North West | L00 Ground Level | Wet Areas
C-PW-062040 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 46 | 003 | 03 |  | Building | CCTV | Museum | North West | L00 Ground Level | Wet Areas
C-PW-062050 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-19 | 2022-09-21 | 01 | 10 | 01 | 46 | 003 | 03 |  | Building | CCTV | Museum | North West | L00 Ground Level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 147 | 2022-03-26 | 2022-09-21
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 147 | 2022-03-26 | 2022-09-21
C-PW-062060 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-07 | 01 | 09 | 01 | 46 | 003 | 03 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Wet Areas
C-PW-062070 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-07 | 2022-04-19 | 01 | 09 | 01 | 46 | 003 | 03 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Wet Areas
C-PW-062080 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-19 | 2022-09-21 | 01 | 09 | 01 | 46 | 003 | 03 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 146 | 2022-03-28 | 2022-09-21
C-PW-062090 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-28 | 2022-04-09 | 01 | 09 | 01 | 46 | 003 | 03 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Wet Areas
C-PW-062100 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-09 | 2022-04-21 | 01 | 09 | 01 | 46 | 003 | 03 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Wet Areas
C-PW-062110 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-19 | 2022-09-21 | 01 | 09 | 01 | 46 | 003 | 03 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Wet Areas
FIRE FIGHTING WORKS |  | 94 | 2022-04-18 | 2022-08-13
C-PW-062120 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-04-18 | 2022-05-07 | 01 | 09 | 01 | 46 | 003 | 03 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Wet Areas
C-PW-062130 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-08 | 2022-05-16 | 01 | 09 | 01 | 46 | 003 | 03 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Wet Areas
C-PW-062140 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-04 | 2022-08-13 | 01 | 09 | 01 | 46 | 003 | 03 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Wet Areas
RESTAURANT,VIP VIEWING LOUNGE- NORTH |  | 189 | 2022-03-17 | 2022-11-01
MECHANICAL |  | 161 | 2022-04-16 | 2022-10-31
HVAC SYSTEM WORKS |  | 160 | 2022-04-18 | 2022-10-31
C-PW-062150 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-04-18 | 2022-05-12 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062160 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 18 | 2022-04-21 | 2022-05-16 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062170 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-12 | 2022-05-25 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062180 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-22 | 2022-10-31 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 25 | 2022-04-16 | 2022-05-18
C-PW-062190 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-16 | 2022-05-11 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062200 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-07 | 2022-05-18 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 150 | 2022-04-21 | 2022-10-23
C-PW-062210 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-21 | 2022-05-16 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062220 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-05-22 | 2022-06-02 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062230 | Final Fix - Water Meter Installation | 3 | 2022-10-19 | 2022-10-23 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 183 | 2022-03-17 | 2022-10-26
C-PW-062240 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-17 | 2022-04-02 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062250 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-04-28 | 2022-05-23 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062260 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-23 | 2022-06-08 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062270 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-10 | 2022-10-19 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062280 | Final Fix Electrical (Light Fixtures) | 12 | 2022-10-12 | 2022-10-26 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062290 | Final Fix Electrical (Installation of Lighting Control Devices) | 12 | 2022-10-12 | 2022-10-26 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELV |  | 174 | 2022-04-04 | 2022-11-01
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-04-04 | 2022-05-04
C-PW-062300 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062310 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-16 | 2022-04-27 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062320 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-04-27 | 2022-05-04 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-04-05 | 2022-05-05
C-PW-062330 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062340 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062350 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-04-30 | 2022-05-05 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 24 | 2022-04-07 | 2022-05-09
C-PW-062360 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062370 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062380 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-05-05 | 2022-05-09 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 146 | 2022-04-28 | 2022-10-24
C-PW-062390 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062400 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062410 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-24 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 144 | 2022-04-30 | 2022-10-24
C-PW-062420 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062430 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-16 | 2022-05-28 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062440 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-22 | 2022-10-24 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 144 | 2022-05-05 | 2022-10-26
C-PW-062450 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062460 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-17 | 2022-05-29 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062470 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-26 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 142 | 2022-05-07 | 2022-10-26
C-PW-062480 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-07 | 2022-05-19 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062490 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-19 | 2022-05-31 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062500 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-26 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-26 | 2022-11-01
C-PW-062510 | Active Component System Works | 6 | 2022-10-26 | 2022-11-01 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 69 | 2022-05-08 | 2022-08-01
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 54 | 2022-05-19 | 2022-07-24
C-PW-062520 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-19 | 2022-05-31 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062530 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-31 | 2022-06-12 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062540 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-21 | 2022-07-24 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 52 | 2022-05-21 | 2022-07-24
C-PW-062550 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-21 | 2022-06-02 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062560 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-02 | 2022-06-14 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062570 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-07-21 | 2022-07-24 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 69 | 2022-05-08 | 2022-08-01
C-PW-062580 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-05-08 | 2022-05-25 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062590 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-21 | 2022-05-30 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-062600 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-07-21 | 2022-08-01 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
STAFF OFFICE,VIP VIEWING LOBBY,SECURITY & SCAN AREAS- NORTH |  | 184 | 2022-03-23 | 2022-11-01
MECHANICAL |  | 160 | 2022-04-18 | 2022-10-31
HVAC SYSTEM WORKS |  | 160 | 2022-04-18 | 2022-10-31
C-PW-062610 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-04-18 | 2022-05-12 | 01 | 06 | 01 | 46 | 003 | 05 |  | Building | HVAC | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062620 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 18 | 2022-04-27 | 2022-05-22 | 01 | 06 | 01 | 46 | 003 | 05 |  | Building | HVAC | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062630 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-17 | 2022-05-30 | 01 | 06 | 01 | 46 | 003 | 05 |  | Building | HVAC | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062640 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-22 | 2022-10-31 | 01 | 06 | 01 | 46 | 003 | 05 |  | Building | HVAC | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 29 | 2022-04-21 | 2022-05-29
C-PW-062650 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-21 | 2022-05-16 | 01 | 08 | 01 | 46 | 003 | 05 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062660 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-17 | 2022-05-29 | 01 | 08 | 01 | 46 | 003 | 05 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-04-27 | 2022-06-04
C-PW-062670 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-27 | 2022-05-22 | 01 | 08 | 01 | 46 | 003 | 05 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062680 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-22 | 2022-06-04 | 01 | 08 | 01 | 46 | 003 | 05 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 184 | 2022-03-23 | 2022-11-01
C-PW-062690 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-23 | 2022-04-07 | 01 | 07 | 01 | 46 | 003 | 05 |  | Building | Electrical | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062700 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-04-21 | 2022-05-16 | 01 | 07 | 01 | 46 | 003 | 05 |  | Building | Electrical | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062710 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-17 | 2022-06-01 | 01 | 07 | 01 | 46 | 003 | 05 |  | Building | Electrical | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062720 | LV Switchgears (DB's) | 5 | 2022-06-01 | 2022-06-07 | 01 | 07 | 01 | 46 | 003 | 05 |  | Building | Electrical | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062730 | Cable/Wire Termination & Dressing | 7 | 2022-06-07 | 2022-06-15 | 01 | 07 | 01 | 46 | 003 | 05 |  | Building | Electrical | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062740 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-18 | 2022-10-26 | 01 | 07 | 01 | 46 | 003 | 05 |  | Building | Electrical | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062750 | Final Fix Electrical (Light Fixtures) | 8 | 2022-10-19 | 2022-10-29 | 01 | 07 | 01 | 46 | 003 | 05 |  | Building | Electrical | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062760 | Final Fix Electrical (Installation of Lighting Control Panels) | 8 | 2022-10-22 | 2022-10-31 | 01 | 07 | 01 | 46 | 003 | 05 |  | Building | Electrical | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062770 | Final Fix Electrical (Installation of Lighting Control Devices) | 8 | 2022-10-23 | 2022-11-01 | 01 | 07 | 01 | 46 | 003 | 05 |  | Building | Electrical | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
ELV |  | 171 | 2022-04-04 | 2022-10-30
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 160 | 2022-04-04 | 2022-10-17
C-PW-062780 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062790 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-16 | 2022-04-27 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062800 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-13 | 2022-10-17 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 159 | 2022-04-05 | 2022-10-17
C-PW-062810 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062820 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062830 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-13 | 2022-10-17 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 159 | 2022-04-07 | 2022-10-19
C-PW-062840 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062850 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062860 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-19 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 159 | 2022-04-09 | 2022-10-22
C-PW-062870 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-21 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062880 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-21 | 2022-05-07 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062890 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-18 | 2022-10-22 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 158 | 2022-04-11 | 2022-10-22
C-PW-062900 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-11 | 2022-04-23 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062910 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-23 | 2022-05-09 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062920 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-18 | 2022-10-22 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 158 | 2022-04-13 | 2022-10-23
C-PW-062930 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-13 | 2022-04-25 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062940 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-25 | 2022-05-10 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062950 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-20 | 2022-10-23 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 156 | 2022-04-14 | 2022-10-23
C-PW-062960 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062970 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-062980 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-20 | 2022-10-23 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-23 | 2022-10-30
C-PW-062990 | Active Component System Works | 6 | 2022-10-23 | 2022-10-30 | 01 | 10 | 01 | 46 | 003 | 05 |  | Building | CCTV | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 83 | 2022-04-27 | 2022-08-09
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 77 | 2022-04-27 | 2022-08-03
C-PW-063000 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 09 | 01 | 46 | 003 | 05 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-063010 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-12 | 2022-05-24 | 01 | 09 | 01 | 46 | 003 | 05 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-063020 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-31 | 2022-08-03 | 01 | 09 | 01 | 46 | 003 | 05 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 76 | 2022-04-28 | 2022-08-03
C-PW-063030 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-28 | 2022-05-14 | 01 | 09 | 01 | 46 | 003 | 05 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-063040 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 46 | 003 | 05 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-063050 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-07-31 | 2022-08-03 | 01 | 09 | 01 | 46 | 003 | 05 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 61 | 2022-05-26 | 2022-08-09
C-PW-063060 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-05-26 | 2022-06-13 | 01 | 09 | 01 | 46 | 003 | 05 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-063070 | 2nd Fix Piping System - (Fittings) | 8 | 2022-06-14 | 2022-06-22 | 01 | 09 | 01 | 46 | 003 | 05 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-063080 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-07-31 | 2022-08-09 | 01 | 09 | 01 | 46 | 003 | 05 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Storage / Offices / Admin Areas
MAIN LOBBY |  | 269 | 2022-06-05 | 2023-04-24
MEETING SPACE |  | 70 | 2022-10-30 | 2023-01-21
C-PW-063570 | Wall & Floor MEP works 1st & 2nd Fix | 14 | 2022-10-30 | 2022-11-14 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063580 | Final Fix MEP works | 8 | 2023-01-11 | 2023-01-21 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
CAFE |  | 80 | 2022-10-29 | 2023-02-01
C-PW-063590 | Wall & Floor MEP works 1st & 2nd Fix | 16 | 2022-10-29 | 2022-11-16 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063600 | Final Fix MEP works | 8 | 2023-01-23 | 2023-02-01 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
TICKET/INFO POINT |  | 82 | 2022-07-04 | 2022-10-12
C-PW-063610 | Wall & Floor MEP works 1st & 2nd Fix | 16 | 2022-07-04 | 2022-07-26 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063620 | Final Fix MEP works | 8 | 2022-10-02 | 2022-10-12 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
PERFORMANCE SPACE |  | 78 | 2022-08-17 | 2022-11-17
C-PW-063630 | Wall & Floor MEP works 1st & 2nd Fix | 16 | 2022-08-17 | 2022-09-05 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063640 | Final Fix MEP works | 8 | 2022-11-08 | 2022-11-17 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
RETAIL |  | 78 | 2022-08-06 | 2022-11-06
C-PW-063650 | Wall & Floor MEP works 1st & 2nd Fix | 16 | 2022-08-06 | 2022-08-24 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063660 | Final Fix MEP works | 8 | 2022-10-27 | 2022-11-06 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
CIRCULATIONS & CORRIDORS |  | 269 | 2022-06-05 | 2023-04-24
C-PW-063670 | Wall & Floor MEP works 1st & 2nd Fix | 14 | 2022-06-05 | 2022-06-20 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063680 | Final Fix MEP works | 8 | 2023-04-12 | 2023-04-24 | 01 | 14 | 01 | 46 | 003 | 01 |  | Building | General MEP | Museum | North West | L00 Ground Level | Circulation / Common Areas
ENTRANCE LOBBY |  | 134 | 2022-03-19 | 2022-08-31
CITY ENTRANCE |  | 91 | 2022-03-19 | 2022-07-06
MEP WORKS |  | 91 | 2022-03-19 | 2022-07-06
MECHANICAL |  | 82 | 2022-03-19 | 2022-06-26
HVAC SYSTEM WORKS |  | 82 | 2022-03-19 | 2022-06-26
C-PW-063690 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 9 | 2022-03-19 | 2022-03-29 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063700 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 9 | 2022-03-19 | 2022-03-29 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063710 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 7 | 2022-03-29 | 2022-04-06 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063720 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 5 | 2022-06-20 | 2022-06-26 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 16 | 2022-03-24 | 2022-04-12
C-PW-063730 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-03-24 | 2022-04-04 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063740 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-04-04 | 2022-04-12 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 16 | 2022-03-30 | 2022-04-18
C-PW-063750 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-03-30 | 2022-04-10 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063760 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-04-10 | 2022-04-18 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 78 | 2022-04-03 | 2022-07-06
C-PW-063770 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-04-03 | 2022-04-12 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063780 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-04-12 | 2022-04-24 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063790 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-04-25 | 2022-05-10 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063800 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-06-19 | 2022-06-26 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063810 | Final Fix Electrical (Light Fixtures) | 14 | 2022-06-21 | 2022-07-06 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063820 | Final Fix Electrical (Installation of Lighting Control Devices) | 14 | 2022-06-21 | 2022-07-06 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELV |  | 38 | 2022-04-04 | 2022-05-22
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-04-04 | 2022-05-04
C-PW-063830 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063840 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-16 | 2022-04-27 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063850 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-04-27 | 2022-05-04 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-04-05 | 2022-05-05
C-PW-063860 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063870 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063880 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-04-30 | 2022-05-05 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 24 | 2022-04-07 | 2022-05-09
C-PW-063890 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063900 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063910 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-05-05 | 2022-05-09 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 24 | 2022-04-09 | 2022-05-10
C-PW-063920 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-21 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063930 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-21 | 2022-05-07 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063940 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-05-08 | 2022-05-10 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-04-11 | 2022-05-11
C-PW-063950 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-11 | 2022-04-23 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063960 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-23 | 2022-05-09 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063970 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-05-09 | 2022-05-11 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 23 | 2022-04-13 | 2022-05-14
C-PW-063980 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-13 | 2022-04-25 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-063990 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-25 | 2022-05-10 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064000 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-05-10 | 2022-05-14 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-04-14 | 2022-05-15
C-PW-064010 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064020 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064030 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-05-12 | 2022-05-15 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-05-15 | 2022-05-22
C-PW-064040 | Active Component System Works | 6 | 2022-05-15 | 2022-05-22 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEMS |  | 69 | 2022-03-30 | 2022-06-22
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 43 | 2022-04-27 | 2022-06-19
C-PW-064050 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064060 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-12 | 2022-05-24 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064070 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-06-16 | 2022-06-19 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 41 | 2022-04-28 | 2022-06-19
C-PW-064080 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-28 | 2022-05-14 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064090 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064100 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-06-16 | 2022-06-19 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 69 | 2022-03-30 | 2022-06-22
C-PW-064110 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 10 | 2022-03-30 | 2022-04-11 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064120 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-11 | 2022-04-20 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064130 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-06-16 | 2022-06-22 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
GARDEN ENTRANCE |  | 123 | 2022-04-02 | 2022-08-31
MEP WORKS |  | 123 | 2022-04-02 | 2022-08-31
MECHANICAL |  | 117 | 2022-04-02 | 2022-08-23
HVAC SYSTEM WORKS |  | 117 | 2022-04-02 | 2022-08-23
C-PW-064140 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 9 | 2022-04-02 | 2022-04-11 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064150 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 9 | 2022-04-05 | 2022-04-14 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064160 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 7 | 2022-04-16 | 2022-04-24 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064170 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-08-17 | 2022-08-23 | 01 | 06 | 01 | 46 | 003 | 01 |  | Building | HVAC | Museum | North West | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 16 | 2022-04-02 | 2022-04-19
C-PW-064180 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-04-02 | 2022-04-11 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064190 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-04-11 | 2022-04-19 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 16 | 2022-04-06 | 2022-04-25
C-PW-064200 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-04-06 | 2022-04-17 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064210 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-04-17 | 2022-04-25 | 01 | 08 | 01 | 46 | 003 | 01 |  | Building | Plumbing | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 74 | 2022-05-31 | 2022-08-31
C-PW-064220 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-05-31 | 2022-06-09 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064230 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-06-09 | 2022-06-22 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064240 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-06-22 | 2022-07-04 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064250 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-08-17 | 2022-08-23 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064260 | Final Fix Electrical (Light Fixtures) | 10 | 2022-08-18 | 2022-08-31 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064270 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-08-18 | 2022-08-31 | 01 | 07 | 01 | 46 | 003 | 01 |  | Building | Electrical | Museum | North West | L00 Ground Level | Circulation / Common Areas
ELV |  | 38 | 2022-06-02 | 2022-07-20
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-06-02 | 2022-06-29
C-PW-064280 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064290 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-14 | 2022-06-27 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064300 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-06-27 | 2022-06-29 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-06-05 | 2022-07-02
C-PW-064310 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-05 | 2022-06-16 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064320 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-16 | 2022-06-28 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064330 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-06-28 | 2022-07-02 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 24 | 2022-06-06 | 2022-07-04
C-PW-064340 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-06 | 2022-06-18 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064350 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064360 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-07-02 | 2022-07-04 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 24 | 2022-06-08 | 2022-07-06
C-PW-064370 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064380 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-20 | 2022-07-02 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064390 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-07-03 | 2022-07-06 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-06-09 | 2022-07-06
C-PW-064400 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-09 | 2022-06-22 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064410 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-22 | 2022-07-04 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064420 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-07-04 | 2022-07-06 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 23 | 2022-06-12 | 2022-07-09
C-PW-064430 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-12 | 2022-06-23 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064440 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-23 | 2022-07-06 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064450 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-07-06 | 2022-07-09 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-06-14 | 2022-07-14
C-PW-064460 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064470 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-26 | 2022-07-07 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064480 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-07-07 | 2022-07-14 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-07-14 | 2022-07-20
C-PW-064490 | Active Component System Works | 6 | 2022-07-14 | 2022-07-20 | 01 | 10 | 01 | 46 | 003 | 01 |  | Building | CCTV | Museum | North West | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEMS |  | 103 | 2022-04-06 | 2022-08-13
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 34 | 2022-06-26 | 2022-08-09
C-PW-064500 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-26 | 2022-07-07 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064510 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-07 | 2022-07-24 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064520 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-07 | 2022-08-09 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 33 | 2022-06-28 | 2022-08-09
C-PW-064530 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-28 | 2022-07-13 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064540 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-13 | 2022-07-25 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064550 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-07 | 2022-08-09 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 103 | 2022-04-06 | 2022-08-13
C-PW-064560 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 10 | 2022-04-06 | 2022-04-19 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064570 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-19 | 2022-04-28 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
C-PW-064580 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-08-07 | 2022-08-13 | 01 | 09 | 01 | 46 | 003 | 01 |  | Building | Firefighting | Museum | North West | L00 Ground Level | Circulation / Common Areas
NORTH EAST |  | 294 | 2022-01-02 | 2022-12-20
GALLERY C & FALCONRY AND CONSERVATION GALLERY - EAST |  | 275 | 2022-01-02 | 2022-11-28
MECHANICAL |  | 141 | 2022-06-05 | 2022-11-22
DRAINAGE WORKS |  | 14 | 2022-06-05 | 2022-06-21
C-PW-064590 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-06-05 | 2022-06-15 | 01 | 08 | 01 | 44 | 003 | 01 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064600 | 2nd Fix Piping System (Fittings, Insulation) | 6 | 2022-06-15 | 2022-06-21 | 01 | 08 | 01 | 44 | 003 | 01 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 14 | 2022-06-15 | 2022-07-02
C-PW-064610 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-06-15 | 2022-06-26 | 01 | 08 | 01 | 44 | 003 | 01 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064620 | 2nd Fix Piping System (Fittings, Insulation) | 6 | 2022-06-26 | 2022-07-02 | 01 | 08 | 01 | 44 | 003 | 01 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Circulation / Common Areas
HVAC SYSTEM WORKS |  | 126 | 2022-06-22 | 2022-11-22
C-PW-064630 | 1st Fix HVAC (Supports, Ducts, Insulation) | 12 | 2022-06-22 | 2022-07-05 | 01 | 06 | 01 | 44 | 003 | 01 |  | Building | HVAC | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064640 | 1st Fix HVAC (VAV's/CAV's box & Dampers - VCD,NRD,MDs) | 10 | 2022-07-06 | 2022-07-20 | 01 | 06 | 01 | 44 | 003 | 01 |  | Building | HVAC | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064650 | 1st Fix HVAC (CHW Piping, Drain Pipes & insulation) | 12 | 2022-07-16 | 2022-07-31 | 01 | 06 | 01 | 44 | 003 | 01 |  | Building | HVAC | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064660 | 2nd Fix HVAC (Plenums, Flex Ducts) | 12 | 2022-07-20 | 2022-08-04 | 01 | 06 | 01 | 44 | 003 | 01 |  | Building | HVAC | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064670 | Final Fix HVAC (Grills, Diffusers) | 7 | 2022-11-14 | 2022-11-22 | 01 | 06 | 01 | 44 | 003 | 01 |  | Building | HVAC | Museum | North East | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 275 | 2022-01-02 | 2022-11-28
C-PW-064680 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-01-02 | 2022-01-13 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064690 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-06-27 | 2022-07-17 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064700 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-17 | 2022-08-02 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064710 | LV Switchgears (DB's) | 6 | 2022-08-03 | 2022-08-09 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064720 | Cable/Wire Termination & Dressing | 7 | 2022-08-09 | 2022-08-17 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064730 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-11-14 | 2022-11-22 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064740 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-15 | 2022-11-23 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064750 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-17 | 2022-11-26 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064760 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-20 | 2022-11-28 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
ELV WORKS |  | 245 | 2022-02-05 | 2022-11-27
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 237 | 2022-02-05 | 2022-11-16
C-PW-064770 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-05 | 2022-02-16 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064780 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-02-16 | 2022-02-28 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064790 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-14 | 2022-11-16 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 235 | 2022-02-06 | 2022-11-16
C-PW-064800 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-02-06 | 2022-02-17 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064810 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-02-19 | 2022-03-02 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064820 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-14 | 2022-11-16 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 233 | 2022-02-08 | 2022-11-16
C-PW-064830 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-02-08 | 2022-02-20 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064840 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-02-20 | 2022-03-03 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064850 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-14 | 2022-11-16 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 233 | 2022-02-09 | 2022-11-19
C-PW-064860 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-02-09 | 2022-02-22 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064870 | 2nd Fix AV System Works (Wiring) | 10 | 2022-02-22 | 2022-03-06 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064880 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-19 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 232 | 2022-02-12 | 2022-11-19
C-PW-064890 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-02-12 | 2022-02-23 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064900 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-02-23 | 2022-03-08 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064910 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-15 | 2022-11-19 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 232 | 2022-02-14 | 2022-11-20
C-PW-064920 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-14 | 2022-02-26 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064930 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-02-26 | 2022-03-09 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064940 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-17 | 2022-11-20 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 230 | 2022-02-15 | 2022-11-20
C-PW-064950 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-15 | 2022-02-27 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064960 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-02-28 | 2022-03-12 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-064970 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-17 | 2022-11-20 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-20 | 2022-11-27
C-PW-064980 | Active Component System Works | 6 | 2022-11-20 | 2022-11-27 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 270 | 2022-01-02 | 2022-11-22
FIRE ALARM & PUBLIC ADDRESS |  | 263 | 2022-01-09 | 2022-11-21
C-PW-064990 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-01-09 | 2022-01-20 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-065000 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-01-22 | 2022-02-02 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-065010 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 3 | 2022-11-17 | 2022-11-21 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 268 | 2022-01-02 | 2022-11-19
C-PW-065020 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-02 | 2022-01-13 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-065030 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-01-13 | 2022-01-25 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-065040 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 3 | 2022-11-15 | 2022-11-19 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 132 | 2022-06-15 | 2022-11-22
C-PW-065050 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 12 | 2022-06-15 | 2022-06-29 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-065060 | 2nd Fix Piping System - (Fittings) | 10 | 2022-06-29 | 2022-07-13 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-065070 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-11-14 | 2022-11-22 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
WILDLIFE KITCHEN & STORAGE,PREPARATION RECEPTION & SHELTER AREAS - EAST |  | 283 | 2022-01-02 | 2022-12-08
MECHANICAL |  | 142 | 2022-06-15 | 2022-12-05
HOT & COLD WATER SYSTEM |  | 138 | 2022-06-21 | 2022-12-05
C-PW-065080 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-21 | 2022-07-16 | 01 | 08 | 01 | 44 | 003 | 05 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065090 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-16 | 2022-07-27 | 01 | 08 | 01 | 44 | 003 | 05 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065100 | Final Fix - Electric Water Heater & Water Meter Installation | 3 | 2022-12-01 | 2022-12-05 | 01 | 08 | 01 | 44 | 003 | 05 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 29 | 2022-06-15 | 2022-07-23
C-PW-065110 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-15 | 2022-07-06 | 01 | 08 | 01 | 44 | 003 | 05 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065120 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-06 | 2022-07-23 | 01 | 08 | 01 | 44 | 003 | 05 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
HVAC SYSTEM WORKS |  | 131 | 2022-06-25 | 2022-12-01
C-PW-065130 | 1st Fix HVAC (Supports, Ducts, Insulation, VAV/CAV Box & Dampers - VCD,NRD,MDs) | 18 | 2022-06-25 | 2022-07-19 | 01 | 06 | 01 | 44 | 003 | 05 |  | Building | HVAC | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065140 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 18 | 2022-06-28 | 2022-07-23 | 01 | 06 | 01 | 44 | 003 | 05 |  | Building | HVAC | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065150 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-07-19 | 2022-08-02 | 01 | 06 | 01 | 44 | 003 | 05 |  | Building | HVAC | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065160 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-21 | 2022-12-01 | 01 | 06 | 01 | 44 | 003 | 05 |  | Building | HVAC | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 242 | 2022-02-13 | 2022-12-03
C-PW-065170 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 12 | 2022-02-13 | 2022-02-27 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065180 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-07-17 | 2022-08-08 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065190 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-08-08 | 2022-08-24 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065200 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-21 | 2022-12-01 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065210 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-23 | 2022-12-03 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065220 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-23 | 2022-12-03 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
ELV WORKS |  | 245 | 2022-02-14 | 2022-12-08
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 234 | 2022-02-14 | 2022-11-23
C-PW-065230 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-14 | 2022-02-27 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065240 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-02-27 | 2022-03-10 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065250 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-21 | 2022-11-23 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 224 | 2022-02-27 | 2022-11-23
C-PW-065260 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-02-27 | 2022-03-10 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065270 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-03-10 | 2022-03-22 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065280 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-21 | 2022-11-23 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 225 | 2022-02-28 | 2022-11-27
C-PW-065290 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-02-28 | 2022-03-13 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065300 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-03-13 | 2022-03-24 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065310 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-24 | 2022-11-27 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 225 | 2022-03-02 | 2022-11-28
C-PW-065320 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-03-02 | 2022-03-14 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065330 | 2nd Fix AV System Works (Wiring) | 10 | 2022-03-14 | 2022-03-27 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065340 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-26 | 2022-11-28 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 223 | 2022-03-05 | 2022-11-28
C-PW-065350 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-05 | 2022-03-16 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065360 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-03-16 | 2022-03-28 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065370 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-26 | 2022-11-28 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 223 | 2022-03-06 | 2022-12-01
C-PW-065380 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-06 | 2022-03-17 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065390 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-19 | 2022-03-30 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065400 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-28 | 2022-12-01 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 221 | 2022-03-08 | 2022-12-01
C-PW-065410 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-08 | 2022-03-20 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065420 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-20 | 2022-03-31 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065430 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-28 | 2022-12-01 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-12-01 | 2022-12-08
C-PW-065440 | Active Component System Works | 6 | 2022-12-01 | 2022-12-08 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 272 | 2022-01-02 | 2022-11-23
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 272 | 2022-01-02 | 2022-11-23
C-PW-065450 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-02 | 2022-01-13 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065460 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-01-13 | 2022-01-25 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065470 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-21 | 2022-11-23 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 265 | 2022-01-09 | 2022-11-23
C-PW-065480 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-01-09 | 2022-01-20 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065490 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-01-22 | 2022-02-02 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065500 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-21 | 2022-11-23 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 86 | 2022-06-29 | 2022-10-12
C-PW-065510 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 18 | 2022-06-29 | 2022-07-24 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065520 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-24 | 2022-08-03 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065530 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-10-03 | 2022-10-12 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
INTERVIEW,SECURITY SCAN, FIRST AID ROOMS AND OFFICE AREAS - EAST |  | 269 | 2022-01-02 | 2022-11-20
MECHANICAL |  | 74 | 2022-08-08 | 2022-11-03
HOT & COLD WATER SYSTEM |  | 24 | 2022-08-14 | 2022-09-11
C-PW-065540 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-08-14 | 2022-08-29 | 01 | 08 | 01 | 44 | 003 | 05 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065550 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-30 | 2022-09-11 | 01 | 08 | 01 | 44 | 003 | 05 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 24 | 2022-08-08 | 2022-09-05
C-PW-065560 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-08-08 | 2022-08-24 | 01 | 08 | 01 | 44 | 003 | 05 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065570 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-24 | 2022-09-05 | 01 | 08 | 01 | 44 | 003 | 05 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
HVAC SYSTEM WORKS |  | 66 | 2022-08-17 | 2022-11-03
C-PW-065580 | 1st Fix HVAC (Supports, Ducts, Insulation, VAV/CAV Box & Dampers - VCD,NRD,MDs) | 14 | 2022-08-17 | 2022-09-03 | 01 | 06 | 01 | 44 | 003 | 05 |  | Building | HVAC | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065590 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 14 | 2022-08-21 | 2022-09-06 | 01 | 06 | 01 | 44 | 003 | 05 |  | Building | HVAC | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065600 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-09-06 | 2022-09-18 | 01 | 06 | 01 | 44 | 003 | 05 |  | Building | HVAC | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065610 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-25 | 2022-11-03 | 01 | 06 | 01 | 44 | 003 | 05 |  | Building | HVAC | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 86 | 2022-08-08 | 2022-11-17
C-PW-065620 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-08-08 | 2022-08-20 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065630 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-08-21 | 2022-09-06 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065640 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-09-06 | 2022-09-21 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065650 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-07 | 2022-11-16 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065660 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-09 | 2022-11-17 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065670 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-09 | 2022-11-17 | 01 | 07 | 01 | 44 | 003 | 05 |  | Building | Electrical | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
ELV |  | 86 | 2022-08-10 | 2022-11-20
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 78 | 2022-08-10 | 2022-11-09
C-PW-065680 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-08-10 | 2022-08-22 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065690 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-08-22 | 2022-09-03 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065700 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-07 | 2022-11-09 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 76 | 2022-08-11 | 2022-11-09
C-PW-065710 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-08-11 | 2022-08-24 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065720 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-08-24 | 2022-09-05 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065730 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-07 | 2022-11-09 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 74 | 2022-08-14 | 2022-11-09
C-PW-065740 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-08-14 | 2022-08-25 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065750 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-08-25 | 2022-09-07 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065760 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-07 | 2022-11-09 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 74 | 2022-08-16 | 2022-11-12
C-PW-065770 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-08-16 | 2022-08-28 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065780 | 2nd Fix AV System Works (Wiring) | 10 | 2022-08-28 | 2022-09-08 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065790 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-09 | 2022-11-12 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 73 | 2022-08-17 | 2022-11-12
C-PW-065800 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-08-17 | 2022-08-29 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065810 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-08-30 | 2022-09-11 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065820 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-09 | 2022-11-12 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 73 | 2022-08-20 | 2022-11-13
C-PW-065830 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-08-20 | 2022-08-31 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065840 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-31 | 2022-09-12 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065850 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 71 | 2022-08-21 | 2022-11-13
C-PW-065860 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-08-21 | 2022-09-03 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065870 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-09-03 | 2022-09-14 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065880 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-14 | 2022-11-20
C-PW-065890 | Active Component System Works | 6 | 2022-11-14 | 2022-11-20 | 01 | 10 | 01 | 44 | 003 | 05 |  | Building | CCTV | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 260 | 2022-01-02 | 2022-11-09
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 260 | 2022-01-02 | 2022-11-09
C-PW-065900 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-02 | 2022-01-13 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065910 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-01-13 | 2022-01-25 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065920 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-07 | 2022-11-09 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 253 | 2022-01-09 | 2022-11-09
C-PW-065930 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-01-09 | 2022-01-20 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065940 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-01-22 | 2022-02-02 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065950 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-07 | 2022-11-09 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 56 | 2022-08-21 | 2022-10-26
C-PW-065960 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-08-21 | 2022-09-06 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065970 | 2nd Fix Piping System - (Fittings) | 8 | 2022-09-06 | 2022-09-15 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-065980 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-10-17 | 2022-10-26 | 01 | 09 | 01 | 44 | 003 | 05 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Storage / Offices / Admin Areas
CIRCULATIONS & CORRIDORS - EAST |  | 294 | 2022-01-02 | 2022-12-20
MECHANICAL |  | 106 | 2022-07-06 | 2022-11-14
DRAINAGE WORKS |  | 29 | 2022-07-06 | 2022-08-14
C-PW-065990 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-06 | 2022-08-02 | 01 | 08 | 01 | 44 | 003 | 01 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066000 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-02 | 2022-08-14 | 01 | 08 | 01 | 44 | 003 | 01 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-07-16 | 2022-08-20
C-PW-066010 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-16 | 2022-08-07 | 01 | 08 | 01 | 44 | 003 | 01 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066020 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-08 | 2022-08-20 | 01 | 08 | 01 | 44 | 003 | 01 |  | Building | Plumbing | Museum | North East | L00 Ground Level | Circulation / Common Areas
HVAC SYSTEM WORKS |  | 94 | 2022-07-25 | 2022-11-14
C-PW-066030 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 14 | 2022-07-25 | 2022-08-11 | 01 | 06 | 01 | 44 | 003 | 01 |  | Building | HVAC | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066040 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 14 | 2022-07-28 | 2022-08-15 | 01 | 06 | 01 | 44 | 003 | 01 |  | Building | HVAC | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066050 | 2nd Fix HVAC (FCUs, Valves Package, Duct Heaters & Humidifiers) | 10 | 2022-08-15 | 2022-08-27 | 01 | 06 | 01 | 44 | 003 | 01 |  | Building | HVAC | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066060 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-11-06 | 2022-11-14 | 01 | 06 | 01 | 44 | 003 | 01 |  | Building | HVAC | Museum | North East | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 244 | 2022-02-27 | 2022-12-18
C-PW-066070 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-02-27 | 2022-03-10 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066080 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-08-08 | 2022-08-24 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066090 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-08-24 | 2022-09-08 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066100 | LV Switchgears (DB's) | 5 | 2022-09-10 | 2022-09-14 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066110 | Cable/Wire Termination & Dressing | 7 | 2022-09-14 | 2022-09-22 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066120 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-12-05 | 2022-12-13 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066130 | Final Fix Electrical (Light Fixtures) | 7 | 2022-12-06 | 2022-12-14 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066140 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-12-08 | 2022-12-17 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066150 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-12-10 | 2022-12-18 | 01 | 07 | 01 | 44 | 003 | 01 |  | Building | Electrical | Museum | North East | L00 Ground Level | Circulation / Common Areas
ELV |  | 265 | 2022-02-05 | 2022-12-20
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 253 | 2022-02-05 | 2022-12-07
C-PW-066160 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-05 | 2022-02-16 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066170 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-02-16 | 2022-02-28 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066180 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-12-05 | 2022-12-07 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 252 | 2022-02-06 | 2022-12-07
C-PW-066190 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-02-06 | 2022-02-17 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066200 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-02-19 | 2022-03-02 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066210 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-12-05 | 2022-12-07 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 253 | 2022-02-08 | 2022-12-10
C-PW-066220 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-02-08 | 2022-02-20 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066230 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-02-20 | 2022-03-03 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066240 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-12-07 | 2022-12-10 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 253 | 2022-02-09 | 2022-12-12
C-PW-066250 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-02-09 | 2022-02-22 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066260 | 2nd Fix AV System Works (Wiring) | 10 | 2022-02-22 | 2022-03-06 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066270 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-12-10 | 2022-12-12 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 251 | 2022-02-12 | 2022-12-12
C-PW-066280 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-02-12 | 2022-02-23 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066290 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-02-23 | 2022-03-08 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066300 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-12-10 | 2022-12-12 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 251 | 2022-02-14 | 2022-12-13
C-PW-066310 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-14 | 2022-02-26 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066320 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-02-26 | 2022-03-09 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066330 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-12-11 | 2022-12-13 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 249 | 2022-02-15 | 2022-12-13
C-PW-066340 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-15 | 2022-02-27 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066350 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-02-28 | 2022-03-12 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066360 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-12-11 | 2022-12-13 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-12-14 | 2022-12-20
C-PW-066370 | Active Component System Works | 6 | 2022-12-14 | 2022-12-20 | 01 | 10 | 01 | 44 | 003 | 01 |  | Building | CCTV | Museum | North East | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 282 | 2022-01-02 | 2022-12-07
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 282 | 2022-01-02 | 2022-12-07
C-PW-066380 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-02 | 2022-01-13 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066390 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-01-13 | 2022-01-25 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066400 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-12-05 | 2022-12-07 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 276 | 2022-01-09 | 2022-12-07
C-PW-066410 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-01-09 | 2022-01-20 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066420 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-01-22 | 2022-02-02 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066430 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-12-05 | 2022-12-07 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 89 | 2022-08-01 | 2022-11-14
C-PW-066440 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-08-01 | 2022-08-16 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066450 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-08-17 | 2022-08-25 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
C-PW-066460 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 7 | 2022-11-06 | 2022-11-14 | 01 | 09 | 01 | 44 | 003 | 01 |  | Building | Firefighting | Museum | North East | L00 Ground Level | Circulation / Common Areas
SOUTH WEST |  | 289 | 2022-01-02 | 2022-12-14
SECURITY, SCAN, INTERVIEW & CASH AREAS - WEST |  | 100 | 2022-05-05 | 2022-09-03
MECHANICAL |  | 93 | 2022-05-05 | 2022-08-25
HVAC SYSTEM WORKS |  | 85 | 2022-05-15 | 2022-08-25
C-PW-066470 | 1st Fix HVAC (Supports, Ducts, Insulation, VAV/CAV Box & Dampers - VCD,NRD,MDs) | 18 | 2022-05-15 | 2022-06-05 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066480 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 18 | 2022-05-18 | 2022-06-08 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066490 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-06-05 | 2022-06-16 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066500 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-08-16 | 2022-08-25 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 29 | 2022-05-05 | 2022-06-07
C-PW-066510 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-05 | 2022-05-26 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066520 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-26 | 2022-06-07 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-05-10 | 2022-06-13
C-PW-066530 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-10 | 2022-06-01 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066540 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-01 | 2022-06-13 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 100 | 2022-05-05 | 2022-09-03
C-PW-066550 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-05-05 | 2022-05-21 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066560 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-05-09 | 2022-05-30 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066570 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-30 | 2022-06-15 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066580 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-08-16 | 2022-08-25 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066590 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-18 | 2022-08-27 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066600 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-25 | 2022-09-03 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
ELV |  | 91 | 2022-05-10 | 2022-08-29
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 82 | 2022-05-10 | 2022-08-20
C-PW-066610 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-10 | 2022-05-23 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066620 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-23 | 2022-06-04 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066630 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-16 | 2022-08-20 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 72 | 2022-05-23 | 2022-08-20
C-PW-066640 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-05-23 | 2022-06-04 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066650 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-04 | 2022-06-15 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066660 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-16 | 2022-08-20 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 70 | 2022-05-24 | 2022-08-20
C-PW-066670 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-05-24 | 2022-06-06 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066680 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-06 | 2022-06-18 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066690 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-16 | 2022-08-20 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 70 | 2022-05-26 | 2022-08-21
C-PW-066700 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-26 | 2022-06-07 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066710 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-07 | 2022-06-20 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066720 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-18 | 2022-08-21 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 69 | 2022-05-29 | 2022-08-21
C-PW-066730 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-29 | 2022-06-09 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066740 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-09 | 2022-06-21 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066750 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-18 | 2022-08-21 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 69 | 2022-05-30 | 2022-08-23
C-PW-066760 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-30 | 2022-06-11 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066770 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-12 | 2022-06-23 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066780 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-21 | 2022-08-23 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 67 | 2022-06-01 | 2022-08-23
C-PW-066790 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-01 | 2022-06-13 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066800 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-13 | 2022-06-25 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066810 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-21 | 2022-08-23 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-08-23 | 2022-08-29
C-PW-066820 | Active Component System Works | 6 | 2022-08-23 | 2022-08-29 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 74 | 2022-05-19 | 2022-08-20
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 55 | 2022-06-12 | 2022-08-20
C-PW-066830 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-12 | 2022-06-23 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066840 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-23 | 2022-07-05 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066850 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-16 | 2022-08-20 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 54 | 2022-06-13 | 2022-08-20
C-PW-066860 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-13 | 2022-06-25 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066870 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-26 | 2022-07-07 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066880 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-16 | 2022-08-20 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 61 | 2022-05-19 | 2022-08-03
C-PW-066890 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-05-19 | 2022-06-07 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066900 | 2nd Fix Piping System - (Fittings) | 8 | 2022-06-07 | 2022-06-16 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066910 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-07-24 | 2022-08-03 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
ARTIFACT WORKSHOPS, SEP WORK & TOOL ROOMS - WEST |  | 98 | 2022-05-21 | 2022-09-17
MECHANICAL |  | 87 | 2022-05-26 | 2022-09-10
HVAC SYSTEM WORKS |  | 79 | 2022-06-05 | 2022-09-10
C-PW-066920 | 1st Fix HVAC (Supports, Ducts, Insulation, VAV/CAV Box & Dampers - VCD,NRD,MDs) | 17 | 2022-06-05 | 2022-06-25 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066930 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-06-08 | 2022-06-28 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066940 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-06-26 | 2022-07-07 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066950 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-09-04 | 2022-09-10 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 25 | 2022-05-26 | 2022-06-25
C-PW-066960 | 1st Fix Piping System (Supports, Piping) | 17 | 2022-05-26 | 2022-06-15 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066970 | 2nd Fix Piping System (Fittings, Insulation) | 8 | 2022-06-15 | 2022-06-25 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 25 | 2022-06-01 | 2022-06-29
C-PW-066980 | 1st Fix Piping System (Supports, Piping) | 17 | 2022-06-01 | 2022-06-20 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-066990 | 2nd Fix Piping System (Fittings, Insulation) | 8 | 2022-06-21 | 2022-06-29 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 98 | 2022-05-21 | 2022-09-17
C-PW-067000 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 13 | 2022-05-21 | 2022-06-05 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067010 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-06-08 | 2022-06-28 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067020 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-28 | 2022-07-17 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067030 | LV Switchgears (DB's) | 5 | 2022-07-18 | 2022-07-23 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067040 | Cable/Wire Termination & Dressing | 7 | 2022-07-23 | 2022-08-01 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067050 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-09-04 | 2022-09-10 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067060 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-05 | 2022-09-13 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067070 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-07 | 2022-09-15 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067080 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-08 | 2022-09-17 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
ELV |  | 38 | 2022-05-25 | 2022-07-09
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-05-25 | 2022-06-21
C-PW-067090 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067100 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067110 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-06-19 | 2022-06-21 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-05-28 | 2022-06-23
C-PW-067120 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-05-28 | 2022-06-08 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067130 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067140 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-06-21 | 2022-06-23 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 24 | 2022-05-29 | 2022-06-26
C-PW-067150 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-05-29 | 2022-06-11 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067160 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067170 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-06-23 | 2022-06-26 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 24 | 2022-05-31 | 2022-06-28
C-PW-067180 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-31 | 2022-06-12 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067190 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-12 | 2022-06-25 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067200 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-06-26 | 2022-06-28 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-06-02 | 2022-06-29
C-PW-067210 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067220 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067230 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-06-26 | 2022-06-29 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 23 | 2022-06-04 | 2022-06-30
C-PW-067240 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-04 | 2022-06-15 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067250 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-16 | 2022-06-28 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067260 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-06-28 | 2022-06-30 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-06-06 | 2022-07-03
C-PW-067270 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-06 | 2022-06-18 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067280 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-18 | 2022-06-29 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067290 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-06-30 | 2022-07-03 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-07-03 | 2022-07-09
C-PW-067300 | Active Component System Works | 6 | 2022-07-03 | 2022-07-09 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 58 | 2022-06-11 | 2022-08-22
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 23 | 2022-06-16 | 2022-07-17
C-PW-067310 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-16 | 2022-06-28 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067320 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-28 | 2022-07-13 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067330 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-13 | 2022-07-17 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 23 | 2022-06-18 | 2022-07-18
C-PW-067340 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-18 | 2022-06-29 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067350 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-30 | 2022-07-16 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067360 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-07-16 | 2022-07-18 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 58 | 2022-06-11 | 2022-08-22
C-PW-067370 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-06-11 | 2022-06-26 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067380 | 2nd Fix Piping System - (Fittings) | 8 | 2022-06-26 | 2022-07-05 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-067390 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-08-16 | 2022-08-22 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
SEP TOILETS - WEST |  | 138 | 2022-04-04 | 2022-09-20
MECHANICAL |  | 79 | 2022-06-15 | 2022-09-20
HVAC SYSTEM WORKS |  | 68 | 2022-06-25 | 2022-09-17
C-PW-067400 | 1st Fix HVAC (Supports, Ducts, Insulation, VAV/CAV Box & Dampers - VCD,NRD,MDs) | 14 | 2022-06-25 | 2022-07-13 | 01 | 06 | 01 | 47 | 003 | 03 |  | Building | HVAC | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067410 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-07-13 | 2022-07-26 | 01 | 06 | 01 | 47 | 003 | 03 |  | Building | HVAC | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067420 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-09-10 | 2022-09-17 | 01 | 06 | 01 | 47 | 003 | 03 |  | Building | HVAC | Museum | South West | L00 Ground Level | Wet Areas
DRAINAGE WORKS |  | 76 | 2022-06-15 | 2022-09-17
C-PW-067430 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-06-15 | 2022-06-30 | 01 | 08 | 01 | 47 | 003 | 03 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067440 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-30 | 2022-07-17 | 01 | 08 | 01 | 47 | 003 | 03 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067450 | Final Fix (Installation of Sanitaryware & Accessories) | 6 | 2022-09-10 | 2022-09-17 | 01 | 08 | 01 | 47 | 003 | 03 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Wet Areas
HOT & COLD WATER SYSTEM |  | 74 | 2022-06-21 | 2022-09-20
C-PW-067460 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-06-21 | 2022-07-06 | 01 | 08 | 01 | 47 | 003 | 03 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067470 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-07-14 | 2022-07-26 | 01 | 08 | 01 | 47 | 003 | 03 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067480 | Final Fix - Water Meter Installation | 3 | 2022-09-17 | 2022-09-20 | 01 | 08 | 01 | 47 | 003 | 03 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Wet Areas
ELECTRICAL WORKS |  | 138 | 2022-04-04 | 2022-09-20
C-PW-067490 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-04-04 | 2022-04-16 | 01 | 07 | 01 | 47 | 003 | 03 |  | Building | Electrical | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067500 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-06-28 | 2022-07-17 | 01 | 07 | 01 | 47 | 003 | 03 |  | Building | Electrical | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067510 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-18 | 2022-08-03 | 01 | 07 | 01 | 47 | 003 | 03 |  | Building | Electrical | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067520 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-09-10 | 2022-09-17 | 01 | 07 | 01 | 47 | 003 | 03 |  | Building | Electrical | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067530 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-12 | 2022-09-20 | 01 | 07 | 01 | 47 | 003 | 03 |  | Building | Electrical | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067540 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-12 | 2022-09-20 | 01 | 07 | 01 | 47 | 003 | 03 |  | Building | Electrical | Museum | South West | L00 Ground Level | Wet Areas
ELV |  | 121 | 2022-04-16 | 2022-09-12
AV SYSTEM |  | 121 | 2022-04-16 | 2022-09-12
C-PW-067550 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-16 | 2022-04-27 | 01 | 10 | 01 | 47 | 003 | 03 |  | Building | CCTV | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067560 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-18 | 2022-07-31 | 01 | 10 | 01 | 47 | 003 | 03 |  | Building | CCTV | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067570 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-12 | 01 | 10 | 01 | 47 | 003 | 03 |  | Building | CCTV | Museum | South West | L00 Ground Level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 120 | 2022-04-18 | 2022-09-12
C-PW-067580 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 47 | 003 | 03 |  | Building | CCTV | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067590 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 47 | 003 | 03 |  | Building | CCTV | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067600 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-12 | 01 | 10 | 01 | 47 | 003 | 03 |  | Building | CCTV | Museum | South West | L00 Ground Level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 118 | 2022-04-19 | 2022-09-12
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 118 | 2022-04-19 | 2022-09-12
C-PW-067610 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-19 | 2022-05-05 | 01 | 09 | 01 | 47 | 003 | 03 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067620 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-05 | 2022-05-17 | 01 | 09 | 01 | 47 | 003 | 03 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067630 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-12 | 01 | 09 | 01 | 47 | 003 | 03 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 117 | 2022-04-21 | 2022-09-12
C-PW-067640 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-21 | 2022-05-07 | 01 | 09 | 01 | 47 | 003 | 03 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067650 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-07 | 2022-05-19 | 01 | 09 | 01 | 47 | 003 | 03 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067660 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-12 | 01 | 09 | 01 | 47 | 003 | 03 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Wet Areas
FIRE FIGHTING WORKS |  | 54 | 2022-06-30 | 2022-09-05
C-PW-067670 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-06-30 | 2022-07-19 | 01 | 09 | 01 | 47 | 003 | 03 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067680 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-19 | 2022-07-28 | 01 | 09 | 01 | 47 | 003 | 03 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Wet Areas
C-PW-067690 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-08-30 | 2022-09-05 | 01 | 09 | 01 | 47 | 003 | 03 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Wet Areas
SEP GALLERIES & LOBBY - WEST |  | 133 | 2022-05-05 | 2022-10-12
MECHANICAL |  | 130 | 2022-05-05 | 2022-10-08
HVAC SYSTEM WORKS |  | 130 | 2022-05-05 | 2022-10-08
C-PW-067700 | 1st Fix HVAC (Dampers - VCD,NRD,MDs) | 14 | 2022-05-05 | 2022-05-21 | 01 | 06 | 01 | 47 | 003 | 01 |  | Building | HVAC | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067710 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 14 | 2022-05-09 | 2022-05-24 | 01 | 06 | 01 | 47 | 003 | 01 |  | Building | HVAC | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067720 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 14 | 2022-05-24 | 2022-06-09 | 01 | 06 | 01 | 47 | 003 | 01 |  | Building | HVAC | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067730 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-28 | 2022-10-08 | 01 | 06 | 01 | 47 | 003 | 01 |  | Building | HVAC | Museum | South West | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 23 | 2022-06-30 | 2022-08-01
C-PW-067740 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-06-30 | 2022-07-20 | 01 | 08 | 01 | 47 | 003 | 01 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067750 | 2nd Fix Piping System (Fittings, Insulation) | 14 | 2022-07-16 | 2022-08-01 | 01 | 08 | 01 | 47 | 003 | 01 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 23 | 2022-07-06 | 2022-08-07
C-PW-067760 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-07-06 | 2022-07-26 | 01 | 08 | 01 | 47 | 003 | 01 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067770 | 2nd Fix Piping System (Fittings, Insulation) | 14 | 2022-07-21 | 2022-08-07 | 01 | 08 | 01 | 47 | 003 | 01 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 130 | 2022-05-05 | 2022-10-10
C-PW-067780 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-05-05 | 2022-05-21 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067790 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-05-09 | 2022-05-24 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067800 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-24 | 2022-06-09 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067810 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-28 | 2022-10-08 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067820 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-01 | 2022-10-10 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067830 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-01 | 2022-10-10 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
ELV |  | 128 | 2022-05-10 | 2022-10-12
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 119 | 2022-05-10 | 2022-10-01
C-PW-067840 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-10 | 2022-05-23 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067850 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-23 | 2022-06-04 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067860 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-01 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 118 | 2022-05-12 | 2022-10-01
C-PW-067870 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-05-12 | 2022-05-24 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067880 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-24 | 2022-06-06 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067890 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-01 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 116 | 2022-05-15 | 2022-10-01
C-PW-067900 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067910 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-26 | 2022-06-07 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067920 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-01 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 116 | 2022-05-16 | 2022-10-03
C-PW-067930 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-16 | 2022-05-28 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067940 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-29 | 2022-06-09 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067950 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-01 | 2022-10-03 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 114 | 2022-05-18 | 2022-10-03
C-PW-067960 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-18 | 2022-05-30 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067970 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-30 | 2022-06-11 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-067980 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-01 | 2022-10-03 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 114 | 2022-05-19 | 2022-10-05
C-PW-067990 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-19 | 2022-06-01 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068000 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-01 | 2022-06-13 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068010 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-02 | 2022-10-05 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 113 | 2022-05-22 | 2022-10-05
C-PW-068020 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068030 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-02 | 2022-06-15 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068040 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-02 | 2022-10-05 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-05 | 2022-10-12
C-PW-068050 | Active Component System Works | 6 | 2022-10-05 | 2022-10-12 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 106 | 2022-06-01 | 2022-10-08
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 101 | 2022-06-01 | 2022-10-01
C-PW-068060 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-01 | 2022-06-13 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068070 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-13 | 2022-06-25 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068080 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-01 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 99 | 2022-06-02 | 2022-10-01
C-PW-068090 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-15 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068100 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-15 | 2022-06-27 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068110 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-01 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 68 | 2022-07-19 | 2022-10-08
C-PW-068120 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 12 | 2022-07-19 | 2022-08-03 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068130 | 2nd Fix Piping System - (Fittings) | 12 | 2022-08-01 | 2022-08-15 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068140 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-28 | 2022-10-08 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
FUTURE EXPANSION ROOMS - WEST |  | 210 | 2022-01-02 | 2022-09-12
ELECTRICAL WORKS |  | 81 | 2022-06-05 | 2022-09-12
C-PW-068150 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-06-05 | 2022-06-13 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068160 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-06-11 | 2022-06-20 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068170 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-06-21 | 2022-07-03 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068180 | LV Switchgears (DB's) | 5 | 2022-07-03 | 2022-07-09 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068190 | Cable/Wire Termination & Dressing | 7 | 2022-07-09 | 2022-07-20 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068200 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-08-29 | 2022-09-03 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068210 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-30 | 2022-09-07 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068220 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-01 | 2022-09-10 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068230 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-04 | 2022-09-12 | 01 | 07 | 01 | 47 | 003 | 05 |  | Building | Electrical | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
MECHANICAL |  | 114 | 2022-04-14 | 2022-09-03
HVAC SYSTEM WORKS |  | 114 | 2022-04-14 | 2022-09-03
C-PW-068240 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 9 | 2022-04-14 | 2022-04-25 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068250 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-04-25 | 2022-05-08 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068260 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 5 | 2022-08-29 | 2022-09-03 | 01 | 06 | 01 | 47 | 003 | 05 |  | Building | HVAC | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 13 | 2022-06-15 | 2022-06-29
C-PW-068270 | 1st Fix Piping System (Supports, Piping) | 6 | 2022-06-15 | 2022-06-21 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068280 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-06-21 | 2022-06-29 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 13 | 2022-06-21 | 2022-07-05
C-PW-068290 | 1st Fix Piping System (Supports, Piping) | 6 | 2022-06-21 | 2022-06-27 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068300 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-06-27 | 2022-07-05 | 01 | 08 | 01 | 47 | 003 | 05 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
ELV |  | 38 | 2022-06-07 | 2022-07-25
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-06-07 | 2022-07-04
C-PW-068310 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068320 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068330 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-06-30 | 2022-07-04 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-06-08 | 2022-07-05
C-PW-068340 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068350 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-21 | 2022-07-03 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068360 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-07-03 | 2022-07-05 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 24 | 2022-06-11 | 2022-07-09
C-PW-068370 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068380 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-22 | 2022-07-04 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068390 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-07-05 | 2022-07-09 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 24 | 2022-06-12 | 2022-07-13
C-PW-068400 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-12 | 2022-06-25 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068410 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-25 | 2022-07-06 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068420 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-07-07 | 2022-07-13 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-06-14 | 2022-07-14
C-PW-068430 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068440 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-26 | 2022-07-09 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068450 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-07-09 | 2022-07-14 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 23 | 2022-06-16 | 2022-07-17
C-PW-068460 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-16 | 2022-06-28 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068470 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-28 | 2022-07-13 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068480 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-07-13 | 2022-07-17 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-06-18 | 2022-07-18
C-PW-068490 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-18 | 2022-06-29 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068500 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-30 | 2022-07-16 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068510 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-07-16 | 2022-07-18 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-07-18 | 2022-07-25
C-PW-068520 | Active Component System Works | 6 | 2022-07-18 | 2022-07-25 | 01 | 10 | 01 | 47 | 003 | 05 |  | Building | CCTV | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 204 | 2022-01-02 | 2022-09-04
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 201 | 2022-01-02 | 2022-08-31
C-PW-068530 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-02 | 2022-01-13 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068540 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-01-13 | 2022-01-25 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068550 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-29 | 2022-08-31 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 112 | 2022-04-14 | 2022-08-31
C-PW-068560 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068570 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-27 | 2022-05-12 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068580 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-29 | 2022-08-31 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 56 | 2022-06-26 | 2022-09-04
C-PW-068590 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 9 | 2022-06-26 | 2022-07-06 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068600 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-06 | 2022-07-19 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-068610 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-08-29 | 2022-09-04 | 01 | 09 | 01 | 47 | 003 | 05 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Storage / Offices / Admin Areas
CIRCULATIONS & CORRIDORS - WEST |  | 146 | 2022-06-21 | 2022-12-14
MECHANICAL |  | 98 | 2022-07-20 | 2022-11-13
HVAC SYSTEM WORKS |  | 90 | 2022-07-31 | 2022-11-13
C-PW-068620 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 14 | 2022-07-31 | 2022-08-15 | 01 | 06 | 01 | 47 | 003 | 01 |  | Building | HVAC | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068630 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 14 | 2022-08-03 | 2022-08-20 | 01 | 06 | 01 | 47 | 003 | 01 |  | Building | HVAC | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068640 | 2nd Fix HVAC (FCUs, Valves Package, Duct Heaters & Humidifiers) | 8 | 2022-08-20 | 2022-08-29 | 01 | 06 | 01 | 47 | 003 | 01 |  | Building | HVAC | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068650 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-11-05 | 2022-11-13 | 01 | 06 | 01 | 47 | 003 | 01 |  | Building | HVAC | Museum | South West | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 25 | 2022-07-20 | 2022-08-20
C-PW-068660 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-20 | 2022-08-11 | 01 | 08 | 01 | 47 | 003 | 01 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068670 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-07 | 2022-08-20 | 01 | 08 | 01 | 47 | 003 | 01 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 25 | 2022-07-26 | 2022-08-24
C-PW-068680 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-26 | 2022-08-17 | 01 | 08 | 01 | 47 | 003 | 01 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068690 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-13 | 2022-08-24 | 01 | 08 | 01 | 47 | 003 | 01 |  | Building | Plumbing | Museum | South West | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 146 | 2022-06-21 | 2022-12-14
C-PW-068700 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-06-21 | 2022-07-03 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068710 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-08-03 | 2022-08-20 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068720 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-08-20 | 2022-08-31 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068730 | LV Switchgears (DB's) | 5 | 2022-08-31 | 2022-09-06 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068740 | Cable/Wire Termination & Dressing | 7 | 2022-09-06 | 2022-09-14 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068750 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-11-29 | 2022-12-08 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068760 | Final Fix Electrical (Light Fixtures) | 7 | 2022-12-03 | 2022-12-11 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068770 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-12-04 | 2022-12-12 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068780 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-12-06 | 2022-12-14 | 01 | 07 | 01 | 47 | 003 | 01 |  | Building | Electrical | Museum | South West | L00 Ground Level | Circulation / Common Areas
ELV |  | 143 | 2022-06-22 | 2022-12-13
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 134 | 2022-06-22 | 2022-12-03
C-PW-068790 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-22 | 2022-07-04 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068800 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-05 | 2022-07-20 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068810 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-29 | 2022-12-03 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 133 | 2022-06-25 | 2022-12-03
C-PW-068820 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-25 | 2022-07-06 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068830 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-06 | 2022-07-21 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068840 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-29 | 2022-12-03 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 131 | 2022-06-26 | 2022-12-03
C-PW-068850 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-26 | 2022-07-09 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068860 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068870 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-29 | 2022-12-03 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 131 | 2022-06-28 | 2022-12-05
C-PW-068880 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-28 | 2022-07-13 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068890 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-13 | 2022-07-26 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068900 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-12-03 | 2022-12-05 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 130 | 2022-06-30 | 2022-12-05
C-PW-068910 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-30 | 2022-07-16 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068920 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-16 | 2022-07-27 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068930 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-12-03 | 2022-12-05 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 130 | 2022-07-02 | 2022-12-07
C-PW-068940 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-02 | 2022-07-17 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068950 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-18 | 2022-07-31 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068960 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-12-04 | 2022-12-07 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 128 | 2022-07-04 | 2022-12-07
C-PW-068970 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-04 | 2022-07-19 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068980 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-19 | 2022-08-01 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-068990 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-12-04 | 2022-12-07 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-12-07 | 2022-12-13
C-PW-069000 | Active Component System Works | 6 | 2022-12-07 | 2022-12-13 | 01 | 10 | 01 | 47 | 003 | 01 |  | Building | CCTV | Museum | South West | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 116 | 2022-07-18 | 2022-12-03
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 116 | 2022-07-18 | 2022-12-03
C-PW-069010 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-18 | 2022-07-31 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-069020 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-31 | 2022-08-11 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-069030 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-29 | 2022-12-03 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 114 | 2022-07-19 | 2022-12-03
C-PW-069040 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-19 | 2022-08-01 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-069050 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-02 | 2022-08-14 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-069060 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-29 | 2022-12-03 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 79 | 2022-08-11 | 2022-11-13
C-PW-069070 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-08-11 | 2022-08-30 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-069080 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-08-25 | 2022-09-03 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
C-PW-069090 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 7 | 2022-11-05 | 2022-11-13 | 01 | 09 | 01 | 47 | 003 | 01 |  | Building | Firefighting | Museum | South West | L00 Ground Level | Circulation / Common Areas
SUBSTATION 1 |  | 141 | 2022-01-02 | 2022-06-18
MEP WORKS |  | 43 | 2022-01-02 | 2022-02-21
MECHANICAL |  | 11 | 2022-01-02 | 2022-01-15
HVAC SYSTEM WORKS |  | 11 | 2022-01-02 | 2022-01-15
C-PW-069100 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 5 | 2022-01-02 | 2022-01-06 | 01 | 06 | 01 | 47 | 003 | 02 |  | Building | HVAC | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069110 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 4 | 2022-01-06 | 2022-01-11 | 01 | 06 | 01 | 47 | 003 | 02 |  | Building | HVAC | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069120 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 2 | 2022-01-11 | 2022-01-15 | 01 | 06 | 01 | 47 | 003 | 02 |  | Building | HVAC | Museum | South West | L00 Ground Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 38 | 2022-01-02 | 2022-02-14
C-PW-069130 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-01-02 | 2022-01-10 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069140 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-01-05 | 2022-01-15 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069150 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 7 | 2022-01-16 | 2022-01-24 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069160 | Final Fix Electrical (Power Socket / Isolators) | 1 | 2022-01-24 | 2022-01-24 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069170 | Final Fix Electrical (Light Fixtures) | 3 | 2022-02-03 | 2022-02-07 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069180 | Final Fix Electrical (Installation of Lighting Control Panels) | 3 | 2022-02-09 | 2022-02-13 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069190 | Final Fix Electrical (Installation of Lighting Control Devices) | 3 | 2022-02-10 | 2022-02-14 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
ELV |  | 29 | 2022-01-03 | 2022-02-06
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 12 | 2022-01-03 | 2022-01-17
C-PW-069200 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 5 | 2022-01-03 | 2022-01-09 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069210 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 5 | 2022-01-09 | 2022-01-15 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069220 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-01-15 | 2022-01-17 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
INTERCOM SYSTEM |  | 12 | 2022-01-03 | 2022-01-17
C-PW-069230 | 1st Fix Intercom System Works (Conduits & Boxes) | 5 | 2022-01-03 | 2022-01-09 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069240 | 2nd Fix Intercom System Works (Wiring) | 5 | 2022-01-09 | 2022-01-15 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069250 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-01-15 | 2022-01-17 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 12 | 2022-01-03 | 2022-01-17
C-PW-069260 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 5 | 2022-01-03 | 2022-01-09 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069270 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 5 | 2022-01-09 | 2022-01-15 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069280 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-01-15 | 2022-01-17 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 22 | 2022-01-05 | 2022-01-31
C-PW-069290 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 5 | 2022-01-05 | 2022-01-10 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069300 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 5 | 2022-01-11 | 2022-01-16 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069310 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-01-29 | 2022-01-31 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 21 | 2022-01-06 | 2022-01-31
C-PW-069320 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 5 | 2022-01-06 | 2022-01-12 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069330 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 5 | 2022-01-12 | 2022-01-18 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069340 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-01-29 | 2022-01-31 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-01-31 | 2022-02-06
C-PW-069350 | Active Component System Works | 6 | 2022-01-31 | 2022-02-06 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEMS |  | 39 | 2022-01-06 | 2022-02-21
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 12 | 2022-01-11 | 2022-01-24
C-PW-069360 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 5 | 2022-01-11 | 2022-01-16 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069370 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 5 | 2022-01-16 | 2022-01-22 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069380 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-01-22 | 2022-01-24 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 34 | 2022-01-12 | 2022-02-21
C-PW-069390 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 5 | 2022-01-12 | 2022-01-18 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069400 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 5 | 2022-01-18 | 2022-01-24 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069410 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-02-19 | 2022-02-21 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 10 | 2022-01-06 | 2022-01-18
C-PW-069420 | 1st Fix Piping System - (Installation of supports & piping for Fire suppression system) | 5 | 2022-01-06 | 2022-01-12 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069430 | 2nd Fix Piping System - (Clean Agent fire Suppression system) & testing | 4 | 2022-01-12 | 2022-01-17 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069440 | Final Fix Piping System (Cylinders, Sprinkler Heads, Fixtures, Etc.) | 1 | 2022-01-17 | 2022-01-18 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
ADDC RELATED WORKS - SUBSTATION 1 |  | 98 | 2022-02-21 | 2022-06-18
C-PW-069450 | ADDC Civil Inspection and Obtain Approvals (By Main Contractor) | 7 | 2022-02-21 | 2022-03-01 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069460 | Access for MEP 2nd Fix/ Plinths and Trenches | 1 | 2022-03-01 | 2022-03-02 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069470 | MEP Cable Ladders in Trenches | 14 | 2022-03-02 | 2022-03-17 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069480 | ADDC Inspection and Clearance for HV Equipment Installation | 7 | 2022-03-19 | 2022-03-27 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069490 | MEP High Level Containment & Services | 23 | 2022-03-02 | 2022-03-29 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069500 | Installation of HV Panels, 48V DC system | 7 | 2022-03-27 | 2022-04-04 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069510 | Installation of Transformers | 14 | 2022-03-27 | 2022-04-11 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069520 | Installation of the S/S Control System | 26 | 2022-04-04 | 2022-05-08 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069530 | Cabling and Termination of Transformers (HV Side) | 36 | 2022-04-04 | 2022-05-19 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069540 | Cabling and Termination of the LV Side | 36 | 2022-04-12 | 2022-05-28 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069550 | Busbar Installation | 26 | 2022-04-24 | 2022-05-28 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069560 | S/S Cold Testing and Testing of the Control Systems | 21 | 2022-05-25 | 2022-06-18 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
GENERATOR 1, SWITCH ROOM & OIL STORE |  | 78 | 2022-03-19 | 2022-06-21
MECHANICAL |  | 77 | 2022-03-19 | 2022-06-20
HVAC SYSTEM WORKS |  | 73 | 2022-03-23 | 2022-06-20
C-PW-069570 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 18 | 2022-03-23 | 2022-04-13 | 01 | 06 | 01 | 47 | 003 | 02 |  | Building | HVAC | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069580 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-04-05 | 2022-04-14 | 01 | 06 | 01 | 47 | 003 | 02 |  | Building | HVAC | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069590 | Final Fix HVAC (Exhaust Louvre's,Grills, Diffusers, FCU Mouth Connection & Testing) | 6 | 2022-06-13 | 2022-06-20 | 01 | 06 | 01 | 47 | 003 | 02 |  | Building | HVAC | Museum | South West | L00 Ground Level | MEP / Service Rooms
DRAINAGE WORKS |  | 18 | 2022-03-19 | 2022-04-09
C-PW-069600 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-03-19 | 2022-03-30 | 01 | 08 | 01 | 47 | 003 | 02 |  | Building | Plumbing | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069610 | 2nd Fix Piping System (Fittings, Insulation) | 8 | 2022-03-31 | 2022-04-09 | 01 | 08 | 01 | 47 | 003 | 02 |  | Building | Plumbing | Museum | South West | L00 Ground Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 78 | 2022-03-19 | 2022-06-21
C-PW-069620 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 16 | 2022-03-19 | 2022-04-06 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069630 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 22 | 2022-03-27 | 2022-04-21 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069640 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 22 | 2022-04-21 | 2022-05-19 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069650 | Installation of Panels,DB's, equipments, wiring & termination | 9 | 2022-05-10 | 2022-05-19 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069660 | Installation of Generator, wiring & termination | 15 | 2022-04-28 | 2022-05-19 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069670 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-06-12 | 2022-06-16 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069680 | Final Fix Electrical (Light Fixtures) | 3 | 2022-06-13 | 2022-06-16 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069690 | Final Fix Electrical (Installation of Lighting Control Panels) | 3 | 2022-06-15 | 2022-06-19 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069700 | Final Fix Electrical (Installation of Lighting Control Devices) | 3 | 2022-06-18 | 2022-06-21 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
ELV |  | 38 | 2022-03-27 | 2022-05-15
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-03-27 | 2022-04-23
C-PW-069710 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-27 | 2022-04-09 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069720 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-09 | 2022-04-20 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069730 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-04-20 | 2022-04-23 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-03-29 | 2022-04-25
C-PW-069740 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-29 | 2022-04-10 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069750 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-10 | 2022-04-23 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069760 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-04-23 | 2022-04-25 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
INTERCOM SYSTEM |  | 23 | 2022-03-31 | 2022-04-27
C-PW-069770 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069780 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-12 | 2022-04-24 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069790 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-04-24 | 2022-04-27 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
AV SYSTEM |  | 23 | 2022-04-02 | 2022-04-28
C-PW-069800 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-02 | 2022-04-13 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069810 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069820 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-04-26 | 2022-04-28 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-04-04 | 2022-05-04
C-PW-069830 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069840 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-16 | 2022-04-27 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069850 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-04-28 | 2022-05-04 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 23 | 2022-04-05 | 2022-05-05
C-PW-069860 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-05 | 2022-04-18 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069870 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069880 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-04-30 | 2022-05-05 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-04-07 | 2022-05-08
C-PW-069890 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069900 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-19 | 2022-05-05 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069910 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-05-05 | 2022-05-08 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-05-08 | 2022-05-15
C-PW-069920 | Active Component System Works | 6 | 2022-05-08 | 2022-05-15 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 73 | 2022-03-24 | 2022-06-21
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 23 | 2022-04-18 | 2022-05-18
C-PW-069930 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-18 | 2022-04-30 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069940 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-30 | 2022-05-15 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069950 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-05-16 | 2022-05-18 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 23 | 2022-04-19 | 2022-05-19
C-PW-069960 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-19 | 2022-05-05 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069970 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-05 | 2022-05-17 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-069980 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-05-17 | 2022-05-19 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
FIRE FIGHTING SYSTEM WORKS |  | 73 | 2022-03-24 | 2022-06-21
C-PW-069990 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-03-24 | 2022-04-12 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070000 | 2nd Fix Piping System - (Foam water fire Suppression system) & testing | 12 | 2022-04-12 | 2022-04-26 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070010 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-06-15 | 2022-06-21 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
LOADING AREA FAN ROOM |  | 71 | 2022-03-31 | 2022-06-26
MECHANICAL |  | 65 | 2022-03-31 | 2022-06-18
HVAC SYSTEM WORKS |  | 57 | 2022-04-10 | 2022-06-18
C-PW-070020 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 15 | 2022-04-10 | 2022-04-27 | 01 | 06 | 01 | 47 | 003 | 02 |  | Building | HVAC | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070030 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 13 | 2022-04-27 | 2022-05-15 | 01 | 06 | 01 | 47 | 003 | 02 |  | Building | HVAC | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070040 | Final Fix HVAC (Exhaust Louvre's,Grills, Diffusers, FCU Mouth Connection & Testing) | 6 | 2022-06-12 | 2022-06-18 | 01 | 06 | 01 | 47 | 003 | 02 |  | Building | HVAC | Museum | South West | L00 Ground Level | MEP / Service Rooms
DRAINAGE WORKS |  | 62 | 2022-03-31 | 2022-06-15
C-PW-070050 | 1st Fix Piping System (Supports, Piping) | 7 | 2022-03-31 | 2022-04-09 | 01 | 08 | 01 | 47 | 003 | 02 |  | Building | Plumbing | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070060 | 2nd Fix Piping System | 6 | 2022-04-09 | 2022-04-14 | 01 | 08 | 01 | 47 | 003 | 02 |  | Building | Plumbing | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070070 | Final Fix Fittings | 3 | 2022-06-12 | 2022-06-15 | 01 | 08 | 01 | 47 | 003 | 02 |  | Building | Plumbing | Museum | South West | L00 Ground Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 58 | 2022-04-05 | 2022-06-15
C-PW-070080 | 1st Fix Piping System (Supports, Piping) | 7 | 2022-04-05 | 2022-04-13 | 01 | 08 | 01 | 47 | 003 | 02 |  | Building | Plumbing | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070090 | 2nd Fix Piping System | 7 | 2022-04-14 | 2022-04-23 | 01 | 08 | 01 | 47 | 003 | 02 |  | Building | Plumbing | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070100 | Final Fix Fittings | 3 | 2022-06-12 | 2022-06-15 | 01 | 08 | 01 | 47 | 003 | 02 |  | Building | Plumbing | Museum | South West | L00 Ground Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 66 | 2022-04-06 | 2022-06-26
C-PW-070110 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 6 | 2022-04-06 | 2022-04-13 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070120 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 7 | 2022-04-27 | 2022-05-09 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070130 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 7 | 2022-05-09 | 2022-05-17 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070140 | LV Switchgears (DB's) | 5 | 2022-05-17 | 2022-05-23 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070150 | Cable/Wire Termination & Dressing | 7 | 2022-05-23 | 2022-05-31 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070160 | Final Fix Electrical (Power Socket / Isolators) | 3 | 2022-06-12 | 2022-06-15 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070170 | Final Fix Electrical (Light Fixtures) | 7 | 2022-06-13 | 2022-06-21 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070180 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-06-15 | 2022-06-23 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070190 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-06-18 | 2022-06-26 | 01 | 07 | 01 | 47 | 003 | 02 |  | Building | Electrical | Museum | South West | L00 Ground Level | MEP / Service Rooms
ELV |  | 63 | 2022-04-09 | 2022-06-25
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 54 | 2022-04-09 | 2022-06-14
C-PW-070200 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-20 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070210 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-20 | 2022-05-05 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070220 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 53 | 2022-04-10 | 2022-06-14
C-PW-070230 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-10 | 2022-04-23 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070240 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-23 | 2022-05-08 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070250 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
INTERCOM SYSTEM |  | 51 | 2022-04-12 | 2022-06-14
C-PW-070260 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-12 | 2022-04-24 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070270 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-24 | 2022-05-10 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070280 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
AV SYSTEM |  | 51 | 2022-04-14 | 2022-06-16
C-PW-070290 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070300 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070310 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-06-13 | 2022-06-16 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 50 | 2022-04-16 | 2022-06-16
C-PW-070320 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-16 | 2022-04-27 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070330 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070340 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-06-13 | 2022-06-16 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 50 | 2022-04-18 | 2022-06-18
C-PW-070350 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070360 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070370 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-06-15 | 2022-06-18 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 48 | 2022-04-19 | 2022-06-18
C-PW-070380 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-19 | 2022-05-05 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070390 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070400 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-06-15 | 2022-06-18 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-06-18 | 2022-06-25
C-PW-070410 | Active Component System Works | 6 | 2022-06-18 | 2022-06-25 | 01 | 10 | 01 | 47 | 003 | 02 |  | Building | CCTV | Museum | South West | L00 Ground Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 54 | 2022-04-10 | 2022-06-15
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 36 | 2022-04-30 | 2022-06-14
C-PW-070420 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070430 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-16 | 2022-05-28 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070440 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 34 | 2022-05-05 | 2022-06-14
C-PW-070450 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070460 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-17 | 2022-05-29 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070470 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
FIRE FIGHTING SYSTEM WORKS |  | 54 | 2022-04-10 | 2022-06-15
C-PW-070480 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 6 | 2022-04-10 | 2022-04-17 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070490 | 2nd Fix Piping System - (Clean Agent/Foam water sprinkler fire Suppression system) & testing | 5 | 2022-04-17 | 2022-04-23 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
C-PW-070500 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 3 | 2022-06-12 | 2022-06-15 | 01 | 09 | 01 | 47 | 003 | 02 |  | Building | Firefighting | Museum | South West | L00 Ground Level | MEP / Service Rooms
SOUTH EAST |  | 255 | 2022-01-02 | 2022-11-05
LIBRARY, SHK.ZAYED LIFE & TIMES GALLERY AND LOBBY - SOUTH |  | 206 | 2022-01-02 | 2022-09-06
MECHANICAL |  | 199 | 2022-01-02 | 2022-08-30
HVAC SYSTEM WORKS |  | 130 | 2022-03-23 | 2022-08-30
C-PW-070510 | 1st Fix HVAC (Dampers - VCD,NRD,MDs) | 14 | 2022-03-23 | 2022-04-07 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070520 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 18 | 2022-03-27 | 2022-04-17 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070530 | 2nd Fix HVAC (Droppers, Dampers, Duct Leakage) | 18 | 2022-04-17 | 2022-05-11 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070540 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-08-22 | 2022-08-30 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 13 | 2022-01-02 | 2022-01-16
C-PW-070550 | 1st Fix Piping System (Supports, Piping) | 7 | 2022-01-02 | 2022-01-10 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070560 | 2nd Fix Piping System (Fittings, Insulation) | 6 | 2022-01-10 | 2022-01-16 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 13 | 2022-03-19 | 2022-04-03
C-PW-070570 | 1st Fix Piping System (Supports, Piping) | 7 | 2022-03-19 | 2022-03-27 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070580 | 2nd Fix Piping System (Fittings, Insulation) | 6 | 2022-03-28 | 2022-04-03 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 141 | 2022-03-10 | 2022-08-30
C-PW-070590 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-03-10 | 2022-03-19 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070600 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-03-19 | 2022-03-29 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070610 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-03-29 | 2022-04-14 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070620 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-08-13 | 2022-08-21 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070630 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-22 | 2022-08-30 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070640 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-22 | 2022-08-30 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
ELV |  | 140 | 2022-03-19 | 2022-09-06
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 129 | 2022-03-19 | 2022-08-24
C-PW-070650 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-19 | 2022-03-31 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070660 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070670 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-22 | 2022-08-24 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 127 | 2022-03-21 | 2022-08-24
C-PW-070680 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-21 | 2022-04-02 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070690 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-02 | 2022-04-14 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070700 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-22 | 2022-08-24 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 121 | 2022-03-31 | 2022-08-27
C-PW-070710 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070720 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-12 | 2022-04-24 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070730 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-24 | 2022-08-27 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 121 | 2022-04-02 | 2022-08-29
C-PW-070740 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-02 | 2022-04-14 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070750 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070760 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-27 | 2022-08-29 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 119 | 2022-04-04 | 2022-08-29
C-PW-070770 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070780 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-16 | 2022-04-28 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070790 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-27 | 2022-08-29 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 118 | 2022-04-06 | 2022-08-31
C-PW-070800 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-06 | 2022-04-19 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070810 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070820 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-28 | 2022-08-31 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 117 | 2022-04-09 | 2022-08-31
C-PW-070830 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-20 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070840 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-20 | 2022-05-07 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070850 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-28 | 2022-08-31 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-08-31 | 2022-09-06
C-PW-070860 | Active Component System Works | 6 | 2022-08-31 | 2022-09-06 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 127 | 2022-03-27 | 2022-08-30
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 102 | 2022-04-19 | 2022-08-24
C-PW-070870 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-19 | 2022-05-04 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070880 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-04 | 2022-05-16 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070890 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-22 | 2022-08-24 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 92 | 2022-05-04 | 2022-08-24
C-PW-070900 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-04 | 2022-05-16 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070910 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-17 | 2022-05-29 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070920 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-22 | 2022-08-24 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 127 | 2022-03-27 | 2022-08-30
C-PW-070930 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-03-27 | 2022-04-14 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070940 | 2nd Fix Piping System - (Fittings) | 12 | 2022-04-14 | 2022-04-28 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-070950 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-08-22 | 2022-08-30 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
PANTRY AREA, TOILETS & JANITOR ROOMS - SOUTH |  | 89 | 2022-03-03 | 2022-06-18
MECHANICAL |  | 67 | 2022-03-03 | 2022-05-24
DRAINAGE WORKS |  | 28 | 2022-03-03 | 2022-04-05
C-PW-070960 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-03 | 2022-03-19 | 01 | 08 | 01 | 45 | 003 | 03 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Wet Areas
C-PW-070970 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-03-19 | 2022-03-30 | 01 | 08 | 01 | 45 | 003 | 03 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Wet Areas
C-PW-070980 | Final Fix (Installation of Sanitaryware & Accessories) | 5 | 2022-03-30 | 2022-04-05 | 01 | 08 | 01 | 45 | 003 | 03 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Wet Areas
HOT & COLD WATER SYSTEM |  | 41 | 2022-03-28 | 2022-05-18
C-PW-070990 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-28 | 2022-04-13 | 01 | 08 | 01 | 45 | 003 | 03 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071000 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-04-16 | 2022-04-26 | 01 | 08 | 01 | 45 | 003 | 03 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071010 | Final Fix - Water Meter Installation | 3 | 2022-05-15 | 2022-05-18 | 01 | 08 | 01 | 45 | 003 | 03 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Wet Areas
HVAC SYSTEM WORKS |  | 42 | 2022-04-02 | 2022-05-24
C-PW-071020 | 1st Fix HVAC (Supports, Ducts, Insulation, VAV/CAV Box & Dampers - VCD,NRD,MDs) | 14 | 2022-04-02 | 2022-04-17 | 01 | 06 | 01 | 45 | 003 | 03 |  | Building | HVAC | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071030 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 14 | 2022-04-17 | 2022-05-07 | 01 | 06 | 01 | 45 | 003 | 03 |  | Building | HVAC | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071040 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-07 | 2022-05-17 | 01 | 06 | 01 | 45 | 003 | 03 |  | Building | HVAC | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071050 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-05-17 | 2022-05-24 | 01 | 06 | 01 | 45 | 003 | 03 |  | Building | HVAC | Museum | South East | L00 Ground Level | Wet Areas
ELECTRICAL WORKS |  | 49 | 2022-03-19 | 2022-05-18
C-PW-071060 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-03-19 | 2022-03-31 | 01 | 07 | 01 | 45 | 003 | 03 |  | Building | Electrical | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071070 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-04-05 | 2022-04-20 | 01 | 07 | 01 | 45 | 003 | 03 |  | Building | Electrical | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071080 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 12 | 2022-04-20 | 2022-05-08 | 01 | 07 | 01 | 45 | 003 | 03 |  | Building | Electrical | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071090 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-05-08 | 2022-05-15 | 01 | 07 | 01 | 45 | 003 | 03 |  | Building | Electrical | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071100 | Final Fix Electrical (Light Fixtures) | 7 | 2022-05-10 | 2022-05-18 | 01 | 07 | 01 | 45 | 003 | 03 |  | Building | Electrical | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071110 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-05-10 | 2022-05-18 | 01 | 07 | 01 | 45 | 003 | 03 |  | Building | Electrical | Museum | South East | L00 Ground Level | Wet Areas
ELV |  | 41 | 2022-03-31 | 2022-05-21
AV SYSTEM |  | 34 | 2022-03-31 | 2022-05-12
C-PW-071120 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 45 | 003 | 03 |  | Building | CCTV | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071130 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-20 | 2022-05-07 | 01 | 10 | 01 | 45 | 003 | 03 |  | Building | CCTV | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071140 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-05-10 | 2022-05-12 | 01 | 10 | 01 | 45 | 003 | 03 |  | Building | CCTV | Museum | South East | L00 Ground Level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 39 | 2022-04-02 | 2022-05-21
C-PW-071150 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-02 | 2022-04-14 | 01 | 10 | 01 | 45 | 003 | 03 |  | Building | CCTV | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071160 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 45 | 003 | 03 |  | Building | CCTV | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071170 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-05-18 | 2022-05-21 | 01 | 10 | 01 | 45 | 003 | 03 |  | Building | CCTV | Museum | South East | L00 Ground Level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 62 | 2022-04-04 | 2022-06-18
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 58 | 2022-04-04 | 2022-06-14
C-PW-071180 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-16 | 01 | 09 | 01 | 45 | 003 | 03 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071190 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-16 | 2022-04-28 | 01 | 09 | 01 | 45 | 003 | 03 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071200 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 09 | 01 | 45 | 003 | 03 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 57 | 2022-04-06 | 2022-06-14
C-PW-071210 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-06 | 2022-04-18 | 01 | 09 | 01 | 45 | 003 | 03 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071220 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-18 | 2022-04-30 | 01 | 09 | 01 | 45 | 003 | 03 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071230 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 09 | 01 | 45 | 003 | 03 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Wet Areas
FIRE FIGHTING WORKS |  | 53 | 2022-04-14 | 2022-06-18
C-PW-071240 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-04-14 | 2022-04-30 | 01 | 09 | 01 | 45 | 003 | 03 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071250 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-30 | 2022-05-12 | 01 | 09 | 01 | 45 | 003 | 03 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Wet Areas
C-PW-071260 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-06-12 | 2022-06-18 | 01 | 09 | 01 | 45 | 003 | 03 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Wet Areas
COLLECTION RESEARCH, WORKSHOPS & SECURITY/FIRE STAFF ROOMS - SOUTH |  | 222 | 2022-01-02 | 2022-09-25
MECHANICAL |  | 128 | 2022-04-14 | 2022-09-19
DRAINAGE WORKS |  | 24 | 2022-04-14 | 2022-05-16
C-PW-071270 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-04-14 | 2022-04-30 | 01 | 08 | 01 | 45 | 003 | 05 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071280 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-30 | 2022-05-16 | 01 | 08 | 01 | 45 | 003 | 05 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 24 | 2022-04-20 | 2022-05-21
C-PW-071290 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-04-20 | 2022-05-09 | 01 | 08 | 01 | 45 | 003 | 05 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071300 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-09 | 2022-05-21 | 01 | 08 | 01 | 45 | 003 | 05 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
HVAC SYSTEM WORKS |  | 120 | 2022-04-24 | 2022-09-19
C-PW-071310 | 1st Fix HVAC (Supports, Ducts, Insulation, VAV/CAV Box & Dampers - VCD,NRD,MDs) | 14 | 2022-04-24 | 2022-05-12 | 01 | 06 | 01 | 45 | 003 | 05 |  | Building | HVAC | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071320 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 14 | 2022-05-07 | 2022-05-22 | 01 | 06 | 01 | 45 | 003 | 05 |  | Building | HVAC | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071330 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-22 | 2022-06-04 | 01 | 06 | 01 | 45 | 003 | 05 |  | Building | HVAC | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071340 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-10 | 2022-09-19 | 01 | 06 | 01 | 45 | 003 | 05 |  | Building | HVAC | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 130 | 2022-04-14 | 2022-09-21
C-PW-071350 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-04-14 | 2022-04-26 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071360 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-04-27 | 2022-05-16 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071370 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-17 | 2022-06-01 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071380 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-07-07 | 2022-07-20 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071390 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-10 | 2022-09-18 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071400 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-11 | 2022-09-19 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071410 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-13 | 2022-09-21 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
ELV |  | 132 | 2022-04-16 | 2022-09-25
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 121 | 2022-04-16 | 2022-09-12
C-PW-071420 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-16 | 2022-04-28 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071430 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071440 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-12 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 119 | 2022-04-18 | 2022-09-12
C-PW-071450 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071460 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-30 | 2022-05-16 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071470 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-12 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 120 | 2022-04-20 | 2022-09-14
C-PW-071480 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-20 | 2022-05-05 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071490 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071500 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 120 | 2022-04-21 | 2022-09-17
C-PW-071510 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-21 | 2022-05-07 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071520 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-08 | 2022-05-19 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071530 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-14 | 2022-09-17 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 118 | 2022-04-24 | 2022-09-17
C-PW-071540 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-24 | 2022-05-09 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071550 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-09 | 2022-05-21 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071560 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-14 | 2022-09-17 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 118 | 2022-04-25 | 2022-09-19
C-PW-071570 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-25 | 2022-05-11 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071580 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071590 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-15 | 2022-09-19 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 117 | 2022-04-27 | 2022-09-19
C-PW-071600 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071610 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-12 | 2022-05-25 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071620 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-15 | 2022-09-19 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-19 | 2022-09-25
C-PW-071630 | Active Component System Works | 6 | 2022-09-19 | 2022-09-25 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 211 | 2022-01-02 | 2022-09-12
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 211 | 2022-01-02 | 2022-09-12
C-PW-071640 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-02 | 2022-01-13 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071650 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-01-13 | 2022-01-25 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071660 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-12 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 145 | 2022-03-19 | 2022-09-12
C-PW-071670 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-19 | 2022-03-31 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071680 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-31 | 2022-04-12 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071690 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-12 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 64 | 2022-04-30 | 2022-07-20
C-PW-071700 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-04-30 | 2022-05-19 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071710 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-19 | 2022-05-29 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071720 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-07-07 | 2022-07-20 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
FUTURE EXPANSION ROOMS - SOUTH |  | 231 | 2022-01-02 | 2022-10-05
MECHANICAL |  | 119 | 2022-04-30 | 2022-09-24
HVAC SYSTEM WORKS |  | 111 | 2022-05-12 | 2022-09-24
C-PW-071730 | 1st Fix HVAC (Supports, Ducts, Insulation, VAV/CAV Box & Dampers - VCD,NRD,MDs) | 9 | 2022-05-12 | 2022-05-23 | 01 | 06 | 01 | 45 | 003 | 05 |  | Building | HVAC | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071740 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 9 | 2022-05-17 | 2022-05-26 | 01 | 06 | 01 | 45 | 003 | 05 |  | Building | HVAC | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071750 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-05-26 | 2022-06-05 | 01 | 06 | 01 | 45 | 003 | 05 |  | Building | HVAC | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071760 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 5 | 2022-09-19 | 2022-09-24 | 01 | 06 | 01 | 45 | 003 | 05 |  | Building | HVAC | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 13 | 2022-04-30 | 2022-05-18
C-PW-071770 | 1st Fix Piping System (Supports, Piping) | 6 | 2022-04-30 | 2022-05-10 | 01 | 08 | 01 | 45 | 003 | 05 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071780 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-05-10 | 2022-05-18 | 01 | 08 | 01 | 45 | 003 | 05 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 13 | 2022-05-09 | 2022-05-24
C-PW-071790 | 1st Fix Piping System (Supports, Piping) | 6 | 2022-05-09 | 2022-05-16 | 01 | 08 | 01 | 45 | 003 | 05 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071800 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-05-16 | 2022-05-24 | 01 | 08 | 01 | 45 | 003 | 05 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 130 | 2022-04-26 | 2022-10-03
C-PW-071810 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-04-26 | 2022-05-08 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071820 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-05-17 | 2022-05-26 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071830 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-05-26 | 2022-06-08 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071840 | LV Switchgears (DB's) | 5 | 2022-06-08 | 2022-06-13 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071850 | Cable/Wire Termination & Dressing | 7 | 2022-06-14 | 2022-06-22 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071860 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-09-19 | 2022-09-24 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071870 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-20 | 2022-09-28 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071880 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-22 | 2022-10-01 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071890 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-25 | 2022-10-03 | 01 | 07 | 01 | 45 | 003 | 05 |  | Building | Electrical | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
ELV |  | 130 | 2022-04-28 | 2022-10-05
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 119 | 2022-04-28 | 2022-09-22
C-PW-071900 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071910 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071920 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 3 | 2022-09-19 | 2022-09-22 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 118 | 2022-04-30 | 2022-09-22
C-PW-071930 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-16 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071940 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-16 | 2022-05-28 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071950 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-20 | 2022-09-22 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 118 | 2022-05-05 | 2022-09-25
C-PW-071960 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071970 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-17 | 2022-05-30 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-071980 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-22 | 2022-09-25 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 118 | 2022-05-08 | 2022-09-27
C-PW-071990 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-08 | 2022-05-19 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072000 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-19 | 2022-05-31 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072010 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 117 | 2022-05-09 | 2022-09-27
C-PW-072020 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-09 | 2022-05-21 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072030 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072040 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 117 | 2022-05-11 | 2022-09-28
C-PW-072050 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072060 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-23 | 2022-06-04 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072070 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-26 | 2022-09-28 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 115 | 2022-05-12 | 2022-09-28
C-PW-072080 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-12 | 2022-05-25 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072090 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072100 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-26 | 2022-09-28 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-29 | 2022-10-05
C-PW-072110 | Active Component System Works | 6 | 2022-09-29 | 2022-10-05 | 01 | 10 | 01 | 45 | 003 | 05 |  | Building | CCTV | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 219 | 2022-01-02 | 2022-09-22
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 219 | 2022-01-02 | 2022-09-22
C-PW-072120 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-02 | 2022-01-13 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072130 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-01-13 | 2022-01-25 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072140 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-20 | 2022-09-22 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 154 | 2022-03-19 | 2022-09-22
C-PW-072150 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-19 | 2022-03-31 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072160 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-31 | 2022-04-12 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072170 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-20 | 2022-09-22 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 53 | 2022-05-19 | 2022-07-24
C-PW-072180 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 9 | 2022-05-19 | 2022-05-30 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072190 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-30 | 2022-06-08 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
C-PW-072200 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-07-17 | 2022-07-24 | 01 | 09 | 01 | 45 | 003 | 05 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Storage / Offices / Admin Areas
MAJLIS & VIP ARRIVAL LOBBY AREAS - SOUTH |  | 234 | 2022-01-02 | 2022-10-10
MECHANICAL |  | 132 | 2022-04-30 | 2022-10-10
HVAC SYSTEM WORKS |  | 121 | 2022-05-12 | 2022-10-05
C-PW-072210 | 1st Fix HVAC (Supports, Ducts, Insulation, VAV/CAV Box & Dampers - VCD,NRD,MDs) | 18 | 2022-05-12 | 2022-06-04 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072220 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 18 | 2022-05-22 | 2022-06-13 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072230 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-06-08 | 2022-06-20 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072240 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-09-27 | 2022-10-05 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-04-30 | 2022-06-06
C-PW-072250 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-30 | 2022-05-25 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072260 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-25 | 2022-06-06 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 127 | 2022-05-09 | 2022-10-10
C-PW-072270 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-09 | 2022-05-30 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072280 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-31 | 2022-06-12 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072290 | Electric Water Heater Installation | 3 | 2022-10-05 | 2022-10-10 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 134 | 2022-04-26 | 2022-10-08
C-PW-072300 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-26 | 2022-05-16 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072310 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-05-17 | 2022-06-07 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072320 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-07 | 2022-06-22 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072330 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-09-27 | 2022-10-05 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072340 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-29 | 2022-10-08 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072350 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-29 | 2022-10-08 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
ELV |  | 126 | 2022-05-05 | 2022-10-03
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 114 | 2022-05-05 | 2022-09-20
C-PW-072360 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072370 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-17 | 2022-05-30 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072380 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-18 | 2022-09-20 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 113 | 2022-05-08 | 2022-09-20
C-PW-072390 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-05-08 | 2022-05-19 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072400 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-19 | 2022-05-31 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072410 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-18 | 2022-09-20 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 114 | 2022-05-09 | 2022-09-24
C-PW-072420 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-05-09 | 2022-05-21 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072430 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-22 | 2022-06-02 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072440 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-20 | 2022-09-24 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 114 | 2022-05-11 | 2022-09-25
C-PW-072450 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-11 | 2022-05-23 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072460 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-23 | 2022-06-04 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072470 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-22 | 2022-09-25 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 112 | 2022-05-12 | 2022-09-25
C-PW-072480 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-12 | 2022-05-25 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072490 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-25 | 2022-06-06 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072500 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-22 | 2022-09-25 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 112 | 2022-05-15 | 2022-09-27
C-PW-072510 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072520 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-26 | 2022-06-08 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072530 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 110 | 2022-05-17 | 2022-09-27
C-PW-072540 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-17 | 2022-05-29 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072550 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-29 | 2022-06-09 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072560 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-27 | 2022-10-03
C-PW-072570 | Active Component System Works | 6 | 2022-09-27 | 2022-10-03 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 218 | 2022-01-02 | 2022-09-20
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 218 | 2022-01-02 | 2022-09-20
C-PW-072580 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-02 | 2022-01-13 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072590 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-01-13 | 2022-01-25 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072600 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-18 | 2022-09-20 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 152 | 2022-03-19 | 2022-09-20
C-PW-072610 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-19 | 2022-03-31 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072620 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-31 | 2022-04-12 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072630 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-18 | 2022-09-20 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 99 | 2022-05-19 | 2022-09-17
C-PW-072640 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-05-19 | 2022-06-07 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072650 | 2nd Fix Piping System - (Fittings) | 8 | 2022-06-07 | 2022-06-16 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072660 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 7 | 2022-09-08 | 2022-09-17 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
CIRCULATIONS & CORRIDORS - SOUTH |  | 255 | 2022-01-02 | 2022-11-05
MECHANICAL |  | 130 | 2022-05-25 | 2022-10-30
HVAC SYSTEM WORKS |  | 122 | 2022-06-04 | 2022-10-30
C-PW-072670 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 18 | 2022-06-04 | 2022-06-25 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072680 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 18 | 2022-06-07 | 2022-06-28 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072690 | 2nd Fix HVAC (FCUs, Valves Package, Duct Heaters & Humidifiers) | 10 | 2022-06-25 | 2022-07-06 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072700 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-10-22 | 2022-10-30 | 01 | 06 | 01 | 45 | 003 | 01 |  | Building | HVAC | Museum | South East | L00 Ground Level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-05-25 | 2022-06-27
C-PW-072710 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-25 | 2022-06-15 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072720 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-15 | 2022-06-27 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-05-31 | 2022-07-03
C-PW-072730 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-31 | 2022-06-21 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072740 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-21 | 2022-07-03 | 01 | 08 | 01 | 45 | 003 | 01 |  | Building | Plumbing | Museum | South East | L00 Ground Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 143 | 2022-05-16 | 2022-11-05
C-PW-072750 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-05-16 | 2022-05-31 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072760 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-06-07 | 2022-06-28 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072770 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-28 | 2022-07-18 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072780 | LV Switchgears (DB's) | 5 | 2022-07-18 | 2022-07-24 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072790 | Cable/Wire Termination & Dressing | 7 | 2022-07-24 | 2022-08-02 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072800 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-10-22 | 2022-10-30 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072810 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-24 | 2022-11-01 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072820 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-10-25 | 2022-11-02 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072830 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-27 | 2022-11-05 | 01 | 07 | 01 | 45 | 003 | 01 |  | Building | Electrical | Museum | South East | L00 Ground Level | Circulation / Common Areas
ELV |  | 220 | 2022-02-05 | 2022-10-27
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 209 | 2022-02-05 | 2022-10-15
C-PW-072840 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-05 | 2022-02-16 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072850 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072860 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-12 | 2022-10-15 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 172 | 2022-03-19 | 2022-10-15
C-PW-072870 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-19 | 2022-03-31 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072880 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072890 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-12 | 2022-10-15 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 173 | 2022-03-21 | 2022-10-18
C-PW-072900 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-03-21 | 2022-04-02 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072910 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-02 | 2022-04-14 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072920 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-15 | 2022-10-18 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
AV SYSTEM |  | 173 | 2022-03-23 | 2022-10-19
C-PW-072930 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-03-23 | 2022-04-04 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072940 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072950 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-19 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 171 | 2022-03-24 | 2022-10-19
C-PW-072960 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-24 | 2022-04-05 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072970 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-06 | 2022-04-18 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-072980 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-17 | 2022-10-19 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 171 | 2022-03-27 | 2022-10-22
C-PW-072990 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-27 | 2022-04-07 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-073000 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-073010 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-19 | 2022-10-22 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 170 | 2022-03-28 | 2022-10-22
C-PW-073020 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-28 | 2022-04-10 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-073030 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-10 | 2022-04-21 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-073040 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-19 | 2022-10-22 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-22 | 2022-10-27
C-PW-073050 | Active Component System Works | 6 | 2022-10-22 | 2022-10-27 | 01 | 10 | 01 | 45 | 003 | 01 |  | Building | CCTV | Museum | South East | L00 Ground Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 238 | 2022-01-02 | 2022-10-15
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 238 | 2022-01-02 | 2022-10-15
C-PW-073060 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-01-02 | 2022-01-13 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-073070 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-01-13 | 2022-01-25 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-073080 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-12 | 2022-10-15 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 172 | 2022-03-19 | 2022-10-15
C-PW-073090 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-19 | 2022-03-31 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-073100 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-31 | 2022-04-12 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-073110 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-12 | 2022-10-15 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 86 | 2022-06-09 | 2022-09-22
C-PW-073120 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-09 | 2022-06-27 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-073130 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-06-28 | 2022-07-06 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
C-PW-073140 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 8 | 2022-09-13 | 2022-09-22 | 01 | 09 | 01 | 45 | 003 | 01 |  | Building | Firefighting | Museum | South East | L00 Ground Level | Circulation / Common Areas
SUBSTATION 2 |  | 133 | 2022-01-02 | 2022-06-09
MEP WORKS |  | 43 | 2022-01-02 | 2022-02-21
MECHANICAL WORKS |  | 11 | 2022-01-02 | 2022-01-15
HVAC SYSTEM WORKS |  | 11 | 2022-01-02 | 2022-01-15
C-PW-073150 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 5 | 2022-01-02 | 2022-01-06 | 01 | 06 | 01 | 45 | 003 | 02 |  | Building | HVAC | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073160 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 4 | 2022-01-06 | 2022-01-11 | 01 | 06 | 01 | 45 | 003 | 02 |  | Building | HVAC | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073170 | Final Fix HVAC (Louvers, Grills, Diffusers) | 2 | 2022-01-11 | 2022-01-15 | 01 | 06 | 01 | 45 | 003 | 02 |  | Building | HVAC | Museum | South East | L00 Ground Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 38 | 2022-01-02 | 2022-02-14
C-PW-073180 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 5 | 2022-01-02 | 2022-01-06 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073190 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 6 | 2022-01-05 | 2022-01-11 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073200 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 6 | 2022-01-11 | 2022-01-18 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073210 | Final Fix Electrical (Power Socket / Isolators) | 1 | 2022-01-18 | 2022-01-19 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073220 | Final Fix Electrical (Light Fixtures) | 3 | 2022-02-03 | 2022-02-07 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073230 | Final Fix Electrical (Installation of Lighting Control Panels) | 3 | 2022-02-09 | 2022-02-13 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073240 | Final Fix Electrical (Installation of Lighting Control Devices) | 3 | 2022-02-10 | 2022-02-14 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
ELV |  | 29 | 2022-01-03 | 2022-02-06
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 12 | 2022-01-03 | 2022-01-17
C-PW-073250 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 5 | 2022-01-03 | 2022-01-09 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073260 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 5 | 2022-01-09 | 2022-01-15 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073270 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-01-15 | 2022-01-17 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
INTERCOM SYSTEM |  | 12 | 2022-01-03 | 2022-01-17
C-PW-073280 | 1st Fix Intercom System Works (Conduits & Boxes) | 5 | 2022-01-03 | 2022-01-09 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073290 | 2nd Fix Intercom System Works (Wiring) | 5 | 2022-01-09 | 2022-01-15 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073300 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-01-15 | 2022-01-17 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 12 | 2022-01-03 | 2022-01-17
C-PW-073310 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 5 | 2022-01-03 | 2022-01-09 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073320 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 5 | 2022-01-09 | 2022-01-15 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073330 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-01-15 | 2022-01-17 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 22 | 2022-01-05 | 2022-01-31
C-PW-073340 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 5 | 2022-01-05 | 2022-01-10 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073350 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 5 | 2022-01-11 | 2022-01-16 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073360 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-01-29 | 2022-01-31 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 21 | 2022-01-06 | 2022-01-31
C-PW-073370 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 5 | 2022-01-06 | 2022-01-12 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073380 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 5 | 2022-01-12 | 2022-01-18 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073390 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-01-29 | 2022-01-31 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-01-31 | 2022-02-06
C-PW-073400 | Active Component System Works | 6 | 2022-01-31 | 2022-02-06 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 43 | 2022-01-02 | 2022-02-21
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 14 | 2022-01-02 | 2022-01-17
C-PW-073410 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 5 | 2022-01-02 | 2022-01-06 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073420 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 5 | 2022-01-06 | 2022-01-12 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073430 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-01-15 | 2022-01-17 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 42 | 2022-01-03 | 2022-02-21
C-PW-073440 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 5 | 2022-01-03 | 2022-01-09 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073450 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 5 | 2022-01-09 | 2022-01-15 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073460 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-02-19 | 2022-02-21 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 10 | 2022-01-06 | 2022-01-18
C-PW-073470 | 1st Fix Piping System - (Installation of supports & piping for Fire suppression system) | 5 | 2022-01-06 | 2022-01-12 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073480 | 2nd Fix Piping System - (Clean Agent fire Suppression system) & testing | 4 | 2022-01-12 | 2022-01-17 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073490 | Final Fix Piping System (Cylinders, Sprinkler Heads, Fixtures, Etc.) | 1 | 2022-01-17 | 2022-01-18 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
ADDC RELATED WORKS - SUBSTATION 2 |  | 90 | 2022-02-21 | 2022-06-09
C-PW-073500 | Readiness for Transformer Installattion inclusive of Authority Approval & Related MEP Containment | 15 | 2022-02-21 | 2022-03-10 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-OW-073510 | Installation of HV Panels, 48V DC System | 7 | 2022-03-10 | 2022-03-19 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073520 | Installation of Transformers | 14 | 2022-03-10 | 2022-03-26 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073530 | Installation of Busbar | 26 | 2022-03-07 | 2022-04-06 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073540 | Installation of the S/S Control System | 26 | 2022-03-27 | 2022-04-26 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073560 | Cabling and Termination of the LV Side | 36 | 2022-04-04 | 2022-05-18 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073550 | Cabling and Termination of Transformers (HV Side) | 36 | 2022-04-04 | 2022-05-18 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073570 | S/S Cold Testing and Testing of the Control Systems | 21 | 2022-05-16 | 2022-06-09 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
GENERATOR 2, SWITCH ROOM & OIL STORE |  | 173 | 2022-03-07 | 2022-10-02
MECHANICAL |  | 91 | 2022-06-05 | 2022-09-24
HVAC SYSTEM WORKS |  | 83 | 2022-06-14 | 2022-09-24
C-PW-073580 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 18 | 2022-06-14 | 2022-07-05 | 01 | 06 | 01 | 45 | 003 | 02 |  | Building | HVAC | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073590 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-07-06 | 2022-07-18 | 01 | 06 | 01 | 45 | 003 | 02 |  | Building | HVAC | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073600 | Final Fix HVAC (Louvers, Grills, Diffusers) | 6 | 2022-09-18 | 2022-09-24 | 01 | 06 | 01 | 45 | 003 | 02 |  | Building | HVAC | Museum | South East | L00 Ground Level | MEP / Service Rooms
DRAINAGE WORKS |  | 18 | 2022-06-05 | 2022-06-26
C-PW-073610 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-06-05 | 2022-06-16 | 01 | 08 | 01 | 45 | 003 | 02 |  | Building | Plumbing | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073620 | 2nd Fix Piping System (Fittings, Insulation) | 8 | 2022-06-18 | 2022-06-26 | 01 | 08 | 01 | 45 | 003 | 02 |  | Building | Plumbing | Museum | South East | L00 Ground Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 18 | 2022-06-11 | 2022-07-02
C-PW-073630 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-06-11 | 2022-06-22 | 01 | 08 | 01 | 45 | 003 | 02 |  | Building | Plumbing | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073640 | 2nd Fix Piping System (Fittings, Insulation) | 8 | 2022-06-22 | 2022-07-02 | 01 | 08 | 01 | 45 | 003 | 02 |  | Building | Plumbing | Museum | South East | L00 Ground Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 98 | 2022-06-05 | 2022-10-02
C-PW-073650 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 16 | 2022-06-05 | 2022-06-23 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073660 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 22 | 2022-06-18 | 2022-07-17 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073670 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 22 | 2022-07-17 | 2022-08-11 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073680 | Installation of Panels, DB's, equipment, wiring & termination | 9 | 2022-08-02 | 2022-08-11 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073690 | Installation of Generator, wiring & termination | 15 | 2022-08-13 | 2022-08-30 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073700 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-09-15 | 2022-09-21 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073710 | Final Fix Electrical (Light Fixtures) | 3 | 2022-09-21 | 2022-09-25 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073720 | Final Fix Electrical (Installation of Lighting Control Panels) | 3 | 2022-09-25 | 2022-09-28 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073730 | Final Fix Electrical (Installation of Lighting Control Devices) | 3 | 2022-09-28 | 2022-10-02 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
ELV |  | 38 | 2022-06-07 | 2022-07-25
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-06-07 | 2022-07-04
C-PW-073740 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073750 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073760 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-07-02 | 2022-07-04 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-06-08 | 2022-07-05
C-PW-073770 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-08 | 2022-06-21 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073780 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-21 | 2022-07-03 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073790 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-07-03 | 2022-07-05 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
INTERCOM SYSTEM |  | 23 | 2022-06-11 | 2022-07-07
C-PW-073800 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073810 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-22 | 2022-07-05 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073820 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-07-05 | 2022-07-07 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
AV SYSTEM |  | 23 | 2022-06-13 | 2022-07-13
C-PW-073830 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-13 | 2022-06-25 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073840 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-25 | 2022-07-06 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073850 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-07-06 | 2022-07-13 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-06-14 | 2022-07-14
C-PW-073860 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073870 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073880 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-07-09 | 2022-07-14 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 23 | 2022-06-16 | 2022-07-17
C-PW-073890 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-16 | 2022-06-28 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073900 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-28 | 2022-07-13 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073910 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-07-14 | 2022-07-17 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-06-18 | 2022-07-18
C-PW-073920 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-18 | 2022-06-30 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073930 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-30 | 2022-07-16 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073940 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-07-16 | 2022-07-18 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-07-19 | 2022-07-25
C-PW-073950 | Active Component System Works | 6 | 2022-07-19 | 2022-07-25 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 170 | 2022-03-07 | 2022-09-29
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 99 | 2022-03-07 | 2022-07-04
C-PW-073960 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-07 | 2022-03-19 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073970 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-19 | 2022-03-31 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-073980 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-02 | 2022-07-04 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 89 | 2022-03-19 | 2022-07-04
C-PW-073990 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-19 | 2022-03-31 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074000 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-31 | 2022-04-12 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074010 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-07-02 | 2022-07-04 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
FIRE FIGHTING SYSTEM WORKS |  | 91 | 2022-06-11 | 2022-09-29
C-PW-074020 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-11 | 2022-06-29 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074030 | 2nd Fix Piping System - (Foam water fire Suppression system) & testing | 12 | 2022-06-25 | 2022-07-09 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074040 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-09-24 | 2022-09-29 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
WATER TANKS, FIRE & DOMESTIC WATER PUMP ROOM |  | 171 | 2022-03-05 | 2022-09-28
MECHANICAL |  | 156 | 2022-03-05 | 2022-09-10
HVAC SYSTEM WORKS |  | 47 | 2022-07-16 | 2022-09-10
C-PW-074050 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 7 | 2022-07-16 | 2022-07-24 | 01 | 06 | 01 | 45 | 003 | 02 |  | Building | HVAC | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074060 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 6 | 2022-07-24 | 2022-08-01 | 01 | 06 | 01 | 45 | 003 | 02 |  | Building | HVAC | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074070 | Final Fix HVAC (Exhaust Louvre's,Grills, Diffusers, FCU Mouth Connection & Testing) | 3 | 2022-09-06 | 2022-09-10 | 01 | 06 | 01 | 45 | 003 | 02 |  | Building | HVAC | Museum | South East | L00 Ground Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 52 | 2022-03-05 | 2022-05-07
C-PW-074080 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-03-05 | 2022-03-14 | 01 | 08 | 01 | 45 | 003 | 02 |  | Building | Plumbing | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074090 | 2nd Fix Piping System (Install Booster, Lifting Pumps, Copper Ionization Unit & Connections) | 16 | 2022-03-14 | 2022-04-02 | 01 | 08 | 01 | 45 | 003 | 02 |  | Building | Plumbing | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074100 | GRP Water Tanks Installation | 20 | 2022-03-14 | 2022-04-06 | 01 | 08 | 01 | 45 | 003 | 02 |  | Building | Plumbing | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074110 | Water Tanks Leakage Testing | 10 | 2022-04-06 | 2022-04-19 | 01 | 08 | 01 | 45 | 003 | 02 |  | Building | Plumbing | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074120 | 2nd Fix Piping System (Fittings, Level Indicator, Connection & Testing) | 6 | 2022-04-19 | 2022-04-25 | 01 | 08 | 01 | 45 | 003 | 02 |  | Building | Plumbing | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074130 | Final Fix Fittings incl. Water meter | 7 | 2022-04-25 | 2022-05-07 | 01 | 08 | 01 | 45 | 003 | 02 |  | Building | Plumbing | Museum | South East | L00 Ground Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 60 | 2022-06-23 | 2022-09-06
C-PW-074140 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-06-23 | 2022-07-02 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074150 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-07-19 | 2022-07-31 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074160 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 9 | 2022-07-31 | 2022-08-10 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074170 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-08-10 | 2022-08-16 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074180 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-13 | 2022-08-21 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074190 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-21 | 2022-08-29 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074200 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-29 | 2022-09-06 | 01 | 07 | 01 | 45 | 003 | 02 |  | Building | Electrical | Museum | South East | L00 Ground Level | MEP / Service Rooms
ELV |  | 47 | 2022-07-02 | 2022-08-30
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-07-02 | 2022-08-02
C-PW-074210 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-07-02 | 2022-07-18 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074220 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-18 | 2022-07-31 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074230 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-07-31 | 2022-08-02 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-07-18 | 2022-08-15
C-PW-074240 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-07-18 | 2022-07-31 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074250 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-31 | 2022-08-11 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074260 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-13 | 2022-08-15 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
INTERCOM SYSTEM |  | 23 | 2022-07-19 | 2022-08-16
C-PW-074270 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-07-19 | 2022-08-02 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074280 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-08-02 | 2022-08-14 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074290 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-14 | 2022-08-16 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
AV SYSTEM |  | 23 | 2022-07-21 | 2022-08-18
C-PW-074300 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-21 | 2022-08-03 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074310 | 2nd Fix AV System Works (Wiring) | 10 | 2022-08-03 | 2022-08-16 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074320 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-16 | 2022-08-18 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-07-24 | 2022-08-21
C-PW-074330 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-07-24 | 2022-08-06 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074340 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-08-06 | 2022-08-17 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074350 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-17 | 2022-08-21 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 23 | 2022-07-25 | 2022-08-22
C-PW-074360 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-25 | 2022-08-07 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074370 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-08 | 2022-08-20 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074380 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-20 | 2022-08-22 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-07-27 | 2022-08-24
C-PW-074390 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-27 | 2022-08-09 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074400 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-09 | 2022-08-21 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074410 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-22 | 2022-08-24 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-08-24 | 2022-08-30
C-PW-074420 | Active Component System Works | 6 | 2022-08-24 | 2022-08-30 | 01 | 10 | 01 | 45 | 003 | 02 |  | Building | CCTV | Museum | South East | L00 Ground Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 76 | 2022-06-27 | 2022-09-28
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 23 | 2022-08-08 | 2022-09-04
C-PW-074430 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-08-08 | 2022-08-20 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074440 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-08-20 | 2022-08-31 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074450 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-31 | 2022-09-04 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 23 | 2022-08-09 | 2022-09-05
C-PW-074460 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-08-09 | 2022-08-21 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074470 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-22 | 2022-09-03 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074480 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-03 | 2022-09-05 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
FIRE FIGHTING SYSTEM WORKS |  | 76 | 2022-06-27 | 2022-09-28
C-PW-074490 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 18 | 2022-06-27 | 2022-07-23 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074500 | 2nd Fix Piping System (Installation of Breeching Inlets-Sprinkler & Stand Pipe) | 4 | 2022-07-23 | 2022-07-27 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074510 | 2nd Fix Piping System - (Fire Pump Set, Valves & Accessories and Connections | 18 | 2022-07-27 | 2022-08-17 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
C-PW-074520 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-09-22 | 2022-09-28 | 01 | 09 | 01 | 45 | 003 | 02 |  | Building | Firefighting | Museum | South East | L00 Ground Level | MEP / Service Rooms
LEVEL 01 MEZZANINE |  | 605 | 2021-05-03 | 2023-05-06
CIVIL WORKS |  | 341 | 2021-05-03 | 2022-06-20
ZONE 02A |  | 38 | 2021-09-09 | 2021-10-24
C-PW-074530 | Construction of Level 01 Slab - Zone 2A | 26 | 2021-09-09 | 2021-10-09 | 01 | 01 | 01 | 07 | 004 | 30 |  | Building | Civil | Museum | Zone 02A | L01 Mezzanine Level | Civil SubZones
C-PW-074540 | Construction of Verticals up to Level 02 Slab - Zone 2A | 26 | 2021-09-23 | 2021-10-24 | 01 | 01 | 01 | 07 | 004 | 30 |  | Building | Civil | Museum | Zone 02A | L01 Mezzanine Level | Civil SubZones
ZONE 02B |  | 76 | 2021-10-26 | 2022-01-25
C-PW-074550 | Construction of Verticals up to Level - 02 Slab - Zone 2B | 26 | 2021-10-26 | 2021-11-24 | 01 | 01 | 01 | 08 | 004 | 30 |  | Building | Civil | Museum | Zone 02B | L01 Mezzanine Level | Civil SubZones
C-PW-074560 | Construction of Falconry Walls (White concrete) up to +14.75 stage 1 | 26 | 2021-11-02 | 2021-12-04 | 01 | 01 | 01 | 08 | 004 | 30 |  | Building | Civil | Museum | Zone 02B | L01 Mezzanine Level | Civil SubZones
C-PW-074570 | Construction of Falconry Leave outs up to Level 01 Slab | 30 | 2021-11-09 | 2021-12-15 | 01 | 01 | 01 | 08 | 004 | 30 |  | Building | Civil | Museum | Zone 02B | L01 Mezzanine Level | Civil SubZones
C-PW-074580 | Construction of Falconry Walls from +14.75 to +19.45 and Arches 1,2,3 & 4 | 30 | 2021-11-16 | 2021-12-22 | 01 | 01 | 01 | 08 | 004 | 30 |  | Building | Civil | Museum | Zone 02B | L01 Mezzanine Level | Civil SubZones
C-PW-074590 | Construction of remaining Falconry Arches & Top slab | 52 | 2021-11-23 | 2022-01-25 | 01 | 01 | 01 | 08 | 004 | 30 |  | Building | Civil | Museum | Zone 02B | L01 Mezzanine Level | Civil SubZones
ZONE 02C |  | 24 | 2021-12-21 | 2022-01-18
C-PW-074600 | Construction of Verticals up to Level 02 Slab - Zone 2C | 24 | 2021-12-21 | 2022-01-18 | 01 | 01 | 01 | 09 | 004 | 30 |  | Building | Civil | Museum | Zone 02C | L01 Mezzanine Level | Civil SubZones
ZONE 02D |  | 32 | 2022-02-19 | 2022-03-27
C-PW-074610 | Construction of Level 01 Slab - Zone 2D | 26 | 2022-02-19 | 2022-03-20 | 01 | 01 | 01 | 10 | 004 | 30 |  | Building | Civil | Museum | Zone 02D | L01 Mezzanine Level | Civil SubZones
C-PW-074620 | Construction of Verticals up to Level 02 Slab - Zone 2D | 26 | 2022-02-26 | 2022-03-27 | 01 | 01 | 01 | 10 | 004 | 30 |  | Building | Civil | Museum | Zone 02D | L01 Mezzanine Level | Civil SubZones
ZONE 02E |  | 30 | 2021-10-06 | 2021-11-10
C-PW-074630 | Construction of Level 01 Slab - Zone 2E | 24 | 2021-10-06 | 2021-11-03 | 01 | 01 | 01 | 11 | 004 | 30 |  | Building | Civil | Museum | Zone 02E | L01 Mezzanine Level | Civil SubZones
C-PW-074640 | Construction of Verticals up to Level 02 Slab - Zone 2E | 24 | 2021-10-13 | 2021-11-10 | 01 | 01 | 01 | 11 | 004 | 30 |  | Building | Civil | Museum | Zone 02E | L01 Mezzanine Level | Civil SubZones
ZONE 02G |  | 42 | 2021-11-09 | 2021-12-29
C-PW-074650 | Construction of Verticals from Level 01to Level 02 Stage 02 - Zone 2G | 28 | 2021-11-09 | 2021-12-13 | 01 | 01 | 01 | 13 | 004 | 30 |  | Building | Civil | Museum | Zone 02G | L01 Mezzanine Level | Civil SubZones
C-PW-074660 | Construction of Level 01 Slab - Zone 2G | 24 | 2021-12-01 | 2021-12-29 | 01 | 01 | 01 | 13 | 004 | 30 |  | Building | Civil | Museum | Zone 02G | L01 Mezzanine Level | Civil SubZones
ZONE 02H |  | 26 | 2021-11-18 | 2021-12-20
C-PW-074670 | Construction of verticals up to Level 02 Slab - Zone 2H | 26 | 2021-11-18 | 2021-12-20 | 01 | 01 | 01 | 14 | 004 | 30 |  | Building | Civil | Museum | Zone 02H | L01 Mezzanine Level | Civil SubZones
ZONE 03A |  | 64 | 2021-12-29 | 2022-03-14
C-PW-074680 | Construction of Level 01 Slab - Zone 3A | 21 | 2021-12-29 | 2022-01-23 | 01 | 01 | 01 | 15 | 004 | 30 |  | Building | Civil | Museum | Zone 03A | L01 Mezzanine Level | Civil SubZones
C-PW-074690 | Construction of Level 01 Slab - Zone 3A - Upstands | 15 | 2022-01-24 | 2022-02-09 | 01 | 01 | 01 | 15 | 004 | 30 |  | Building | Civil | Museum | Zone 03A | L01 Mezzanine Level | Civil SubZones
C-PW-074700 | Curing and Formwork Removal of Level 01 Slab - Zone 3A | 28 | 2022-02-10 | 2022-03-14 | 01 | 01 | 01 | 15 | 004 | 30 |  | Building | Civil | Museum | Zone 03A | L01 Mezzanine Level | Civil SubZones
ZONE 03B |  | 281 | 2021-05-03 | 2022-04-07
C-PW-074710 | Site Survey for Action (Item 23 - Immediate) | 1 | 2021-05-03 | 2021-05-03 | 01 | 01 | 01 | 16 | 004 | 30 |  | Building | Civil | Museum | Zone 03B | L01 Mezzanine Level | Civil SubZones
C-PW-074720 | Construction of Level 01 Slab - Zone 3B (Item 23 - Immediate) | 10 | 2021-08-21 | 2021-08-31 | 01 | 01 | 01 | 16 | 004 | 30 |  | Building | Civil | Museum | Zone 03B | L01 Mezzanine Level | Civil SubZones
C-PW-074730 | Construction of Level 01 Slab - Zone 3B | 24 | 2022-02-02 | 2022-03-01 | 01 | 01 | 01 | 16 | 004 | 30 |  | Building | Civil | Museum | Zone 03B | L01 Mezzanine Level | Civil SubZones
C-PW-074740 | Construction of Verticals up to Level 02 Slab - Zone 3B | 32 | 2022-03-02 | 2022-04-07 | 01 | 01 | 01 | 16 | 004 | 30 |  | Building | Civil | Museum | Zone 03B | L01 Mezzanine Level | Civil SubZones
ZONE 03C |  | 32 | 2022-05-15 | 2022-06-20
C-PW-074750 | Construction of Level 01 Slab - Zone 3C | 24 | 2022-05-15 | 2022-06-11 | 01 | 01 | 01 | 17 | 004 | 30 |  | Building | Civil | Museum | Zone 03C | L01 Mezzanine Level | Civil SubZones
C-PW-074760 | Construction of Verticals up to Level 02 Slab -Zone 3C | 26 | 2022-05-22 | 2022-06-20 | 01 | 01 | 01 | 17 | 004 | 30 |  | Building | Civil | Museum | Zone 03C | L01 Mezzanine Level | Civil SubZones
STEEL STRUCTURE |  | 63 | 2021-11-02 | 2022-01-17
ZONE 02A |  | 34 | 2021-11-02 | 2021-12-13
C-PW-074770 | Erection of Mezzanine beams / Welding / Deck Sheet Laying - Zone 2A | 12 | 2021-11-02 | 2021-11-15 | 01 | 02 | 01 | 07 | 004 | 30 |  | Building | Primary Steel Structure | Museum | Zone 02A | L01 Mezzanine Level | Civil SubZones
C-PW-074780 | Slab Casting - Zone 2A | 12 | 2021-11-16 | 2021-11-29 | 01 | 01 | 01 | 07 | 004 | 30 |  | Building | Civil | Museum | Zone 02A | L01 Mezzanine Level | Civil SubZones
C-PW-074790 | Application of cementitious Fireproofing works - Zone 2A | 10 | 2021-12-01 | 2021-12-13 | 01 | 02 | 01 | 07 | 004 | 30 |  | Building | Primary Steel Structure | Museum | Zone 02A | L01 Mezzanine Level | Civil SubZones
ZONE 02B |  | 43 | 2021-11-25 | 2022-01-17
C-PW-074800 | Erection of Mezzanine beams / Welding / Deck Sheet Laying | 26 | 2021-11-25 | 2021-12-27 | 01 | 02 | 01 | 08 | 004 | 30 |  | Building | Primary Steel Structure | Museum | Zone 02B | L01 Mezzanine Level | Civil SubZones
C-PW-074810 | Slab Casting | 7 | 2021-12-28 | 2022-01-05 | 01 | 01 | 01 | 08 | 004 | 30 |  | Building | Civil | Museum | Zone 02B | L01 Mezzanine Level | Civil SubZones
C-PW-074820 | Application of cementitious Fireproofing works | 10 | 2022-01-06 | 2022-01-17 | 01 | 02 | 01 | 08 | 004 | 30 |  | Building | Primary Steel Structure | Museum | Zone 02B | L01 Mezzanine Level | Civil SubZones
ARCHITECTURAL WORKS |  | 394 | 2022-01-17 | 2023-05-06
NORTH WEST |  | 383 | 2022-01-17 | 2023-04-23
COMMON WORKS- NORTH |  | 31 | 2022-01-17 | 2022-02-22
C-PW-074830 | General Block Work | 17 | 2022-01-17 | 2022-02-05 | 01 | 04 | 01 | 46 | 004 | 01 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Circulation / Common Areas
C-PW-074840 | Marking & Chasing Walls for MEP Services | 14 | 2022-02-05 | 2022-02-22 | 01 | 04 | 01 | 46 | 004 | 01 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Circulation / Common Areas
STAFF MALE AND FEMALE WC'S, MALE ABLUTIONS & PRAYER ROOM - NORTH |  | 146 | 2022-04-14 | 2022-10-10
C-PW-074850 | Floor Waterproofing Works | 16 | 2022-04-14 | 2022-05-05 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-074860 | Floor Screed Works | 8 | 2022-05-07 | 2022-05-15 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-074870 | Plastering Works - Walls | 10 | 2022-05-16 | 2022-05-26 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-074880 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-05 | 01 | 14 | 01 | 46 | 004 | 03 |  | Building | General MEP | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-074890 | Wall Finishes (Ceramic Wall Tiles, Plaster Board Partition & Plaster Render) | 19 | 2022-06-14 | 2022-07-06 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-074900 | Ceiling Grid / Support Works | 14 | 2022-06-30 | 2022-07-20 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-074910 | Ceiling Finishes (Metal tile ceiling, Acoustic Timber Ceiling & Plaster board ceiling) | 14 | 2022-07-20 | 2022-08-08 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-074920 | Floor Finishes (Terrazzo Resin flooring system, Reconstructed Stone Tiles, Stone Flooring) | 22 | 2022-08-08 | 2022-09-03 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-074930 | Door Frames & Architrave Fixing | 8 | 2022-09-03 | 2022-09-12 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-074940 | Door Shuttering & Ironmongery | 8 | 2022-09-11 | 2022-09-19 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-074950 | Furniture : Installation of Lockers, shelves & Shoe Cupboards | 11 | 2022-09-26 | 2022-10-10 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
OFFICES, RECEPTIONS, MAIL ROOM, CALL CENTER, COMMERCIAL SERVICES & MEETING ROOMS- NORTH |  | 146 | 2022-06-14 | 2022-12-07
C-PW-074960 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-26 | 01 | 14 | 01 | 46 | 004 | 05 |  | Building | General MEP | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-074970 | Plastering Works - Walls | 14 | 2022-06-14 | 2022-06-30 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-074980 | Wall Finishes (Plasterboard, Glazed Partition, Bespoke Partial Glazed System) | 21 | 2022-06-26 | 2022-07-23 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-074990 | Ceiling Grid / Support Works | 19 | 2022-07-13 | 2022-08-06 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075000 | Ceiling Finishes (Plasterboard Ceilings, Acoustic Timber Ceiling & Fabric Lining Ceiling) | 19 | 2022-08-07 | 2022-08-29 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075010 | Concrete Screed SCR-202 | 5 | 2022-08-29 | 2022-09-03 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075020 | Waterproofing RFS 101 | 5 | 2022-09-04 | 2022-09-08 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075030 | Floor Finishes (Carpet Tile, Stone Flooring & Raised Access Floor) | 19 | 2022-08-29 | 2022-09-20 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075040 | RW-402 Gutter (ACO Drain) around Courtyard | 10 | 2022-09-08 | 2022-09-20 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075050 | Door Frames & Architrave Fixing | 11 | 2022-09-20 | 2022-10-03 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075060 | Door Shuttering & Ironmongery | 11 | 2022-10-17 | 2022-10-30 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075070 | Bespoke AV Walls, Bespoke Copy Point Furniture & Shelves | 10 | 2022-10-31 | 2022-11-10 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075080 | EPS Filling INS 151(Avg 150 mm thick) | 5 | 2022-11-10 | 2022-11-16 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075090 | Final Finishes | 10 | 2022-11-10 | 2022-11-22 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075100 | SCR 106 Troweled Finish | 8 | 2022-11-16 | 2022-11-26 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075110 | Concrete -CON 150 Abrasive Blast Finish to In-Situ Concrete | 5 | 2022-11-26 | 2022-12-03 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075120 | Steel Angle Support Screed /Sand | 5 | 2022-12-03 | 2022-12-07 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
OFFICE BALCONY- NORTH |  | 267 | 2022-06-05 | 2023-04-23
C-PW-075130 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-05 | 01 | 14 | 01 | 46 | 004 | 05 |  | Building | General MEP | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075140 | Wall Finishes (Plaster render,PVC,Stone Wall Linings) | 19 | 2022-07-23 | 2022-08-15 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075150 | Ceiling Grid / Support Works | 14 | 2022-08-10 | 2022-08-27 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075160 | Ceiling Finishes (Suspended Plaster board ceiling) | 14 | 2022-08-29 | 2022-09-14 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075170 | Floor Finishes (Polished Conc floor finish,Resin & Timber board flooring) | 17 | 2022-09-14 | 2022-10-04 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075180 | Door Frames & Architrave Fixing | 11 | 2022-10-04 | 2022-10-18 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075190 | Door Shuttering & Ironmongery | 3 | 2022-10-31 | 2022-11-03 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075200 | Joinery Fixing, Installation of Lockers | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075210 | Final Finishes | 6 | 2023-04-12 | 2023-04-23 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
FILE STORAGE, MALL ROOM & MASTER ROOM- NORTH |  | 260 | 2022-06-13 | 2023-04-23
C-PW-075230 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-13 | 01 | 14 | 01 | 46 | 004 | 05 |  | Building | General MEP | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075220 | Plastering Works - Walls | 11 | 2022-06-30 | 2022-07-17 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075240 | Wall Finishes (Ceramic Wall Tile & Plaster Rendered Finish) | 19 | 2022-07-18 | 2022-08-10 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075250 | Ceiling Grid / Support Works | 5 | 2022-08-10 | 2022-08-15 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075260 | Ceiling Finishes (Plaster board ceiling) | 5 | 2022-08-16 | 2022-08-21 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075270 | Floor Finishes (Carpet Tile, Polished Concrete & RAF) | 11 | 2022-08-21 | 2022-09-03 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075280 | Door Frames & Architrave Fixing | 6 | 2022-09-04 | 2022-09-11 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075290 | Door Shuttering & Ironmongery | 2 | 2022-10-31 | 2022-11-01 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075300 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075310 | Final Finishes | 6 | 2023-04-12 | 2023-04-23 | 01 | 04 | 01 | 46 | 004 | 05 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
IT ROOM- NORTH |  | 237 | 2022-07-13 | 2023-04-23
C-PW-075320 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-07-13 | 01 | 14 | 01 | 46 | 004 | 02 |  | Building | General MEP | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-075330 | Wall Finishes (Plaster Board, Light Weight Gypsum Plaster & Interior Paint) | 19 | 2022-08-10 | 2022-09-01 | 01 | 04 | 01 | 46 | 004 | 02 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-075340 | Ceiling Grid / Support Works | 14 | 2022-08-27 | 2022-09-12 | 01 | 04 | 01 | 46 | 004 | 02 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-075350 | Ceiling Finishes (Plaster board ceiling) | 14 | 2022-09-13 | 2022-09-29 | 01 | 04 | 01 | 46 | 004 | 02 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-075360 | Floor Finishes (RAF & Carpet Floor Tiles) | 11 | 2022-09-29 | 2022-10-13 | 01 | 04 | 01 | 46 | 004 | 02 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-075370 | Door Frames & Architrave Fixing | 6 | 2022-10-13 | 2022-10-20 | 01 | 04 | 01 | 46 | 004 | 02 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-075380 | Door Shuttering & Ironmongery | 2 | 2022-11-01 | 2022-11-03 | 01 | 04 | 01 | 46 | 004 | 02 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-075390 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 46 | 004 | 02 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-075400 | Final Finishes | 6 | 2023-04-12 | 2023-04-23 | 01 | 04 | 01 | 46 | 004 | 02 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
STAFF MALE AND FEMALE WC'S, FEMALE ABLUTIONS & PRAYER ROOM - NORTH |  | 137 | 2022-05-16 | 2022-10-29
C-PW-075410 | Floor Waterproofing Works | 16 | 2022-05-16 | 2022-06-02 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075420 | Floor Screed Works | 8 | 2022-06-04 | 2022-06-12 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075440 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-07-31 | 01 | 14 | 01 | 46 | 004 | 03 |  | Building | General MEP | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075430 | Plastering Works - Walls | 11 | 2022-07-18 | 2022-08-01 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075450 | Wall Finishes (Ceramic Tile, Polished Plaster, Plaster Render & Feature Lining) | 19 | 2022-08-01 | 2022-08-23 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075460 | Ceiling Grid / Support Works | 14 | 2022-08-16 | 2022-09-01 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075470 | Ceiling Finishes (Suspended plasterboard ceiling) | 14 | 2022-09-01 | 2022-09-18 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075480 | Floor Finishes (Reconstructed Stone Tile & Carpet Broadloom) | 14 | 2022-09-18 | 2022-10-05 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075490 | Door Frames & Architrave Fixing | 5 | 2022-10-05 | 2022-10-11 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075500 | Door Shuttering & Ironmongery | 5 | 2022-10-12 | 2022-10-17 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075510 | Furniture: Shoe Cupboard Installation | 5 | 2022-10-17 | 2022-10-23 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-075520 | Final Finishes | 5 | 2022-10-23 | 2022-10-29 | 01 | 04 | 01 | 46 | 004 | 03 |  | Building | Architecture | Museum | North West | L01 Mezzanine Level | Wet Areas
NORTH EAST |  | 368 | 2022-02-16 | 2023-05-06
CIRCULATIONS & CORRIDORS- NORTH |  | 115 | 2022-07-24 | 2022-12-08
C-PW-075540 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-07-24 | 01 | 14 | 01 | 44 | 004 | 01 |  | Building | General MEP | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075530 | Plastering Works - Walls | 11 | 2022-08-01 | 2022-08-14 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075550 | Wall Finishes (Acoustic Wall Lining, Plaster Render & Glazed Partition) | 19 | 2022-09-01 | 2022-09-24 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075560 | Ceiling Grid / Support Works | 14 | 2022-09-18 | 2022-10-05 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075570 | Ceiling Finishes (Suspended Plaster board ceiling) | 14 | 2022-10-05 | 2022-10-23 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075580 | Floor Finishes (Polished Concrete, Stone Tile, RAF & Carpet Tile) | 11 | 2022-10-23 | 2022-11-05 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075590 | Door Frames & Architrave Fixing | 6 | 2022-11-05 | 2022-11-13 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075600 | Door Shuttering & Ironmongery | 5 | 2022-11-13 | 2022-11-17 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075610 | FHR Enclosures (Bronze & Timber Faced Doors) | 10 | 2022-11-19 | 2022-12-01 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075620 | Final Finishes | 6 | 2022-12-01 | 2022-12-08 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
COMMON WORKS - EAST |  | 26 | 2022-02-16 | 2022-03-17
C-PW-075630 | General Block Work | 22 | 2022-02-16 | 2022-03-14 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075640 | Marking & Chasing Walls for MEP Services | 14 | 2022-03-01 | 2022-03-17 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
PUBLIC MALE & FEMALE WC - EAST |  | 129 | 2022-05-12 | 2022-10-16
C-PW-075650 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-05-12 | 01 | 14 | 01 | 44 | 004 | 03 |  | Building | General MEP | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-075660 | Floor Waterproofing Works | 16 | 2022-06-04 | 2022-06-21 | 01 | 04 | 01 | 44 | 004 | 03 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-075670 | Floor Screed Works | 8 | 2022-06-22 | 2022-06-30 | 01 | 04 | 01 | 44 | 004 | 03 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-075680 | Wall Finishes (Ceramic Wall Tile & Wall Lining) | 20 | 2022-06-22 | 2022-07-18 | 01 | 04 | 01 | 44 | 004 | 03 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-075690 | Ceiling Grid / Support Works | 14 | 2022-07-13 | 2022-07-31 | 01 | 04 | 01 | 44 | 004 | 03 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-075700 | Ceiling Finishes (Metal tile ceiling & Plaster board ceiling) | 14 | 2022-07-31 | 2022-08-16 | 01 | 04 | 01 | 44 | 004 | 03 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-075710 | Floor Finishes (Terrazzo Resin flooring system) | 17 | 2022-08-17 | 2022-09-05 | 01 | 04 | 01 | 44 | 004 | 03 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-075720 | Door Frames & Architrave Fixing | 8 | 2022-09-05 | 2022-09-14 | 01 | 04 | 01 | 44 | 004 | 03 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-075730 | Door Shuttering & Ironmongery | 5 | 2022-09-17 | 2022-09-22 | 01 | 04 | 01 | 44 | 004 | 03 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-075740 | Mirrors & Accessories | 10 | 2022-09-22 | 2022-10-03 | 01 | 04 | 01 | 44 | 004 | 03 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-075750 | Final Finishes | 10 | 2022-10-03 | 2022-10-16 | 01 | 04 | 01 | 44 | 004 | 03 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Wet Areas
FALCONRY CLASSROOMS - EAST |  | 275 | 2022-06-08 | 2023-05-06
C-PW-075760 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-08 | 01 | 14 | 01 | 44 | 004 | 01 |  | Building | General MEP | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075770 | Wall Finishes (Plaster Render, Magnetic Paint, Plaster Board Lining, Internal Folding Wall Partition) | 19 | 2022-06-08 | 2022-06-30 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075780 | Ceiling Grid / Support Works | 14 | 2022-06-25 | 2022-07-16 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075790 | Ceiling Finishes (Plaster board ceiling) | 14 | 2022-07-16 | 2022-08-02 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075800 | Floor Finishes (Vinyl Sheeting) | 11 | 2022-08-02 | 2022-08-15 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075810 | Door Frames & Architrave Fixing | 6 | 2022-09-14 | 2022-09-22 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075820 | Door Shuttering & Ironmongery | 2 | 2022-09-22 | 2022-09-24 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075830 | Joinery Fixing & Fitout Works | 16 | 2023-04-08 | 2023-04-27 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-075840 | Final Finishes | 6 | 2023-04-29 | 2023-05-06 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
FALCONRY OFFICE, MEETING ROOM & BALCONY - EAST |  | 115 | 2022-06-28 | 2022-11-15
C-PW-075860 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-07-13 | 01 | 14 | 01 | 44 | 004 | 05 |  | Building | General MEP | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075850 | Plastering Works - Walls | 11 | 2022-06-28 | 2022-07-14 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075870 | Wall Finishes (Bespoke Partially Glazed Partition, Interior Paint, Dressed Sandstone) | 19 | 2022-07-14 | 2022-08-07 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075880 | Ceiling Grid / Support Works | 14 | 2022-08-06 | 2022-08-22 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075890 | Ceiling Finishes (Plaster Board & GRC Soffit) | 14 | 2022-08-22 | 2022-09-07 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075900 | Floor Finishes (Carpet Tiles & Flexible Terrazo) | 22 | 2022-09-08 | 2022-10-04 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075910 | Handrails in Balcony | 5 | 2022-10-04 | 2022-10-11 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075920 | Door Frames & Architrave Fixing | 8 | 2022-10-11 | 2022-10-20 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075930 | Door Shuttering & Ironmongery | 6 | 2022-10-20 | 2022-10-27 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075940 | Projector Screen Installation | 5 | 2022-10-27 | 2022-11-02 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075950 | Final Finishes | 6 | 2022-11-08 | 2022-11-15 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FALCONRY OFFICE IT ROOM - EAST |  | 264 | 2022-06-08 | 2023-04-23
C-PW-075960 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-08 | 01 | 14 | 01 | 44 | 004 | 05 |  | Building | General MEP | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075970 | Wall Finishes (Interior Paint & Mild Steel Panel) | 19 | 2022-06-08 | 2022-06-30 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075980 | Ceiling Grid / Support Works | 14 | 2022-06-25 | 2022-07-16 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-075990 | Ceiling Finishes (Plaster board ceiling & Plaster board Tiles) | 14 | 2022-07-16 | 2022-08-02 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076000 | Floor Finishes (Epoxy Resin Flooring & Raised Access Floor) | 11 | 2022-08-02 | 2022-08-15 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076010 | Door Frames & Architrave Fixing | 6 | 2022-08-15 | 2022-08-23 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076020 | Door Shuttering & Ironmongery | 2 | 2022-10-27 | 2022-10-30 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076030 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076040 | Final Finishes | 6 | 2023-04-12 | 2023-04-23 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FALCONRY STORAGES & FALCONRY OFFICE SUPPLIES - EAST |  | 277 | 2022-05-28 | 2023-04-26
C-PW-076050 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-08 | 01 | 14 | 01 | 44 | 004 | 05 |  | Building | General MEP | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076060 | Plastering Works - Walls | 11 | 2022-05-28 | 2022-06-09 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076070 | Wall Finishes (Render, Interior Paint & Wall Protection) | 19 | 2022-06-09 | 2022-07-02 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076080 | Ceiling Grid / Support Works | 11 | 2022-06-29 | 2022-07-16 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076090 | Ceiling Finishes (Dust Sealer, Plaster Board & Plaster Board Tile) | 14 | 2022-07-17 | 2022-08-03 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076100 | Floor Finishes (Carpet Tile & Epoxy Resin Flooring) | 11 | 2022-10-04 | 2022-10-18 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076110 | Door Frames & Architrave Fixing | 6 | 2022-10-20 | 2022-10-27 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076120 | Door Shuttering & Ironmongery | 5 | 2022-10-27 | 2022-11-02 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076130 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076140 | Final Finishes | 10 | 2023-04-12 | 2023-04-26 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FALCONRY OUTDOOR SHELTERS - EAST |  | 78 | 2022-06-02 | 2022-09-06
C-PW-076150 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-02 | 01 | 14 | 01 | 44 | 004 | 05 |  | Building | General MEP | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076160 | Wall Finishes (Ceramic Wall Tiling) | 19 | 2022-06-04 | 2022-06-26 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076170 | Ceiling Grid / Support Works | 14 | 2022-06-20 | 2022-07-06 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076180 | Ceiling Finishes (Stretch PVC Lining) | 14 | 2022-07-06 | 2022-07-27 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076190 | Floor Finishes (Ceramic Tile) | 11 | 2022-07-27 | 2022-08-10 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076200 | Door Frames & Architrave Fixing | 6 | 2022-08-10 | 2022-08-17 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076210 | Door Shuttering & Ironmongery | 6 | 2022-08-17 | 2022-08-24 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076220 | Final Finishes | 6 | 2022-08-30 | 2022-09-06 | 01 | 04 | 01 | 44 | 004 | 05 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
MALE & FEMALE CHANGING ROOM - EAST |  | 124 | 2022-06-14 | 2022-11-12
C-PW-076250 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-14 | 01 | 14 | 01 | 44 | 004 | 01 |  | Building | General MEP | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076230 | Floor Waterproofing Works | 16 | 2022-06-22 | 2022-07-13 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076240 | Floor Screed Works | 8 | 2022-07-14 | 2022-07-23 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076260 | Wall Finishes (HPL WC Cubicles & Ceramic Wall tiles) | 19 | 2022-07-24 | 2022-08-16 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076270 | Ceiling Grid / Support Works | 14 | 2022-08-10 | 2022-08-27 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076280 | Ceiling Finishes (Plaster board ceiling) | 14 | 2022-08-27 | 2022-09-13 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076290 | Floor Finishes (Ceramic Tiles) | 17 | 2022-09-13 | 2022-10-02 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076300 | Door Frames & Architrave Fixing | 8 | 2022-10-03 | 2022-10-12 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076310 | Door Shuttering & Ironmongery | 5 | 2022-10-13 | 2022-10-18 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076320 | Sanitary Ware, Mirrors & Accessories | 10 | 2022-10-18 | 2022-10-30 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076330 | Installation of Lockers | 5 | 2022-10-30 | 2022-11-05 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076340 | Final Finishes | 6 | 2022-11-05 | 2022-11-12 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
LOBBY & CIRCULATIONS - EAST |  | 258 | 2022-06-14 | 2023-04-22
C-PW-076350 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-30 | 01 | 14 | 01 | 44 | 004 | 01 |  | Building | General MEP | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076360 | Plastering Works - Walls | 17 | 2022-06-14 | 2022-07-04 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076370 | Wall Finishes (Plaster Render, Light Weight Gypsum Plaster, Interior Paint & Metal Panel Cladding) | 19 | 2022-07-04 | 2022-07-31 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076380 | Ceiling Grid / Support Works | 14 | 2022-07-24 | 2022-08-11 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076390 | Ceiling Finishes (Interior Paint, Plaster Board, Plaster Board Tile & GRC Soffit) | 14 | 2022-08-11 | 2022-08-28 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076400 | Floor Finishes (Floating Screed, Polished Concrete & Epoxy Resin flooring) | 11 | 2022-08-28 | 2022-09-10 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076410 | Door Frames & Architrave Fixing | 6 | 2022-09-10 | 2022-09-18 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076420 | Door Shuttering & Ironmongery | 6 | 2022-09-25 | 2022-10-02 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076430 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076440 | Final Finishes | 6 | 2023-04-12 | 2023-04-22 | 01 | 04 | 01 | 44 | 004 | 01 |  | Building | Architecture | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
SOUTH EAST |  | 309 | 2022-04-13 | 2023-04-23
COMMON WORKS - SOUTH |  | 30 | 2022-04-13 | 2022-05-22
C-PW-076450 | General Block Work | 17 | 2022-04-13 | 2022-05-05 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076460 | Marking & Chasing Walls for MEP Services | 19 | 2022-04-26 | 2022-05-22 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
SCHOOL ARRIVAL, CLASS ROOMS & LUNCH ROOM - SOUTH |  | 82 | 2022-07-05 | 2022-10-15
C-PW-076470 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-07-05 | 01 | 14 | 01 | 45 | 004 | 01 |  | Building | General MEP | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076480 | Wall Finishes (Plaster Render, Metal & Fin wall system & Wall Protection) | 19 | 2022-07-06 | 2022-08-02 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076490 | Ceiling Grid / Support Works | 14 | 2022-07-24 | 2022-08-11 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076500 | Ceiling Finishes (Plasterboard) | 14 | 2022-08-11 | 2022-08-28 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076510 | Floor Finishes (Vinyl sheeting) | 14 | 2022-08-28 | 2022-09-13 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076520 | Door Frames & Architrave Fixing | 5 | 2022-09-14 | 2022-09-19 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076530 | Roller Shutter Installation | 5 | 2022-09-15 | 2022-09-20 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076540 | Door Shuttering & Ironmongery | 5 | 2022-09-19 | 2022-09-25 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076550 | Installation of Lockers, Sliding Timber Screen, Kitchen Base Units, Kitchenette & Wall Lining | 10 | 2022-09-25 | 2022-10-06 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076560 | Final Finishes | 6 | 2022-10-06 | 2022-10-15 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
STORAGE 2, STORAGE 3 & CLASSROOM STORAGE - SOUTH |  | 244 | 2022-06-30 | 2023-04-23
C-PW-076570 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-30 | 01 | 14 | 01 | 45 | 004 | 05 |  | Building | General MEP | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076580 | Wall Finishes (Plaster Render, Paint Finish & Wall Protection) | 14 | 2022-06-30 | 2022-07-21 | 01 | 04 | 01 | 45 | 004 | 05 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076590 | Ceiling Grid / Support Works | 10 | 2022-07-21 | 2022-08-02 | 01 | 04 | 01 | 45 | 004 | 05 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076600 | Ceiling Finishes (Plasterboard Ceiling) | 14 | 2022-08-02 | 2022-08-20 | 01 | 04 | 01 | 45 | 004 | 05 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076610 | Floor Finishes (Vinyl Sheeting & Epoxy Resin Flooring) | 11 | 2022-08-20 | 2022-09-01 | 01 | 04 | 01 | 45 | 004 | 05 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076620 | Door Frames & Architrave Fixing | 6 | 2022-09-01 | 2022-09-08 | 01 | 04 | 01 | 45 | 004 | 05 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076630 | Door Shuttering & Ironmongery | 5 | 2022-09-25 | 2022-10-01 | 01 | 04 | 01 | 45 | 004 | 05 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076640 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 004 | 05 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-076650 | Final Finishes | 6 | 2023-04-12 | 2023-04-23 | 01 | 04 | 01 | 45 | 004 | 05 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
PUBLIC MALE & FEMALE W/C AND ABLUTION - SOUTH |  | 154 | 2022-05-05 | 2022-11-07
C-PW-076660 | Floor Waterproofing Works | 14 | 2022-05-05 | 2022-05-23 | 01 | 04 | 01 | 45 | 004 | 03 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-076670 | Floor Screed Works | 7 | 2022-05-23 | 2022-05-31 | 01 | 04 | 01 | 45 | 004 | 03 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-076680 | MEP Clearance for Suspended Ceiling in Toilets | 0 |  | 2022-06-30 | 01 | 14 | 01 | 45 | 004 | 03 |  | Building | General MEP | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-076690 | Wall Finishes (Plaster Render, Interior Paint, Ceramic Wall Tile & Water Resistant Wall Lining) | 14 | 2022-06-30 | 2022-07-20 | 01 | 04 | 01 | 45 | 004 | 03 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-076700 | Ceiling Grid / Support Works in Toilets | 6 | 2022-07-18 | 2022-07-24 | 01 | 04 | 01 | 45 | 004 | 03 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-076710 | Ceiling Finishes (Metal tile ceiling & Plaster board ceiling) | 14 | 2022-07-25 | 2022-08-11 | 01 | 04 | 01 | 45 | 004 | 03 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-076720 | Floor Finishes (Resin flooring system, Reconstructed Stone Tiles) | 14 | 2022-07-28 | 2022-08-15 | 01 | 04 | 01 | 45 | 004 | 03 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-076730 | Door Frames & Architrave Fixing | 7 | 2022-08-15 | 2022-08-23 | 01 | 04 | 01 | 45 | 004 | 03 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-076740 | Door Shuttering & Ironmongery | 6 | 2022-10-01 | 2022-10-08 | 01 | 04 | 01 | 45 | 004 | 03 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-076750 | Shoe Cupboard, Ablution Seating & Bench Fixing | 5 | 2022-10-26 | 2022-11-01 | 01 | 04 | 01 | 45 | 004 | 03 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-076760 | Final Finishes | 5 | 2022-11-01 | 2022-11-07 | 01 | 04 | 01 | 45 | 004 | 03 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Wet Areas
PUBLIC MALE & FEMALE PRAYER - SOUTH |  | 231 | 2022-07-19 | 2023-04-23
C-PW-076770 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-07-19 | 01 | 14 | 01 | 45 | 004 | 01 |  | Building | General MEP | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076780 | Wall Finishes (Plaster Render) | 19 | 2022-07-20 | 2022-08-13 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076790 | Ceiling Grid / Support Works | 14 | 2022-08-06 | 2022-08-22 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076800 | Ceiling Finishes (Suspended plasterboard ceiling) | 14 | 2022-08-23 | 2022-09-08 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076810 | Floor Finishes (Carpet Boardloom) | 14 | 2022-09-08 | 2022-09-25 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076820 | Door Frames & Architrave Fixing | 5 | 2022-09-25 | 2022-10-01 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076830 | Door Shuttering & Ironmongery | 5 | 2022-10-03 | 2022-10-08 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076840 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076850 | Final Finishes | 6 | 2023-04-12 | 2023-04-23 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
GALLERY A & B AV / IT ROOM & LOBBY - SOUTH |  | 213 | 2022-08-11 | 2023-04-23
C-PW-076860 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-11 | 01 | 14 | 01 | 45 | 004 | 02 |  | Building | General MEP | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-076870 | Wall Finishes (Interior Paint & Mild Steel Panel System) | 19 | 2022-08-11 | 2022-09-03 | 01 | 04 | 01 | 45 | 004 | 02 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-076880 | Ceiling Grid / Support Works | 14 | 2022-08-27 | 2022-09-12 | 01 | 04 | 01 | 45 | 004 | 02 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-076890 | Roller Shutter Installation | 5 | 2022-09-15 | 2022-09-20 | 01 | 04 | 01 | 45 | 004 | 02 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-076900 | Ceiling Finishes | 14 | 2022-09-12 | 2022-09-28 | 01 | 04 | 01 | 45 | 004 | 02 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-076910 | Floor Finishes | 14 | 2022-09-29 | 2022-10-17 | 01 | 04 | 01 | 45 | 004 | 02 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-076920 | Door Frames & Architrave Fixing | 5 | 2022-10-17 | 2022-10-23 | 01 | 04 | 01 | 45 | 004 | 02 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-076930 | Door Shuttering & Ironmongery | 3 | 2022-10-23 | 2022-10-26 | 01 | 04 | 01 | 45 | 004 | 02 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-076940 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 004 | 02 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-076950 | Final Finishes | 6 | 2023-04-12 | 2023-04-23 | 01 | 04 | 01 | 45 | 004 | 02 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
CIRCULATION - SOUTH |  | 191 | 2022-09-05 | 2023-04-23
C-PW-076960 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-09-05 | 01 | 14 | 01 | 45 | 004 | 01 |  | Building | General MEP | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076970 | Plastering Works - Walls | 11 | 2022-09-08 | 2022-09-21 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076980 | Wall Finishes (Interior Paints, Plaster render finish & Wall Protection) | 19 | 2022-09-21 | 2022-10-15 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-076990 | Ceiling Grid / Support Works | 14 | 2022-10-10 | 2022-10-26 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-077000 | Ceiling Finishes (Plaster board ceiling) | 14 | 2022-10-26 | 2022-11-12 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-077010 | Floor Finishes (Vinyl Sheeting, Polished Concrete & Epoxy Resin flooring) | 11 | 2022-11-12 | 2022-11-24 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-077020 | Door Frames & Architrave Fixing | 6 | 2022-11-26 | 2022-12-04 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-077030 | Door Shuttering & Ironmongery | 5 | 2022-12-04 | 2022-12-10 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-077040 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-077050 | Final Finishes | 6 | 2023-04-12 | 2023-04-23 | 01 | 04 | 01 | 45 | 004 | 01 |  | Building | Architecture | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
MEP WORKS |  | 286 | 2022-01-13 | 2022-12-24
NORTH WEST |  | 208 | 2022-03-10 | 2022-11-17
STAFF MALE AND FEMALE WC'S, MALE ABLUTIONS & PRAYER ROOM - NORTH |  | 170 | 2022-03-10 | 2022-10-03
MECHANICAL |  | 170 | 2022-03-10 | 2022-10-03
HVAC SYSTEM WORKS |  | 144 | 2022-04-06 | 2022-09-28
C-PW-077060 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-04-06 | 2022-04-27 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077070 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-04-27 | 2022-05-21 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077080 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-21 | 2022-06-01 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077090 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-20 | 2022-09-28 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
DRAINAGE WORKS |  | 165 | 2022-03-10 | 2022-09-26
C-PW-077100 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-10 | 2022-03-31 | 01 | 08 | 01 | 46 | 004 | 03 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077110 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-03-31 | 2022-04-12 | 01 | 08 | 01 | 46 | 004 | 03 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077120 | Final Fix (Installation of Sanitaryware & Accessories) | 7 | 2022-09-18 | 2022-09-26 | 01 | 08 | 01 | 46 | 004 | 03 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Wet Areas
HOT & COLD WATER SYSTEM |  | 165 | 2022-03-15 | 2022-10-03
C-PW-077130 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-15 | 2022-04-06 | 01 | 08 | 01 | 46 | 004 | 03 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077140 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-04-06 | 2022-04-18 | 01 | 08 | 01 | 46 | 004 | 03 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077150 | Final Fix - Water Meter Installation | 3 | 2022-09-29 | 2022-10-03 | 01 | 08 | 01 | 46 | 004 | 03 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Wet Areas
ELECTRICAL WORKS |  | 170 | 2022-03-10 | 2022-10-03
C-PW-077160 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-10 | 2022-03-26 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077170 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-04-27 | 2022-05-21 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077180 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-21 | 2022-06-05 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077190 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-20 | 2022-09-28 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077200 | Final Fix Electrical (Light Fixtures) | 10 | 2022-09-21 | 2022-10-03 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077210 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-09-21 | 2022-10-03 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
ELV |  | 125 | 2022-04-14 | 2022-09-14
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 125 | 2022-04-14 | 2022-09-14
C-PW-077220 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077230 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-21 | 2022-06-01 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077240 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
AV SYSTEM |  | 123 | 2022-04-16 | 2022-09-14
C-PW-077250 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-16 | 2022-04-27 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077260 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077270 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
DATA AND TELECOMMUNICATION |  | 122 | 2022-04-18 | 2022-09-14
C-PW-077280 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077290 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077300 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 122 | 2022-04-18 | 2022-09-14
C-PW-077310 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077320 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077330 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 148 | 2022-03-19 | 2022-09-14
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 120 | 2022-04-19 | 2022-09-14
C-PW-077340 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-19 | 2022-05-05 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077350 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-05 | 2022-05-17 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077360 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 120 | 2022-04-19 | 2022-09-14
C-PW-077370 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-19 | 2022-05-05 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077380 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-05 | 2022-05-17 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077390 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
FIRE FIGHTING WORKS |  | 123 | 2022-03-19 | 2022-08-17
C-PW-077400 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-03-19 | 2022-04-06 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077410 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-06 | 2022-04-16 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-077420 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-08 | 2022-08-17 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
OFFICES, RECEPTIONS, MAIL ROOM, CALL CENTER, COMMERCIAL SERVICES & MEETING ROOMS- NORTH |  | 208 | 2022-03-10 | 2022-11-17
MECHANICAL |  | 201 | 2022-03-10 | 2022-11-08
HVAC SYSTEM WORKS |  | 201 | 2022-03-10 | 2022-11-08
C-PW-077430 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-03-12 | 2022-03-31 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077440 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-03-10 | 2022-03-31 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077450 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 14 | 2022-03-31 | 2022-04-16 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077460 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-31 | 2022-11-08 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 32 | 2022-03-31 | 2022-05-11
C-PW-077470 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-31 | 2022-04-21 | 01 | 08 | 01 | 46 | 004 | 05 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077480 | 2nd Fix Piping System (Fittings, Insulation) | 14 | 2022-04-21 | 2022-05-11 | 01 | 08 | 01 | 46 | 004 | 05 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 32 | 2022-04-06 | 2022-05-17
C-PW-077490 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-06 | 2022-04-27 | 01 | 08 | 01 | 46 | 004 | 05 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077500 | 2nd Fix Piping System (Fittings, Insulation) | 14 | 2022-04-27 | 2022-05-17 | 01 | 08 | 01 | 46 | 004 | 05 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 195 | 2022-03-26 | 2022-11-17
C-PW-077510 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-26 | 2022-04-11 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077520 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-03-28 | 2022-04-16 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077530 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-04-17 | 2022-05-05 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077540 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-31 | 2022-11-08 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077550 | Final Fix Electrical (Light Fixtures) | 14 | 2022-11-01 | 2022-11-17 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077560 | Final Fix Electrical (Installation of Lighting Control Devices) | 14 | 2022-11-01 | 2022-11-17 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELV |  | 165 | 2022-04-14 | 2022-11-01
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 156 | 2022-04-14 | 2022-10-22
C-PW-077570 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077580 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077590 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-19 | 2022-10-22 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 156 | 2022-04-14 | 2022-10-22
C-PW-077600 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077610 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077620 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-19 | 2022-10-22 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 156 | 2022-04-14 | 2022-10-22
C-PW-077630 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077640 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077650 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-19 | 2022-10-22 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 130 | 2022-05-19 | 2022-10-24
C-PW-077660 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-19 | 2022-05-31 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077670 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-31 | 2022-06-12 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077680 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-24 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 130 | 2022-05-19 | 2022-10-24
C-PW-077690 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-19 | 2022-05-31 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077700 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-31 | 2022-06-12 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077710 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-22 | 2022-10-24 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 130 | 2022-05-21 | 2022-10-25
C-PW-077720 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-21 | 2022-06-01 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077730 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-02 | 2022-06-14 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077740 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-25 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 130 | 2022-05-21 | 2022-10-25
C-PW-077750 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-21 | 2022-06-01 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077760 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-02 | 2022-06-14 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077770 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-25 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-26 | 2022-11-01
C-PW-077780 | Active Component System Works | 6 | 2022-10-26 | 2022-11-01 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 163 | 2022-04-06 | 2022-10-22
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 117 | 2022-06-02 | 2022-10-22
C-PW-077790 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077800 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-14 | 2022-06-26 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077810 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-19 | 2022-10-22 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 117 | 2022-06-02 | 2022-10-22
C-PW-077820 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077830 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-14 | 2022-06-26 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077840 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-19 | 2022-10-22 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 125 | 2022-04-06 | 2022-09-07
C-PW-077850 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-04-06 | 2022-04-21 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077860 | 2nd Fix Piping System - (Fittings) | 10 | 2022-04-21 | 2022-05-08 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077870 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-29 | 2022-09-07 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
OFFICE BALCONY- NORTH |  | 187 | 2022-03-31 | 2022-11-14
MECHANICAL |  | 186 | 2022-03-31 | 2022-11-13
HVAC SYSTEM WORKS |  | 186 | 2022-03-31 | 2022-11-13
C-PW-077880 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-03-31 | 2022-04-21 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077890 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-04-21 | 2022-05-15 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077900 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-15 | 2022-05-26 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077910 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-03 | 2022-11-13 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 178 | 2022-04-11 | 2022-11-13
C-PW-077920 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-11 | 2022-04-26 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077930 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-04-26 | 2022-05-19 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077940 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-19 | 2022-06-05 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077950 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-03 | 2022-11-13 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077960 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-05 | 2022-11-13 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077970 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-05 | 2022-11-13 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELV |  | 165 | 2022-04-26 | 2022-11-14
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 156 | 2022-04-26 | 2022-11-03
C-PW-077980 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-12 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-077990 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-12 | 2022-05-24 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078000 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-01 | 2022-11-03 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 156 | 2022-04-26 | 2022-11-03
C-PW-078010 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-12 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078020 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-12 | 2022-05-24 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078030 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-01 | 2022-11-03 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 156 | 2022-04-26 | 2022-11-03
C-PW-078040 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-12 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078050 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-12 | 2022-05-24 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078060 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-01 | 2022-11-03 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 156 | 2022-04-28 | 2022-11-06
C-PW-078070 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078080 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-14 | 2022-05-26 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078090 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-03 | 2022-11-06 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 156 | 2022-04-28 | 2022-11-06
C-PW-078100 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078110 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-14 | 2022-05-26 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078120 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-03 | 2022-11-06 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 156 | 2022-05-04 | 2022-11-08
C-PW-078130 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-04 | 2022-05-16 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078140 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-16 | 2022-05-28 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078150 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-05 | 2022-11-08 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 156 | 2022-05-04 | 2022-11-08
C-PW-078160 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-04 | 2022-05-16 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078170 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-16 | 2022-05-28 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078180 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-05 | 2022-11-08 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-08 | 2022-11-14
C-PW-078190 | Active Component System Works | 6 | 2022-11-08 | 2022-11-14 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 160 | 2022-04-21 | 2022-11-03
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 143 | 2022-05-16 | 2022-11-03
C-PW-078200 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-16 | 2022-05-28 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078210 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-09 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078220 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-01 | 2022-11-03 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 143 | 2022-05-16 | 2022-11-03
C-PW-078230 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-16 | 2022-05-28 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078240 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-09 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078250 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-01 | 2022-11-03 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 126 | 2022-04-21 | 2022-09-24
C-PW-078260 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-21 | 2022-05-14 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078270 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-14 | 2022-05-23 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078280 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-14 | 2022-09-24 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
FILE STORAGE, MALL ROOM & MASTER ROOM- NORTH |  | 179 | 2022-04-11 | 2022-11-14
MECHANICAL |  | 166 | 2022-04-21 | 2022-11-10
DRAINAGE WORKS |  | 29 | 2022-04-21 | 2022-05-29
C-PW-078290 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-21 | 2022-05-17 | 01 | 08 | 01 | 46 | 004 | 05 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078300 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-17 | 2022-05-29 | 01 | 08 | 01 | 46 | 004 | 05 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
HVAC SYSTEM WORKS |  | 158 | 2022-05-04 | 2022-11-10
C-PW-078310 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-05-07 | 2022-05-26 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078320 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-05-04 | 2022-05-26 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078330 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-26 | 2022-06-07 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078340 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-01 | 2022-11-10 | 01 | 06 | 01 | 46 | 004 | 05 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-04-27 | 2022-06-04
C-PW-078350 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-27 | 2022-05-22 | 01 | 08 | 01 | 46 | 004 | 05 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078360 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-23 | 2022-06-04 | 01 | 08 | 01 | 46 | 004 | 05 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 176 | 2022-04-11 | 2022-11-12
C-PW-078370 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-11 | 2022-04-26 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078380 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-05-09 | 2022-05-28 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078390 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-28 | 2022-06-13 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078400 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-01 | 2022-11-10 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078410 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-03 | 2022-11-12 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078420 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-03 | 2022-11-12 | 01 | 07 | 01 | 46 | 004 | 05 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELV |  | 174 | 2022-04-17 | 2022-11-14
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 165 | 2022-04-17 | 2022-11-03
C-PW-078430 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-17 | 2022-04-28 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078440 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078450 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-01 | 2022-11-03 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 165 | 2022-04-17 | 2022-11-03
C-PW-078460 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-17 | 2022-04-28 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078470 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078480 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-01 | 2022-11-03 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 165 | 2022-04-17 | 2022-11-03
C-PW-078490 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-17 | 2022-04-28 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078500 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078510 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-01 | 2022-11-03 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 165 | 2022-04-18 | 2022-11-06
C-PW-078520 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078530 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-04 | 2022-05-16 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078540 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-03 | 2022-11-06 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 165 | 2022-04-18 | 2022-11-06
C-PW-078550 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078560 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-04 | 2022-05-16 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078570 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-03 | 2022-11-06 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 165 | 2022-04-20 | 2022-11-08
C-PW-078580 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-20 | 2022-05-05 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078590 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078600 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-05 | 2022-11-08 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 165 | 2022-04-20 | 2022-11-08
C-PW-078610 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-20 | 2022-05-05 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078620 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078630 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-05 | 2022-11-08 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-08 | 2022-11-14
C-PW-078640 | Active Component System Works | 6 | 2022-11-08 | 2022-11-14 | 01 | 10 | 01 | 46 | 004 | 05 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 151 | 2022-05-05 | 2022-11-03
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 151 | 2022-05-05 | 2022-11-03
C-PW-078650 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078660 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-18 | 2022-05-30 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078670 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-01 | 2022-11-03 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 151 | 2022-05-05 | 2022-11-03
C-PW-078680 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078690 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-18 | 2022-05-30 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078700 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-01 | 2022-11-03 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 92 | 2022-05-10 | 2022-08-30
C-PW-078710 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-05-10 | 2022-05-29 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078720 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-29 | 2022-06-07 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-078730 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-21 | 2022-08-30 | 01 | 09 | 01 | 46 | 004 | 05 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Storage / Offices / Admin Areas
IT ROOM- NORTH |  | 167 | 2022-04-26 | 2022-11-17
MECHANICAL |  | 149 | 2022-05-17 | 2022-11-13
HVAC SYSTEM WORKS |  | 136 | 2022-06-01 | 2022-11-13
C-PW-078740 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-06-02 | 2022-06-22 | 01 | 06 | 01 | 46 | 004 | 02 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078750 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-06-01 | 2022-06-22 | 01 | 06 | 01 | 46 | 004 | 02 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078760 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-06-22 | 2022-07-04 | 01 | 06 | 01 | 46 | 004 | 02 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078770 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-03 | 2022-11-13 | 01 | 06 | 01 | 46 | 004 | 02 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 29 | 2022-05-17 | 2022-06-19
C-PW-078780 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-17 | 2022-06-07 | 01 | 08 | 01 | 46 | 004 | 02 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078790 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-07 | 2022-06-19 | 01 | 08 | 01 | 46 | 004 | 02 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 24 | 2022-05-28 | 2022-06-25
C-PW-078800 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-05-28 | 2022-06-13 | 01 | 08 | 01 | 46 | 004 | 02 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078810 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-13 | 2022-06-25 | 01 | 08 | 01 | 46 | 004 | 02 |  | Building | Plumbing | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 167 | 2022-04-26 | 2022-11-17
C-PW-078820 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-26 | 2022-05-16 | 01 | 07 | 01 | 46 | 004 | 02 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078830 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-06-05 | 2022-06-23 | 01 | 07 | 01 | 46 | 004 | 02 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078840 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-25 | 2022-07-13 | 01 | 07 | 01 | 46 | 004 | 02 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078850 | LV Switchgears (DB's) | 5 | 2022-07-13 | 2022-07-19 | 01 | 07 | 01 | 46 | 004 | 02 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078860 | Cable/Wire Termination & Dressing | 7 | 2022-07-19 | 2022-07-27 | 01 | 07 | 01 | 46 | 004 | 02 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078870 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-03 | 2022-11-13 | 01 | 07 | 01 | 46 | 004 | 02 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078880 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-05 | 2022-11-13 | 01 | 07 | 01 | 46 | 004 | 02 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078890 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-07 | 2022-11-15 | 01 | 07 | 01 | 46 | 004 | 02 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078900 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-09 | 2022-11-17 | 01 | 07 | 01 | 46 | 004 | 02 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
ELV |  | 162 | 2022-05-05 | 2022-11-16
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 153 | 2022-05-05 | 2022-11-06
C-PW-078910 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078920 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-18 | 2022-05-30 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078930 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-03 | 2022-11-06 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 153 | 2022-05-05 | 2022-11-06
C-PW-078940 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078950 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-18 | 2022-05-30 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078960 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-03 | 2022-11-06 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
INTERCOM SYSTEM |  | 153 | 2022-05-05 | 2022-11-06
C-PW-078970 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078980 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-18 | 2022-05-30 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-078990 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-03 | 2022-11-06 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
AV SYSTEM |  | 153 | 2022-05-08 | 2022-11-08
C-PW-079000 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-08 | 2022-05-19 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079010 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-19 | 2022-05-31 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079020 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-05 | 2022-11-08 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 153 | 2022-05-08 | 2022-11-08
C-PW-079030 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-08 | 2022-05-19 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079040 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-19 | 2022-05-31 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079050 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-05 | 2022-11-08 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 153 | 2022-05-09 | 2022-11-09
C-PW-079060 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-09 | 2022-05-22 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079070 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079080 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-07 | 2022-11-09 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 153 | 2022-05-09 | 2022-11-09
C-PW-079090 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-09 | 2022-05-22 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079100 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079110 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-07 | 2022-11-09 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-09 | 2022-11-16
C-PW-079120 | Active Component System Works | 6 | 2022-11-09 | 2022-11-16 | 01 | 10 | 01 | 46 | 004 | 02 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 140 | 2022-05-22 | 2022-11-07
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 139 | 2022-05-22 | 2022-11-06
C-PW-079130 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-22 | 2022-06-02 | 01 | 09 | 01 | 46 | 004 | 02 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079140 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-02 | 2022-06-14 | 01 | 09 | 01 | 46 | 004 | 02 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079150 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-03 | 2022-11-06 | 01 | 09 | 01 | 46 | 004 | 02 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 139 | 2022-05-22 | 2022-11-06
C-PW-079160 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-22 | 2022-06-02 | 01 | 09 | 01 | 46 | 004 | 02 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079170 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-02 | 2022-06-14 | 01 | 09 | 01 | 46 | 004 | 02 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079180 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-03 | 2022-11-06 | 01 | 09 | 01 | 46 | 004 | 02 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 127 | 2022-06-06 | 2022-11-07
C-PW-079190 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-06 | 2022-06-25 | 01 | 09 | 01 | 46 | 004 | 02 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079200 | 2nd Fix Piping System - (Fittings) | 8 | 2022-06-25 | 2022-07-04 | 01 | 09 | 01 | 46 | 004 | 02 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
C-PW-079210 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 3 | 2022-11-03 | 2022-11-07 | 01 | 09 | 01 | 46 | 004 | 02 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | MEP / Service Rooms
STAFF MALE AND FEMALE WC'S, FEMALE ABLUTIONS & PRAYER ROOM - NORTH |  | 139 | 2022-05-16 | 2022-10-30
MECHANICAL |  | 116 | 2022-06-07 | 2022-10-26
HVAC SYSTEM WORKS |  | 108 | 2022-06-16 | 2022-10-26
C-PW-079220 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-06-19 | 2022-07-07 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079230 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-06-16 | 2022-07-07 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079240 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-07-09 | 2022-07-24 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079250 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-17 | 2022-10-26 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
DRAINAGE WORKS |  | 113 | 2022-06-07 | 2022-10-23
C-PW-079260 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-07 | 2022-06-28 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079270 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-29 | 2022-07-14 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079280 | Final Fix (Installation of Sanitaryware & Accessories) | 5 | 2022-10-17 | 2022-10-23 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
HOT & COLD WATER SYSTEM |  | 28 | 2022-06-13 | 2022-07-19
C-PW-079290 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-13 | 2022-07-04 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079300 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-06-29 | 2022-07-16 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079310 | Final Fix - Water Meter Installation | 3 | 2022-07-16 | 2022-07-19 | 01 | 06 | 01 | 46 | 004 | 03 |  | Building | HVAC | Museum | North West | L01 Mezzanine Level | Wet Areas
ELECTRICAL WORKS |  | 139 | 2022-05-16 | 2022-10-30
C-PW-079320 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-05-16 | 2022-05-31 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079330 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-06-20 | 2022-07-13 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079340 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-13 | 2022-07-31 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079350 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-17 | 2022-10-26 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079360 | Final Fix Electrical (Light Fixtures) | 10 | 2022-10-19 | 2022-10-30 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079370 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-10-19 | 2022-10-30 | 01 | 07 | 01 | 46 | 004 | 03 |  | Building | Electrical | Museum | North West | L01 Mezzanine Level | Wet Areas
ELV |  | 125 | 2022-05-22 | 2022-10-20
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 125 | 2022-05-22 | 2022-10-20
C-PW-079380 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079390 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-13 | 2022-07-25 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079400 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-20 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
AV SYSTEM |  | 123 | 2022-05-23 | 2022-10-20
C-PW-079410 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-23 | 2022-06-05 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079420 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-05 | 2022-06-16 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079430 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-20 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
DATA AND TELECOMMUNICATION |  | 122 | 2022-05-25 | 2022-10-20
C-PW-079440 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079450 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-06 | 2022-06-19 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079460 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-20 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 120 | 2022-05-28 | 2022-10-20
C-PW-079470 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-28 | 2022-06-08 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079480 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079490 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-20 | 01 | 10 | 01 | 46 | 004 | 03 |  | Building | CCTV | Museum | North West | L01 Mezzanine Level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 119 | 2022-05-29 | 2022-10-20
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 119 | 2022-05-29 | 2022-10-20
C-PW-079500 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-29 | 2022-06-09 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079510 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-11 | 2022-06-22 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079520 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-20 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 119 | 2022-05-29 | 2022-10-20
C-PW-079530 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-29 | 2022-06-09 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079540 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-11 | 2022-06-22 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079550 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-20 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
FIRE FIGHTING WORKS |  | 87 | 2022-06-13 | 2022-09-27
C-PW-079560 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-13 | 2022-07-02 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079570 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-02 | 2022-07-14 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
C-PW-079580 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-18 | 2022-09-27 | 01 | 09 | 01 | 46 | 004 | 03 |  | Building | Firefighting | Museum | North West | L01 Mezzanine Level | Wet Areas
NORTH EAST |  | 211 | 2022-03-22 | 2022-12-03
CIRCULATIONS & CORRIDORS- NORTH |  | 167 | 2022-05-16 | 2022-12-03
MECHANICAL |  | 143 | 2022-06-07 | 2022-11-27
HVAC SYSTEM WORKS |  | 131 | 2022-06-22 | 2022-11-27
C-PW-079590 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 9 | 2022-06-22 | 2022-07-03 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079600 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 9 | 2022-06-25 | 2022-07-04 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079610 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-07-04 | 2022-07-17 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079620 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-19 | 2022-11-27 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
DRAINAGE WORKS |  | 16 | 2022-06-07 | 2022-06-26
C-PW-079630 | 1st Fix Piping System (Supports, Piping) | 8 | 2022-06-07 | 2022-06-16 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079640 | 2nd Fix Piping System (Fittings, Insulation) | 8 | 2022-06-16 | 2022-06-26 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 18 | 2022-06-13 | 2022-07-04
C-PW-079650 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-06-13 | 2022-06-25 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079660 | 2nd Fix Piping System (Fittings, Insulation) | 8 | 2022-06-25 | 2022-07-04 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 167 | 2022-05-16 | 2022-12-03
C-PW-079670 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-05-16 | 2022-05-25 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079680 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-06-26 | 2022-07-07 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079690 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-07-09 | 2022-07-24 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079700 | LV Switchgears (DB's) | 5 | 2022-07-24 | 2022-07-31 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079710 | Cable/Wire Termination & Dressing | 7 | 2022-07-31 | 2022-08-08 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079720 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-19 | 2022-11-27 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079730 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-20 | 2022-11-28 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079740 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-22 | 2022-12-01 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079750 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-23 | 2022-12-03 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ELV |  | 159 | 2022-05-21 | 2022-11-27
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 14 | 2022-05-21 | 2022-06-05
C-PW-079760 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 6 | 2022-05-21 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079770 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 6 | 2022-05-28 | 2022-06-02 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079780 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-06-02 | 2022-06-05 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 150 | 2022-05-21 | 2022-11-17
C-PW-079790 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 6 | 2022-05-21 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079800 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 6 | 2022-05-28 | 2022-06-02 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079810 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-14 | 2022-11-17 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 150 | 2022-05-21 | 2022-11-17
C-PW-079820 | 1st Fix Intercom System Works (Conduits & Boxes) | 6 | 2022-05-21 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079830 | 2nd Fix Intercom System Works (Wiring) | 6 | 2022-05-28 | 2022-06-02 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079840 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-14 | 2022-11-17 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
AV SYSTEM |  | 150 | 2022-05-23 | 2022-11-19
C-PW-079850 | 1st Fix AV System Works (Conduits & Boxes) | 6 | 2022-05-23 | 2022-05-29 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079860 | 2nd Fix AV System Works (Wiring) | 6 | 2022-05-29 | 2022-06-05 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079870 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-16 | 2022-11-19 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 150 | 2022-05-23 | 2022-11-19
C-PW-079880 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 6 | 2022-05-23 | 2022-05-29 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079890 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 6 | 2022-05-29 | 2022-06-05 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079900 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-16 | 2022-11-19 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 150 | 2022-05-24 | 2022-11-21
C-PW-079910 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 6 | 2022-05-24 | 2022-05-31 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079920 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 6 | 2022-05-31 | 2022-06-06 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079930 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-19 | 2022-11-21 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 150 | 2022-05-24 | 2022-11-21
C-PW-079940 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 6 | 2022-05-24 | 2022-05-31 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079950 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 6 | 2022-05-31 | 2022-06-06 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079960 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-19 | 2022-11-21 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-21 | 2022-11-27
C-PW-079970 | Active Component System Works | 6 | 2022-11-21 | 2022-11-27 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 127 | 2022-05-31 | 2022-10-31
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 122 | 2022-05-31 | 2022-10-25
C-PW-079980 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 6 | 2022-05-31 | 2022-06-06 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-079990 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 6 | 2022-06-06 | 2022-06-13 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080000 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-25 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 122 | 2022-05-31 | 2022-10-25
C-PW-080010 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 6 | 2022-05-31 | 2022-06-06 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080020 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 6 | 2022-06-06 | 2022-06-13 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080030 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-25 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 103 | 2022-06-28 | 2022-10-31
C-PW-080040 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 10 | 2022-06-28 | 2022-07-13 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080050 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-07-13 | 2022-07-23 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080060 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 7 | 2022-10-23 | 2022-10-31 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
PUBLIC MALE & FEMALE WC - EAST |  | 162 | 2022-03-22 | 2022-10-05
MECHANICAL |  | 162 | 2022-03-22 | 2022-10-05
HVAC SYSTEM WORKS |  | 151 | 2022-03-31 | 2022-10-02
C-PW-080070 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 13 | 2022-04-02 | 2022-04-17 | 01 | 06 | 01 | 44 | 004 | 03 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080080 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-03-31 | 2022-04-21 | 01 | 06 | 01 | 44 | 004 | 03 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080090 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-04-17 | 2022-04-28 | 01 | 06 | 01 | 44 | 004 | 03 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080100 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-22 | 2022-10-02 | 01 | 06 | 01 | 44 | 004 | 03 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Wet Areas
DRAINAGE WORKS |  | 156 | 2022-03-22 | 2022-09-27
C-PW-080110 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-22 | 2022-04-12 | 01 | 08 | 01 | 44 | 004 | 03 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080120 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-12 | 2022-04-24 | 01 | 08 | 01 | 44 | 004 | 03 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080130 | Final Fix (Installation of Sanitaryware & Accessories) | 5 | 2022-09-22 | 2022-09-27 | 01 | 08 | 01 | 44 | 004 | 03 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Wet Areas
HOT & COLD WATER SYSTEM |  | 158 | 2022-03-27 | 2022-10-05
C-PW-080140 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-27 | 2022-04-18 | 01 | 08 | 01 | 44 | 004 | 03 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080150 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-04-18 | 2022-04-30 | 01 | 08 | 01 | 44 | 004 | 03 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080160 | Final Fix - Water Meter Installation | 3 | 2022-10-02 | 2022-10-05 | 01 | 08 | 01 | 44 | 004 | 03 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Wet Areas
ELECTRICAL WORKS |  | 160 | 2022-03-22 | 2022-10-02
C-PW-080170 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-03-22 | 2022-04-06 | 01 | 07 | 01 | 44 | 004 | 03 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080180 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-04-04 | 2022-04-23 | 01 | 07 | 01 | 44 | 004 | 03 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080190 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-04-24 | 2022-05-12 | 01 | 07 | 01 | 44 | 004 | 03 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080200 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-22 | 2022-10-02 | 01 | 07 | 01 | 44 | 004 | 03 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080210 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-24 | 2022-10-02 | 01 | 07 | 01 | 44 | 004 | 03 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080220 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-24 | 2022-10-02 | 01 | 07 | 01 | 44 | 004 | 03 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Wet Areas
ELV |  | 126 | 2022-04-26 | 2022-09-27
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 124 | 2022-04-26 | 2022-09-25
C-PW-080230 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080240 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080250 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-22 | 2022-09-25 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
AV SYSTEM |  | 124 | 2022-04-27 | 2022-09-27
C-PW-080260 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080270 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080280 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
DATA AND TELECOMMUNICATION |  | 123 | 2022-04-30 | 2022-09-27
C-PW-080290 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080300 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080310 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 121 | 2022-05-04 | 2022-09-27
C-PW-080320 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-04 | 2022-05-17 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080330 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-17 | 2022-05-29 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080340 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 44 | 004 | 03 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 146 | 2022-03-30 | 2022-09-25
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 117 | 2022-05-07 | 2022-09-25
C-PW-080350 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-07 | 2022-05-18 | 01 | 09 | 01 | 44 | 004 | 03 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080360 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-18 | 2022-05-31 | 01 | 09 | 01 | 44 | 004 | 03 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080370 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-22 | 2022-09-25 | 01 | 09 | 01 | 44 | 004 | 03 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 117 | 2022-05-07 | 2022-09-25
C-PW-080380 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-07 | 2022-05-18 | 01 | 09 | 01 | 44 | 004 | 03 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080390 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-18 | 2022-05-31 | 01 | 09 | 01 | 44 | 004 | 03 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080400 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-22 | 2022-09-25 | 01 | 09 | 01 | 44 | 004 | 03 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Wet Areas
FIRE FIGHTING WORKS |  | 121 | 2022-03-30 | 2022-08-25
C-PW-080410 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-03-30 | 2022-04-18 | 01 | 09 | 01 | 44 | 004 | 03 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080420 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-18 | 2022-04-27 | 01 | 09 | 01 | 44 | 004 | 03 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Wet Areas
C-PW-080430 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-17 | 2022-08-25 | 01 | 09 | 01 | 44 | 004 | 03 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Wet Areas
FALCONRY CLASSROOMS - EAST |  | 148 | 2022-04-06 | 2022-10-04
MECHANICAL |  | 142 | 2022-04-12 | 2022-10-03
HVAC SYSTEM WORKS |  | 134 | 2022-04-21 | 2022-10-03
C-PW-080440 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-04-24 | 2022-05-16 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080450 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-04-21 | 2022-05-16 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080460 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-16 | 2022-05-29 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080470 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-24 | 2022-10-03 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-04-12 | 2022-05-19
C-PW-080480 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-12 | 2022-05-07 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080490 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-07 | 2022-05-19 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-04-18 | 2022-05-24
C-PW-080500 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-18 | 2022-05-12 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080510 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-12 | 2022-05-24 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 148 | 2022-04-06 | 2022-10-04
C-PW-080520 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-06 | 2022-04-23 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080530 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-04-25 | 2022-05-18 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080540 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-18 | 2022-06-02 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080550 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-24 | 2022-10-03 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080560 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-26 | 2022-10-04 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080570 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-26 | 2022-10-04 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ELV |  | 32 | 2022-04-26 | 2022-06-05
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-04-26 | 2022-05-26
C-PW-080580 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080590 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080600 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-05-23 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-04-26 | 2022-05-26
C-PW-080610 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080620 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080630 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-05-23 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 23 | 2022-04-26 | 2022-05-26
C-PW-080640 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080650 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080660 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-05-23 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
AV SYSTEM |  | 23 | 2022-04-27 | 2022-05-28
C-PW-080670 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080680 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080690 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-05-25 | 2022-05-28 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-04-27 | 2022-05-28
C-PW-080700 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080710 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080720 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-05-25 | 2022-05-28 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 23 | 2022-04-30 | 2022-05-30
C-PW-080730 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080740 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080750 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-05-28 | 2022-05-30 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-04-30 | 2022-05-30
C-PW-080760 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080770 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080780 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-05-28 | 2022-05-30 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-05-30 | 2022-06-05
C-PW-080790 | Active Component System Works | 6 | 2022-05-30 | 2022-06-05 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 90 | 2022-04-20 | 2022-08-11
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 66 | 2022-05-15 | 2022-08-04
C-PW-080800 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080810 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080820 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-02 | 2022-08-04 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 66 | 2022-05-15 | 2022-08-04
C-PW-080830 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080840 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080850 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-02 | 2022-08-04 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 90 | 2022-04-20 | 2022-08-11
C-PW-080860 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-20 | 2022-05-12 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080870 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-16 | 2022-05-25 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-080880 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-02 | 2022-08-11 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
FALCONRY OFFICE, MEETING ROOM & BALCONY - EAST |  | 194 | 2022-03-22 | 2022-11-13
MECHANICAL |  | 189 | 2022-03-22 | 2022-11-06
HVAC SYSTEM WORKS |  | 173 | 2022-04-10 | 2022-11-06
C-PW-080890 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 14 | 2022-04-10 | 2022-04-25 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-080900 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 14 | 2022-04-11 | 2022-04-27 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-080910 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-04-27 | 2022-05-12 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-080920 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-27 | 2022-11-06 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 29 | 2022-03-22 | 2022-04-24
C-PW-080930 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-22 | 2022-04-12 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-080940 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-12 | 2022-04-24 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-03-27 | 2022-04-30
C-PW-080950 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-27 | 2022-04-18 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-080960 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-18 | 2022-04-30 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 194 | 2022-03-22 | 2022-11-13
C-PW-080970 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-03-22 | 2022-04-03 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-080980 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-04-14 | 2022-05-04 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-080990 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-04 | 2022-05-19 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081000 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-27 | 2022-11-06 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081010 | Final Fix Electrical (Light Fixtures) | 12 | 2022-10-30 | 2022-11-13 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081020 | Final Fix Electrical (Installation of Lighting Control Devices) | 12 | 2022-10-30 | 2022-11-13 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELV |  | 157 | 2022-04-26 | 2022-11-03
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 148 | 2022-04-26 | 2022-10-25
C-PW-081030 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081040 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081050 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-25 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 148 | 2022-04-26 | 2022-10-25
C-PW-081060 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081070 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081080 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-25 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 148 | 2022-04-26 | 2022-10-25
C-PW-081090 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081100 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081110 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-25 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 121 | 2022-06-02 | 2022-10-26
C-PW-081120 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081130 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081140 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-24 | 2022-10-26 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 121 | 2022-06-02 | 2022-10-26
C-PW-081150 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081160 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081170 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-24 | 2022-10-26 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 121 | 2022-06-04 | 2022-10-29
C-PW-081180 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-04 | 2022-06-15 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081190 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-16 | 2022-06-28 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081200 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-26 | 2022-10-29 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 121 | 2022-06-04 | 2022-10-29
C-PW-081210 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-04 | 2022-06-15 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081220 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-16 | 2022-06-28 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081230 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-26 | 2022-10-29 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-29 | 2022-11-03
C-PW-081240 | Active Component System Works | 6 | 2022-10-29 | 2022-11-03 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 169 | 2022-04-02 | 2022-10-25
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 107 | 2022-06-16 | 2022-10-25
C-PW-081250 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-16 | 2022-06-28 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081260 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-28 | 2022-07-13 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081270 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-25 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 107 | 2022-06-16 | 2022-10-25
C-PW-081280 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-16 | 2022-06-28 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081290 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-28 | 2022-07-13 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081300 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-25 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 137 | 2022-04-02 | 2022-09-17
C-PW-081310 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-04-02 | 2022-04-18 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081320 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-18 | 2022-04-27 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081330 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-08 | 2022-09-17 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FALCONRY OFFICE IT ROOM - EAST |  | 191 | 2022-03-26 | 2022-11-13
MECHANICAL |  | 187 | 2022-03-26 | 2022-11-08
HVAC SYSTEM WORKS |  | 179 | 2022-04-04 | 2022-11-08
C-PW-081340 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-04-05 | 2022-04-25 | 01 | 06 | 01 | 44 | 004 | 02 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081350 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-04-04 | 2022-04-25 | 01 | 06 | 01 | 44 | 004 | 02 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081360 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-04-25 | 2022-05-10 | 01 | 06 | 01 | 44 | 004 | 02 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081370 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-30 | 2022-11-08 | 01 | 06 | 01 | 44 | 004 | 02 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 29 | 2022-03-26 | 2022-04-27
C-PW-081380 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-26 | 2022-04-16 | 01 | 08 | 01 | 44 | 004 | 02 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081390 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-16 | 2022-04-27 | 01 | 08 | 01 | 44 | 004 | 02 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 29 | 2022-03-31 | 2022-05-07
C-PW-081400 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-31 | 2022-04-21 | 01 | 08 | 01 | 44 | 004 | 02 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081410 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-21 | 2022-05-07 | 01 | 08 | 01 | 44 | 004 | 02 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 184 | 2022-04-03 | 2022-11-13
C-PW-081420 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-03 | 2022-04-18 | 01 | 07 | 01 | 44 | 004 | 02 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081430 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-04-07 | 2022-04-27 | 01 | 07 | 01 | 44 | 004 | 02 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081440 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-04-27 | 2022-05-16 | 01 | 07 | 01 | 44 | 004 | 02 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081450 | LV Switchgears (DB's) | 5 | 2022-05-16 | 2022-05-22 | 01 | 07 | 01 | 44 | 004 | 02 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081460 | Cable/Wire Termination & Dressing | 7 | 2022-05-22 | 2022-05-30 | 01 | 07 | 01 | 44 | 004 | 02 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081470 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-30 | 2022-11-08 | 01 | 07 | 01 | 44 | 004 | 02 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081480 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-31 | 2022-11-08 | 01 | 07 | 01 | 44 | 004 | 02 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081490 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-02 | 2022-11-10 | 01 | 07 | 01 | 44 | 004 | 02 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081500 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-05 | 2022-11-13 | 01 | 07 | 01 | 44 | 004 | 02 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
ELV |  | 162 | 2022-04-26 | 2022-11-09
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 153 | 2022-04-26 | 2022-10-30
C-PW-081510 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081520 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081530 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-27 | 2022-10-30 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 153 | 2022-04-26 | 2022-10-30
C-PW-081540 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081550 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081560 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-27 | 2022-10-30 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
INTERCOM SYSTEM |  | 153 | 2022-04-26 | 2022-10-30
C-PW-081570 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081580 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081590 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-27 | 2022-10-30 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
AV SYSTEM |  | 153 | 2022-04-27 | 2022-11-01
C-PW-081600 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081610 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081620 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 153 | 2022-04-27 | 2022-11-01
C-PW-081630 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081640 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081650 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 153 | 2022-04-30 | 2022-11-03
C-PW-081660 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081670 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081680 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 153 | 2022-04-30 | 2022-11-03
C-PW-081690 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081700 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081710 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-03 | 2022-11-09
C-PW-081720 | Active Component System Works | 6 | 2022-11-03 | 2022-11-09 | 01 | 10 | 01 | 44 | 004 | 02 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 173 | 2022-04-03 | 2022-10-30
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 139 | 2022-05-15 | 2022-10-30
C-PW-081730 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 44 | 004 | 02 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081740 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 09 | 01 | 44 | 004 | 02 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081750 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-27 | 2022-10-30 | 01 | 09 | 01 | 44 | 004 | 02 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 139 | 2022-05-15 | 2022-10-30
C-PW-081760 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 44 | 004 | 02 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081770 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 09 | 01 | 44 | 004 | 02 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081780 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-27 | 2022-10-30 | 01 | 09 | 01 | 44 | 004 | 02 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 105 | 2022-04-03 | 2022-08-11
C-PW-081790 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-03 | 2022-04-21 | 01 | 09 | 01 | 44 | 004 | 02 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081800 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-21 | 2022-05-04 | 01 | 09 | 01 | 44 | 004 | 02 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-081810 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-02 | 2022-08-11 | 01 | 09 | 01 | 44 | 004 | 02 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | MEP / Service Rooms
FALCONRY STORAGES & FALCONRY OFFICE SUPPLIES - EAST |  | 176 | 2022-04-16 | 2022-11-16
MECHANICAL |  | 172 | 2022-04-16 | 2022-11-12
HVAC SYSTEM WORKS |  | 164 | 2022-04-25 | 2022-11-12
C-PW-081820 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-04-27 | 2022-05-19 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081830 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-04-25 | 2022-05-19 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081840 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 14 | 2022-05-21 | 2022-06-05 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081850 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-02 | 2022-11-12 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 32 | 2022-04-16 | 2022-05-26
C-PW-081860 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-16 | 2022-05-10 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081870 | 2nd Fix Piping System (Fittings, Insulation) | 14 | 2022-05-11 | 2022-05-26 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 32 | 2022-04-21 | 2022-06-01
C-PW-081880 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-21 | 2022-05-16 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081890 | 2nd Fix Piping System (Fittings, Insulation) | 14 | 2022-05-16 | 2022-06-01 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 173 | 2022-04-19 | 2022-11-16
C-PW-081900 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-19 | 2022-05-08 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081910 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-04-28 | 2022-05-22 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081920 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-22 | 2022-06-07 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081930 | LV Switchgears (DB's) | 5 | 2022-06-07 | 2022-06-12 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081940 | Cable/Wire Termination & Dressing | 7 | 2022-06-13 | 2022-06-21 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081950 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-02 | 2022-11-12 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081960 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-05 | 2022-11-13 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081970 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-06 | 2022-11-14 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-081980 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-08 | 2022-11-16 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELV |  | 163 | 2022-04-26 | 2022-11-12
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 155 | 2022-04-26 | 2022-11-01
C-PW-081990 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082000 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082010 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 155 | 2022-04-26 | 2022-11-01
C-PW-082020 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082030 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082040 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 155 | 2022-04-26 | 2022-11-01
C-PW-082050 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082060 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082070 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 155 | 2022-04-27 | 2022-11-03
C-PW-082080 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082090 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082100 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 155 | 2022-04-27 | 2022-11-03
C-PW-082110 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082120 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082130 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 155 | 2022-04-30 | 2022-11-05
C-PW-082140 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082150 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082160 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-02 | 2022-11-05 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 155 | 2022-04-30 | 2022-11-05
C-PW-082170 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082180 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082190 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-02 | 2022-11-05 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-05 | 2022-11-12
C-PW-082200 | Active Component System Works | 6 | 2022-11-05 | 2022-11-12 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 156 | 2022-04-24 | 2022-11-01
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 141 | 2022-05-15 | 2022-11-01
C-PW-082210 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082220 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082230 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 141 | 2022-05-15 | 2022-11-01
C-PW-082240 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082250 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082260 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 88 | 2022-04-24 | 2022-08-13
C-PW-082270 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-24 | 2022-05-16 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082280 | 2nd Fix Piping System - (Fittings) | 12 | 2022-05-16 | 2022-05-30 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082290 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-03 | 2022-08-13 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FALCONRY OUTDOOR SHELTERS - EAST |  | 128 | 2022-04-03 | 2022-09-07
MECHANICAL |  | 113 | 2022-04-12 | 2022-08-30
HVAC SYSTEM WORKS |  | 105 | 2022-04-21 | 2022-08-30
C-PW-082300 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-04-24 | 2022-05-16 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082310 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-04-21 | 2022-05-16 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082320 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-16 | 2022-05-29 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082330 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 5 | 2022-08-24 | 2022-08-30 | 01 | 06 | 01 | 44 | 004 | 05 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 29 | 2022-04-12 | 2022-05-19
C-PW-082340 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-12 | 2022-05-07 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082350 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-07 | 2022-05-19 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-04-18 | 2022-05-24
C-PW-082360 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-18 | 2022-05-12 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082370 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-12 | 2022-05-24 | 01 | 08 | 01 | 44 | 004 | 05 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 128 | 2022-04-03 | 2022-09-07
C-PW-082380 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-03 | 2022-04-18 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082390 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-04-25 | 2022-05-18 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082400 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-18 | 2022-06-02 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082410 | LV Switchgears (DB's) | 5 | 2022-06-04 | 2022-06-08 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082420 | Cable/Wire Termination & Dressing | 7 | 2022-06-08 | 2022-06-16 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082430 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-08-24 | 2022-08-30 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082440 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-27 | 2022-09-04 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082450 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-28 | 2022-09-05 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082460 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-30 | 2022-09-07 | 01 | 07 | 01 | 44 | 004 | 05 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELV |  | 106 | 2022-04-26 | 2022-09-04
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 95 | 2022-04-26 | 2022-08-22
C-PW-082470 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082480 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082490 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-20 | 2022-08-22 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 95 | 2022-04-26 | 2022-08-22
C-PW-082500 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082510 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082520 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-20 | 2022-08-22 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 97 | 2022-04-26 | 2022-08-25
C-PW-082530 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082540 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082550 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-22 | 2022-08-25 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 97 | 2022-04-27 | 2022-08-27
C-PW-082560 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082570 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082580 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-24 | 2022-08-27 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 97 | 2022-04-27 | 2022-08-27
C-PW-082590 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082600 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082610 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-24 | 2022-08-27 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 97 | 2022-04-30 | 2022-08-29
C-PW-082620 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082630 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082640 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-27 | 2022-08-29 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 97 | 2022-04-30 | 2022-08-29
C-PW-082650 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082660 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-15 | 2022-05-26 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082670 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-27 | 2022-08-29 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-08-29 | 2022-09-04
C-PW-082680 | Active Component System Works | 6 | 2022-08-29 | 2022-09-04 | 01 | 10 | 01 | 44 | 004 | 05 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 99 | 2022-04-20 | 2022-08-22
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 81 | 2022-05-15 | 2022-08-22
C-PW-082690 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082700 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082710 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-20 | 2022-08-22 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 81 | 2022-05-15 | 2022-08-22
C-PW-082720 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-26 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082730 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082740 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-20 | 2022-08-22 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 82 | 2022-04-20 | 2022-08-02
C-PW-082750 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-20 | 2022-05-12 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082760 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-12 | 2022-05-22 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-082770 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-07-27 | 2022-08-02 | 01 | 09 | 01 | 44 | 004 | 05 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Storage / Offices / Admin Areas
MALE & FEMALE CHANGING ROOM - EAST |  | 157 | 2022-04-19 | 2022-10-29
MECHANICAL |  | 156 | 2022-04-19 | 2022-10-27
HVAC SYSTEM WORKS |  | 148 | 2022-04-28 | 2022-10-27
C-PW-082780 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 13 | 2022-05-04 | 2022-05-19 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082790 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-04-28 | 2022-05-24 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082800 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-19 | 2022-05-31 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082810 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-18 | 2022-10-27 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-04-19 | 2022-05-26
C-PW-082820 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-19 | 2022-05-15 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082830 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-15 | 2022-05-26 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 32 | 2022-04-25 | 2022-06-05
C-PW-082840 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-25 | 2022-05-19 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082850 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-05-21 | 2022-06-01 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082860 | Final Fix - Water Meter Installation | 3 | 2022-06-01 | 2022-06-05 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 144 | 2022-05-08 | 2022-10-29
C-PW-082870 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-05-08 | 2022-05-24 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082880 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-05-10 | 2022-05-29 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082890 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-30 | 2022-06-14 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082900 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-18 | 2022-10-27 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082910 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-20 | 2022-10-29 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082920 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-20 | 2022-10-29 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ELV |  | 135 | 2022-05-14 | 2022-10-24
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 133 | 2022-05-14 | 2022-10-22
C-PW-082930 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082940 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-25 | 2022-06-07 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082950 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-18 | 2022-10-22 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
AV SYSTEM |  | 131 | 2022-05-16 | 2022-10-22
C-PW-082960 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-16 | 2022-05-28 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082970 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-082980 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-18 | 2022-10-22 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 130 | 2022-05-17 | 2022-10-22
C-PW-082990 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-17 | 2022-05-29 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083000 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-30 | 2022-06-11 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083010 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-18 | 2022-10-22 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 130 | 2022-05-19 | 2022-10-24
C-PW-083020 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-19 | 2022-05-31 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083030 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-31 | 2022-06-12 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083040 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-22 | 2022-10-24 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 146 | 2022-04-25 | 2022-10-22
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 126 | 2022-05-21 | 2022-10-22
C-PW-083050 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-21 | 2022-06-02 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083060 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-02 | 2022-06-14 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083070 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-18 | 2022-10-22 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 126 | 2022-05-21 | 2022-10-22
C-PW-083080 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-21 | 2022-06-02 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083090 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-02 | 2022-06-14 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083100 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-18 | 2022-10-22 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 122 | 2022-04-25 | 2022-09-22
C-PW-083110 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-25 | 2022-05-17 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083120 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-17 | 2022-05-26 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083130 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-13 | 2022-09-22 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
LOBBY & CIRCULATIONS - EAST |  | 144 | 2022-04-24 | 2022-10-17
MECHANICAL |  | 140 | 2022-04-24 | 2022-10-12
HVAC SYSTEM WORKS |  | 132 | 2022-05-07 | 2022-10-12
C-PW-083140 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 17 | 2022-05-08 | 2022-05-28 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083150 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 18 | 2022-05-07 | 2022-05-28 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083160 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-28 | 2022-06-08 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083170 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-03 | 2022-10-12 | 01 | 06 | 01 | 44 | 004 | 01 |  | Building | HVAC | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-04-24 | 2022-05-30
C-PW-083180 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-24 | 2022-05-18 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083190 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-18 | 2022-05-30 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-04-28 | 2022-06-05
C-PW-083200 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-28 | 2022-05-24 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083210 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-24 | 2022-06-05 | 01 | 08 | 01 | 44 | 004 | 01 |  | Building | Plumbing | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 121 | 2022-05-24 | 2022-10-17
C-PW-083220 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-05-24 | 2022-06-08 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083230 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-05-25 | 2022-06-14 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083240 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-14 | 2022-06-30 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083250 | LV Switchgears (DB's) | 5 | 2022-06-30 | 2022-07-05 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083260 | Cable/Wire Termination & Dressing | 7 | 2022-07-06 | 2022-07-18 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083270 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-03 | 2022-10-12 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083280 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-04 | 2022-10-13 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083290 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-10-06 | 2022-10-16 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083300 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-08 | 2022-10-17 | 01 | 07 | 01 | 44 | 004 | 01 |  | Building | Electrical | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ELV |  | 110 | 2022-05-30 | 2022-10-11
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 102 | 2022-05-30 | 2022-09-29
C-PW-083310 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-30 | 2022-06-11 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083320 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083330 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-09-29 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 102 | 2022-05-30 | 2022-09-29
C-PW-083340 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-05-30 | 2022-06-11 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083350 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083360 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-09-29 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 102 | 2022-05-30 | 2022-09-29
C-PW-083370 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-05-30 | 2022-06-11 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083380 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083390 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-09-29 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
AV SYSTEM |  | 102 | 2022-05-31 | 2022-10-02
C-PW-083400 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-31 | 2022-06-12 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083410 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-13 | 2022-06-25 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083420 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 102 | 2022-05-31 | 2022-10-02
C-PW-083430 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-31 | 2022-06-12 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083440 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-13 | 2022-06-25 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083450 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 102 | 2022-06-02 | 2022-10-03
C-PW-083460 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083470 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083480 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-01 | 2022-10-03 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 102 | 2022-06-02 | 2022-10-03
C-PW-083490 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083500 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083510 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-01 | 2022-10-03 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-03 | 2022-10-11
C-PW-083520 | Active Component System Works | 6 | 2022-10-03 | 2022-10-11 | 01 | 10 | 01 | 44 | 004 | 01 |  | Building | CCTV | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 122 | 2022-05-05 | 2022-09-29
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 88 | 2022-06-14 | 2022-09-29
C-PW-083530 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-26 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083540 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-27 | 2022-07-09 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083550 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-09-29 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 88 | 2022-06-14 | 2022-09-29
C-PW-083560 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-26 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083570 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-27 | 2022-07-09 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083580 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-09-29 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 102 | 2022-05-05 | 2022-09-06
C-PW-083590 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-05-05 | 2022-05-24 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083600 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-05-24 | 2022-06-02 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083610 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 8 | 2022-08-28 | 2022-09-06 | 01 | 09 | 01 | 44 | 004 | 01 |  | Building | Firefighting | Museum | North East | L01 Mezzanine Level | Circulation / Common Areas
SOUTH EAST |  | 286 | 2022-01-13 | 2022-12-24
SCHOOL ARRIVAL, CLASS ROOMS & LUNCH ROOM - SOUTH |  | 223 | 2022-01-13 | 2022-10-08
MECHANICAL |  | 220 | 2022-01-13 | 2022-10-04
HVAC SYSTEM WORKS |  | 107 | 2022-05-28 | 2022-10-04
C-PW-083620 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-05-30 | 2022-06-18 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083630 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-05-28 | 2022-06-18 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083640 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-06-18 | 2022-06-30 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083650 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-25 | 2022-10-04 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-01-13 | 2022-02-15
C-PW-083660 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-01-13 | 2022-02-03 | 01 | 08 | 01 | 45 | 004 | 01 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083670 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-02-03 | 2022-02-15 | 01 | 08 | 01 | 45 | 004 | 01 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-05-28 | 2022-06-30
C-PW-083680 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-05-28 | 2022-06-18 | 01 | 08 | 01 | 45 | 004 | 01 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083690 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-18 | 2022-06-30 | 01 | 08 | 01 | 45 | 004 | 01 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 220 | 2022-01-13 | 2022-10-05
C-PW-083700 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-01-13 | 2022-01-29 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083710 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-05-31 | 2022-06-20 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083720 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-20 | 2022-07-05 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083730 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-25 | 2022-10-04 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083740 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-27 | 2022-10-05 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083750 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-27 | 2022-10-05 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
ELV |  | 115 | 2022-05-22 | 2022-10-08
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 107 | 2022-05-22 | 2022-09-27
C-PW-083760 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083770 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-02 | 2022-06-15 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083780 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 107 | 2022-05-22 | 2022-09-27
C-PW-083790 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083800 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-02 | 2022-06-15 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083810 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 107 | 2022-05-22 | 2022-09-27
C-PW-083820 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083830 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-02 | 2022-06-15 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083840 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
AV SYSTEM |  | 107 | 2022-05-24 | 2022-09-29
C-PW-083850 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-24 | 2022-06-05 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083860 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-05 | 2022-06-16 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083870 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-09-29 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 107 | 2022-05-24 | 2022-09-29
C-PW-083880 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-24 | 2022-06-05 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083890 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-05 | 2022-06-16 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083900 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-27 | 2022-09-29 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 107 | 2022-05-25 | 2022-10-02
C-PW-083910 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083920 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083930 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 107 | 2022-05-25 | 2022-10-02
C-PW-083940 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083950 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083960 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-02 | 2022-10-08
C-PW-083970 | Active Component System Works | 6 | 2022-10-02 | 2022-10-08 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 102 | 2022-05-28 | 2022-09-27
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 93 | 2022-06-07 | 2022-09-27
C-PW-083980 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-07 | 2022-06-19 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-083990 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-084000 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 93 | 2022-06-07 | 2022-09-27
C-PW-084010 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-07 | 2022-06-19 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-084020 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-084030 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 83 | 2022-05-28 | 2022-09-06
C-PW-084040 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-05-28 | 2022-06-15 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-084050 | 2nd Fix Piping System - (Fittings) | 8 | 2022-06-15 | 2022-06-25 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-084060 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-08-28 | 2022-09-06 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
STORAGE 2, STORAGE 3 & CLASSROOM STORAGE - SOUTH |  | 126 | 2022-05-16 | 2022-10-16
MECHANICAL |  | 120 | 2022-05-16 | 2022-10-06
HVAC SYSTEM WORKS |  | 112 | 2022-05-25 | 2022-10-06
C-PW-084070 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 9 | 2022-05-25 | 2022-06-04 | 01 | 06 | 01 | 45 | 004 | 05 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084080 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 13 | 2022-05-26 | 2022-06-11 | 01 | 06 | 01 | 45 | 004 | 05 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084090 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-06-11 | 2022-06-20 | 01 | 06 | 01 | 45 | 004 | 05 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084100 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-10-01 | 2022-10-06 | 01 | 06 | 01 | 45 | 004 | 05 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 13 | 2022-05-16 | 2022-05-30
C-PW-084110 | 1st Fix Piping System (Supports, Piping) | 6 | 2022-05-16 | 2022-05-22 | 01 | 08 | 01 | 45 | 004 | 05 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084120 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-05-22 | 2022-05-30 | 01 | 08 | 01 | 45 | 004 | 05 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 13 | 2022-05-22 | 2022-06-05
C-PW-084130 | 1st Fix Piping System (Supports, Piping) | 6 | 2022-05-22 | 2022-05-28 | 01 | 08 | 01 | 45 | 004 | 05 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084140 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-05-28 | 2022-06-05 | 01 | 08 | 01 | 45 | 004 | 05 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 126 | 2022-05-16 | 2022-10-16
C-PW-084150 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-05-16 | 2022-05-24 | 01 | 07 | 01 | 45 | 004 | 05 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084160 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-05-29 | 2022-06-08 | 01 | 07 | 01 | 45 | 004 | 05 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084170 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-06-08 | 2022-06-20 | 01 | 07 | 01 | 45 | 004 | 05 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084180 | LV Switchgears (DB's) | 5 | 2022-06-20 | 2022-06-26 | 01 | 07 | 01 | 45 | 004 | 05 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084190 | Cable/Wire Termination & Dressing | 7 | 2022-06-26 | 2022-07-04 | 01 | 07 | 01 | 45 | 004 | 05 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084200 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-10-01 | 2022-10-06 | 01 | 07 | 01 | 45 | 004 | 05 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084210 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-03 | 2022-10-12 | 01 | 07 | 01 | 45 | 004 | 05 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084220 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-10-04 | 2022-10-13 | 01 | 07 | 01 | 45 | 004 | 05 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084230 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-06 | 2022-10-16 | 01 | 07 | 01 | 45 | 004 | 05 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ELV |  | 115 | 2022-05-22 | 2022-10-08
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 107 | 2022-05-22 | 2022-09-27
C-PW-084240 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084250 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-02 | 2022-06-15 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084260 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 107 | 2022-05-22 | 2022-09-27
C-PW-084270 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084280 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-02 | 2022-06-15 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084290 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 107 | 2022-05-22 | 2022-09-27
C-PW-084300 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084310 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-02 | 2022-06-15 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084320 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
AV SYSTEM |  | 107 | 2022-05-24 | 2022-09-29
C-PW-084330 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-24 | 2022-06-05 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084340 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-05 | 2022-06-16 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084350 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-09-29 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 107 | 2022-05-24 | 2022-09-29
C-PW-084360 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-24 | 2022-06-05 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084370 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-05 | 2022-06-16 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084380 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-27 | 2022-09-29 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 107 | 2022-05-25 | 2022-10-02
C-PW-084390 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084400 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084410 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 107 | 2022-05-25 | 2022-10-02
C-PW-084420 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084430 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084440 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-28 | 2022-10-02 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-02 | 2022-10-08
C-PW-084450 | Active Component System Works | 6 | 2022-10-02 | 2022-10-08 | 01 | 10 | 01 | 45 | 004 | 05 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 107 | 2022-05-22 | 2022-09-27
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 93 | 2022-06-07 | 2022-09-27
C-PW-084460 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-07 | 2022-06-19 | 01 | 09 | 01 | 45 | 004 | 05 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084470 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 09 | 01 | 45 | 004 | 05 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084480 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 09 | 01 | 45 | 004 | 05 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 93 | 2022-06-07 | 2022-09-27
C-PW-084490 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-07 | 2022-06-19 | 01 | 09 | 01 | 45 | 004 | 05 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084500 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 09 | 01 | 45 | 004 | 05 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084510 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-25 | 2022-09-27 | 01 | 09 | 01 | 45 | 004 | 05 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 79 | 2022-05-22 | 2022-08-25
C-PW-084520 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 9 | 2022-05-22 | 2022-05-31 | 01 | 09 | 01 | 45 | 004 | 05 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084530 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-31 | 2022-06-09 | 01 | 09 | 01 | 45 | 004 | 05 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
C-PW-084540 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-08-20 | 2022-08-25 | 01 | 09 | 01 | 45 | 004 | 05 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Storage / Offices / Admin Areas
PUBLIC MALE & FEMALE W/C AND ABLUTION - SOUTH |  | 238 | 2022-01-13 | 2022-10-26
MECHANICAL |  | 238 | 2022-01-13 | 2022-10-26
HVAC SYSTEM WORKS |  | 228 | 2022-01-13 | 2022-10-16
C-PW-084550 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 14 | 2022-01-13 | 2022-01-29 | 01 | 06 | 01 | 45 | 004 | 03 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084560 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-01-15 | 2022-02-03 | 01 | 06 | 01 | 45 | 004 | 03 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084570 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-02-03 | 2022-02-15 | 01 | 06 | 01 | 45 | 004 | 03 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084580 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-10-08 | 2022-10-16 | 01 | 06 | 01 | 45 | 004 | 03 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Wet Areas
DRAINAGE WORKS |  | 130 | 2022-05-22 | 2022-10-26
C-PW-084590 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-05-22 | 2022-06-07 | 01 | 08 | 01 | 45 | 004 | 03 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084600 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-07 | 2022-06-19 | 01 | 08 | 01 | 45 | 004 | 03 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084610 | Final Fix (Installation of Sanitaryware & Accessories) | 3 | 2022-10-23 | 2022-10-26 | 01 | 08 | 01 | 45 | 004 | 03 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Wet Areas
HOT & COLD WATER SYSTEM |  | 119 | 2022-05-28 | 2022-10-19
C-PW-084620 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-05-28 | 2022-06-13 | 01 | 08 | 01 | 45 | 004 | 03 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084630 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-06-13 | 2022-06-25 | 01 | 08 | 01 | 45 | 004 | 03 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084640 | Final Fix - Water Meter Installation | 3 | 2022-10-16 | 2022-10-19 | 01 | 08 | 01 | 45 | 004 | 03 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Wet Areas
ELECTRICAL WORKS |  | 122 | 2022-05-24 | 2022-10-19
C-PW-084650 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-05-24 | 2022-06-05 | 01 | 07 | 01 | 45 | 004 | 03 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084660 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-05-26 | 2022-06-14 | 01 | 07 | 01 | 45 | 004 | 03 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084670 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-14 | 2022-06-30 | 01 | 07 | 01 | 45 | 004 | 03 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084680 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-10-08 | 2022-10-16 | 01 | 07 | 01 | 45 | 004 | 03 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084690 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-11 | 2022-10-19 | 01 | 07 | 01 | 45 | 004 | 03 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084700 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-11 | 2022-10-19 | 01 | 07 | 01 | 45 | 004 | 03 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Wet Areas
ELV |  | 114 | 2022-05-26 | 2022-10-12
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 114 | 2022-05-26 | 2022-10-12
C-PW-084710 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-26 | 2022-06-07 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084720 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084730 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-12 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
AV SYSTEM |  | 113 | 2022-05-28 | 2022-10-12
C-PW-084740 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-28 | 2022-06-08 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084750 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-09 | 2022-06-21 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084760 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-12 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
DATA AND TELECOMMUNICATION |  | 111 | 2022-05-30 | 2022-10-12
C-PW-084770 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-30 | 2022-06-11 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084780 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084790 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-12 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 109 | 2022-05-31 | 2022-10-12
C-PW-084800 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-31 | 2022-06-13 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084810 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-13 | 2022-06-25 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084820 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-12 | 01 | 10 | 01 | 45 | 004 | 03 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 113 | 2022-05-28 | 2022-10-12
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 108 | 2022-06-02 | 2022-10-12
C-PW-084830 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 09 | 01 | 45 | 004 | 03 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084840 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-14 | 2022-06-27 | 01 | 09 | 01 | 45 | 004 | 03 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084850 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-12 | 01 | 09 | 01 | 45 | 004 | 03 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 108 | 2022-06-02 | 2022-10-12
C-PW-084860 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-02 | 2022-06-14 | 01 | 09 | 01 | 45 | 004 | 03 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084870 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-14 | 2022-06-27 | 01 | 09 | 01 | 45 | 004 | 03 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084880 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-12 | 01 | 09 | 01 | 45 | 004 | 03 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Wet Areas
FIRE FIGHTING WORKS |  | 66 | 2022-05-28 | 2022-08-17
C-PW-084890 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-05-28 | 2022-06-13 | 01 | 09 | 01 | 45 | 004 | 03 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084900 | 2nd Fix Piping System - (Fittings) | 8 | 2022-06-13 | 2022-06-22 | 01 | 09 | 01 | 45 | 004 | 03 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Wet Areas
C-PW-084910 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-08-11 | 2022-08-17 | 01 | 09 | 01 | 45 | 004 | 03 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Wet Areas
PUBLIC MALE & FEMALE PRAYER - SOUTH |  | 133 | 2022-05-11 | 2022-10-19
MECHANICAL |  | 133 | 2022-05-11 | 2022-10-18
HVAC SYSTEM WORKS |  | 133 | 2022-05-11 | 2022-10-18
C-PW-084920 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-05-12 | 2022-06-01 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-084930 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-05-11 | 2022-06-01 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-084940 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-06-01 | 2022-06-13 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-084950 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-08 | 2022-10-18 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-06-07 | 2022-07-14
C-PW-084960 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-07 | 2022-06-28 | 01 | 08 | 01 | 45 | 004 | 01 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-084970 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-28 | 2022-07-14 | 01 | 08 | 01 | 45 | 004 | 01 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 32 | 2022-06-13 | 2022-07-24
C-PW-084980 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-13 | 2022-07-04 | 01 | 08 | 01 | 45 | 004 | 01 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-084990 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-07-04 | 2022-07-19 | 01 | 08 | 01 | 45 | 004 | 01 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085000 | Final Fix - Water Meter Installation | 3 | 2022-07-20 | 2022-07-24 | 01 | 08 | 01 | 45 | 004 | 01 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 112 | 2022-06-05 | 2022-10-19
C-PW-085010 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-06-05 | 2022-06-21 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085020 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-06-07 | 2022-06-27 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085030 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-27 | 2022-07-16 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085040 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-08 | 2022-10-18 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085050 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-11 | 2022-10-19 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085060 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-11 | 2022-10-19 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
ELV |  | 101 | 2022-06-07 | 2022-10-08
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 99 | 2022-06-07 | 2022-10-05
C-PW-085070 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-07 | 2022-06-19 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085080 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-19 | 2022-07-02 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085090 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-03 | 2022-10-05 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
AV SYSTEM |  | 97 | 2022-06-09 | 2022-10-05
C-PW-085100 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-09 | 2022-06-21 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085110 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-21 | 2022-07-03 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085120 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-03 | 2022-10-05 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 96 | 2022-06-11 | 2022-10-05
C-PW-085130 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-11 | 2022-06-22 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085140 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-23 | 2022-07-05 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085150 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-03 | 2022-10-05 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 97 | 2022-06-13 | 2022-10-08
C-PW-085160 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-13 | 2022-06-25 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085170 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-25 | 2022-07-06 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085180 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-05 | 2022-10-08 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 94 | 2022-06-13 | 2022-10-05
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 93 | 2022-06-14 | 2022-10-05
C-PW-085190 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-27 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085200 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-27 | 2022-07-09 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085210 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-03 | 2022-10-05 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 93 | 2022-06-14 | 2022-10-05
C-PW-085220 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-27 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085230 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-27 | 2022-07-09 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085240 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-03 | 2022-10-05 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 79 | 2022-06-13 | 2022-09-18
C-PW-085250 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-13 | 2022-07-02 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085260 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-02 | 2022-07-14 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085270 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-08 | 2022-09-18 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
GALLERY A & B AV / IT ROOM & LOBBY - SOUTH |  | 249 | 2022-01-13 | 2022-11-09
MECHANICAL |  | 245 | 2022-01-13 | 2022-11-05
HVAC SYSTEM WORKS |  | 245 | 2022-01-13 | 2022-11-05
C-PW-085280 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-01-15 | 2022-02-03 | 01 | 06 | 01 | 45 | 004 | 02 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085290 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-01-13 | 2022-02-03 | 01 | 06 | 01 | 45 | 004 | 02 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085300 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-02-03 | 2022-02-15 | 01 | 06 | 01 | 45 | 004 | 02 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085310 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-26 | 2022-11-05 | 01 | 06 | 01 | 45 | 004 | 02 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
DRAINAGE WORKS |  | 24 | 2022-06-28 | 2022-07-31
C-PW-085320 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-06-28 | 2022-07-18 | 01 | 08 | 01 | 45 | 004 | 02 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085330 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-18 | 2022-07-31 | 01 | 08 | 01 | 45 | 004 | 02 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 29 | 2022-07-04 | 2022-08-11
C-PW-085340 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-04 | 2022-07-28 | 01 | 08 | 01 | 45 | 004 | 02 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085350 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-31 | 2022-08-11 | 01 | 08 | 01 | 45 | 004 | 02 |  | Building | Plumbing | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 116 | 2022-06-21 | 2022-11-09
C-PW-085360 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-06-21 | 2022-07-06 | 01 | 07 | 01 | 45 | 004 | 02 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085370 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-06-23 | 2022-07-16 | 01 | 07 | 01 | 45 | 004 | 02 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085380 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-16 | 2022-08-02 | 01 | 07 | 01 | 45 | 004 | 02 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085390 | LV Switchgears (DB's) | 5 | 2022-08-02 | 2022-08-08 | 01 | 07 | 01 | 45 | 004 | 02 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085400 | Cable/Wire Termination & Dressing | 7 | 2022-08-08 | 2022-08-16 | 01 | 07 | 01 | 45 | 004 | 02 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085410 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-26 | 2022-11-05 | 01 | 07 | 01 | 45 | 004 | 02 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085420 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-29 | 2022-11-06 | 01 | 07 | 01 | 45 | 004 | 02 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085430 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-10-30 | 2022-11-07 | 01 | 07 | 01 | 45 | 004 | 02 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085440 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-01 | 2022-11-09 | 01 | 07 | 01 | 45 | 004 | 02 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
ELV |  | 107 | 2022-06-27 | 2022-11-05
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 98 | 2022-06-27 | 2022-10-25
C-PW-085450 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085460 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085470 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-25 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 98 | 2022-06-27 | 2022-10-25
C-PW-085480 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085490 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085500 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-25 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
INTERCOM SYSTEM |  | 98 | 2022-06-27 | 2022-10-25
C-PW-085510 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085520 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085530 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-25 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
AV SYSTEM |  | 98 | 2022-06-28 | 2022-10-27
C-PW-085540 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-28 | 2022-07-14 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085550 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-14 | 2022-07-26 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085560 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-24 | 2022-10-27 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 98 | 2022-06-28 | 2022-10-27
C-PW-085570 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-28 | 2022-07-14 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085580 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-14 | 2022-07-26 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085590 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-24 | 2022-10-27 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 98 | 2022-06-30 | 2022-10-29
C-PW-085600 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-30 | 2022-07-16 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085610 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-16 | 2022-07-28 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085620 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-26 | 2022-10-29 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 98 | 2022-06-30 | 2022-10-29
C-PW-085630 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-30 | 2022-07-16 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085640 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-16 | 2022-07-28 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085650 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-26 | 2022-10-29 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-29 | 2022-11-05
C-PW-085660 | Active Component System Works | 6 | 2022-10-29 | 2022-11-05 | 01 | 10 | 01 | 45 | 004 | 02 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 92 | 2022-07-04 | 2022-10-25
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 85 | 2022-07-16 | 2022-10-25
C-PW-085670 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-16 | 2022-07-28 | 01 | 09 | 01 | 45 | 004 | 02 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085680 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-28 | 2022-08-10 | 01 | 09 | 01 | 45 | 004 | 02 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085690 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-25 | 01 | 09 | 01 | 45 | 004 | 02 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 85 | 2022-07-16 | 2022-10-25
C-PW-085700 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-16 | 2022-07-28 | 01 | 09 | 01 | 45 | 004 | 02 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085710 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-28 | 2022-08-10 | 01 | 09 | 01 | 45 | 004 | 02 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085720 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-23 | 2022-10-25 | 01 | 09 | 01 | 45 | 004 | 02 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 78 | 2022-07-04 | 2022-10-08
C-PW-085730 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-07-04 | 2022-07-26 | 01 | 09 | 01 | 45 | 004 | 02 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085740 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-26 | 2022-08-06 | 01 | 09 | 01 | 45 | 004 | 02 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
C-PW-085750 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-29 | 2022-10-08 | 01 | 09 | 01 | 45 | 004 | 02 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | MEP / Service Rooms
CIRCULATION - SOUTH |  | 139 | 2022-07-07 | 2022-12-24
MECHANICAL |  | 129 | 2022-07-18 | 2022-12-19
HVAC SYSTEM WORKS |  | 121 | 2022-07-27 | 2022-12-19
C-PW-085760 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 17 | 2022-07-31 | 2022-08-18 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085770 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 18 | 2022-07-27 | 2022-08-18 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085780 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-08-18 | 2022-08-31 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085790 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-12-10 | 2022-12-19 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-07-18 | 2022-08-22
C-PW-085800 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-18 | 2022-08-09 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085810 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-09 | 2022-08-22 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-07-24 | 2022-08-27
C-PW-085820 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-24 | 2022-08-15 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085830 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-15 | 2022-08-27 | 01 | 06 | 01 | 45 | 004 | 01 |  | Building | HVAC | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
ELECTRICAL WORKS |  | 139 | 2022-07-07 | 2022-12-24
C-PW-085840 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-07-07 | 2022-07-26 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085850 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-08-01 | 2022-08-21 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085860 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-08-21 | 2022-09-05 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085870 | LV Switchgears (DB's) | 5 | 2022-09-06 | 2022-09-11 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085880 | Cable/Wire Termination & Dressing | 7 | 2022-09-11 | 2022-09-19 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085890 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-12-10 | 2022-12-19 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085900 | Final Fix Electrical (Light Fixtures) | 7 | 2022-12-11 | 2022-12-19 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085910 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-12-13 | 2022-12-21 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085920 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-12-15 | 2022-12-24 | 01 | 07 | 01 | 45 | 004 | 01 |  | Building | Electrical | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
ELV |  | 32 | 2022-07-09 | 2022-08-20
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-07-09 | 2022-08-09
C-PW-085930 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085940 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-25 | 2022-08-07 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085950 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-07 | 2022-08-09 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-07-09 | 2022-08-09
C-PW-085960 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085970 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-25 | 2022-08-07 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-085980 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-07 | 2022-08-09 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
INTERCOM SYSTEM |  | 23 | 2022-07-09 | 2022-08-09
C-PW-085990 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086000 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-07-25 | 2022-08-07 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086010 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-07 | 2022-08-09 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
AV SYSTEM |  | 23 | 2022-07-14 | 2022-08-11
C-PW-086020 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-14 | 2022-07-26 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086030 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-26 | 2022-08-08 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086040 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-09 | 2022-08-11 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-07-14 | 2022-08-11
C-PW-086050 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-07-14 | 2022-07-26 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086060 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-26 | 2022-08-08 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086070 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-09 | 2022-08-11 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 23 | 2022-07-16 | 2022-08-13
C-PW-086080 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-16 | 2022-07-28 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086090 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-28 | 2022-08-10 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086100 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-10 | 2022-08-13 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-07-16 | 2022-08-13
C-PW-086110 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-16 | 2022-07-28 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086120 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-28 | 2022-08-10 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086130 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-10 | 2022-08-13 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-08-14 | 2022-08-20
C-PW-086140 | Active Component System Works | 6 | 2022-08-14 | 2022-08-20 | 01 | 10 | 01 | 45 | 004 | 01 |  | Building | CCTV | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 102 | 2022-07-28 | 2022-11-26
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 92 | 2022-07-28 | 2022-11-15
C-PW-086150 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-28 | 2022-08-10 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086160 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-08-10 | 2022-08-22 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086170 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-12 | 2022-11-15 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 92 | 2022-07-28 | 2022-11-15
C-PW-086180 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-28 | 2022-08-10 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086190 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-10 | 2022-08-22 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086200 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-12 | 2022-11-15 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 98 | 2022-08-03 | 2022-11-26
C-PW-086210 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-08-03 | 2022-08-22 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086220 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-08-22 | 2022-08-31 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
C-PW-086230 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 8 | 2022-11-16 | 2022-11-26 | 01 | 09 | 01 | 45 | 004 | 01 |  | Building | Firefighting | Museum | South East | L01 Mezzanine Level | Circulation / Common Areas
LEVEL 02 GALLERY |  | 616 | 2021-04-22 | 2023-05-07
CIVIL WORKS |  | 362 | 2021-04-22 | 2022-07-04
ZONE 02A |  | 172 | 2021-04-22 | 2021-11-17
C-PW-086240 | Site Survey for Action (Item 07 - Immediate) | 1 | 2021-04-22 | 2021-04-22 | 01 | 01 | 01 | 07 | 005 | 30 |  | Building | Civil | Museum | Zone 02A | L02 Gallery level | Civil SubZones
C-PW-086250 | Construction of Verticals Zone 2A Walls Over Auditorium (Item 07 - Immediate) | 12 | 2021-07-03 | 2021-07-15 | 01 | 01 | 01 | 07 | 005 | 30 |  | Building | Civil | Museum | Zone 02A | L02 Gallery level | Civil SubZones
C-PW-086260 | Construction of Level 02 Slab - Zone 2A | 26 | 2021-10-11 | 2021-11-10 | 01 | 01 | 01 | 07 | 005 | 30 |  | Building | Civil | Museum | Zone 02A | L02 Gallery level | Civil SubZones
C-PW-086270 | Construction of Verticals up to Level 03 Slab - Zone 2A | 26 | 2021-10-18 | 2021-11-17 | 01 | 01 | 01 | 07 | 005 | 30 |  | Building | Civil | Museum | Zone 02A | L02 Gallery level | Civil SubZones
C-PW-086280 | Construction of WC Planted Walls up to Level 03 Slab - Zone 2A | 26 | 2021-10-18 | 2021-11-17 | 01 | 01 | 01 | 07 | 005 | 30 |  | Building | Civil | Museum | Zone 02A | L02 Gallery level | Civil SubZones
ZONE 02B |  | 212 | 2021-05-04 | 2022-01-18
C-PW-086290 | Site Survey for Action (Item 10 - Immediate) | 1 | 2021-05-04 | 2021-05-04 | 01 | 01 | 01 | 08 | 005 | 30 |  | Building | Civil | Museum | Zone 02B | L02 Gallery level | Civil SubZones
C-PW-086300 | Construction of Verticals up to Level - 03 Slab - Zone 2B (Item 10 - Immediate) | 12 | 2021-08-11 | 2021-08-24 | 01 | 01 | 01 | 08 | 005 | 30 |  | Building | Civil | Museum | Zone 02B | L02 Gallery level | Civil SubZones
C-PW-086310 | Construction of Level - 02 Slab - Zone 2B | 26 | 2021-11-07 | 2021-12-08 | 01 | 01 | 01 | 08 | 005 | 30 |  | Building | Civil | Museum | Zone 02B | L02 Gallery level | Civil SubZones
C-PW-086320 | Construction of Verticals up to Level - 03 Slab - Zone 2B | 26 | 2021-11-14 | 2021-12-15 | 01 | 01 | 01 | 08 | 005 | 30 |  | Building | Civil | Museum | Zone 02B | L02 Gallery level | Civil SubZones
C-PW-086330 | Construction of WC Planted Walls up to Level 03 Slab - Zone 2B | 26 | 2021-11-14 | 2021-12-15 | 01 | 01 | 01 | 08 | 005 | 30 |  | Building | Civil | Museum | Zone 02B | L02 Gallery level | Civil SubZones
C-PW-086340 | Construction of Falconry Leave outs up to Level 02 Slab | 42 | 2021-11-28 | 2022-01-18 | 01 | 01 | 01 | 08 | 005 | 30 |  | Building | Civil | Museum | Zone 02B | L02 Gallery level | Civil SubZones
ZONE 02C |  | 36 | 2022-01-03 | 2022-02-13
C-PW-086350 | Construction of Level 02 Slab - Zone 2C | 24 | 2022-01-03 | 2022-01-30 | 01 | 01 | 01 | 09 | 005 | 30 |  | Building | Civil | Museum | Zone 02C | L02 Gallery level | Civil SubZones
C-PW-086360 | Construction of Verticals up to Level 03 Slab - Zone 2C | 24 | 2022-01-17 | 2022-02-13 | 01 | 01 | 01 | 09 | 005 | 30 |  | Building | Civil | Museum | Zone 02C | L02 Gallery level | Civil SubZones
C-PW-086370 | Construction of WC Planted Walls up to Level 03 Slab - Zone 2C | 24 | 2022-01-17 | 2022-02-13 | 01 | 01 | 01 | 09 | 005 | 30 |  | Building | Civil | Museum | Zone 02C | L02 Gallery level | Civil SubZones
ZONE 02D |  | 311 | 2021-04-26 | 2022-05-09
C-PW-086380 | Site Survey for Action (Item 20 - Immediate) | 1 | 2021-04-26 | 2021-04-26 | 01 | 01 | 01 | 10 | 005 | 30 |  | Building | Civil | Museum | Zone 02D | L02 Gallery level | Civil SubZones
C-PW-086390 | Construction of Level 02 Slab - Zone 2D (Item 20 - Immediate) | 10 | 2021-08-04 | 2021-08-16 | 01 | 01 | 01 | 10 | 005 | 30 |  | Building | Civil | Museum | Zone 02D | L02 Gallery level | Civil SubZones
C-PW-086400 | Construction of Level 02 Slab - Zone 2D | 24 | 2022-03-12 | 2022-04-07 | 01 | 01 | 01 | 10 | 005 | 30 |  | Building | Civil | Museum | Zone 02D | L02 Gallery level | Civil SubZones
C-PW-086410 | Construction of Verticals up to Level 03 Slab - Zone 2D | 26 | 2022-03-23 | 2022-04-21 | 01 | 01 | 01 | 10 | 005 | 30 |  | Building | Civil | Museum | Zone 02D | L02 Gallery level | Civil SubZones
C-PW-086420 | Construction of Level 03 Slab - Zone 2D | 26 | 2022-04-06 | 2022-05-09 | 01 | 01 | 01 | 10 | 005 | 30 |  | Building | Civil | Museum | Zone 02D | L02 Gallery level | Civil SubZones
ZONE 02E |  | 56 | 2021-10-27 | 2022-01-03
C-PW-086430 | Construction of Level 02 Slab - Zone 2E | 24 | 2021-10-27 | 2021-11-23 | 01 | 01 | 01 | 11 | 005 | 30 |  | Building | Civil | Museum | Zone 02E | L02 Gallery level | Civil SubZones
C-PW-086440 | Construction of Verticals up to Level 03 Slab - Zone 2E | 32 | 2021-11-24 | 2022-01-03 | 01 | 01 | 01 | 11 | 005 | 30 |  | Building | Civil | Museum | Zone 02E | L02 Gallery level | Civil SubZones
ZONE 02G |  | 234 | 2021-05-06 | 2022-02-15
C-PW-086450 | Site Survey for Action (Item 18 - Immediate) | 1 | 2021-05-06 | 2021-05-06 | 01 | 01 | 01 | 13 | 005 | 30 |  | Building | Civil | Museum | Zone 02G | L02 Gallery level | Civil SubZones
C-PW-086460 | Construction of Level 02 Slab - Zone 2G (Item 18 - Immediate) | 10 | 2021-08-14 | 2021-08-24 | 01 | 01 | 01 | 13 | 005 | 30 |  | Building | Civil | Museum | Zone 02G | L02 Gallery level | Civil SubZones
C-PW-086470 | Construction of Level 02 Slab - Zone 2G | 28 | 2021-12-30 | 2022-02-01 | 01 | 01 | 01 | 13 | 005 | 30 |  | Building | Civil | Museum | Zone 02G | L02 Gallery level | Civil SubZones
C-PW-086480 | Construction of Verticals up to Level 03 Slab - Zone 2G | 26 | 2022-01-17 | 2022-02-15 | 01 | 01 | 01 | 13 | 005 | 30 |  | Building | Civil | Museum | Zone 02G | L02 Gallery level | Civil SubZones
ZONE 02H |  | 219 | 2021-05-08 | 2022-01-30
C-PW-086490 | Site Survey for Action (Item 15 - Immediate) | 1 | 2021-05-08 | 2021-05-08 | 01 | 01 | 01 | 14 | 005 | 30 |  | Building | Civil | Museum | Zone 02H | L02 Gallery level | Civil SubZones
C-PW-086500 | Construction of Level 02 Slab - Zone 2H around TC1 (Item 15 - Immediate) | 10 | 2021-08-09 | 2021-08-21 | 01 | 01 | 01 | 14 | 005 | 30 |  | Building | Civil | Museum | Zone 02H | L02 Gallery level | Civil SubZones
C-PW-086510 | Construction of Level 02 Slab - Zone 2H | 24 | 2021-12-05 | 2022-01-02 | 01 | 01 | 01 | 14 | 005 | 30 |  | Building | Civil | Museum | Zone 02H | L02 Gallery level | Civil SubZones
C-PW-086520 | Construction of Verticals up to Level 03 Slab - Zone 2H | 24 | 2021-12-19 | 2022-01-16 | 01 | 01 | 01 | 14 | 005 | 30 |  | Building | Civil | Museum | Zone 02H | L02 Gallery level | Civil SubZones
C-PW-086530 | Construction of WC Planted Walls up to Level 03 Slab - Zone 2H | 24 | 2021-12-19 | 2022-01-16 | 01 | 01 | 01 | 14 | 005 | 30 |  | Building | Civil | Museum | Zone 02H | L02 Gallery level | Civil SubZones
C-PW-086540 | Construction of Verticals & Zone 2 Ceiling Slab at Level +24 - Zone 2H | 26 | 2021-12-30 | 2022-01-30 | 01 | 01 | 01 | 14 | 005 | 30 |  | Building | Civil | Museum | Zone 02H | L02 Gallery level | Civil SubZones
ZONE 03B |  | 28 | 2022-04-09 | 2022-05-14
C-PW-086550 | Construction of Level 02 Slab - Zone 3B | 28 | 2022-04-09 | 2022-05-14 | 01 | 01 | 01 | 16 | 005 | 30 |  | Building | Civil | Museum | Zone 03B | L02 Gallery level | Civil SubZones
ZONE 03C |  | 28 | 2022-06-02 | 2022-07-04
C-PW-086560 | Construction of Level 02 Slab - Zone 3C | 28 | 2022-06-02 | 2022-07-04 | 01 | 01 | 01 | 17 | 005 | 30 |  | Building | Civil | Museum | Zone 03C | L02 Gallery level | Civil SubZones
STEEL STRUCTURE |  | 38 | 2022-02-16 | 2022-03-31
ZONE 02G |  | 38 | 2022-02-16 | 2022-03-31
C-PW-086570 | Erection of Hanging Grating Support /Hanging Columns / beams | 18 | 2022-02-16 | 2022-03-08 | 01 | 02 | 01 | 13 | 005 | 30 |  | Building | Primary Steel Structure | Museum | Zone 02G | L02 Gallery level | Civil SubZones
C-PW-086580 | Erection of Infill Beams | 10 | 2022-03-09 | 2022-03-20 | 01 | 02 | 01 | 13 | 005 | 30 |  | Building | Primary Steel Structure | Museum | Zone 02G | L02 Gallery level | Civil SubZones
C-PW-086590 | Application of cementitious Fireproofing works | 10 | 2022-03-21 | 2022-03-31 | 01 | 02 | 01 | 13 | 005 | 30 |  | Building | Primary Steel Structure | Museum | Zone 02G | L02 Gallery level | Civil SubZones
ARCHITECTURAL WORKS |  | 394 | 2022-01-19 | 2023-05-07
NORTH WEST |  | 394 | 2022-01-19 | 2023-05-07
COMMON WORKS- NORTH |  | 26 | 2022-01-19 | 2022-02-17
C-PW-086600 | General Block Work | 11 | 2022-01-19 | 2022-02-01 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086610 | Marking & Chasing Walls for MEP Services | 14 | 2022-02-01 | 2022-02-17 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
GALLERY LOBBY AREAS- NORTH |  | 333 | 2022-03-31 | 2023-05-07
C-PW-086620 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-03-31 | 01 | 14 | 01 | 46 | 005 | 01 |  | Building | General MEP | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086630 | Wall Finishes (Metal Wall System, Balustrade Capping, GRG Balustrade Lining) | 14 | 2022-03-31 | 2022-04-17 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086640 | Ceiling Grid / Support Works | 14 | 2022-04-11 | 2022-04-28 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086650 | Ceiling Finishes (Special Finish for Situ White Concrete) | 14 | 2022-04-28 | 2022-05-18 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086660 | Floor Finishes (Polished Concrete Floor System) | 22 | 2022-05-18 | 2022-06-13 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086670 | Door Frames & Architrave Fixing | 6 | 2022-06-14 | 2022-06-21 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086680 | Door Shuttering & Ironmongery | 6 | 2022-08-18 | 2022-08-25 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086690 | Roller Shutter Installation | 2 | 2022-09-15 | 2022-09-18 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086700 | Joinery Fixing & Fitout Works | 11 | 2023-04-08 | 2023-04-23 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086710 | Installation of Lockers | 6 | 2023-04-23 | 2023-04-30 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-086720 | Final Finishes | 6 | 2023-04-30 | 2023-05-07 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
STAFF MALE & FEMALE WC, WASH UP & LOUNGE KITCHENETTE- NORTH |  | 223 | 2022-01-29 | 2022-10-25
C-PW-086730 | Floor Waterproofing Works | 16 | 2022-01-29 | 2022-02-15 | 01 | 04 | 01 | 46 | 005 | 03 |  | Building | Architecture | Museum | North West | L02 Gallery level | Wet Areas
C-PW-086740 | Installation of Lockers, shelves & Shoe Cupboards | 11 | 2022-02-05 | 2022-02-17 | 01 | 04 | 01 | 46 | 005 | 03 |  | Building | Architecture | Museum | North West | L02 Gallery level | Wet Areas
C-PW-086750 | Floor Screed Works | 16 | 2022-02-16 | 2022-03-06 | 01 | 04 | 01 | 46 | 005 | 03 |  | Building | Architecture | Museum | North West | L02 Gallery level | Wet Areas
C-PW-086760 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-05-22 | 01 | 14 | 01 | 46 | 005 | 03 |  | Building | General MEP | Museum | North West | L02 Gallery level | Wet Areas
C-PW-086770 | Wall Finishes (PVC wall lining & wall tiles) | 19 | 2022-05-19 | 2022-06-11 | 01 | 04 | 01 | 46 | 005 | 03 |  | Building | Architecture | Museum | North West | L02 Gallery level | Wet Areas
C-PW-086780 | Ceiling Grid / Support Works | 14 | 2022-05-31 | 2022-06-16 | 01 | 04 | 01 | 46 | 005 | 03 |  | Building | Architecture | Museum | North West | L02 Gallery level | Wet Areas
C-PW-086790 | Ceiling Finishes (Metal tile ceiling, & Plaster board ceiling) | 14 | 2022-06-16 | 2022-07-04 | 01 | 04 | 01 | 46 | 005 | 03 |  | Building | Architecture | Museum | North West | L02 Gallery level | Wet Areas
C-PW-086800 | Floor Finishes (Terrazzo Resin Floor system, & Ceramic Tiles) | 22 | 2022-07-04 | 2022-08-03 | 01 | 04 | 01 | 46 | 005 | 03 |  | Building | Architecture | Museum | North West | L02 Gallery level | Wet Areas
C-PW-086810 | Door Frames & Architrave Fixing | 10 | 2022-08-08 | 2022-08-18 | 01 | 04 | 01 | 46 | 005 | 03 |  | Building | Architecture | Museum | North West | L02 Gallery level | Wet Areas
C-PW-086820 | Door Shuttering & Ironmongery | 10 | 2022-08-18 | 2022-08-30 | 01 | 04 | 01 | 46 | 005 | 03 |  | Building | Architecture | Museum | North West | L02 Gallery level | Wet Areas
C-PW-086830 | Final Finishes | 13 | 2022-10-10 | 2022-10-25 | 01 | 04 | 01 | 46 | 005 | 03 |  | Building | Architecture | Museum | North West | L02 Gallery level | Wet Areas
COMMON WORKS - NORTH MEP ROOMS |  | 26 | 2022-02-01 | 2022-03-02
C-PW-086840 | General Block Work | 11 | 2022-02-01 | 2022-02-14 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086850 | Marking & Chasing Walls for MEP Services | 14 | 2022-02-14 | 2022-03-02 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
KITCHEN EXTRACT PLANT ROOM - NORTH |  | 160 | 2022-03-02 | 2022-09-13
C-PW-086860 | Equipment Foundation & Upstand Works | 8 | 2022-03-02 | 2022-03-12 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086870 | Paint 1st Coat - Ceiling (Internal Paint) | 6 | 2022-03-12 | 2022-03-19 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086880 | Paint 1st Coat - Walls (Internal Paint) | 6 | 2022-03-27 | 2022-04-03 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086890 | Floor Finishes (Epoxy Resin Floor System) | 6 | 2022-04-25 | 2022-05-05 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086900 | Doors & Ironmongery | 5 | 2022-08-27 | 2022-08-31 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086910 | Final Coat Paint | 5 | 2022-09-08 | 2022-09-13 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
COOLING ROOM - NORTH |  | 98 | 2022-03-02 | 2022-06-28
C-PW-086920 | Equipment Foundation & Upstand Works (Incl. Acoustic Layers/ Insulators) | 8 | 2022-03-02 | 2022-03-12 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086930 | Paint 1st Coat - Ceiling (Dust Sealer) | 8 | 2022-03-12 | 2022-03-21 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086940 | Paint 1st Coat - Walls (Dust Sealer) | 17 | 2022-03-12 | 2022-03-31 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086950 | Floor Finishes (Epoxy Resin Floor System) | 10 | 2022-05-29 | 2022-06-09 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086960 | Door Frame, Shutter & Ironmongery (Steel Doors) | 5 | 2022-06-09 | 2022-06-15 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086970 | Final Coat Paint | 8 | 2022-06-19 | 2022-06-28 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
GALLERY 3 AV/ IT ROOMS - NORTH |  | 171 | 2022-03-12 | 2022-10-05
C-PW-086980 | Equipment Foundation & Upstand Works (Incl. Acoustic Layers/ Insulators) | 8 | 2022-03-12 | 2022-03-21 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-086990 | Paint 1st Coat - Ceiling (Dust Sealer) | 8 | 2022-03-21 | 2022-03-30 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087000 | Paint 1st Coat - Walls (Dust Sealer) | 17 | 2022-03-21 | 2022-04-10 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087010 | Floor Finishes (Epoxy Resin Floor System) | 10 | 2022-06-11 | 2022-06-21 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087020 | Door Frame, Shutter & Ironmongery (Steel Doors) | 5 | 2022-06-21 | 2022-06-27 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087030 | Roller Shutter Installation | 10 | 2022-09-15 | 2022-09-26 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087040 | Final Coat Paint | 8 | 2022-09-26 | 2022-10-05 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
AHU, ELEC CUPBOARD - NORTH |  | 266 | 2022-06-11 | 2023-04-27
C-PW-087050 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-06-11 | 01 | 14 | 01 | 46 | 005 | 02 |  | Building | General MEP | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087060 | Wall Finishes (Interior Paint & Wall Protection) | 19 | 2022-06-12 | 2022-07-04 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087070 | Ceiling Grid / Support Works | 8 | 2022-07-04 | 2022-07-17 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087080 | Ceiling Finishes (Plaster board ceiling, & Dust Sealer) | 8 | 2022-07-17 | 2022-07-26 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087090 | Floor Finishes (Epoxy Resin Floor System) | 11 | 2022-07-26 | 2022-08-09 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087100 | Door Frames Fixing | 6 | 2022-08-09 | 2022-08-16 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087110 | Door Shuttering & Ironmongery | 6 | 2022-08-16 | 2022-08-24 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087120 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-087130 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 46 | 005 | 02 |  | Building | Architecture | Museum | North West | L02 Gallery level | MEP / Service Rooms
CIRCULATIONS & CORRIDORS- NORTH |  | 310 | 2022-04-18 | 2023-04-27
C-PW-087140 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-04-18 | 01 | 14 | 01 | 46 | 005 | 01 |  | Building | General MEP | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-087150 | Wall Finishes (Dust Sealer, Interior Paint & Wall Protection) | 11 | 2022-04-18 | 2022-05-04 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-087160 | Ceiling Grid / Support Works | 14 | 2022-04-30 | 2022-05-19 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-087170 | Ceiling Finishes (Interior Paint) | 14 | 2022-05-19 | 2022-06-05 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-087180 | Floor Finishes (Epoxy Resin Floor System) | 11 | 2022-06-05 | 2022-06-18 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-087190 | Door Frames & Architrave Fixing | 6 | 2022-06-21 | 2022-06-28 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-087200 | Door Shuttering & Ironmongery | 6 | 2022-08-27 | 2022-09-01 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-087210 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-087220 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 46 | 005 | 01 |  | Building | Architecture | Museum | North West | L02 Gallery level | Circulation / Common Areas
NORTH EAST |  | 362 | 2022-02-16 | 2023-04-27
COMMON WORKS - EAST |  | 26 | 2022-02-21 | 2022-03-22
C-PW-087230 | General Block Work | 11 | 2022-02-21 | 2022-03-06 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087240 | Marking & Chasing Walls for MEP Services | 14 | 2022-03-06 | 2022-03-22 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
MEMBERS MALE & FEMALE WC - EAST |  | 360 | 2022-02-16 | 2023-04-26
C-PW-087250 | Floor Waterproofing Works | 16 | 2022-02-16 | 2022-03-06 | 01 | 04 | 01 | 44 | 005 | 03 |  | Building | Architecture | Museum | North East | L02 Gallery level | Wet Areas
C-PW-087260 | Floor Screed Works | 16 | 2022-03-07 | 2022-03-24 | 01 | 04 | 01 | 44 | 005 | 03 |  | Building | Architecture | Museum | North East | L02 Gallery level | Wet Areas
C-PW-087270 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-05-14 | 01 | 14 | 01 | 44 | 005 | 03 |  | Building | General MEP | Museum | North East | L02 Gallery level | Wet Areas
C-PW-087280 | Wall Finishes (PVC wall lining & wall tiles) | 19 | 2022-05-04 | 2022-05-26 | 01 | 04 | 01 | 44 | 005 | 03 |  | Building | Architecture | Museum | North East | L02 Gallery level | Wet Areas
C-PW-087290 | Ceiling Grid / Support Works | 14 | 2022-05-15 | 2022-06-01 | 01 | 04 | 01 | 44 | 005 | 03 |  | Building | Architecture | Museum | North East | L02 Gallery level | Wet Areas
C-PW-087300 | Ceiling Finishes (Metal tile ceiling, & Plaster board ceiling) | 14 | 2022-06-01 | 2022-06-18 | 01 | 04 | 01 | 44 | 005 | 03 |  | Building | Architecture | Museum | North East | L02 Gallery level | Wet Areas
C-PW-087310 | Floor Finishes (Terrazzo Resin Floor system, & Ceramic Tiles) | 22 | 2022-06-18 | 2022-07-17 | 01 | 04 | 01 | 44 | 005 | 03 |  | Building | Architecture | Museum | North East | L02 Gallery level | Wet Areas
C-PW-087320 | Door Frames & Architrave Fixing | 8 | 2022-07-18 | 2022-07-26 | 01 | 04 | 01 | 44 | 005 | 03 |  | Building | Architecture | Museum | North East | L02 Gallery level | Wet Areas
C-PW-087330 | Door Shuttering & Ironmongery | 8 | 2022-07-25 | 2022-08-04 | 01 | 04 | 01 | 44 | 005 | 03 |  | Building | Architecture | Museum | North East | L02 Gallery level | Wet Areas
C-PW-087340 | Joinery Fixing | 10 | 2023-04-08 | 2023-04-18 | 01 | 04 | 01 | 44 | 005 | 03 |  | Building | Architecture | Museum | North East | L02 Gallery level | Wet Areas
C-PW-087350 | Final Finishes | 13 | 2023-04-09 | 2023-04-26 | 01 | 04 | 01 | 44 | 005 | 03 |  | Building | Architecture | Museum | North East | L02 Gallery level | Wet Areas
GALLERY LOBBY, WALKWAY & VIEWING PLATFORM - EAST |  | 301 | 2022-04-27 | 2023-04-27
C-PW-087360 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-04-27 | 01 | 14 | 01 | 44 | 005 | 01 |  | Building | General MEP | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087370 | Wall Finishes (Plaster render, Internal glazed screen, Metal Wall System, Bronze skirting) | 11 | 2022-04-28 | 2022-05-15 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087380 | Ceiling Grid / Support Works | 14 | 2022-05-12 | 2022-05-29 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087390 | Ceiling Finishes (Special Finish for Situ White Concrete) | 14 | 2022-05-30 | 2022-06-15 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087400 | Floor Finishes (Polished Concrete Floor System) | 22 | 2022-06-15 | 2022-07-14 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087410 | Door Frames & Architrave Fixing | 8 | 2022-07-14 | 2022-07-24 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087420 | Door Shuttering & Ironmongery | 8 | 2022-08-31 | 2022-09-08 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087430 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087440 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
ELECT. CUPBOARD - EAST |  | 276 | 2022-05-31 | 2023-04-27
C-PW-087450 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-05-31 | 01 | 14 | 01 | 44 | 005 | 02 |  | Building | General MEP | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-087460 | Wall Finishes (Interior Paint) | 19 | 2022-05-31 | 2022-06-22 | 01 | 04 | 01 | 44 | 005 | 02 |  | Building | Architecture | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-087470 | Ceiling Grid / Support Works | 3 | 2022-06-22 | 2022-06-26 | 01 | 04 | 01 | 44 | 005 | 02 |  | Building | Architecture | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-087480 | Ceiling Finishes (Plaster board ceiling, & Dust Sealer) | 3 | 2022-06-26 | 2022-06-29 | 01 | 04 | 01 | 44 | 005 | 02 |  | Building | Architecture | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-087490 | Floor Finishes (Epoxy Resin Floor System) | 11 | 2022-06-30 | 2022-07-17 | 01 | 04 | 01 | 44 | 005 | 02 |  | Building | Architecture | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-087500 | Door Frames & Architrave Fixing | 6 | 2022-08-16 | 2022-08-24 | 01 | 04 | 01 | 44 | 005 | 02 |  | Building | Architecture | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-087510 | Door Shuttering & Ironmongery | 2 | 2022-08-30 | 2022-08-31 | 01 | 04 | 01 | 44 | 005 | 02 |  | Building | Architecture | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-087520 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 44 | 005 | 02 |  | Building | Architecture | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-087530 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 44 | 005 | 02 |  | Building | Architecture | Museum | North East | L02 Gallery level | MEP / Service Rooms
CIRCULATIONS - EAST |  | 320 | 2022-04-05 | 2023-04-27
C-PW-087540 | Plastering Works - Walls | 14 | 2022-04-05 | 2022-04-21 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087550 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-05-17 | 01 | 14 | 01 | 44 | 005 | 01 |  | Building | General MEP | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087560 | Wall Finishes (Interior Paint, Wall Protection & Corner Guards) | 19 | 2022-05-17 | 2022-06-08 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087570 | Ceiling Grid / Support Works | 14 | 2022-06-04 | 2022-06-20 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087580 | Ceiling Finishes (Interior Paint) | 14 | 2022-06-20 | 2022-07-06 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087590 | Floor Finishes (Epoxy Resin Floor System) | 11 | 2022-07-14 | 2022-07-27 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087600 | Door Frames & Architrave Fixing | 6 | 2022-07-28 | 2022-08-06 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087610 | Door Shuttering & Ironmongery | 6 | 2022-09-06 | 2022-09-13 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087620 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087630 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
GALLERY 4&5 LOBBY AREAS - SOUTH |  | 224 | 2022-08-04 | 2023-04-27
C-PW-087640 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-04 | 01 | 14 | 01 | 44 | 005 | 01 |  | Building | General MEP | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087650 | Wall Finishes (Wall Lining, & Metal wall system) | 10 | 2022-08-04 | 2022-08-15 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087660 | Ceiling Grid / Support Works | 10 | 2022-08-14 | 2022-08-24 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087670 | Ceiling Finishes (Special Finish for Situ White Concrete) | 10 | 2022-08-25 | 2022-09-05 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087680 | Floor Finishes (Polished Concrete Floor System) | 10 | 2022-09-05 | 2022-09-17 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087690 | Roller Shutter Installation | 5 | 2022-09-15 | 2022-09-20 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087700 | Door Frames & Architrave Fixing | 5 | 2022-09-17 | 2022-09-21 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087710 | Door Shuttering & Ironmongery | 5 | 2022-09-24 | 2022-09-29 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087720 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-087730 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 44 | 005 | 01 |  | Building | Architecture | Museum | North East | L02 Gallery level | Circulation / Common Areas
SOUTH WEST |  | 210 | 2022-08-20 | 2023-04-27
CIRCULATIONS & CORRIDORS - WEST |  | 210 | 2022-08-20 | 2023-04-27
C-PW-087740 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-20 | 01 | 14 | 01 | 47 | 005 | 01 |  | Building | General MEP | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-087750 | Wall Finishes (Wall Protection) | 17 | 2022-09-05 | 2022-09-25 | 01 | 04 | 01 | 47 | 005 | 01 |  | Building | Architecture | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-087760 | Ceiling Grid / Support Works | 14 | 2022-09-19 | 2022-10-05 | 01 | 04 | 01 | 47 | 005 | 01 |  | Building | Architecture | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-087770 | Ceiling Finishes (Interior Paint) | 14 | 2022-10-06 | 2022-10-24 | 01 | 04 | 01 | 47 | 005 | 01 |  | Building | Architecture | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-087780 | Floor Finishes (Epoxy Resin Floor System) | 11 | 2022-10-24 | 2022-11-06 | 01 | 04 | 01 | 47 | 005 | 01 |  | Building | Architecture | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-087790 | Door Frames & Architrave Fixing | 6 | 2022-11-06 | 2022-11-13 | 01 | 04 | 01 | 47 | 005 | 01 |  | Building | Architecture | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-087800 | Door Shuttering & Ironmongery | 6 | 2022-11-14 | 2022-11-21 | 01 | 04 | 01 | 47 | 005 | 01 |  | Building | Architecture | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-087810 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 47 | 005 | 01 |  | Building | Architecture | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-087820 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 47 | 005 | 01 |  | Building | Architecture | Museum | South West | L02 Gallery level | Circulation / Common Areas
SOUTH EAST |  | 309 | 2022-04-25 | 2023-05-03
COMMON WORKS - SOUTH |  | 34 | 2022-04-25 | 2022-06-06
C-PW-087930 | General Block Work | 22 | 2022-04-25 | 2022-05-24 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-087940 | Marking & Chasing Walls for MEP Services | 22 | 2022-05-11 | 2022-06-06 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
COMMON WORKS - SOUTH - MEP ROOMS |  | 19 | 2022-05-24 | 2022-06-15
C-PW-087950 | General Block Work | 8 | 2022-05-24 | 2022-06-02 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-087960 | Marking & Chasing Walls for MEP Services | 11 | 2022-06-02 | 2022-06-15 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
COOLING ROOM - SOUTH |  | 85 | 2022-06-15 | 2022-09-27
C-PW-087970 | Paint 1st Coat - Ceiling (Dust Sealer) | 8 | 2022-06-15 | 2022-06-25 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-087980 | Paint 1st Coat - Walls (Dust Sealer) | 17 | 2022-06-25 | 2022-07-18 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-087990 | Floor Finishes (Epoxy Resin Floor System) | 10 | 2022-08-28 | 2022-09-08 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088000 | Door Frame, Shutter & Ironmongery (Steel Doors) | 5 | 2022-09-08 | 2022-09-14 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088010 | Final Coat Paint | 8 | 2022-09-18 | 2022-09-27 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
GALLERY 4 AV, GALLERY 5 AV/ IT ROOM - SOUTH |  | 90 | 2022-06-15 | 2022-10-03
C-PW-088020 | Equipment Foundation & Upstand Works | 8 | 2022-06-15 | 2022-06-25 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088030 | Floor Trench Works | 10 | 2022-06-25 | 2022-07-06 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088040 | Paint 1st Coat - Ceiling (Dust Sealer) | 6 | 2022-07-06 | 2022-07-16 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088050 | Paint 1st Coat - Walls (Dust Sealer) | 6 | 2022-07-16 | 2022-07-24 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088060 | Grating Works | 5 | 2022-07-21 | 2022-07-27 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088070 | Floor Finishes (Epoxy Resin Floor System) | 6 | 2022-09-08 | 2022-09-15 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088080 | Doors & Ironmongery (Louvre Doors) | 5 | 2022-09-15 | 2022-09-21 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088090 | Final Coat Paint | 5 | 2022-09-27 | 2022-10-03 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
STORAGE - SOUTH |  | 200 | 2022-08-27 | 2023-04-23
C-PW-088100 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-27 | 01 | 14 | 01 | 45 | 005 | 05 |  | Building | General MEP | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-088110 | Wall Finishes (Paint Finish, Wall protection & Glazed security screen) | 6 | 2022-08-27 | 2022-09-03 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-088120 | Ceiling Grid / Support Works | 10 | 2022-09-06 | 2022-09-18 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-088130 | Ceiling Finishes (Dust Sealer) | 14 | 2022-09-18 | 2022-10-04 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-088140 | Floor Finishes (Epoxy Resin Floor System) | 11 | 2022-10-04 | 2022-10-18 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-088150 | Door Frames & Architrave Fixing | 6 | 2022-10-29 | 2022-11-05 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-088160 | Door Shuttering & Ironmongery | 3 | 2022-11-08 | 2022-11-12 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-088170 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-088180 | Final Finishes | 6 | 2023-04-12 | 2023-04-23 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
GALLERY 5 LOBBY AREAS - SOUTH |  | 224 | 2022-08-04 | 2023-04-27
C-PW-088190 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-04 | 01 | 14 | 01 | 45 | 005 | 01 |  | Building | General MEP | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088200 | Wall Finishes (Wall Lining, & Metal wall system) | 10 | 2022-08-04 | 2022-08-15 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088210 | Ceiling Grid / Support Works | 10 | 2022-08-14 | 2022-08-24 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088220 | Ceiling Finishes (Special Finish for Situ White Concrete) | 10 | 2022-08-25 | 2022-09-05 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088230 | Floor Finishes (Polished Concrete Floor System) | 10 | 2022-09-05 | 2022-09-17 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088240 | Roller Shutter Installation | 5 | 2022-09-15 | 2022-09-20 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088250 | Door Frames & Architrave Fixing | 5 | 2022-09-17 | 2022-09-21 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088260 | Door Shuttering & Ironmongery | 5 | 2022-09-24 | 2022-09-29 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088270 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088280 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
VIP MALE & FEMALETOILET, PUBLIC MALE & FEMALE WC - SOUTH |  | 270 | 2022-06-06 | 2023-04-27
C-PW-088290 | Floor Waterproofing Works | 14 | 2022-06-06 | 2022-06-22 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088300 | Floor Screed Works | 7 | 2022-06-23 | 2022-07-02 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088310 | MEP Clearance for Suspended Ceiling in Toilets | 0 |  | 2022-07-13 | 01 | 14 | 01 | 45 | 005 | 03 |  | Building | General MEP | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088320 | Wall Finishes (WC cubicles & wall lining) | 14 | 2022-07-04 | 2022-07-25 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088330 | Ceiling Grid / Support Works in Toilets | 6 | 2022-07-21 | 2022-07-28 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088340 | Ceiling Finishes (Metal tile ceiling & Plasterboard) | 11 | 2022-07-26 | 2022-08-09 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088350 | Floor Finishes (Terrazzo Resin Flooring System) | 14 | 2022-07-31 | 2022-08-16 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088360 | Door Frames & Architrave Fixing | 6 | 2022-08-16 | 2022-08-23 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088370 | Door Shuttering & Ironmongery | 5 | 2022-08-25 | 2022-08-31 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088380 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088390 | Installation of Lockers | 4 | 2023-04-12 | 2023-04-17 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088400 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
VIP RECEPTION, MALE DINING, FEMALE DINING & COURTYARD - SOUTH |  | 229 | 2022-08-04 | 2023-05-03
C-PW-088410 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-04 | 01 | 14 | 01 | 45 | 005 | 01 |  | Building | General MEP | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088420 | Wall Finishes (Plaster Render, Skirting, & Metal wall system) | 19 | 2022-08-04 | 2022-08-27 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088430 | Ceiling Grid / Support Works | 14 | 2022-08-20 | 2022-09-05 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088440 | Ceiling Finishes (Dust Sealer, & Acoustic Timber) | 14 | 2022-09-05 | 2022-09-21 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088450 | Floor Finishes (Epoxy Resin Floor System, & Stone Flooring) | 14 | 2022-10-19 | 2022-11-05 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088460 | Door Frames & Architrave Fixing | 5 | 2022-11-05 | 2022-11-10 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088470 | Door Shuttering & Ironmongery | 5 | 2022-11-10 | 2022-11-16 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088480 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088490 | Final Finishes | 11 | 2023-04-18 | 2023-05-03 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
MALE & FEMALE ABLUTIONS & PANTRIES - SOUTH |  | 256 | 2022-06-23 | 2023-04-27
C-PW-088500 | Floor Waterproofing Works | 14 | 2022-06-23 | 2022-07-13 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088510 | Floor Screed Works | 7 | 2022-07-13 | 2022-07-21 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088520 | MEP Clearance for Suspended Ceiling in Toilets | 0 |  | 2022-09-01 | 01 | 14 | 01 | 45 | 005 | 03 |  | Building | General MEP | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088530 | Wall Finishes (Plaster Render & wall lining) | 14 | 2022-08-22 | 2022-09-07 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088540 | Ceiling Grid / Support Works in Toilets | 6 | 2022-09-05 | 2022-09-11 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088550 | Ceiling Finishes (Plasterboard & Acoustic Timber) | 11 | 2022-09-08 | 2022-09-21 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088560 | Floor Finishes (Resin Floor System, Stone Tiles) | 14 | 2022-09-12 | 2022-09-29 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088570 | Door Frames & Architrave Fixing | 6 | 2022-09-29 | 2022-10-05 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088580 | Door Shuttering & Ironmongery | 5 | 2022-10-08 | 2022-10-15 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088590 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088600 | Installation of Lockers | 4 | 2023-04-12 | 2023-04-17 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
C-PW-088610 | Final Finishes & Fittings | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 45 | 005 | 03 |  | Building | Architecture | Museum | South East | L02 Gallery level | Wet Areas
PRAYER & MAJLIS - SOUTH |  | 245 | 2022-07-05 | 2023-04-27
C-PW-088620 | Plastering Works - Walls | 22 | 2022-07-05 | 2022-08-04 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088630 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-09-01 | 01 | 14 | 01 | 45 | 005 | 01 |  | Building | General MEP | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088640 | Wall Finishes (Plaster Render, Polished Plaster, Skirting & Feature Lining) | 11 | 2022-08-24 | 2022-09-06 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088650 | Ceiling Grid / Support Works | 13 | 2022-09-03 | 2022-09-18 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088660 | Ceiling Finishes (Plasterboard, & Acoustic Timber) | 13 | 2022-09-21 | 2022-10-06 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088670 | Floor Finishes (Carpet Broadloom, Stone Flooring) | 13 | 2022-10-06 | 2022-10-23 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088680 | Door Frames & Architrave Fixing | 5 | 2022-10-23 | 2022-10-29 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088690 | Door Shuttering & Ironmongery | 5 | 2022-10-29 | 2022-11-02 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088700 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088710 | Installation of Lockers | 3 | 2023-04-12 | 2023-04-16 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088720 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
CIRCULATIONS - SOUTH |  | 214 | 2022-08-16 | 2023-04-27
C-PW-088730 | Plastering Works - Walls | 22 | 2022-08-16 | 2022-09-11 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088740 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-09-14 | 01 | 14 | 01 | 45 | 005 | 01 |  | Building | General MEP | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088750 | Wall Finishes (Wall protection, Corner guards, Plaster Render, Wall Lining, Skirting, & Paint) | 11 | 2022-09-15 | 2022-09-28 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088760 | Ceiling Grid / Support Works | 10 | 2022-09-28 | 2022-10-10 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088770 | Ceiling Finishes (Interior Paint) | 10 | 2022-10-10 | 2022-10-22 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088780 | Floor Finishes (Epoxy Resin Floor System) | 10 | 2022-10-22 | 2022-11-01 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088790 | Door Frames & Architrave Fixing | 6 | 2022-11-02 | 2022-11-09 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088800 | Door Shuttering & Ironmongery | 3 | 2022-11-13 | 2022-11-16 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088810 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088820 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
COMMON WORKS - WEST |  | 22 | 2022-05-24 | 2022-06-19
C-PW-088830 | General Block Work | 14 | 2022-05-24 | 2022-06-09 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088840 | Marking & Chasing Walls for MEP Services | 14 | 2022-06-02 | 2022-06-19 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
COMMON WORKS - WEST - MEP ROOMS |  | 21 | 2022-06-09 | 2022-07-04
C-PW-088850 | General Block Work | 10 | 2022-06-09 | 2022-06-21 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088860 | Marking & Chasing Walls for MEP Services | 10 | 2022-06-23 | 2022-07-04 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
GALLERY 1 LOBBY AREAS - WEST |  | 208 | 2022-08-22 | 2023-04-27
C-PW-088870 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-22 | 01 | 14 | 01 | 45 | 005 | 01 |  | Building | General MEP | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088880 | Wall Finishes (Interior Paint) | 10 | 2022-09-03 | 2022-09-13 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088890 | Roller Shutter Installation | 5 | 2022-09-15 | 2022-09-20 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088900 | Ceiling Grid / Support Works | 10 | 2022-09-13 | 2022-09-25 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088910 | Ceiling Finishes (Special Finish for Situ White Concrete) | 10 | 2022-09-25 | 2022-10-05 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088920 | Floor Finishes (Polished Concrete Floor System) | 10 | 2022-10-06 | 2022-10-18 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088930 | Door Frames & Architrave Fixing | 8 | 2022-10-18 | 2022-10-27 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088940 | Door Shuttering & Ironmongery | 3 | 2022-10-27 | 2022-10-31 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088950 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-088960 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
COOLING ROOMS, GALLERY 1&2 AV/IT ROOM - WEST |  | 203 | 2022-08-15 | 2023-04-12
C-PW-088970 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-15 | 01 | 14 | 01 | 45 | 005 | 02 |  | Building | General MEP | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088980 | Wall Finishes (Interior Paint) | 14 | 2022-08-15 | 2022-08-31 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-088990 | Ceiling Grid / Support Works | 14 | 2022-08-27 | 2022-09-12 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-089000 | Ceiling Finishes (Dust Sealer) | 14 | 2022-09-12 | 2022-09-28 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-089010 | Floor Finishes (Epoxy Resin Floor System) | 11 | 2022-09-29 | 2022-10-13 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-089020 | Door Frames & Architrave Fixing | 6 | 2022-10-13 | 2022-10-20 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-089030 | Door Shuttering & Ironmongery | 6 | 2022-10-31 | 2022-11-08 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-089040 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 02 |  | Building | Architecture | Museum | South East | L02 Gallery level | MEP / Service Rooms
GALLERY 1&2 LOBBY AREAS - WEST |  | 204 | 2022-08-28 | 2023-04-27
C-PW-089050 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-28 | 01 | 14 | 01 | 45 | 005 | 01 |  | Building | General MEP | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-089060 | Wall Finishes (Interior Paint) | 10 | 2022-08-28 | 2022-09-07 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-089070 | Ceiling Grid / Support Works | 10 | 2022-09-08 | 2022-09-19 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-089080 | Ceiling Finishes (Special Finish for Situ White Concrete) | 10 | 2022-09-19 | 2022-10-01 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-089090 | Floor Finishes (Polished Concrete Floor System) | 10 | 2022-10-01 | 2022-10-12 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-089100 | Door Frames & Architrave Fixing | 8 | 2022-10-17 | 2022-10-25 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-089110 | Door Shuttering & Ironmongery | 3 | 2022-10-26 | 2022-10-30 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-089120 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-089130 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 45 | 005 | 01 |  | Building | Architecture | Museum | South East | L02 Gallery level | Circulation / Common Areas
STORAGE AREA - WEST |  | 200 | 2022-08-31 | 2023-04-27
C-PW-089140 | MEP Clearance for Suspended Ceiling | 0 |  | 2022-08-31 | 01 | 14 | 01 | 45 | 005 | 05 |  | Building | General MEP | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-089150 | Wall Finishes (Interior Paint) | 11 | 2022-08-31 | 2022-09-13 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-089160 | Ceiling Grid / Support Works | 5 | 2022-09-13 | 2022-09-19 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-089170 | Ceiling Finishes (Dust Sealer) | 5 | 2022-09-19 | 2022-09-25 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-089180 | Floor Finishes (Epoxy Resin Floor System) | 11 | 2022-09-25 | 2022-10-08 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-089190 | Door Frames & Architrave Fixing | 6 | 2022-10-08 | 2022-10-16 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-089200 | Door Shuttering & Ironmongery | 6 | 2022-10-17 | 2022-10-24 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-089210 | Joinery Fixing | 5 | 2023-04-08 | 2023-04-12 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-089220 | Final Finishes | 6 | 2023-04-18 | 2023-04-27 | 01 | 04 | 01 | 45 | 005 | 05 |  | Building | Architecture | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
MEP WORKS |  | 285 | 2021-12-23 | 2022-12-03
NORTH WEST |  | 241 | 2021-12-23 | 2022-10-10
GALLERY LOBBY AREAS- NORTH |  | 218 | 2021-12-23 | 2022-09-13
MECHANICAL |  | 211 | 2021-12-23 | 2022-09-04
HVAC SYSTEM WORKS |  | 161 | 2022-02-20 | 2022-09-04
C-PW-089230 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 15 | 2022-02-20 | 2022-03-09 | 01 | 06 | 01 | 46 | 005 | 01 |  | Building | HVAC | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089240 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-02-22 | 2022-03-13 | 01 | 06 | 01 | 46 | 005 | 01 |  | Building | HVAC | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089250 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-03-14 | 2022-03-26 | 01 | 06 | 01 | 46 | 005 | 01 |  | Building | HVAC | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089260 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-08-27 | 2022-09-04 | 01 | 06 | 01 | 46 | 005 | 01 |  | Building | HVAC | Museum | North West | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2021-12-23 | 2022-01-26
C-PW-089270 | 1st Fix Piping System (Supports, Piping) | 18 | 2021-12-23 | 2022-01-15 | 01 | 08 | 01 | 46 | 005 | 01 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089280 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-01-15 | 2022-01-26 | 01 | 08 | 01 | 46 | 005 | 01 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-02-13 | 2022-03-17
C-PW-089290 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-02-13 | 2022-03-06 | 01 | 08 | 01 | 46 | 005 | 01 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089300 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-03-06 | 2022-03-17 | 01 | 08 | 01 | 46 | 005 | 01 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 218 | 2021-12-23 | 2022-09-13
C-PW-089310 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 13 | 2021-12-23 | 2022-01-08 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089320 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-02-23 | 2022-03-15 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089330 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-03-15 | 2022-03-31 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089340 | LV Switchgears (DB's) | 5 | 2022-03-31 | 2022-04-05 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089350 | Cable/Wire Termination & Dressing | 7 | 2022-04-06 | 2022-04-14 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089360 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-08-27 | 2022-09-04 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089370 | Final Fix Electrical (Light Fixtures) | 10 | 2022-08-28 | 2022-09-08 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089380 | Final Fix Electrical (Installation of Lighting Control Panels) | 10 | 2022-08-30 | 2022-09-11 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089390 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-08-31 | 2022-09-13 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
ELV |  | 162 | 2022-02-17 | 2022-09-03
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 153 | 2022-02-17 | 2022-08-23
C-PW-089400 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-17 | 2022-03-01 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089410 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-02 | 2022-03-14 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089420 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-21 | 2022-08-23 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 151 | 2022-02-20 | 2022-08-23
C-PW-089430 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-02-20 | 2022-03-03 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089440 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-03-03 | 2022-03-15 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089450 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-21 | 2022-08-23 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 150 | 2022-02-21 | 2022-08-23
C-PW-089460 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-02-21 | 2022-03-06 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089470 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-03-06 | 2022-03-17 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089480 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-21 | 2022-08-23 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 150 | 2022-02-23 | 2022-08-25
C-PW-089490 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-02-23 | 2022-03-07 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089500 | 2nd Fix AV System Works (Wiring) | 10 | 2022-03-07 | 2022-03-20 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089510 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-22 | 2022-08-25 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 148 | 2022-02-26 | 2022-08-25
C-PW-089520 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-02-26 | 2022-03-09 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089530 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-03-09 | 2022-03-21 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089540 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-22 | 2022-08-25 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 148 | 2022-02-27 | 2022-08-27
C-PW-089550 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-27 | 2022-03-10 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089560 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-12 | 2022-03-23 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089570 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-24 | 2022-08-27 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 147 | 2022-03-01 | 2022-08-27
C-PW-089580 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-01 | 2022-03-13 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089590 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-13 | 2022-03-24 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089600 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-24 | 2022-08-27 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-08-27 | 2022-09-03
C-PW-089610 | Active Component System Works | 6 | 2022-08-27 | 2022-09-03 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 159 | 2022-02-10 | 2022-08-23
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 153 | 2022-02-17 | 2022-08-23
C-PW-089620 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-17 | 2022-03-01 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089630 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-02 | 2022-03-14 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089640 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-21 | 2022-08-23 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 151 | 2022-02-20 | 2022-08-23
C-PW-089650 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-02-20 | 2022-03-03 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089660 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-03 | 2022-03-15 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089670 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-21 | 2022-08-23 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 88 | 2022-02-10 | 2022-05-28
C-PW-089680 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-02-10 | 2022-03-01 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089690 | 2nd Fix Piping System - (Fittings) | 8 | 2022-03-01 | 2022-03-10 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-089700 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-05-18 | 2022-05-28 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
KITCHEN EXTRACT PLANT ROOM - NORTH |  | 147 | 2022-03-19 | 2022-09-14
MECHANICAL |  | 111 | 2022-04-21 | 2022-09-06
HVAC SYSTEM WORKS |  | 108 | 2022-04-25 | 2022-09-06
C-PW-089710 | 1st Fix HVAC (CHW Piping, Drain Pipes & Pressure Testing) | 7 | 2022-04-27 | 2022-05-09 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089720 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs & Testing) | 10 | 2022-04-25 | 2022-05-10 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089730 | 2nd Fix HVAC (FCUs, Droppers) | 6 | 2022-05-09 | 2022-05-15 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089740 | 2nd Fix HVAC (AHU) | 6 | 2022-05-15 | 2022-05-22 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089750 | Final Fix HVAC (Exhaust Louvre's,Grills, Diffusers, FCU Mouth Connection & Testing) | 3 | 2022-09-03 | 2022-09-06 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
COLD WATER SYSTEM WORKS |  | 12 | 2022-04-21 | 2022-05-09
C-PW-089760 | 1st Fix Piping System (Supports, Piping) | 6 | 2022-04-21 | 2022-04-27 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089770 | 2nd Fix Piping System (Valves & fittings) | 3 | 2022-04-27 | 2022-05-04 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089780 | Final Fix Fittings (Bib Tap) | 3 | 2022-05-05 | 2022-05-09 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
ELECTRICAL WORKS |  | 147 | 2022-03-19 | 2022-09-14
C-PW-089790 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-03-19 | 2022-03-27 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089800 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-04-28 | 2022-05-12 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089810 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 9 | 2022-05-12 | 2022-05-23 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089820 | LV Switchgears (DB's) | 5 | 2022-05-23 | 2022-05-28 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089830 | Cable/Wire Termination & Dressing | 7 | 2022-05-29 | 2022-06-06 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089840 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-08-31 | 2022-09-06 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089850 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-03 | 2022-09-11 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089860 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-05 | 2022-09-13 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089870 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-06 | 2022-09-14 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
ELV |  | 140 | 2022-03-21 | 2022-09-08
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 131 | 2022-03-21 | 2022-08-29
C-PW-089880 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-21 | 2022-04-02 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089890 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-02 | 2022-04-13 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089900 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-27 | 2022-08-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 130 | 2022-03-22 | 2022-08-29
C-PW-089910 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-22 | 2022-04-03 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089920 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089930 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-27 | 2022-08-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
INTERCOM SYSTEM |  | 128 | 2022-03-24 | 2022-08-29
C-PW-089940 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-03-24 | 2022-04-05 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089950 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089960 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-27 | 2022-08-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
AV SYSTEM |  | 128 | 2022-03-26 | 2022-08-30
C-PW-089970 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-07 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089980 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-089990 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-28 | 2022-08-30 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 127 | 2022-03-28 | 2022-08-30
C-PW-090000 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-28 | 2022-04-09 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090010 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-09 | 2022-04-21 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090020 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-28 | 2022-08-30 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 127 | 2022-03-30 | 2022-09-01
C-PW-090030 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-30 | 2022-04-11 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090040 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-11 | 2022-04-23 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090050 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 125 | 2022-03-31 | 2022-09-01
C-PW-090060 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090070 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-13 | 2022-04-25 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090080 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-01 | 2022-09-08
C-PW-090090 | Active Component System Works | 6 | 2022-09-01 | 2022-09-08 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 140 | 2022-03-21 | 2022-09-08
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 131 | 2022-03-21 | 2022-08-29
C-PW-090100 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-21 | 2022-04-02 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090110 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-02 | 2022-04-13 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090120 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-27 | 2022-08-29 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 130 | 2022-03-22 | 2022-08-29
C-PW-090130 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-22 | 2022-04-03 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090140 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-04 | 2022-04-16 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090150 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-27 | 2022-08-29 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
FIRE FIGHTING SYSTEM WORKS |  | 108 | 2022-04-27 | 2022-09-08
C-PW-090160 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 9 | 2022-04-27 | 2022-05-10 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090170 | 2nd Fix Piping System - (Droppers & testing) | 3 | 2022-05-10 | 2022-05-14 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090180 | Final Fix Piping System (Sprinkler Heads) | 3 | 2022-09-05 | 2022-09-08 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
COOLING ROOM - NORTH |  | 82 | 2022-03-21 | 2022-06-29
MECHANICAL |  | 78 | 2022-03-21 | 2022-06-23
HVAC SYSTEM WORKS |  | 65 | 2022-04-05 | 2022-06-23
C-PW-090190 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-04-05 | 2022-04-25 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090200 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-04-05 | 2022-04-26 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090210 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-04-25 | 2022-05-08 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090220 | Final Fix HVAC (Exhaust Louvre's,Grills, Diffusers, FCU Mouth Connection & Testing) | 6 | 2022-06-16 | 2022-06-23 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
DRAINAGE WORKS |  | 30 | 2022-03-21 | 2022-04-26
C-PW-090230 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-21 | 2022-04-12 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090240 | 2nd Fix Piping System (Fittings, Insulation) | 12 | 2022-04-12 | 2022-04-26 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 26 | 2022-04-02 | 2022-05-04
C-PW-090250 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-04-02 | 2022-04-17 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090260 | 2nd Fix Piping System (Fittings, Insulation) | 12 | 2022-04-18 | 2022-05-04 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
ELECTRICAL WORKS |  | 58 | 2022-04-18 | 2022-06-29
C-PW-090270 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-04-18 | 2022-05-04 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090280 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-05-04 | 2022-05-16 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090290 | LV Switchgears (DB's) | 5 | 2022-05-16 | 2022-05-22 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090300 | Cable/Wire Termination & Dressing | 7 | 2022-05-22 | 2022-05-30 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090310 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-06-15 | 2022-06-20 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090320 | Final Fix Electrical (Light Fixtures) | 7 | 2022-06-16 | 2022-06-25 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090330 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-06-19 | 2022-06-27 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090340 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-06-21 | 2022-06-29 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
ELV |  | 53 | 2022-04-20 | 2022-06-25
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 44 | 2022-04-20 | 2022-06-14
C-PW-090350 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-20 | 2022-05-05 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090360 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-05 | 2022-05-18 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090370 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 42 | 2022-04-23 | 2022-06-14
C-PW-090380 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-23 | 2022-05-08 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090390 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-08 | 2022-05-19 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090400 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
INTERCOM SYSTEM |  | 41 | 2022-04-24 | 2022-06-14
C-PW-090410 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-24 | 2022-05-09 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090420 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-10 | 2022-05-22 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090430 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
AV SYSTEM |  | 41 | 2022-04-26 | 2022-06-15
C-PW-090440 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090450 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090460 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-06-13 | 2022-06-15 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 39 | 2022-04-27 | 2022-06-15
C-PW-090470 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-14 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090480 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090490 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-06-13 | 2022-06-15 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 39 | 2022-04-30 | 2022-06-18
C-PW-090500 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090510 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-15 | 2022-05-28 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090520 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-06-15 | 2022-06-18 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 38 | 2022-05-05 | 2022-06-18
C-PW-090530 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090540 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-17 | 2022-05-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090550 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-06-15 | 2022-06-18 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-06-18 | 2022-06-25
C-PW-090560 | Active Component System Works | 6 | 2022-06-18 | 2022-06-25 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 71 | 2022-03-30 | 2022-06-25
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 44 | 2022-04-20 | 2022-06-14
C-PW-090570 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-20 | 2022-05-05 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090580 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-05 | 2022-05-18 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090590 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 42 | 2022-04-23 | 2022-06-14
C-PW-090600 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-23 | 2022-05-08 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090610 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-08 | 2022-05-19 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090620 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-06-12 | 2022-06-14 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
FIRE FIGHTING SYSTEM WORKS |  | 71 | 2022-03-30 | 2022-06-25
C-PW-090630 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-03-30 | 2022-04-17 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090640 | 2nd Fix Piping System - (Clean Agent/Foam water sprinkler fire Suppression system) & testing | 12 | 2022-04-18 | 2022-05-04 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090650 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-06-19 | 2022-06-25 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
GALLERY 3 AV/ IT ROOMS - NORTH |  | 85 | 2022-03-30 | 2022-07-14
MECHANICAL |  | 80 | 2022-03-30 | 2022-07-05
HVAC SYSTEM WORKS |  | 67 | 2022-04-14 | 2022-07-05
C-PW-090660 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-04-17 | 2022-05-09 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090670 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-04-14 | 2022-05-09 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090680 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-05-10 | 2022-05-18 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090690 | Final Fix HVAC (Exhaust Louvre's,Grills, Diffusers, FCU Mouth Connection & Testing) | 6 | 2022-06-29 | 2022-07-05 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
DRAINAGE WORKS |  | 30 | 2022-03-30 | 2022-05-09
C-PW-090700 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-30 | 2022-04-21 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090710 | 2nd Fix Piping System (Fittings, Insulation) | 12 | 2022-04-21 | 2022-05-09 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 26 | 2022-04-11 | 2022-05-14
C-PW-090720 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-04-11 | 2022-04-26 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090730 | 2nd Fix Piping System (Fittings, Insulation) | 12 | 2022-04-27 | 2022-05-14 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
ELECTRICAL WORKS |  | 58 | 2022-05-04 | 2022-07-14
C-PW-090740 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-05-04 | 2022-05-16 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090750 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-16 | 2022-06-01 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090760 | LV Switchgears (DB's) | 5 | 2022-06-01 | 2022-06-06 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090770 | Cable/Wire Termination & Dressing | 7 | 2022-06-07 | 2022-06-15 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090780 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-06-27 | 2022-07-04 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090790 | Final Fix Electrical (Light Fixtures) | 7 | 2022-06-29 | 2022-07-07 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090800 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-06-30 | 2022-07-09 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090810 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-07-03 | 2022-07-14 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
ELV |  | 56 | 2022-05-05 | 2022-07-13
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 47 | 2022-05-05 | 2022-06-29
C-PW-090820 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-18 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090830 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-18 | 2022-05-30 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090840 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-06-27 | 2022-06-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 46 | 2022-05-08 | 2022-06-29
C-PW-090850 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-05-08 | 2022-05-19 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090860 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-05-19 | 2022-06-01 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090870 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-06-27 | 2022-06-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
INTERCOM SYSTEM |  | 44 | 2022-05-10 | 2022-06-29
C-PW-090880 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-05-10 | 2022-05-22 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090890 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-05-22 | 2022-06-02 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090900 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-06-27 | 2022-06-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
AV SYSTEM |  | 44 | 2022-05-11 | 2022-07-02
C-PW-090910 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090920 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-24 | 2022-06-05 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090930 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-06-29 | 2022-07-02 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 42 | 2022-05-14 | 2022-07-02
C-PW-090940 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090950 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-25 | 2022-06-06 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090960 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-06-29 | 2022-07-02 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 42 | 2022-05-15 | 2022-07-04
C-PW-090970 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-15 | 2022-05-28 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090980 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-28 | 2022-06-08 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-090990 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-06-30 | 2022-07-04 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 41 | 2022-05-17 | 2022-07-04
C-PW-091000 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-17 | 2022-05-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091010 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-29 | 2022-06-11 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091020 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-06-30 | 2022-07-04 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-07-04 | 2022-07-13
C-PW-091030 | Active Component System Works | 6 | 2022-07-04 | 2022-07-13 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 70 | 2022-04-05 | 2022-06-29
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 47 | 2022-05-05 | 2022-06-29
C-PW-091040 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-18 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091050 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-18 | 2022-05-30 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091060 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-06-27 | 2022-06-29 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 46 | 2022-05-08 | 2022-06-29
C-PW-091070 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-05-08 | 2022-05-19 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091080 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-19 | 2022-06-01 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091090 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-06-27 | 2022-06-29 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
FIRE FIGHTING SYSTEM WORKS |  | 34 | 2022-04-05 | 2022-05-18
C-PW-091100 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-05 | 2022-04-24 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091110 | 2nd Fix Piping System - (Clean Agent/Foam water sprinkler fire Suppression system) & testing | 12 | 2022-04-24 | 2022-05-11 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091120 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-05-11 | 2022-05-18 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
STAFF MALE & FEMALE WC, WASH UP & LOUNGE KITCHEN- NORTH |  | 199 | 2022-02-10 | 2022-10-10
MECHANICAL |  | 155 | 2022-04-04 | 2022-10-10
HVAC SYSTEM WORKS |  | 75 | 2022-04-13 | 2022-07-17
C-PW-091130 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 15 | 2022-04-13 | 2022-05-04 | 01 | 06 | 01 | 46 | 005 | 03 |  | Building | HVAC | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091140 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-04-14 | 2022-05-08 | 01 | 06 | 01 | 46 | 005 | 03 |  | Building | HVAC | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091150 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-08 | 2022-05-19 | 01 | 06 | 01 | 46 | 005 | 03 |  | Building | HVAC | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091160 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-07-04 | 2022-07-17 | 01 | 06 | 01 | 46 | 005 | 03 |  | Building | HVAC | Museum | North West | L02 Gallery level | Wet Areas
DRAINAGE WORKS |  | 155 | 2022-04-04 | 2022-10-10
C-PW-091170 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-04 | 2022-04-25 | 01 | 08 | 01 | 46 | 005 | 03 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091180 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-25 | 2022-05-10 | 01 | 08 | 01 | 46 | 005 | 03 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091190 | Final Fix (Installation of Sanitaryware & Accessories) | 5 | 2022-10-03 | 2022-10-10 | 01 | 08 | 01 | 46 | 005 | 03 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Wet Areas
HOT & COLD WATER SYSTEM |  | 78 | 2022-04-09 | 2022-07-16
C-PW-091200 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-04-09 | 2022-04-25 | 01 | 08 | 01 | 46 | 005 | 03 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091210 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-04-26 | 2022-05-11 | 01 | 08 | 01 | 46 | 005 | 03 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091220 | Final Fix - Water Meter Installation | 3 | 2022-07-09 | 2022-07-16 | 01 | 08 | 01 | 46 | 005 | 03 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Wet Areas
ELECTRICAL WORKS |  | 125 | 2022-02-10 | 2022-07-13
C-PW-091230 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 13 | 2022-02-10 | 2022-02-24 | 01 | 07 | 01 | 46 | 005 | 03 |  | Building | Electrical | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091240 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-04-17 | 2022-05-09 | 01 | 07 | 01 | 46 | 005 | 03 |  | Building | Electrical | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091250 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-10 | 2022-05-25 | 01 | 07 | 01 | 46 | 005 | 03 |  | Building | Electrical | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091260 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-06-29 | 2022-07-09 | 01 | 07 | 01 | 46 | 005 | 03 |  | Building | Electrical | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091270 | Final Fix Electrical (Light Fixtures) | 7 | 2022-07-02 | 2022-07-13 | 01 | 07 | 01 | 46 | 005 | 03 |  | Building | Electrical | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091280 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-07-02 | 2022-07-13 | 01 | 07 | 01 | 46 | 005 | 03 |  | Building | Electrical | Museum | North West | L02 Gallery level | Wet Areas
ELV |  | 79 | 2022-02-17 | 2022-05-24
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 79 | 2022-02-17 | 2022-05-24
C-PW-091290 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-17 | 2022-03-01 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091300 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-10 | 2022-05-22 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091310 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-05-22 | 2022-05-24 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
AV SYSTEM |  | 78 | 2022-02-20 | 2022-05-24
C-PW-091320 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-02-20 | 2022-03-03 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091330 | 2nd Fix AV System Works (Wiring) | 10 | 2022-03-03 | 2022-03-15 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091340 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-05-22 | 2022-05-24 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
DATA AND TELECOMMUNICATION |  | 76 | 2022-02-21 | 2022-05-24
C-PW-091350 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-21 | 2022-03-06 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091360 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-06 | 2022-03-17 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091370 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-05-22 | 2022-05-24 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 74 | 2022-02-23 | 2022-05-24
C-PW-091380 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-23 | 2022-03-07 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091390 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-07 | 2022-03-20 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091400 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-05-22 | 2022-05-24 | 01 | 10 | 01 | 46 | 005 | 03 |  | Building | CCTV | Museum | North West | L02 Gallery level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 115 | 2022-02-26 | 2022-07-17
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 110 | 2022-02-26 | 2022-07-06
C-PW-091410 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-26 | 2022-03-09 | 01 | 09 | 01 | 46 | 005 | 03 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091420 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-09 | 2022-03-21 | 01 | 09 | 01 | 46 | 005 | 03 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091430 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-07-04 | 2022-07-06 | 01 | 09 | 01 | 46 | 005 | 03 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 108 | 2022-02-27 | 2022-07-06
C-PW-091440 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-02-27 | 2022-03-10 | 01 | 09 | 01 | 46 | 005 | 03 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091450 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-12 | 2022-03-23 | 01 | 09 | 01 | 46 | 005 | 03 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091460 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-07-04 | 2022-07-06 | 01 | 09 | 01 | 46 | 005 | 03 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Wet Areas
FIRE FIGHTING WORKS |  | 78 | 2022-04-09 | 2022-07-17
C-PW-091470 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 12 | 2022-04-09 | 2022-04-23 | 01 | 09 | 01 | 46 | 005 | 03 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091480 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-23 | 2022-05-05 | 01 | 09 | 01 | 46 | 005 | 03 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Wet Areas
C-PW-091490 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-07-04 | 2022-07-17 | 01 | 09 | 01 | 46 | 005 | 03 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Wet Areas
AHU, ELEC CUPBOARD - NORTH |  | 159 | 2022-02-26 | 2022-09-07
MECHANICAL |  | 105 | 2022-04-25 | 2022-09-03
HVAC SYSTEM WORKS |  | 97 | 2022-05-08 | 2022-09-03
C-PW-091500 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 15 | 2022-05-08 | 2022-05-25 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091510 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-05-10 | 2022-05-29 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091520 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-29 | 2022-06-11 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091530 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-08-24 | 2022-09-03 | 01 | 06 | 01 | 46 | 005 | 02 |  | Building | HVAC | Museum | North West | L02 Gallery level | MEP / Service Rooms
DRAINAGE WORKS |  | 29 | 2022-04-25 | 2022-06-01
C-PW-091540 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-25 | 2022-05-19 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091550 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-19 | 2022-06-01 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 24 | 2022-05-04 | 2022-06-01
C-PW-091560 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-05-04 | 2022-05-19 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091570 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-05-19 | 2022-06-01 | 01 | 08 | 01 | 46 | 005 | 02 |  | Building | Plumbing | Museum | North West | L02 Gallery level | MEP / Service Rooms
ELECTRICAL WORKS |  | 159 | 2022-02-26 | 2022-09-07
C-PW-091580 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-02-26 | 2022-03-13 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091590 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 13 | 2022-05-11 | 2022-05-26 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091600 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-26 | 2022-06-11 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091610 | LV Switchgears (DB's) | 5 | 2022-06-12 | 2022-06-16 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091620 | Cable/Wire Termination & Dressing | 7 | 2022-06-16 | 2022-06-25 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091630 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-08-24 | 2022-09-03 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091640 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-25 | 2022-09-03 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091650 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-28 | 2022-09-05 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091660 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-30 | 2022-09-07 | 01 | 07 | 01 | 46 | 005 | 02 |  | Building | Electrical | Museum | North West | L02 Gallery level | MEP / Service Rooms
ELV |  | 157 | 2022-02-27 | 2022-09-06
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 148 | 2022-02-27 | 2022-08-27
C-PW-091670 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-27 | 2022-03-10 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091680 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-12 | 2022-03-23 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091690 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-24 | 2022-08-27 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 146 | 2022-03-01 | 2022-08-27
C-PW-091700 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-01 | 2022-03-13 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091710 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-03-13 | 2022-03-24 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091720 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-24 | 2022-08-27 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
INTERCOM SYSTEM |  | 145 | 2022-03-02 | 2022-08-27
C-PW-091730 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-03-02 | 2022-03-15 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091740 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-03-15 | 2022-03-27 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091750 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-24 | 2022-08-27 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
AV SYSTEM |  | 145 | 2022-03-05 | 2022-08-29
C-PW-091760 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-03-05 | 2022-03-16 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091770 | 2nd Fix AV System Works (Wiring) | 10 | 2022-03-16 | 2022-03-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091780 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-25 | 2022-08-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 143 | 2022-03-07 | 2022-08-29
C-PW-091790 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-07 | 2022-03-19 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091800 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-03-19 | 2022-03-30 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091810 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-25 | 2022-08-29 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 143 | 2022-03-08 | 2022-08-30
C-PW-091820 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-08 | 2022-03-20 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091830 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-21 | 2022-04-02 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091840 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-28 | 2022-08-30 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 142 | 2022-03-10 | 2022-08-30
C-PW-091850 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-10 | 2022-03-22 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091860 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-22 | 2022-04-03 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091870 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-28 | 2022-08-30 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-08-30 | 2022-09-06
C-PW-091880 | Active Component System Works | 6 | 2022-08-30 | 2022-09-06 | 01 | 10 | 01 | 46 | 005 | 02 |  | Building | CCTV | Museum | North West | L02 Gallery level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 148 | 2022-02-27 | 2022-08-27
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 148 | 2022-02-27 | 2022-08-27
C-PW-091890 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-27 | 2022-03-10 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091900 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-12 | 2022-03-23 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091910 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-24 | 2022-08-27 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 146 | 2022-03-01 | 2022-08-27
C-PW-091920 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-01 | 2022-03-13 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091930 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-13 | 2022-03-24 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091940 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-24 | 2022-08-27 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 76 | 2022-05-04 | 2022-08-06
C-PW-091950 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-05-04 | 2022-05-23 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091960 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-23 | 2022-06-01 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
C-PW-091970 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-07-26 | 2022-08-06 | 01 | 09 | 01 | 46 | 005 | 02 |  | Building | Firefighting | Museum | North West | L02 Gallery level | MEP / Service Rooms
CIRCULATIONS & CORRIDORS- NORTH |  | 177 | 2022-02-13 | 2022-09-15
MECHANICAL |  | 173 | 2022-02-13 | 2022-09-11
HVAC SYSTEM WORKS |  | 152 | 2022-03-09 | 2022-09-11
C-PW-091980 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 15 | 2022-03-09 | 2022-03-27 | 01 | 06 | 01 | 46 | 005 | 01 |  | Building | HVAC | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-091990 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 17 | 2022-03-12 | 2022-03-31 | 01 | 06 | 01 | 46 | 005 | 01 |  | Building | HVAC | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092000 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-03-31 | 2022-04-12 | 01 | 06 | 01 | 46 | 005 | 01 |  | Building | HVAC | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092010 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-01 | 2022-09-11 | 01 | 06 | 01 | 46 | 005 | 01 |  | Building | HVAC | Museum | North West | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-02-13 | 2022-03-17
C-PW-092020 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-02-13 | 2022-03-06 | 01 | 08 | 01 | 46 | 005 | 01 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092030 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-03-06 | 2022-03-17 | 01 | 08 | 01 | 46 | 005 | 01 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-03-06 | 2022-04-09
C-PW-092040 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-03-06 | 2022-03-27 | 01 | 08 | 01 | 46 | 005 | 01 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092050 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-03-28 | 2022-04-09 | 01 | 08 | 01 | 46 | 005 | 01 |  | Building | Plumbing | Museum | North West | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 177 | 2022-02-13 | 2022-09-15
C-PW-092060 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 13 | 2022-02-13 | 2022-02-27 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092070 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-03-14 | 2022-04-02 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092080 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-04-02 | 2022-04-18 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092090 | LV Switchgears (DB's) | 5 | 2022-04-18 | 2022-04-24 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092100 | Cable/Wire Termination & Dressing | 7 | 2022-04-24 | 2022-05-05 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092110 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-01 | 2022-09-11 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092120 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-04 | 2022-09-12 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092130 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-05 | 2022-09-13 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092140 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-07 | 2022-09-15 | 01 | 07 | 01 | 46 | 005 | 01 |  | Building | Electrical | Museum | North West | L02 Gallery level | Circulation / Common Areas
ELV |  | 170 | 2022-02-17 | 2022-09-12
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 161 | 2022-02-17 | 2022-09-01
C-PW-092150 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-17 | 2022-03-01 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092160 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-02 | 2022-03-14 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092170 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 159 | 2022-02-20 | 2022-09-01
C-PW-092180 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-02-20 | 2022-03-03 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092190 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-03-03 | 2022-03-15 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092200 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 158 | 2022-02-21 | 2022-09-01
C-PW-092210 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-02-21 | 2022-03-06 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092220 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-03-06 | 2022-03-17 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092230 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 158 | 2022-02-23 | 2022-09-04
C-PW-092240 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-02-23 | 2022-03-07 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092250 | 2nd Fix AV System Works (Wiring) | 10 | 2022-03-07 | 2022-03-20 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092260 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-31 | 2022-09-04 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 156 | 2022-02-26 | 2022-09-04
C-PW-092270 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-02-26 | 2022-03-09 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092280 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-03-09 | 2022-03-21 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092290 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-31 | 2022-09-04 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 156 | 2022-02-27 | 2022-09-05
C-PW-092300 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-27 | 2022-03-10 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092310 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-03-12 | 2022-03-23 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092320 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-03 | 2022-09-05 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 155 | 2022-03-01 | 2022-09-05
C-PW-092330 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-01 | 2022-03-13 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092340 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-03-13 | 2022-03-24 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092350 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-03 | 2022-09-05 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-05 | 2022-09-12
C-PW-092360 | Active Component System Works | 6 | 2022-09-05 | 2022-09-12 | 01 | 10 | 01 | 46 | 005 | 01 |  | Building | CCTV | Museum | North West | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 161 | 2022-02-17 | 2022-09-01
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 161 | 2022-02-17 | 2022-09-01
C-PW-092370 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-17 | 2022-03-01 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092380 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-02 | 2022-03-14 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092390 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 159 | 2022-02-20 | 2022-09-01
C-PW-092400 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-02-20 | 2022-03-03 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092410 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-03 | 2022-03-15 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092420 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 70 | 2022-03-15 | 2022-06-08
C-PW-092430 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-03-15 | 2022-04-03 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092440 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-04-03 | 2022-04-12 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
C-PW-092450 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 8 | 2022-05-31 | 2022-06-08 | 01 | 09 | 01 | 46 | 005 | 01 |  | Building | Firefighting | Museum | North West | L02 Gallery level | Circulation / Common Areas
NORTH EAST |  | 237 | 2021-12-30 | 2022-10-12
MEMBERS MALE & FEMALE WC - EAST |  | 188 | 2021-12-30 | 2022-08-15
MECHANICAL |  | 188 | 2021-12-30 | 2022-08-15
HVAC SYSTEM WORKS |  | 114 | 2022-03-26 | 2022-08-14
C-PW-092460 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 15 | 2022-03-26 | 2022-04-12 | 01 | 06 | 01 | 44 | 005 | 03 |  | Building | HVAC | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092470 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-03-28 | 2022-04-17 | 01 | 06 | 01 | 44 | 005 | 03 |  | Building | HVAC | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092480 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-04-17 | 2022-04-28 | 01 | 06 | 01 | 44 | 005 | 03 |  | Building | HVAC | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092490 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-08-04 | 2022-08-14 | 01 | 06 | 01 | 44 | 005 | 03 |  | Building | HVAC | Museum | North East | L02 Gallery level | Wet Areas
DRAINAGE WORKS |  | 186 | 2021-12-30 | 2022-08-14
C-PW-092500 | 1st Fix Piping System (Supports, Piping) | 18 | 2021-12-30 | 2022-01-22 | 01 | 08 | 01 | 44 | 005 | 03 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092510 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-01-22 | 2022-02-02 | 01 | 08 | 01 | 44 | 005 | 03 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092520 | Final Fix (Installation of Sanitaryware & Accessories) | 8 | 2022-08-04 | 2022-08-14 | 01 | 08 | 01 | 44 | 005 | 03 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Wet Areas
HOT & COLD WATER SYSTEM |  | 118 | 2022-03-22 | 2022-08-15
C-PW-092530 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-22 | 2022-04-07 | 01 | 08 | 01 | 44 | 005 | 03 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092540 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-04-09 | 2022-04-20 | 01 | 08 | 01 | 44 | 005 | 03 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092550 | Final Fix - Water Meter Installation | 2 | 2022-08-14 | 2022-08-15 | 01 | 08 | 01 | 44 | 005 | 03 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Wet Areas
ELECTRICAL WORKS |  | 187 | 2021-12-30 | 2022-08-15
C-PW-092560 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2021-12-30 | 2022-01-12 | 01 | 07 | 01 | 44 | 005 | 03 |  | Building | Electrical | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092570 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-03-30 | 2022-04-14 | 01 | 07 | 01 | 44 | 005 | 03 |  | Building | Electrical | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092580 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-04-14 | 2022-05-04 | 01 | 07 | 01 | 44 | 005 | 03 |  | Building | Electrical | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092590 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-08-04 | 2022-08-14 | 01 | 07 | 01 | 44 | 005 | 03 |  | Building | Electrical | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092600 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-07 | 2022-08-15 | 01 | 07 | 01 | 44 | 005 | 03 |  | Building | Electrical | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092610 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-07 | 2022-08-15 | 01 | 07 | 01 | 44 | 005 | 03 |  | Building | Electrical | Museum | North East | L02 Gallery level | Wet Areas
ELV |  | 151 | 2022-02-05 | 2022-08-07
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 151 | 2022-02-05 | 2022-08-07
C-PW-092620 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-02-05 | 2022-02-16 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092630 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092640 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
AV SYSTEM |  | 149 | 2022-02-06 | 2022-08-07
C-PW-092650 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-02-06 | 2022-02-17 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092660 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-18 | 2022-04-30 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092670 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
DATA AND TELECOMMUNICATION |  | 148 | 2022-02-08 | 2022-08-07
C-PW-092680 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-02-08 | 2022-02-20 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092690 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-20 | 2022-05-05 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092700 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 146 | 2022-02-09 | 2022-08-07
C-PW-092710 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-02-09 | 2022-02-22 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092720 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-23 | 2022-05-09 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092730 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 10 | 01 | 44 | 005 | 03 |  | Building | CCTV | Museum | North East | L02 Gallery level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 151 | 2022-02-05 | 2022-08-07
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 151 | 2022-02-05 | 2022-08-07
C-PW-092740 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-02-05 | 2022-02-16 | 01 | 09 | 01 | 44 | 005 | 03 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092750 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-26 | 2022-05-11 | 01 | 09 | 01 | 44 | 005 | 03 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092760 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 09 | 01 | 44 | 005 | 03 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 149 | 2022-02-06 | 2022-08-07
C-PW-092770 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-02-06 | 2022-02-17 | 01 | 09 | 01 | 44 | 005 | 03 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092780 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-28 | 2022-05-14 | 01 | 09 | 01 | 44 | 005 | 03 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092790 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 09 | 01 | 44 | 005 | 03 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Wet Areas
FIRE FIGHTING WORKS |  | 69 | 2022-04-05 | 2022-06-27
C-PW-092800 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 12 | 2022-04-05 | 2022-04-18 | 01 | 09 | 01 | 44 | 005 | 03 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092810 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-19 | 2022-04-27 | 01 | 09 | 01 | 44 | 005 | 03 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Wet Areas
C-PW-092820 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-06-18 | 2022-06-27 | 01 | 09 | 01 | 44 | 005 | 03 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Wet Areas
GALLERY LOBBY, WALKWAY & VIEWING PLATFORM - EAST |  | 159 | 2022-03-12 | 2022-09-21
MECHANICAL |  | 152 | 2022-03-12 | 2022-09-13
HVAC SYSTEM WORKS |  | 144 | 2022-03-21 | 2022-09-13
C-PW-092830 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-03-22 | 2022-04-11 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092840 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-03-21 | 2022-04-11 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092850 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-04-11 | 2022-04-23 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092860 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-04 | 2022-09-13 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 24 | 2022-03-12 | 2022-04-09
C-PW-092870 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-12 | 2022-03-27 | 01 | 08 | 01 | 44 | 005 | 01 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092880 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-03-27 | 2022-04-09 | 01 | 08 | 01 | 44 | 005 | 01 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 24 | 2022-03-17 | 2022-04-13
C-PW-092890 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-03-17 | 2022-04-02 | 01 | 08 | 01 | 44 | 005 | 01 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092900 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-02 | 2022-04-13 | 01 | 08 | 01 | 44 | 005 | 01 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 158 | 2022-03-12 | 2022-09-19
C-PW-092910 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 12 | 2022-03-12 | 2022-03-26 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092920 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-03-24 | 2022-04-12 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092930 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-04-12 | 2022-04-27 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092940 | LV Switchgears (DB's) | 5 | 2022-04-28 | 2022-05-07 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092950 | Cable/Wire Termination & Dressing | 7 | 2022-05-07 | 2022-05-15 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092960 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-01 | 2022-09-11 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092970 | Final Fix Electrical (Light Fixtures) | 10 | 2022-09-04 | 2022-09-15 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092980 | Final Fix Electrical (Installation of Lighting Control Panels) | 10 | 2022-09-05 | 2022-09-18 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-092990 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-09-07 | 2022-09-19 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
ELV |  | 158 | 2022-03-13 | 2022-09-21
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 149 | 2022-03-13 | 2022-09-11
C-PW-093000 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-13 | 2022-03-26 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093010 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-03-26 | 2022-04-06 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093020 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 147 | 2022-03-15 | 2022-09-11
C-PW-093030 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-15 | 2022-03-27 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093040 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-03-27 | 2022-04-09 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093050 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 146 | 2022-03-17 | 2022-09-11
C-PW-093060 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-03-17 | 2022-03-29 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093070 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-03-29 | 2022-04-10 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093080 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 146 | 2022-03-19 | 2022-09-13
C-PW-093090 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-03-19 | 2022-03-30 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093100 | 2nd Fix AV System Works (Wiring) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093110 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-13 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 144 | 2022-03-21 | 2022-09-13
C-PW-093120 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-21 | 2022-04-02 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093130 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-02 | 2022-04-13 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093140 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-10 | 2022-09-13 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 144 | 2022-03-22 | 2022-09-14
C-PW-093150 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-22 | 2022-04-04 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093160 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-04 | 2022-04-16 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093170 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 142 | 2022-03-24 | 2022-09-14
C-PW-093180 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-24 | 2022-04-05 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093190 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-05 | 2022-04-18 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093200 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-14 | 2022-09-21
C-PW-093210 | Active Component System Works | 6 | 2022-09-14 | 2022-09-21 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 149 | 2022-03-13 | 2022-09-11
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 149 | 2022-03-13 | 2022-09-11
C-PW-093220 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-13 | 2022-03-26 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093230 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-03-26 | 2022-04-06 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093240 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 147 | 2022-03-15 | 2022-09-11
C-PW-093250 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-15 | 2022-03-27 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093260 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-03-27 | 2022-04-09 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093270 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 78 | 2022-03-17 | 2022-06-19
C-PW-093280 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-03-17 | 2022-04-04 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093290 | 2nd Fix Piping System - (Fittings) | 8 | 2022-04-05 | 2022-04-13 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093300 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-06-09 | 2022-06-19 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
CIRCULATIONS - EAST |  | 151 | 2022-03-22 | 2022-09-22
MECHANICAL |  | 143 | 2022-03-22 | 2022-09-13
HVAC SYSTEM WORKS |  | 131 | 2022-04-05 | 2022-09-13
C-PW-093310 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 17 | 2022-04-07 | 2022-04-27 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093320 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 18 | 2022-04-05 | 2022-04-27 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093330 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-04-27 | 2022-05-12 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093340 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 7 | 2022-09-05 | 2022-09-13 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 26 | 2022-03-22 | 2022-04-21
C-PW-093350 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-03-22 | 2022-04-10 | 01 | 08 | 01 | 44 | 005 | 01 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093360 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-10 | 2022-04-21 | 01 | 08 | 01 | 44 | 005 | 01 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-04-02 | 2022-05-09
C-PW-093370 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-02 | 2022-04-23 | 01 | 08 | 01 | 44 | 005 | 01 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093380 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-24 | 2022-05-09 | 01 | 08 | 01 | 44 | 005 | 01 |  | Building | Plumbing | Museum | North East | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 151 | 2022-03-22 | 2022-09-22
C-PW-093390 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 12 | 2022-03-22 | 2022-04-05 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093400 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-04-10 | 2022-04-27 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093410 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-04-28 | 2022-05-17 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093420 | LV Switchgears (DB's) | 5 | 2022-05-17 | 2022-05-23 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093430 | Cable/Wire Termination & Dressing | 7 | 2022-05-23 | 2022-05-31 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093440 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-09-08 | 2022-09-17 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093450 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-10 | 2022-09-18 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093460 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-12 | 2022-09-20 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093470 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-14 | 2022-09-22 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
ELV |  | 147 | 2022-03-24 | 2022-09-19
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 138 | 2022-03-24 | 2022-09-08
C-PW-093480 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-24 | 2022-04-05 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093490 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093500 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-06 | 2022-09-08 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 136 | 2022-03-26 | 2022-09-08
C-PW-093510 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-07 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093520 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093530 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-06 | 2022-09-08 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 135 | 2022-03-28 | 2022-09-08
C-PW-093540 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-03-28 | 2022-04-09 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093550 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-09 | 2022-04-21 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093560 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-06 | 2022-09-08 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 135 | 2022-03-30 | 2022-09-11
C-PW-093570 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-03-30 | 2022-04-11 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093580 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-11 | 2022-04-23 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093590 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 133 | 2022-03-31 | 2022-09-11
C-PW-093600 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093610 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-13 | 2022-04-25 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093620 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 133 | 2022-04-03 | 2022-09-13
C-PW-093630 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-03 | 2022-04-14 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093640 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093650 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-13 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 131 | 2022-04-04 | 2022-09-13
C-PW-093660 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-04 | 2022-04-17 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093670 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-17 | 2022-04-28 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093680 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-10 | 2022-09-13 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-13 | 2022-09-19
C-PW-093690 | Active Component System Works | 6 | 2022-09-13 | 2022-09-19 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 138 | 2022-03-24 | 2022-09-08
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 138 | 2022-03-24 | 2022-09-08
C-PW-093700 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-24 | 2022-04-05 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093710 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-05 | 2022-04-17 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093720 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-06 | 2022-09-08 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 136 | 2022-03-26 | 2022-09-08
C-PW-093730 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-07 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093740 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-07 | 2022-04-19 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093750 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-06 | 2022-09-08 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 74 | 2022-04-11 | 2022-07-13
C-PW-093760 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-11 | 2022-04-30 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093770 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-04-30 | 2022-05-12 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-093780 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 7 | 2022-07-02 | 2022-07-13 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
ELECT. CUPBOARD - EAST |  | 136 | 2022-03-31 | 2022-09-14
MECHANICAL |  | 132 | 2022-03-31 | 2022-09-10
HVAC SYSTEM WORKS |  | 124 | 2022-04-10 | 2022-09-10
C-PW-093790 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 14 | 2022-04-10 | 2022-04-26 | 01 | 06 | 01 | 44 | 005 | 02 |  | Building | HVAC | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093800 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-04-26 | 2022-05-18 | 01 | 06 | 01 | 44 | 005 | 02 |  | Building | HVAC | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093810 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-19 | 2022-05-31 | 01 | 06 | 01 | 44 | 005 | 02 |  | Building | HVAC | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093820 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-08-31 | 2022-09-10 | 01 | 06 | 01 | 44 | 005 | 02 |  | Building | HVAC | Museum | North East | L02 Gallery level | MEP / Service Rooms
DRAINAGE WORKS |  | 22 | 2022-03-31 | 2022-04-26
C-PW-093830 | 1st Fix Piping System (Supports, Piping) | 12 | 2022-03-31 | 2022-04-14 | 01 | 08 | 01 | 44 | 005 | 02 |  | Building | Plumbing | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093840 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-14 | 2022-04-26 | 01 | 08 | 01 | 44 | 005 | 02 |  | Building | Plumbing | Museum | North East | L02 Gallery level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 29 | 2022-04-06 | 2022-05-14
C-PW-093850 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-04-06 | 2022-04-27 | 01 | 08 | 01 | 44 | 005 | 02 |  | Building | Plumbing | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093860 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-04-27 | 2022-05-14 | 01 | 08 | 01 | 44 | 005 | 02 |  | Building | Plumbing | Museum | North East | L02 Gallery level | MEP / Service Rooms
ELECTRICAL WORKS |  | 132 | 2022-04-05 | 2022-09-14
C-PW-093870 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-04-05 | 2022-04-21 | 01 | 07 | 01 | 44 | 005 | 02 |  | Building | Electrical | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093880 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-04-13 | 2022-05-07 | 01 | 07 | 01 | 44 | 005 | 02 |  | Building | Electrical | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093890 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-05-07 | 2022-05-23 | 01 | 07 | 01 | 44 | 005 | 02 |  | Building | Electrical | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093900 | LV Switchgears (DB's) | 5 | 2022-05-23 | 2022-05-28 | 01 | 07 | 01 | 44 | 005 | 02 |  | Building | Electrical | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093910 | Cable/Wire Termination & Dressing | 7 | 2022-05-29 | 2022-06-06 | 01 | 07 | 01 | 44 | 005 | 02 |  | Building | Electrical | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093920 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-08-31 | 2022-09-10 | 01 | 07 | 01 | 44 | 005 | 02 |  | Building | Electrical | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093930 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-03 | 2022-09-11 | 01 | 07 | 01 | 44 | 005 | 02 |  | Building | Electrical | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093940 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-04 | 2022-09-12 | 01 | 07 | 01 | 44 | 005 | 02 |  | Building | Electrical | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093950 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-06 | 2022-09-14 | 01 | 07 | 01 | 44 | 005 | 02 |  | Building | Electrical | Museum | North East | L02 Gallery level | MEP / Service Rooms
ELV |  | 128 | 2022-04-07 | 2022-09-12
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 119 | 2022-04-07 | 2022-09-01
C-PW-093960 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093970 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-093980 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 118 | 2022-04-09 | 2022-09-01
C-PW-093990 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-21 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094000 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-04-21 | 2022-05-07 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094010 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
INTERCOM SYSTEM |  | 116 | 2022-04-11 | 2022-09-01
C-PW-094020 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-04-11 | 2022-04-23 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094030 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-04-23 | 2022-05-09 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094040 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
AV SYSTEM |  | 116 | 2022-04-13 | 2022-09-03
C-PW-094050 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-13 | 2022-04-25 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094060 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-25 | 2022-05-10 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094070 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-31 | 2022-09-03 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 114 | 2022-04-14 | 2022-09-03
C-PW-094080 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-14 | 2022-04-26 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094090 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-27 | 2022-05-12 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094100 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-31 | 2022-09-03 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 114 | 2022-04-17 | 2022-09-05
C-PW-094110 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-04-17 | 2022-04-28 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094120 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-28 | 2022-05-14 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094130 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-03 | 2022-09-05 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 113 | 2022-04-18 | 2022-09-05
C-PW-094140 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-04-18 | 2022-05-04 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094150 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-04 | 2022-05-16 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094160 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-03 | 2022-09-05 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-05 | 2022-09-12
C-PW-094170 | Active Component System Works | 6 | 2022-09-05 | 2022-09-12 | 01 | 10 | 01 | 44 | 005 | 02 |  | Building | CCTV | Museum | North East | L02 Gallery level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 119 | 2022-04-07 | 2022-09-01
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 119 | 2022-04-07 | 2022-09-01
C-PW-094180 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-07 | 2022-04-19 | 01 | 09 | 01 | 44 | 005 | 02 |  | Building | Firefighting | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094190 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-19 | 2022-05-04 | 01 | 09 | 01 | 44 | 005 | 02 |  | Building | Firefighting | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094200 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 09 | 01 | 44 | 005 | 02 |  | Building | Firefighting | Museum | North East | L02 Gallery level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 118 | 2022-04-09 | 2022-09-01
C-PW-094210 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-09 | 2022-04-21 | 01 | 09 | 01 | 44 | 005 | 02 |  | Building | Firefighting | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094220 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-21 | 2022-05-07 | 01 | 09 | 01 | 44 | 005 | 02 |  | Building | Firefighting | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094230 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-30 | 2022-09-01 | 01 | 09 | 01 | 44 | 005 | 02 |  | Building | Firefighting | Museum | North East | L02 Gallery level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 70 | 2022-04-16 | 2022-07-09
C-PW-094240 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-16 | 2022-05-08 | 01 | 09 | 01 | 44 | 005 | 02 |  | Building | Firefighting | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094250 | 2nd Fix Piping System - (Fittings) | 8 | 2022-05-08 | 2022-05-17 | 01 | 09 | 01 | 44 | 005 | 02 |  | Building | Firefighting | Museum | North East | L02 Gallery level | MEP / Service Rooms
C-PW-094260 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-06-30 | 2022-07-09 | 01 | 09 | 01 | 44 | 005 | 02 |  | Building | Firefighting | Museum | North East | L02 Gallery level | MEP / Service Rooms
GALLERY 4&5 LOBBY AREAS - SOUTH |  | 237 | 2021-12-30 | 2022-10-12
MECHANICAL |  | 234 | 2021-12-30 | 2022-10-10
HVAC SYSTEM WORKS |  | 90 | 2022-06-21 | 2022-10-10
C-PW-094270 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-06-21 | 2022-07-17 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094280 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-06-27 | 2022-07-20 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094290 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-07-20 | 2022-08-02 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094300 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-29 | 2022-10-10 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2021-12-30 | 2022-02-02
C-PW-094310 | 1st Fix Piping System (Supports, Piping) | 18 | 2021-12-30 | 2022-01-22 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094320 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-01-22 | 2022-02-02 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-06-18 | 2022-07-25
C-PW-094330 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-18 | 2022-07-09 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094340 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-13 | 2022-07-25 | 01 | 06 | 01 | 44 | 005 | 01 |  | Building | HVAC | Museum | North East | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 142 | 2022-04-21 | 2022-10-12
C-PW-094350 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-04-21 | 2022-05-07 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094360 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-06-26 | 2022-07-18 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094370 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-18 | 2022-08-04 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094380 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-27 | 2022-10-06 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094390 | Final Fix Electrical (Light Fixtures) | 10 | 2022-09-29 | 2022-10-12 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094400 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-09-29 | 2022-10-12 | 01 | 07 | 01 | 44 | 005 | 01 |  | Building | Electrical | Museum | North East | L02 Gallery level | Circulation / Common Areas
ELV |  | 101 | 2022-06-06 | 2022-10-06
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 92 | 2022-06-06 | 2022-09-26
C-PW-094410 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-06 | 2022-06-18 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094420 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094430 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 91 | 2022-06-08 | 2022-09-26
C-PW-094440 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094450 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-20 | 2022-07-02 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094460 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 89 | 2022-06-09 | 2022-09-26
C-PW-094470 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-09 | 2022-06-22 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094480 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-22 | 2022-07-04 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094490 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 89 | 2022-06-12 | 2022-09-28
C-PW-094500 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-12 | 2022-06-23 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094510 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-23 | 2022-07-06 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094520 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-26 | 2022-09-28 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 88 | 2022-06-14 | 2022-09-28
C-PW-094530 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094540 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-26 | 2022-07-07 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094550 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-26 | 2022-09-28 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 88 | 2022-06-15 | 2022-10-01
C-PW-094560 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-15 | 2022-06-27 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094570 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-28 | 2022-07-13 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094580 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-10-01 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 86 | 2022-06-18 | 2022-10-01
C-PW-094590 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-18 | 2022-06-29 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094600 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-29 | 2022-07-14 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094610 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-10-01 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-01 | 2022-10-06
C-PW-094620 | Active Component System Works | 6 | 2022-10-01 | 2022-10-06 | 01 | 10 | 01 | 44 | 005 | 01 |  | Building | CCTV | Museum | North East | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 92 | 2022-06-06 | 2022-09-26
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 92 | 2022-06-06 | 2022-09-26
C-PW-094630 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-06 | 2022-06-18 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094640 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094650 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 91 | 2022-06-08 | 2022-09-26
C-PW-094660 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-08 | 2022-06-20 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094670 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-20 | 2022-07-02 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094680 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 64 | 2022-06-27 | 2022-09-14
C-PW-094690 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-27 | 2022-07-19 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094700 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-19 | 2022-07-28 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
C-PW-094710 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-05 | 2022-09-14 | 01 | 09 | 01 | 44 | 005 | 01 |  | Building | Firefighting | Museum | North East | L02 Gallery level | Circulation / Common Areas
SOUTH WEST |  | 141 | 2022-06-14 | 2022-12-03
CIRCULATIONS & CORRIDORS - WEST |  | 141 | 2022-06-14 | 2022-12-03
MECHANICAL |  | 140 | 2022-06-14 | 2022-12-01
HVAC SYSTEM WORKS |  | 132 | 2022-06-23 | 2022-12-01
C-PW-094720 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 18 | 2022-06-23 | 2022-07-18 | 01 | 06 | 01 | 47 | 005 | 01 |  | Building | HVAC | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094730 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 17 | 2022-07-18 | 2022-08-08 | 01 | 06 | 01 | 47 | 005 | 01 |  | Building | HVAC | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094740 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-08-08 | 2022-08-20 | 01 | 06 | 01 | 47 | 005 | 01 |  | Building | HVAC | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094750 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-21 | 2022-12-01 | 01 | 06 | 01 | 47 | 005 | 01 |  | Building | HVAC | Museum | South West | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-06-14 | 2022-07-21
C-PW-094760 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-14 | 2022-07-05 | 01 | 08 | 01 | 47 | 005 | 01 |  | Building | Plumbing | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094770 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-05 | 2022-07-21 | 01 | 08 | 01 | 47 | 005 | 01 |  | Building | Plumbing | Museum | South West | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-06-20 | 2022-07-26
C-PW-094780 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-20 | 2022-07-14 | 01 | 08 | 01 | 47 | 005 | 01 |  | Building | Plumbing | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094790 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-14 | 2022-07-26 | 01 | 08 | 01 | 47 | 005 | 01 |  | Building | Plumbing | Museum | South West | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 141 | 2022-06-14 | 2022-12-03
C-PW-094800 | 1st Fix Electrical Works (Conduits & Boxes) - Power and Lighting System | 13 | 2022-06-14 | 2022-06-29 | 01 | 07 | 01 | 47 | 005 | 01 |  | Building | Electrical | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094810 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-06-30 | 2022-07-26 | 01 | 07 | 01 | 47 | 005 | 01 |  | Building | Electrical | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094820 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-26 | 2022-08-11 | 01 | 07 | 01 | 47 | 005 | 01 |  | Building | Electrical | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094830 | LV Switchgears (DB's) | 5 | 2022-08-11 | 2022-08-17 | 01 | 07 | 01 | 47 | 005 | 01 |  | Building | Electrical | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094840 | Cable/Wire Termination & Dressing | 7 | 2022-08-17 | 2022-08-25 | 01 | 07 | 01 | 47 | 005 | 01 |  | Building | Electrical | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094850 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-17 | 2022-11-27 | 01 | 07 | 01 | 47 | 005 | 01 |  | Building | Electrical | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094860 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-19 | 2022-11-27 | 01 | 07 | 01 | 47 | 005 | 01 |  | Building | Electrical | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094870 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-21 | 2022-11-29 | 01 | 07 | 01 | 47 | 005 | 01 |  | Building | Electrical | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094880 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-23 | 2022-12-03 | 01 | 07 | 01 | 47 | 005 | 01 |  | Building | Electrical | Museum | South West | L02 Gallery level | Circulation / Common Areas
ELV |  | 134 | 2022-06-19 | 2022-11-28
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 125 | 2022-06-19 | 2022-11-17
C-PW-094890 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-19 | 2022-07-02 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094900 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-02 | 2022-07-17 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094910 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-17 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 124 | 2022-06-21 | 2022-11-17
C-PW-094920 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-21 | 2022-07-03 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094930 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-03 | 2022-07-19 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094940 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-17 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 122 | 2022-06-23 | 2022-11-17
C-PW-094950 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-23 | 2022-07-05 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094960 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-07-05 | 2022-07-20 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094970 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-17 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 122 | 2022-06-25 | 2022-11-20
C-PW-094980 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-25 | 2022-07-06 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-094990 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-07 | 2022-07-23 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095000 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-17 | 2022-11-20 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 120 | 2022-06-27 | 2022-11-20
C-PW-095010 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095020 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095030 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-17 | 2022-11-20 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 120 | 2022-06-28 | 2022-11-22
C-PW-095040 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-28 | 2022-07-14 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095050 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-14 | 2022-07-26 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095060 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-19 | 2022-11-22 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 119 | 2022-06-30 | 2022-11-22
C-PW-095070 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-30 | 2022-07-16 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095080 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-16 | 2022-07-28 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095090 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-19 | 2022-11-22 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-22 | 2022-11-28
C-PW-095100 | Active Component System Works | 6 | 2022-11-22 | 2022-11-28 | 01 | 10 | 01 | 47 | 005 | 01 |  | Building | CCTV | Museum | South West | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 125 | 2022-06-19 | 2022-11-17
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 125 | 2022-06-19 | 2022-11-17
C-PW-095110 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-19 | 2022-07-02 | 01 | 09 | 01 | 47 | 005 | 01 |  | Building | Firefighting | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095120 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-02 | 2022-07-17 | 01 | 09 | 01 | 47 | 005 | 01 |  | Building | Firefighting | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095130 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-17 | 01 | 09 | 01 | 47 | 005 | 01 |  | Building | Firefighting | Museum | South West | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 124 | 2022-06-21 | 2022-11-17
C-PW-095140 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-21 | 2022-07-03 | 01 | 09 | 01 | 47 | 005 | 01 |  | Building | Firefighting | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095150 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-03 | 2022-07-19 | 01 | 09 | 01 | 47 | 005 | 01 |  | Building | Firefighting | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095160 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-17 | 01 | 09 | 01 | 47 | 005 | 01 |  | Building | Firefighting | Museum | South West | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 98 | 2022-07-05 | 2022-11-02
C-PW-095170 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-07-05 | 2022-07-26 | 01 | 09 | 01 | 47 | 005 | 01 |  | Building | Firefighting | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095180 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-07-27 | 2022-08-06 | 01 | 09 | 01 | 47 | 005 | 01 |  | Building | Firefighting | Museum | South West | L02 Gallery level | Circulation / Common Areas
C-PW-095190 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 8 | 2022-10-24 | 2022-11-02 | 01 | 09 | 01 | 47 | 005 | 01 |  | Building | Firefighting | Museum | South West | L02 Gallery level | Circulation / Common Areas
SOUTH EAST |  | 277 | 2022-01-03 | 2022-12-01
COOLING ROOM - SOUTH |  | 78 | 2022-06-25 | 2022-09-28
MECHANICAL |  | 73 | 2022-06-25 | 2022-09-22
HVAC SYSTEM WORKS |  | 65 | 2022-07-04 | 2022-09-22
C-PW-095200 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-07-04 | 2022-07-28 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095210 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-07-31 | 2022-08-18 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095220 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-08-18 | 2022-08-28 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095230 | Final Fix HVAC (Exhaust Louvre's,Grills, Diffusers, FCU Mouth Connection & Testing) | 6 | 2022-09-15 | 2022-09-22 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
DRAINAGE WORKS |  | 24 | 2022-06-25 | 2022-07-26
C-PW-095240 | 1st Fix Piping System (Supports, Piping) | 12 | 2022-06-25 | 2022-07-09 | 01 | 08 | 01 | 45 | 005 | 02 |  | Building | Plumbing | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095250 | 2nd Fix Piping System (Fittings, Insulation) | 12 | 2022-07-09 | 2022-07-26 | 01 | 08 | 01 | 45 | 005 | 02 |  | Building | Plumbing | Museum | South East | L02 Gallery level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 30 | 2022-06-30 | 2022-08-09
C-PW-095260 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-30 | 2022-07-25 | 01 | 08 | 01 | 45 | 005 | 02 |  | Building | Plumbing | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095270 | 2nd Fix Piping System (Fittings, Insulation) | 12 | 2022-07-25 | 2022-08-09 | 01 | 08 | 01 | 45 | 005 | 02 |  | Building | Plumbing | Museum | South East | L02 Gallery level | MEP / Service Rooms
ELECTRICAL WORKS |  | 78 | 2022-06-25 | 2022-09-28
C-PW-095280 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 16 | 2022-06-25 | 2022-07-17 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095290 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 22 | 2022-07-17 | 2022-08-13 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095300 | LV Switchgears (DB's) | 5 | 2022-08-13 | 2022-08-17 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095310 | Cable/Wire Termination & Dressing | 7 | 2022-08-18 | 2022-08-27 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095320 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-09-14 | 2022-09-19 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095330 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-15 | 2022-09-24 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095340 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-18 | 2022-09-26 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095350 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-20 | 2022-09-28 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
ELV |  | 70 | 2022-06-27 | 2022-09-21
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 62 | 2022-06-27 | 2022-09-11
C-PW-095360 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095370 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095380 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 60 | 2022-06-28 | 2022-09-11
C-PW-095390 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-28 | 2022-07-14 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095400 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-14 | 2022-07-26 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095410 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
INTERCOM SYSTEM |  | 58 | 2022-06-30 | 2022-09-11
C-PW-095420 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-30 | 2022-07-16 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095430 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-07-16 | 2022-07-28 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095440 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
AV SYSTEM |  | 58 | 2022-07-03 | 2022-09-13
C-PW-095450 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-03 | 2022-07-18 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095460 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-18 | 2022-07-31 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095470 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-11 | 2022-09-13 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 57 | 2022-07-04 | 2022-09-13
C-PW-095480 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-07-04 | 2022-07-19 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095490 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-20 | 2022-08-02 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095500 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-11 | 2022-09-13 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 57 | 2022-07-06 | 2022-09-14
C-PW-095510 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-06 | 2022-07-21 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095520 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-21 | 2022-08-03 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095530 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 55 | 2022-07-07 | 2022-09-14
C-PW-095540 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-07 | 2022-07-24 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095550 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-24 | 2022-08-06 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095560 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-12 | 2022-09-14 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-15 | 2022-09-21
C-PW-095570 | Active Component System Works | 6 | 2022-09-15 | 2022-09-21 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 72 | 2022-06-27 | 2022-09-24
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 62 | 2022-06-27 | 2022-09-11
C-PW-095580 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-27 | 2022-07-09 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095590 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-09 | 2022-07-24 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095600 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 60 | 2022-06-28 | 2022-09-11
C-PW-095610 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-28 | 2022-07-14 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095620 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-14 | 2022-07-26 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095630 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-08 | 2022-09-11 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
FIRE FIGHTING SYSTEM WORKS |  | 69 | 2022-06-30 | 2022-09-24
C-PW-095640 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-30 | 2022-07-23 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095650 | 2nd Fix Piping System - (Clean Agent/Foam water sprinkler fire Suppression system) & testing | 12 | 2022-07-23 | 2022-08-07 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095660 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-09-18 | 2022-09-24 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
GALLERY 4 AV, GALLERY 5 AV/ IT ROOM - SOUTH |  | 69 | 2022-07-16 | 2022-10-05
MECHANICAL |  | 62 | 2022-07-16 | 2022-09-27
HVAC SYSTEM WORKS |  | 50 | 2022-07-31 | 2022-09-27
C-PW-095670 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 5 | 2022-07-31 | 2022-08-04 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095680 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 5 | 2022-08-04 | 2022-08-10 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095690 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 4 | 2022-08-10 | 2022-08-15 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095700 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 5 | 2022-09-21 | 2022-09-27 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
DRAINAGE WORKS |  | 7 | 2022-07-16 | 2022-07-24
C-PW-095710 | 1st Fix Piping System (Supports, Piping) | 4 | 2022-07-16 | 2022-07-20 | 01 | 08 | 01 | 45 | 005 | 02 |  | Building | Plumbing | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095720 | 2nd Fix Piping System (Fittings, Insulation) | 3 | 2022-07-20 | 2022-07-24 | 01 | 08 | 01 | 45 | 005 | 02 |  | Building | Plumbing | Museum | South East | L02 Gallery level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 7 | 2022-07-25 | 2022-08-03
C-PW-095730 | 1st Fix Piping System (Supports, Piping) | 4 | 2022-07-25 | 2022-07-31 | 01 | 08 | 01 | 45 | 005 | 02 |  | Building | Plumbing | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095740 | 2nd Fix Piping System (Fittings, Insulation) | 3 | 2022-07-31 | 2022-08-03 | 01 | 08 | 01 | 45 | 005 | 02 |  | Building | Plumbing | Museum | South East | L02 Gallery level | MEP / Service Rooms
ELECTRICAL WORKS |  | 68 | 2022-07-17 | 2022-10-05
C-PW-095750 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 4 | 2022-07-17 | 2022-07-21 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095760 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 5 | 2022-08-03 | 2022-08-08 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095770 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 5 | 2022-08-09 | 2022-08-14 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095780 | LV Switchgears (DB's) | 5 | 2022-08-14 | 2022-08-20 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095790 | Cable/Wire Termination & Dressing | 7 | 2022-08-20 | 2022-08-28 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095800 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-09-21 | 2022-09-27 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095810 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-24 | 2022-10-02 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095820 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-25 | 2022-10-03 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095830 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-27 | 2022-10-05 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
ELV |  | 62 | 2022-07-19 | 2022-10-01
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 54 | 2022-07-19 | 2022-09-20
C-PW-095840 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-07-19 | 2022-08-01 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095850 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-08-01 | 2022-08-13 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095860 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-18 | 2022-09-20 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 52 | 2022-07-20 | 2022-09-20
C-PW-095870 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-07-20 | 2022-08-03 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095880 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-08-03 | 2022-08-15 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095890 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-18 | 2022-09-20 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
INTERCOM SYSTEM |  | 50 | 2022-07-23 | 2022-09-20
C-PW-095900 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-07-23 | 2022-08-04 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095910 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-08-04 | 2022-08-17 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095920 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-18 | 2022-09-20 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
AV SYSTEM |  | 50 | 2022-07-25 | 2022-09-22
C-PW-095930 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-25 | 2022-08-07 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095940 | 2nd Fix AV System Works (Wiring) | 10 | 2022-08-07 | 2022-08-18 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095950 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-20 | 2022-09-22 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 49 | 2022-07-26 | 2022-09-22
C-PW-095960 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-07-26 | 2022-08-08 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095970 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-08-09 | 2022-08-21 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-095980 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-20 | 2022-09-22 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 49 | 2022-07-28 | 2022-09-24
C-PW-095990 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-28 | 2022-08-10 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-096000 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-10 | 2022-08-22 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-096010 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-21 | 2022-09-24 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 47 | 2022-07-31 | 2022-09-24
C-PW-096020 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-31 | 2022-08-13 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-096030 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-13 | 2022-08-24 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-096040 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-21 | 2022-09-24 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-09-25 | 2022-10-01
C-PW-096050 | Active Component System Works | 6 | 2022-09-25 | 2022-10-01 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 59 | 2022-07-19 | 2022-09-27
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 54 | 2022-07-19 | 2022-09-20
C-PW-096060 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-19 | 2022-08-01 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-096070 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-08-01 | 2022-08-13 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-096080 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-18 | 2022-09-20 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 52 | 2022-07-20 | 2022-09-20
C-PW-096090 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-20 | 2022-08-03 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-096100 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-03 | 2022-08-15 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-096110 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-18 | 2022-09-20 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 46 | 2022-08-04 | 2022-09-27
C-PW-096120 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 5 | 2022-08-04 | 2022-08-10 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-096130 | 2nd Fix Piping System - (Clean Agent fire Suppression system) & testing | 4 | 2022-08-10 | 2022-08-15 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-096140 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-09-21 | 2022-09-27 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
STORAGE - SOUTH |  | 108 | 2022-07-20 | 2022-11-26
MECHANICAL |  | 101 | 2022-07-20 | 2022-11-17
HVAC SYSTEM WORKS |  | 93 | 2022-07-31 | 2022-11-17
C-PW-096150 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 9 | 2022-07-31 | 2022-08-10 | 01 | 06 | 01 | 45 | 005 | 05 |  | Building | HVAC | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096160 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 9 | 2022-08-02 | 2022-08-13 | 01 | 06 | 01 | 45 | 005 | 05 |  | Building | HVAC | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096170 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-08-13 | 2022-08-22 | 01 | 06 | 01 | 45 | 005 | 05 |  | Building | HVAC | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096180 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 5 | 2022-11-13 | 2022-11-17 | 01 | 06 | 01 | 45 | 005 | 05 |  | Building | HVAC | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 13 | 2022-07-20 | 2022-08-06
C-PW-096190 | 1st Fix Piping System (Supports, Piping) | 6 | 2022-07-20 | 2022-07-27 | 01 | 08 | 01 | 45 | 005 | 05 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096200 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-07-27 | 2022-08-06 | 01 | 08 | 01 | 45 | 005 | 05 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 13 | 2022-07-26 | 2022-08-11
C-PW-096210 | 1st Fix Piping System (Supports, Piping) | 6 | 2022-07-26 | 2022-08-03 | 01 | 08 | 01 | 45 | 005 | 05 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096220 | 2nd Fix Piping System (Fittings, Insulation) | 7 | 2022-08-03 | 2022-08-11 | 01 | 08 | 01 | 45 | 005 | 05 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 107 | 2022-07-21 | 2022-11-26
C-PW-096230 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-07-21 | 2022-07-31 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096240 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-08-04 | 2022-08-14 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096250 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-08-14 | 2022-08-27 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096260 | LV Switchgears (DB's) | 5 | 2022-08-27 | 2022-08-31 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096270 | Cable/Wire Termination & Dressing | 7 | 2022-09-01 | 2022-09-10 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096280 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-11-13 | 2022-11-17 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096290 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-14 | 2022-11-22 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096300 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-16 | 2022-11-24 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096310 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-17 | 2022-11-26 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
ELV |  | 103 | 2022-07-24 | 2022-11-23
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 95 | 2022-07-24 | 2022-11-13
C-PW-096320 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-07-24 | 2022-08-06 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096330 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-08-06 | 2022-08-17 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096340 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 93 | 2022-07-25 | 2022-11-13
C-PW-096350 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-07-25 | 2022-08-08 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096360 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-08-08 | 2022-08-20 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096370 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 91 | 2022-07-27 | 2022-11-13
C-PW-096380 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-07-27 | 2022-08-09 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096390 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-08-09 | 2022-08-22 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096400 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
AV SYSTEM |  | 91 | 2022-07-31 | 2022-11-15
C-PW-096410 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-31 | 2022-08-11 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096420 | 2nd Fix AV System Works (Wiring) | 10 | 2022-08-11 | 2022-08-23 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096430 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-13 | 2022-11-15 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 90 | 2022-08-01 | 2022-11-15
C-PW-096440 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-08-01 | 2022-08-13 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096450 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-08-14 | 2022-08-25 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096460 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-13 | 2022-11-15 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 90 | 2022-08-03 | 2022-11-16
C-PW-096470 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-08-03 | 2022-08-15 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096480 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-15 | 2022-08-27 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096490 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-14 | 2022-11-16 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 88 | 2022-08-04 | 2022-11-16
C-PW-096500 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-08-04 | 2022-08-17 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096510 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-17 | 2022-08-29 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096520 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-14 | 2022-11-16 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-17 | 2022-11-23
C-PW-096530 | Active Component System Works | 6 | 2022-11-17 | 2022-11-23 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 95 | 2022-07-24 | 2022-11-13
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 95 | 2022-07-24 | 2022-11-13
C-PW-096540 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-24 | 2022-08-06 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096550 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-08-06 | 2022-08-17 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096560 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 93 | 2022-07-25 | 2022-11-13
C-PW-096570 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-25 | 2022-08-08 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096580 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-08 | 2022-08-20 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096590 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 58 | 2022-08-04 | 2022-10-12
C-PW-096600 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 9 | 2022-08-04 | 2022-08-14 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096610 | 2nd Fix Piping System - (Fittings) | 8 | 2022-08-14 | 2022-08-23 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-096620 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-10-04 | 2022-10-12 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
GALLERY 5 LOBBY AREAS - SOUTH |  | 238 | 2022-01-03 | 2022-10-16
MECHANICAL |  | 232 | 2022-01-03 | 2022-10-10
HVAC SYSTEM WORKS |  | 90 | 2022-06-21 | 2022-10-10
C-PW-096630 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-06-21 | 2022-07-17 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096640 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-06-27 | 2022-07-20 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096650 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-07-20 | 2022-08-02 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096660 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-29 | 2022-10-10 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-01-03 | 2022-02-05
C-PW-096670 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-01-03 | 2022-01-24 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096680 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-01-24 | 2022-02-05 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-06-18 | 2022-07-25
C-PW-096690 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-18 | 2022-07-09 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096700 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-13 | 2022-07-25 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 162 | 2022-03-31 | 2022-10-16
C-PW-096710 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-03-31 | 2022-04-12 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096720 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-06-26 | 2022-07-18 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096730 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-18 | 2022-08-04 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096740 | LV Switchgears (DB's) | 5 | 2022-08-04 | 2022-08-10 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096750 | Cable/Wire Termination & Dressing | 7 | 2022-08-10 | 2022-08-18 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096760 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-27 | 2022-10-06 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096770 | Final Fix Electrical (Light Fixtures) | 10 | 2022-09-29 | 2022-10-12 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096780 | Final Fix Electrical (Installation of Lighting Control Panels) | 10 | 2022-10-02 | 2022-10-15 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096790 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-10-03 | 2022-10-16 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELV |  | 101 | 2022-06-06 | 2022-10-06
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 92 | 2022-06-06 | 2022-09-26
C-PW-096800 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-06 | 2022-06-18 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096810 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096820 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 91 | 2022-06-08 | 2022-09-26
C-PW-096830 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096840 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-06-20 | 2022-07-02 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096850 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 89 | 2022-06-09 | 2022-09-26
C-PW-096860 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-09 | 2022-06-22 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096870 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-06-22 | 2022-07-04 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096880 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 89 | 2022-06-12 | 2022-09-28
C-PW-096890 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-12 | 2022-06-23 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096900 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-23 | 2022-07-06 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096910 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-09-26 | 2022-09-28 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 88 | 2022-06-14 | 2022-09-28
C-PW-096920 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-26 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096930 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-06-26 | 2022-07-07 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096940 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-09-26 | 2022-09-28 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 88 | 2022-06-15 | 2022-10-01
C-PW-096950 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-15 | 2022-06-27 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096960 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-28 | 2022-07-13 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096970 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-10-01 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 86 | 2022-06-18 | 2022-10-01
C-PW-096980 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-18 | 2022-06-29 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-096990 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-29 | 2022-07-14 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097000 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-09-27 | 2022-10-01 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-01 | 2022-10-06
C-PW-097010 | Active Component System Works | 6 | 2022-10-01 | 2022-10-06 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 92 | 2022-06-06 | 2022-09-26
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 92 | 2022-06-06 | 2022-09-26
C-PW-097020 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-06 | 2022-06-18 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097030 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097040 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 91 | 2022-06-08 | 2022-09-26
C-PW-097050 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-08 | 2022-06-20 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097060 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-20 | 2022-07-02 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097070 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-24 | 2022-09-26 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 64 | 2022-06-27 | 2022-09-14
C-PW-097080 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-27 | 2022-07-19 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097090 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-19 | 2022-07-28 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097100 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-05 | 2022-09-14 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
VIP MALE & FEMALETOILET, PUBLIC MALE & FEMALE WC - SOUTH |  | 96 | 2022-05-17 | 2022-09-11
MECHANICAL |  | 96 | 2022-05-17 | 2022-09-11
HVAC SYSTEM WORKS |  | 85 | 2022-05-26 | 2022-09-06
C-PW-097110 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 14 | 2022-05-26 | 2022-06-11 | 01 | 06 | 01 | 45 | 005 | 03 |  | Building | HVAC | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097120 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 14 | 2022-05-28 | 2022-06-13 | 01 | 06 | 01 | 45 | 005 | 03 |  | Building | HVAC | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097130 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-06-13 | 2022-06-25 | 01 | 06 | 01 | 45 | 005 | 03 |  | Building | HVAC | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097140 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-08-31 | 2022-09-06 | 01 | 06 | 01 | 45 | 005 | 03 |  | Building | HVAC | Museum | South East | L02 Gallery level | Wet Areas
DRAINAGE WORKS |  | 92 | 2022-05-17 | 2022-09-06
C-PW-097150 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-05-17 | 2022-06-01 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097160 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-01 | 2022-06-14 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097170 | Final Fix (Installation of Sanitaryware & Accessories) | 5 | 2022-08-31 | 2022-09-06 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
HOT & COLD WATER SYSTEM |  | 91 | 2022-05-23 | 2022-09-11
C-PW-097180 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-05-23 | 2022-06-07 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097190 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-06-08 | 2022-06-20 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097200 | Final Fix - Water Meter Installation | 3 | 2022-09-07 | 2022-09-11 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
ELECTRICAL WORKS |  | 96 | 2022-05-17 | 2022-09-11
C-PW-097210 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-05-17 | 2022-05-29 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097220 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-05-30 | 2022-06-19 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097230 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-19 | 2022-07-04 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097240 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-08-31 | 2022-09-06 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097250 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-03 | 2022-09-11 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097260 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-03 | 2022-09-11 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
ELV |  | 72 | 2022-06-06 | 2022-09-03
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 72 | 2022-06-06 | 2022-09-03
C-PW-097270 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-06 | 2022-06-18 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097280 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-19 | 2022-06-30 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097290 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-31 | 2022-09-03 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
AV SYSTEM |  | 71 | 2022-06-08 | 2022-09-03
C-PW-097300 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-08 | 2022-06-20 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097310 | 2nd Fix AV System Works (Wiring) | 10 | 2022-06-21 | 2022-07-03 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097320 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-31 | 2022-09-03 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
DATA AND TELECOMMUNICATION |  | 69 | 2022-06-09 | 2022-09-03
C-PW-097330 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-09 | 2022-06-22 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097340 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-06-25 | 2022-07-06 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097350 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-31 | 2022-09-03 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 67 | 2022-06-12 | 2022-09-03
C-PW-097360 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-12 | 2022-06-23 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097370 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097380 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-31 | 2022-09-03 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 77 | 2022-06-01 | 2022-09-03
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 66 | 2022-06-14 | 2022-09-03
C-PW-097390 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-14 | 2022-06-26 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097400 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-27 | 2022-07-09 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097410 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-31 | 2022-09-03 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 64 | 2022-06-15 | 2022-09-03
C-PW-097420 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-15 | 2022-06-27 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097430 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-06-28 | 2022-07-13 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097440 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-31 | 2022-09-03 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
FIRE FIGHTING WORKS |  | 61 | 2022-06-01 | 2022-08-15
C-PW-097450 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-06-01 | 2022-06-16 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097460 | 2nd Fix Piping System - (Fittings) | 8 | 2022-06-16 | 2022-06-26 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097470 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-08-09 | 2022-08-15 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
VIP RECEPTION, MALE DINING, FEMALE DINING & COURTYARD - SOUTH |  | 141 | 2022-06-12 | 2022-11-29
MECHANICAL |  | 133 | 2022-06-12 | 2022-11-20
HVAC SYSTEM WORKS |  | 125 | 2022-06-21 | 2022-11-20
C-PW-097480 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-06-21 | 2022-07-16 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097490 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-06-25 | 2022-07-18 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097500 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-07-18 | 2022-07-31 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097510 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-10 | 2022-11-20 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 29 | 2022-06-12 | 2022-07-19
C-PW-097520 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-12 | 2022-07-03 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097530 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-04 | 2022-07-19 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-06-18 | 2022-07-25
C-PW-097540 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-18 | 2022-07-09 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097550 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-09 | 2022-07-25 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 134 | 2022-06-12 | 2022-11-21
C-PW-097560 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-06-12 | 2022-06-28 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097570 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-06-25 | 2022-07-18 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097580 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-18 | 2022-08-04 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097590 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-10 | 2022-11-20 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097600 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-13 | 2022-11-21 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097610 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-13 | 2022-11-21 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELV |  | 135 | 2022-06-19 | 2022-11-29
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 127 | 2022-06-19 | 2022-11-19
C-PW-097620 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-19 | 2022-06-30 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097630 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-06-30 | 2022-07-16 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097640 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-16 | 2022-11-19 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 125 | 2022-06-20 | 2022-11-19
C-PW-097650 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-20 | 2022-07-02 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097660 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-03 | 2022-07-18 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097670 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-16 | 2022-11-19 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 123 | 2022-06-22 | 2022-11-19
C-PW-097680 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-22 | 2022-07-04 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097690 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-07-04 | 2022-07-19 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097700 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-16 | 2022-11-19 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 123 | 2022-06-23 | 2022-11-21
C-PW-097710 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-23 | 2022-07-06 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097720 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-06 | 2022-07-21 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097730 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-17 | 2022-11-21 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 122 | 2022-06-26 | 2022-11-21
C-PW-097740 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-26 | 2022-07-07 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097750 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-07 | 2022-07-24 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097760 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-17 | 2022-11-21 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 122 | 2022-06-28 | 2022-11-22
C-PW-097770 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-28 | 2022-07-13 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097780 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-13 | 2022-07-25 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097790 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-20 | 2022-11-22 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 120 | 2022-06-29 | 2022-11-22
C-PW-097800 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-29 | 2022-07-14 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097810 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-16 | 2022-07-27 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097820 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-20 | 2022-11-22 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-22 | 2022-11-29
C-PW-097830 | Active Component System Works | 6 | 2022-11-22 | 2022-11-29 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 127 | 2022-06-19 | 2022-11-19
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 127 | 2022-06-19 | 2022-11-19
C-PW-097840 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-19 | 2022-06-30 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097850 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-06-30 | 2022-07-16 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097860 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-16 | 2022-11-19 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 125 | 2022-06-20 | 2022-11-19
C-PW-097870 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-20 | 2022-07-02 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097880 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-03 | 2022-07-18 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097890 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-16 | 2022-11-19 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 78 | 2022-06-27 | 2022-10-01
C-PW-097900 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-27 | 2022-07-19 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097910 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-13 | 2022-07-23 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-097920 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-21 | 2022-10-01 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
MALE & FEMALE ABLUTIONS & PANTRIES - SOUTH |  | 94 | 2022-06-28 | 2022-10-20
MECHANICAL |  | 89 | 2022-07-04 | 2022-10-20
HVAC SYSTEM WORKS |  | 81 | 2022-07-17 | 2022-10-20
C-PW-097940 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 10 | 2022-07-18 | 2022-07-31 | 01 | 06 | 01 | 45 | 005 | 03 |  | Building | HVAC | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097930 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 14 | 2022-07-17 | 2022-08-02 | 01 | 06 | 01 | 45 | 005 | 03 |  | Building | HVAC | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097950 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-08-01 | 2022-08-13 | 01 | 06 | 01 | 45 | 005 | 03 |  | Building | HVAC | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097960 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 6 | 2022-10-15 | 2022-10-20 | 01 | 06 | 01 | 45 | 005 | 03 |  | Building | HVAC | Museum | South East | L02 Gallery level | Wet Areas
DRAINAGE WORKS |  | 24 | 2022-07-04 | 2022-08-04
C-PW-097970 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-07-04 | 2022-07-23 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
C-PW-097980 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-23 | 2022-08-04 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
HOT & COLD WATER SYSTEM |  | 81 | 2022-07-09 | 2022-10-17
C-PW-097990 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-07-09 | 2022-07-28 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098000 | 2nd Fix Piping System (Fittings, Insulation incl. Water Heater) | 10 | 2022-07-31 | 2022-08-11 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098010 | Final Fix - Water Meter Installation | 2 | 2022-10-16 | 2022-10-17 | 01 | 08 | 01 | 45 | 005 | 03 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Wet Areas
ELECTRICAL WORKS |  | 92 | 2022-06-28 | 2022-10-19
C-PW-098020 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-06-28 | 2022-07-13 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098030 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 14 | 2022-07-20 | 2022-08-06 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098040 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-08-06 | 2022-08-22 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098050 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-10-08 | 2022-10-15 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098060 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-11 | 2022-10-19 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098070 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-11 | 2022-10-19 | 01 | 07 | 01 | 45 | 005 | 03 |  | Building | Electrical | Museum | South East | L02 Gallery level | Wet Areas
ELV |  | 86 | 2022-06-29 | 2022-10-15
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 84 | 2022-06-29 | 2022-10-11
C-PW-098080 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-29 | 2022-07-16 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098090 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-08-06 | 2022-08-18 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098100 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-11 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
AV SYSTEM |  | 82 | 2022-07-02 | 2022-10-11
C-PW-098110 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-02 | 2022-07-17 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098120 | 2nd Fix AV System Works (Wiring) | 10 | 2022-08-09 | 2022-08-21 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098130 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-11 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
DATA AND TELECOMMUNICATION |  | 81 | 2022-07-04 | 2022-10-11
C-PW-098140 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-04 | 2022-07-19 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098150 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-11 | 2022-08-23 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098160 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-11 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
BMS AND AUTOMATIC CONTROLS |  | 82 | 2022-07-05 | 2022-10-15
C-PW-098170 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-05 | 2022-07-20 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098180 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-15 | 2022-08-27 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098190 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-11 | 2022-10-15 | 01 | 10 | 01 | 45 | 005 | 03 |  | Building | CCTV | Museum | South East | L02 Gallery level | Wet Areas
LIFE AND SAFETY SYSTEM |  | 67 | 2022-07-07 | 2022-09-28
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 64 | 2022-07-07 | 2022-09-25
C-PW-098200 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-07 | 2022-07-23 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098210 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-08-17 | 2022-08-29 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098220 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-21 | 2022-09-25 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
FIRE ALARM & PUBLIC ADDRESS |  | 62 | 2022-07-09 | 2022-09-25
C-PW-098230 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-09 | 2022-07-25 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098240 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-20 | 2022-09-01 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098250 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-21 | 2022-09-25 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
FIRE FIGHTING WORKS |  | 58 | 2022-07-21 | 2022-09-28
C-PW-098260 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 14 | 2022-07-21 | 2022-08-08 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098270 | 2nd Fix Piping System - (Fittings) | 8 | 2022-08-06 | 2022-08-14 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
C-PW-098280 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-09-21 | 2022-09-28 | 01 | 09 | 01 | 45 | 005 | 03 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Wet Areas
PRAYER & MAJLIS - SOUTH |  | 122 | 2022-06-21 | 2022-11-16
MECHANICAL |  | 108 | 2022-07-04 | 2022-11-12
HVAC SYSTEM WORKS |  | 100 | 2022-07-17 | 2022-11-12
C-PW-098290 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-07-17 | 2022-08-06 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098300 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-07-17 | 2022-08-08 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098310 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-08-06 | 2022-08-18 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098320 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-03 | 2022-11-12 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 25 | 2022-07-04 | 2022-08-06
C-PW-098330 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-04 | 2022-07-28 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098340 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-24 | 2022-08-06 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 25 | 2022-07-09 | 2022-08-11
C-PW-098350 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-09 | 2022-08-04 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098360 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-31 | 2022-08-11 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 122 | 2022-06-21 | 2022-11-16
C-PW-098370 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 12 | 2022-06-21 | 2022-07-05 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098380 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-07-20 | 2022-08-09 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098390 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-08-09 | 2022-08-24 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098400 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-03 | 2022-11-12 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098410 | Final Fix Electrical (Light Fixtures) | 10 | 2022-11-05 | 2022-11-16 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098420 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-11-05 | 2022-11-16 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELV |  | 108 | 2022-06-23 | 2022-11-02
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 108 | 2022-06-23 | 2022-11-02
C-PW-098430 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-23 | 2022-07-05 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098440 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-08-09 | 2022-08-21 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098450 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-02 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 106 | 2022-06-25 | 2022-11-02
C-PW-098460 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-25 | 2022-07-07 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098470 | 2nd Fix AV System Works (Wiring) | 10 | 2022-08-11 | 2022-08-23 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098480 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-02 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 105 | 2022-06-27 | 2022-11-02
C-PW-098490 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098500 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-15 | 2022-08-27 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098510 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-02 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 103 | 2022-06-29 | 2022-11-02
C-PW-098520 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-29 | 2022-07-14 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098530 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-17 | 2022-08-29 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098540 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-02 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 102 | 2022-06-30 | 2022-11-02
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 102 | 2022-06-30 | 2022-11-02
C-PW-098550 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-30 | 2022-07-16 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098560 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-08-20 | 2022-09-01 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098570 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-02 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 100 | 2022-07-03 | 2022-11-02
C-PW-098580 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-03 | 2022-07-18 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098590 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-18 | 2022-07-31 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098600 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-02 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 73 | 2022-07-21 | 2022-10-17
C-PW-098610 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-07-21 | 2022-08-10 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098620 | 2nd Fix Piping System - (Fittings) | 8 | 2022-08-06 | 2022-08-14 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098630 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-10-06 | 2022-10-17 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
CIRCULATIONS - SOUTH |  | 106 | 2022-07-27 | 2022-12-01
MECHANICAL |  | 102 | 2022-07-27 | 2022-11-26
HVAC SYSTEM WORKS |  | 94 | 2022-08-07 | 2022-11-26
C-PW-098640 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs incl. Testing) | 18 | 2022-08-07 | 2022-08-28 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098650 | 1st Fix HVAC (CHW Piping, Drain Pipes incl. Testing) | 17 | 2022-08-13 | 2022-08-31 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098660 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-09-01 | 2022-09-13 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098670 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-11-16 | 2022-11-26 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 25 | 2022-07-27 | 2022-08-27
C-PW-098680 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-27 | 2022-08-18 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098690 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-14 | 2022-08-27 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 25 | 2022-08-03 | 2022-08-31
C-PW-098700 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-08-03 | 2022-08-24 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098710 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-20 | 2022-08-31 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 104 | 2022-07-31 | 2022-12-01
C-PW-098720 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-07-31 | 2022-08-16 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098730 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-08-10 | 2022-08-30 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098740 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-08-30 | 2022-09-14 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098750 | LV Switchgears (DB's) | 5 | 2022-09-15 | 2022-09-20 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098760 | Cable/Wire Termination & Dressing | 7 | 2022-09-20 | 2022-09-28 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098770 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-11-16 | 2022-11-26 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098780 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-19 | 2022-11-27 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098790 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-21 | 2022-11-29 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098800 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-22 | 2022-12-01 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELV |  | 100 | 2022-08-02 | 2022-11-28
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 91 | 2022-08-02 | 2022-11-17
C-PW-098810 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-08-02 | 2022-08-14 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098820 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-08-14 | 2022-08-27 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098830 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-17 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 90 | 2022-08-04 | 2022-11-17
C-PW-098840 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-08-04 | 2022-08-16 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098850 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-08-16 | 2022-08-28 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098860 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-17 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 88 | 2022-08-06 | 2022-11-17
C-PW-098870 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-08-06 | 2022-08-17 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098880 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-08-18 | 2022-08-30 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098890 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-17 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 88 | 2022-08-08 | 2022-11-20
C-PW-098900 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-08-08 | 2022-08-20 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098910 | 2nd Fix AV System Works (Wiring) | 10 | 2022-08-20 | 2022-08-31 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098920 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-16 | 2022-11-20 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 86 | 2022-08-09 | 2022-11-20
C-PW-098930 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-08-09 | 2022-08-22 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098940 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-08-22 | 2022-09-03 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098950 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-16 | 2022-11-20 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 86 | 2022-08-11 | 2022-11-21
C-PW-098960 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-08-11 | 2022-08-23 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098970 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-23 | 2022-09-05 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-098980 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-19 | 2022-11-21 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 85 | 2022-08-14 | 2022-11-21
C-PW-098990 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-08-14 | 2022-08-25 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099000 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-25 | 2022-09-06 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099010 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-19 | 2022-11-21 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-21 | 2022-11-28
C-PW-099020 | Active Component System Works | 6 | 2022-11-21 | 2022-11-28 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 91 | 2022-08-02 | 2022-11-17
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 91 | 2022-08-02 | 2022-11-17
C-PW-099030 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-08-02 | 2022-08-14 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099040 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-08-14 | 2022-08-27 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099050 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-17 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 90 | 2022-08-04 | 2022-11-17
C-PW-099060 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-08-04 | 2022-08-16 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099070 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-16 | 2022-08-28 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099080 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-15 | 2022-11-17 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 67 | 2022-08-13 | 2022-10-31
C-PW-099090 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-08-13 | 2022-08-31 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099100 | 2nd Fix Piping System - (Pipe Droppers, ZCV incl. accessories) | 8 | 2022-08-25 | 2022-09-04 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099110 | Final Fix Piping System (Sprinkler Heads, Fixtures, FHRC & accessories incl. Extinguishers) | 8 | 2022-10-22 | 2022-10-31 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
GALLERY 1 LOBBY AREAS - WEST |  | 261 | 2022-01-03 | 2022-11-13
MECHANICAL |  | 259 | 2022-01-03 | 2022-11-09
HVAC SYSTEM WORKS |  | 118 | 2022-06-19 | 2022-11-09
C-PW-099120 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-06-21 | 2022-07-14 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099130 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-06-19 | 2022-07-14 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099140 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-07-14 | 2022-07-26 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099150 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-31 | 2022-11-09 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 25 | 2022-01-03 | 2022-01-31
C-PW-099160 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-01-03 | 2022-01-20 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099170 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-01-19 | 2022-01-31 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-01-08 | 2022-02-10
C-PW-099180 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-01-08 | 2022-01-30 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099190 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-01-30 | 2022-02-10 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 261 | 2022-01-03 | 2022-11-13
C-PW-099200 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-01-03 | 2022-01-18 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099210 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-06-23 | 2022-07-16 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099220 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-16 | 2022-08-02 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099230 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-30 | 2022-11-08 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099240 | Final Fix Electrical (Light Fixtures) | 10 | 2022-10-31 | 2022-11-13 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099250 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-10-31 | 2022-11-13 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELV |  | 120 | 2022-06-19 | 2022-11-12
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 111 | 2022-06-19 | 2022-11-01
C-PW-099260 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-19 | 2022-07-02 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099270 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-02 | 2022-07-17 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099280 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 109 | 2022-06-21 | 2022-11-01
C-PW-099290 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-21 | 2022-07-03 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099300 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-03 | 2022-07-19 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099310 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 108 | 2022-06-23 | 2022-11-01
C-PW-099320 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-23 | 2022-07-05 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099330 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-07-05 | 2022-07-20 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099340 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 108 | 2022-06-25 | 2022-11-03
C-PW-099350 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-06-25 | 2022-07-06 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099360 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-07 | 2022-07-23 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099370 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 106 | 2022-06-27 | 2022-11-03
C-PW-099380 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099390 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099400 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-31 | 2022-11-03 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 106 | 2022-06-28 | 2022-11-05
C-PW-099410 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-06-28 | 2022-07-14 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099420 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-14 | 2022-07-26 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099430 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-02 | 2022-11-05 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 104 | 2022-06-30 | 2022-11-05
C-PW-099440 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-06-30 | 2022-07-16 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099450 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-16 | 2022-07-28 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099460 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-02 | 2022-11-05 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-11-05 | 2022-11-12
C-PW-099470 | Active Component System Works | 6 | 2022-11-05 | 2022-11-12 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 111 | 2022-06-19 | 2022-11-01
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 111 | 2022-06-19 | 2022-11-01
C-PW-099480 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-19 | 2022-07-02 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099490 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-02 | 2022-07-17 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099500 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 109 | 2022-06-21 | 2022-11-01
C-PW-099510 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-21 | 2022-07-03 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099520 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-03 | 2022-07-19 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099530 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-30 | 2022-11-01 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 92 | 2022-06-25 | 2022-10-16
C-PW-099540 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-25 | 2022-07-17 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099550 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-17 | 2022-07-26 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-099560 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-10-06 | 2022-10-16 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
COOLING ROOM, GALLERY 1 AV/IT ROOM - WEST |  | 101 | 2022-06-08 | 2022-10-10
MECHANICAL |  | 96 | 2022-06-08 | 2022-10-03
HVAC SYSTEM WORKS |  | 88 | 2022-06-18 | 2022-10-03
C-PW-099570 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-06-18 | 2022-07-09 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099580 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-07-09 | 2022-08-02 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099590 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-08-02 | 2022-08-14 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099600 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-09-24 | 2022-10-03 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
DRAINAGE WORKS |  | 21 | 2022-06-08 | 2022-07-03
C-PW-099610 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-06-08 | 2022-06-20 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099620 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-06-20 | 2022-07-03 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 29 | 2022-06-14 | 2022-07-20
C-PW-099630 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-06-14 | 2022-07-05 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099640 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-05 | 2022-07-20 | 01 | 06 | 01 | 45 | 005 | 02 |  | Building | HVAC | Museum | South East | L02 Gallery level | MEP / Service Rooms
ELECTRICAL WORKS |  | 79 | 2022-07-04 | 2022-10-10
C-PW-099650 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-07-04 | 2022-07-24 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099660 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-07-06 | 2022-07-28 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099670 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-31 | 2022-08-15 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099680 | LV Switchgears (DB's) | 5 | 2022-08-15 | 2022-08-21 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099690 | Cable/Wire Termination & Dressing | 7 | 2022-08-21 | 2022-08-29 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099700 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-09-25 | 2022-10-04 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099710 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-27 | 2022-10-05 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099720 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-28 | 2022-10-06 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099730 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-01 | 2022-10-10 | 01 | 07 | 01 | 45 | 005 | 02 |  | Building | Electrical | Museum | South East | L02 Gallery level | MEP / Service Rooms
ELV |  | 38 | 2022-07-06 | 2022-08-24
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-07-06 | 2022-08-07
C-PW-099740 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-07-06 | 2022-07-21 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099750 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-21 | 2022-08-03 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099760 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-07-07 | 2022-08-08
C-PW-099770 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-07-07 | 2022-07-24 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099780 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-24 | 2022-08-06 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099790 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-08-06 | 2022-08-08 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
INTERCOM SYSTEM |  | 23 | 2022-07-13 | 2022-08-10
C-PW-099800 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-07-13 | 2022-07-25 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099810 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-07-25 | 2022-08-08 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099820 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-08-08 | 2022-08-10 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
AV SYSTEM |  | 23 | 2022-07-16 | 2022-08-13
C-PW-099830 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-16 | 2022-07-27 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099840 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-27 | 2022-08-09 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099850 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-09 | 2022-08-13 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-07-17 | 2022-08-14
C-PW-099860 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-07-17 | 2022-07-28 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099870 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-31 | 2022-08-11 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099880 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-11 | 2022-08-14 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 23 | 2022-07-19 | 2022-08-16
C-PW-099890 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-19 | 2022-08-01 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099900 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-01 | 2022-08-13 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099910 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-14 | 2022-08-16 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-07-20 | 2022-08-17
C-PW-099920 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-20 | 2022-08-03 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099930 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-03 | 2022-08-15 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099940 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-15 | 2022-08-17 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-08-18 | 2022-08-24
C-PW-099950 | Active Component System Works | 6 | 2022-08-18 | 2022-08-24 | 01 | 10 | 01 | 45 | 005 | 02 |  | Building | CCTV | Museum | South East | L02 Gallery level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 83 | 2022-06-23 | 2022-10-03
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 71 | 2022-07-06 | 2022-10-02
C-PW-099960 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-06 | 2022-07-21 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099970 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-21 | 2022-08-03 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-099980 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-09-29 | 2022-10-02 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 70 | 2022-07-07 | 2022-10-02
C-PW-099990 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-07 | 2022-07-24 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-100000 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-24 | 2022-08-06 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-100010 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-09-29 | 2022-10-02 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 83 | 2022-06-23 | 2022-10-03
C-PW-100020 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-23 | 2022-07-16 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-100030 | 2nd Fix Piping System - (Fittings) | 8 | 2022-07-16 | 2022-07-25 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
C-PW-100040 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-24 | 2022-10-03 | 01 | 09 | 01 | 45 | 005 | 02 |  | Building | Firefighting | Museum | South East | L02 Gallery level | MEP / Service Rooms
GALLERY 1&2 LOBBY AREAS - WEST |  | 114 | 2022-06-25 | 2022-11-10
MECHANICAL |  | 99 | 2022-07-05 | 2022-11-03
HVAC SYSTEM WORKS |  | 91 | 2022-07-18 | 2022-11-03
C-PW-100050 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-07-20 | 2022-08-10 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100060 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-07-18 | 2022-08-10 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100070 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-08-10 | 2022-08-22 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100080 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-26 | 2022-11-03 | 01 | 06 | 01 | 45 | 005 | 01 |  | Building | HVAC | Museum | South East | L02 Gallery level | Circulation / Common Areas
DRAINAGE WORKS |  | 24 | 2022-07-05 | 2022-08-07
C-PW-100090 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-07-05 | 2022-07-25 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100100 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-07-25 | 2022-08-07 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
HOT & COLD WATER SYSTEM |  | 24 | 2022-07-14 | 2022-08-13
C-PW-100110 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-07-14 | 2022-08-01 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100120 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-01 | 2022-08-13 | 01 | 08 | 01 | 45 | 005 | 01 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELECTRICAL WORKS |  | 114 | 2022-06-25 | 2022-11-10
C-PW-100130 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 13 | 2022-06-25 | 2022-07-13 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100140 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-07-23 | 2022-08-11 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100150 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-08-11 | 2022-08-28 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100160 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-27 | 2022-11-06 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100170 | Final Fix Electrical (Light Fixtures) | 10 | 2022-10-30 | 2022-11-10 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100180 | Final Fix Electrical (Installation of Lighting Control Devices) | 10 | 2022-10-30 | 2022-11-10 | 01 | 07 | 01 | 45 | 005 | 01 |  | Building | Electrical | Museum | South East | L02 Gallery level | Circulation / Common Areas
ELV |  | 38 | 2022-06-27 | 2022-08-15
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 23 | 2022-06-27 | 2022-07-27
C-PW-100190 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-06-27 | 2022-07-09 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100200 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-09 | 2022-07-25 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100210 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-07-25 | 2022-07-27 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTRUDER & HOLD-UPS ALARMS |  | 23 | 2022-06-29 | 2022-07-31
C-PW-100220 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-06-29 | 2022-07-14 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100230 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-14 | 2022-07-26 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100240 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-07-26 | 2022-07-31 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
INTERCOM SYSTEM |  | 23 | 2022-06-30 | 2022-08-01
C-PW-100250 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-06-30 | 2022-07-16 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100260 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-07-17 | 2022-07-28 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100270 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-07-28 | 2022-08-01 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
AV SYSTEM |  | 23 | 2022-07-03 | 2022-08-03
C-PW-100280 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-03 | 2022-07-18 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100290 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-18 | 2022-07-31 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100300 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-01 | 2022-08-03 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
VIDEO SURVEILLANCE SYSTEM |  | 23 | 2022-07-04 | 2022-08-04
C-PW-100310 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-07-04 | 2022-07-20 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100320 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-20 | 2022-08-02 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100330 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-02 | 2022-08-04 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
DATA AND TELECOMMUNICATION |  | 23 | 2022-07-06 | 2022-08-07
C-PW-100340 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-06 | 2022-07-21 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100350 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-21 | 2022-08-04 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100360 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-04 | 2022-08-07 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
BMS AND AUTOMATIC CONTROLS |  | 23 | 2022-07-09 | 2022-08-09
C-PW-100370 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100380 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-24 | 2022-08-06 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100390 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-06 | 2022-08-09 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-08-09 | 2022-08-15
C-PW-100400 | Active Component System Works | 6 | 2022-08-09 | 2022-08-15 | 01 | 10 | 01 | 45 | 005 | 01 |  | Building | CCTV | Museum | South East | L02 Gallery level | Circulation / Common Areas
LIFE AND SAFETY SYSTEM |  | 86 | 2022-06-27 | 2022-10-11
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 80 | 2022-06-27 | 2022-10-03
C-PW-100410 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-06-27 | 2022-07-09 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100420 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-09 | 2022-07-25 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100430 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-01 | 2022-10-03 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE ALARM & PUBLIC ADDRESS |  | 79 | 2022-06-29 | 2022-10-03
C-PW-100440 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-06-29 | 2022-07-14 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100450 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-14 | 2022-07-26 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100460 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-01 | 2022-10-03 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
FIRE FIGHTING WORKS |  | 66 | 2022-07-24 | 2022-10-11
C-PW-100470 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-07-24 | 2022-08-13 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100480 | 2nd Fix Piping System - (Fittings) | 8 | 2022-08-07 | 2022-08-16 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
C-PW-100490 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-10-01 | 2022-10-11 | 01 | 09 | 01 | 45 | 005 | 01 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Circulation / Common Areas
STORAGE AREA - WEST |  | 94 | 2022-07-13 | 2022-11-01
MECHANICAL |  | 90 | 2022-07-13 | 2022-10-27
HVAC SYSTEM WORKS |  | 82 | 2022-07-23 | 2022-10-27
C-PW-100500 | 1st Fix HVAC (CHW Piping, Drain Pipes) | 17 | 2022-07-24 | 2022-08-14 | 01 | 06 | 01 | 45 | 005 | 05 |  | Building | HVAC | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100510 | 1st Fix HVAC (Supports, Ducts,Dampers - VCD,NRD,MDs) | 18 | 2022-07-23 | 2022-08-14 | 01 | 06 | 01 | 45 | 005 | 05 |  | Building | HVAC | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100520 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-08-14 | 2022-08-25 | 01 | 06 | 01 | 45 | 005 | 05 |  | Building | HVAC | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100530 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection) | 8 | 2022-10-18 | 2022-10-27 | 01 | 06 | 01 | 45 | 005 | 05 |  | Building | HVAC | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
DRAINAGE WORKS |  | 18 | 2022-07-13 | 2022-08-04
C-PW-100540 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-07-13 | 2022-07-25 | 01 | 08 | 01 | 45 | 005 | 05 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100550 | 2nd Fix Piping System (Fittings, Insulation) | 8 | 2022-07-25 | 2022-08-04 | 01 | 08 | 01 | 45 | 005 | 05 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
HOT & COLD WATER SYSTEM |  | 29 | 2022-07-18 | 2022-08-22
C-PW-100560 | 1st Fix Piping System (Supports, Piping) | 18 | 2022-07-18 | 2022-08-10 | 01 | 08 | 01 | 45 | 005 | 05 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100570 | 2nd Fix Piping System (Fittings, Insulation) | 10 | 2022-08-10 | 2022-08-22 | 01 | 08 | 01 | 45 | 005 | 05 |  | Building | Plumbing | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
ELECTRICAL WORKS |  | 93 | 2022-07-13 | 2022-11-01
C-PW-100580 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 14 | 2022-07-13 | 2022-07-31 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100590 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 17 | 2022-07-26 | 2022-08-15 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100600 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-08-16 | 2022-08-31 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100610 | LV Switchgears (DB's) | 5 | 2022-08-31 | 2022-09-06 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100620 | Cable/Wire Termination & Dressing | 7 | 2022-09-06 | 2022-09-14 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100630 | Final Fix Electrical (Power Socket / Isolators) | 8 | 2022-10-18 | 2022-10-27 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100640 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-20 | 2022-10-29 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100650 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-10-22 | 2022-10-30 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100660 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-24 | 2022-11-01 | 01 | 07 | 01 | 45 | 005 | 05 |  | Building | Electrical | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
ELV |  | 89 | 2022-07-16 | 2022-10-30
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 80 | 2022-07-16 | 2022-10-19
C-PW-100670 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-07-16 | 2022-07-27 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100680 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-27 | 2022-08-09 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100690 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-19 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
INTRUDER & HOLD-UPS ALARMS |  | 79 | 2022-07-17 | 2022-10-19
C-PW-100700 | 1st Fix Intruder & Hold-Ups Alarms Works (Conduits & Boxes) | 10 | 2022-07-17 | 2022-07-31 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100710 | 2nd Fix Intruder & Hold-Ups Alarms Works (Wiring) | 10 | 2022-07-31 | 2022-08-11 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100720 | Final Fix Intruder & Hold-Ups Alarms Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-19 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
INTERCOM SYSTEM |  | 77 | 2022-07-19 | 2022-10-19
C-PW-100730 | 1st Fix Intercom System Works (Conduits & Boxes) | 10 | 2022-07-19 | 2022-08-01 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100740 | 2nd Fix Intercom System Works (Wiring) | 10 | 2022-08-01 | 2022-08-14 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100750 | Final Fix Intercom System Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-19 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
AV SYSTEM |  | 77 | 2022-07-21 | 2022-10-20
C-PW-100760 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-21 | 2022-08-03 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100770 | 2nd Fix AV System Works (Wiring) | 10 | 2022-08-03 | 2022-08-15 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100780 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-18 | 2022-10-20 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
VIDEO SURVEILLANCE SYSTEM |  | 75 | 2022-07-23 | 2022-10-20
C-PW-100790 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-07-23 | 2022-08-04 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100800 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-08-06 | 2022-08-17 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100810 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-18 | 2022-10-20 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
DATA AND TELECOMMUNICATION |  | 75 | 2022-07-25 | 2022-10-23
C-PW-100820 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-25 | 2022-08-07 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100830 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-07 | 2022-08-18 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100840 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-20 | 2022-10-23 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
BMS AND AUTOMATIC CONTROLS |  | 74 | 2022-07-26 | 2022-10-23
C-PW-100850 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-26 | 2022-08-09 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100860 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-09 | 2022-08-21 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100870 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-20 | 2022-10-23 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
ACTIVE COMPONENT SYSTEMS |  | 6 | 2022-10-23 | 2022-10-30
C-PW-100880 | Active Component System Works | 6 | 2022-10-23 | 2022-10-30 | 01 | 10 | 01 | 45 | 005 | 05 |  | Building | CCTV | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
LIFE AND SAFETY SYSTEM |  | 80 | 2022-07-16 | 2022-10-19
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 80 | 2022-07-16 | 2022-10-19
C-PW-100890 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-16 | 2022-07-27 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100900 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-27 | 2022-08-09 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100910 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-19 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
FIRE ALARM & PUBLIC ADDRESS |  | 79 | 2022-07-17 | 2022-10-19
C-PW-100920 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-17 | 2022-07-31 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100930 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-31 | 2022-08-11 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100940 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-17 | 2022-10-19 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
FIRE FIGHTING WORKS |  | 58 | 2022-07-27 | 2022-10-04
C-PW-100950 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-07-27 | 2022-08-16 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100960 | 2nd Fix Piping System - (Fittings) | 8 | 2022-08-16 | 2022-08-25 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
C-PW-100970 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 8 | 2022-09-25 | 2022-10-04 | 01 | 09 | 01 | 45 | 005 | 05 |  | Building | Firefighting | Museum | South East | L02 Gallery level | Storage / Offices / Admin Areas
LEVEL 03 PLENUM |  | 492 | 2021-04-27 | 2022-12-14
CIVIL WORKS |  | 288 | 2021-04-27 | 2022-04-10
ZONE 02A |  | 208 | 2021-04-27 | 2022-01-06
C-PW-101430 | Site Survey for Action (Item 08 - Immediate) | 1 | 2021-04-27 | 2021-04-27 | 01 | 01 | 01 | 07 | 006 | 30 |  | Building | Civil | Museum | Zone 02A | L03 Plenum Level | Civil SubZones
C-PW-101440 | Construction of Level 03 Slab - Zone 2A (Item 08 - Immediate) | 10 | 2021-07-17 | 2021-07-31 | 01 | 01 | 01 | 07 | 006 | 30 |  | Building | Civil | Museum | Zone 02A | L03 Plenum Level | Civil SubZones
C-PW-101450 | Construction of WC Soffit Slabs at Level 03 - Zone 2A | 24 | 2021-11-02 | 2021-11-29 | 01 | 01 | 01 | 07 | 006 | 30 |  | Building | Civil | Museum | Zone 02A | L03 Plenum Level | Civil SubZones
C-PW-101460 | Construction of Level 03 Slab - Zone 2A | 24 | 2021-12-01 | 2021-12-29 | 01 | 01 | 01 | 07 | 006 | 30 |  | Building | Civil | Museum | Zone 02A | L03 Plenum Level | Civil SubZones
C-PW-101470 | Construction of Verticals up to Level 04 Slab - Zone 2A | 24 | 2021-12-09 | 2022-01-06 | 01 | 01 | 01 | 07 | 006 | 30 |  | Building | Civil | Museum | Zone 02A | L03 Plenum Level | Civil SubZones
ZONE 02B |  | 74 | 2021-11-28 | 2022-02-24
C-PW-101480 | Construction of WC Soffit Slabs at Level 03 - Zone 2B | 26 | 2021-11-28 | 2021-12-29 | 01 | 01 | 01 | 08 | 006 | 30 |  | Building | Civil | Museum | Zone 02B | L03 Plenum Level | Civil SubZones
C-PW-101490 | Construction of Level - 03 Slab - Zone 2B | 26 | 2021-12-30 | 2022-01-30 | 01 | 01 | 01 | 08 | 006 | 30 |  | Building | Civil | Museum | Zone 02B | L03 Plenum Level | Civil SubZones
C-PW-101500 | Construction of Verticals up to Level - 04 Slab - Zone 2B | 24 | 2022-01-12 | 2022-02-08 | 01 | 01 | 01 | 08 | 006 | 30 |  | Building | Civil | Museum | Zone 02B | L03 Plenum Level | Civil SubZones
C-PW-101510 | Construction of Falconry Leave outs up to Level 03 Slab | 42 | 2022-01-08 | 2022-02-24 | 01 | 01 | 01 | 08 | 006 | 30 |  | Building | Civil | Museum | Zone 02B | L03 Plenum Level | Civil SubZones
ZONE 02C |  | 60 | 2022-01-31 | 2022-04-10
C-PW-101520 | Construction of WC Soffit Slabs at Level 03 - Zone 2C | 24 | 2022-01-31 | 2022-02-27 | 01 | 01 | 01 | 09 | 006 | 30 |  | Building | Civil | Museum | Zone 02C | L03 Plenum Level | Civil SubZones
C-PW-101530 | Construction of Level 03 Slab - Zone 2C | 24 | 2022-02-28 | 2022-03-27 | 01 | 01 | 01 | 09 | 006 | 30 |  | Building | Civil | Museum | Zone 02C | L03 Plenum Level | Civil SubZones
C-PW-101540 | Construction of Verticals up to Level 04 Slab - Zone 2C | 26 | 2022-03-12 | 2022-04-10 | 01 | 01 | 01 | 09 | 006 | 30 |  | Building | Civil | Museum | Zone 02C | L03 Plenum Level | Civil SubZones
ZONE 02E |  | 28 | 2022-01-04 | 2022-02-05
C-PW-101550 | Construction of Level 03 Slab - Zone 2E | 28 | 2022-01-04 | 2022-02-05 | 01 | 01 | 01 | 11 | 006 | 30 |  | Building | Civil | Museum | Zone 02E | L03 Plenum Level | Civil SubZones
ZONE 02G |  | 265 | 2021-04-28 | 2022-03-15
C-PW-101560 | Site Survey for Action (Item 17 - Immediate) | 1 | 2021-04-28 | 2021-04-28 | 01 | 01 | 01 | 13 | 006 | 30 |  | Building | Civil | Museum | Zone 02G | L03 Plenum Level | Civil SubZones
C-PW-101570 | Site Survey for Action (Item 19 - Immediate) | 1 | 2021-04-29 | 2021-04-29 | 01 | 01 | 01 | 13 | 006 | 30 |  | Building | Civil | Museum | Zone 02G | L03 Plenum Level | Civil SubZones
C-PW-101580 | Construction of Level 03 Slab & Beam - Zone 2G (Item 17 - Immediate) | 10 | 2021-07-17 | 2021-07-31 | 01 | 01 | 01 | 13 | 006 | 30 |  | Building | Civil | Museum | Zone 02G | L03 Plenum Level | Civil SubZones
C-PW-101590 | Construction of Level 03 Slab - Zone 2G (Item 19 - Immediate) | 10 | 2021-08-01 | 2021-08-12 | 01 | 01 | 01 | 13 | 006 | 30 |  | Building | Civil | Museum | Zone 02G | L03 Plenum Level | Civil SubZones
C-PW-101600 | Construction of Level 03 Slab - Zone 2G | 24 | 2022-02-02 | 2022-03-01 | 01 | 01 | 01 | 13 | 006 | 30 |  | Building | Civil | Museum | Zone 02G | L03 Plenum Level | Civil SubZones
C-PW-101610 | Construction of Verticals up to Level 04 Slab - Zone 2G | 23 | 2022-02-17 | 2022-03-15 | 01 | 01 | 01 | 13 | 006 | 30 |  | Building | Civil | Museum | Zone 02G | L03 Plenum Level | Civil SubZones
ZONE 02H |  | 251 | 2021-05-01 | 2022-03-01
C-PW-101620 | Site Survey for Action (Item 14 - Immediate) | 1 | 2021-05-01 | 2021-05-01 | 01 | 01 | 01 | 14 | 006 | 30 |  | Building | Civil | Museum | Zone 02H | L03 Plenum Level | Civil SubZones
C-PW-101630 | Construction of Level 03 Slab - Zone 2H (Item 14 - Immediate) | 10 | 2021-07-28 | 2021-08-08 | 01 | 01 | 01 | 14 | 006 | 30 |  | Building | Civil | Museum | Zone 02H | L03 Plenum Level | Civil SubZones
C-PW-101640 | Construction of WC Soffit Slabs at Level 03 - Zone 2H | 24 | 2022-01-03 | 2022-01-30 | 01 | 01 | 01 | 14 | 006 | 30 |  | Building | Civil | Museum | Zone 02H | L03 Plenum Level | Civil SubZones
C-PW-101650 | Construction of Level 03 Slab - Zone 2H | 24 | 2022-01-17 | 2022-02-13 | 01 | 01 | 01 | 14 | 006 | 30 |  | Building | Civil | Museum | Zone 02H | L03 Plenum Level | Civil SubZones
C-PW-101660 | Construction of Verticals up to Level 04 Slab - Zone 2H | 26 | 2022-01-31 | 2022-03-01 | 01 | 01 | 01 | 14 | 006 | 30 |  | Building | Civil | Museum | Zone 02H | L03 Plenum Level | Civil SubZones
ARCHITECTURAL WORKS |  | 246 | 2022-02-21 | 2022-12-14
NORTH WEST |  | 153 | 2022-02-21 | 2022-08-25
PLENUM AREAS- NORTH |  | 153 | 2022-02-21 | 2022-08-25
C-PW-101670 | General Block Works | 17 | 2022-02-21 | 2022-03-12 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-101680 | Marking & Chasing Walls for MEP Services | 19 | 2022-03-02 | 2022-03-24 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-101690 | First Coat Paint in Ceiling | 17 | 2022-03-13 | 2022-04-02 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-101700 | Wall Waterproofing works | 17 | 2022-04-23 | 2022-05-16 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-101710 | Wall Finishes Works | 17 | 2022-05-10 | 2022-05-29 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-101720 | Floor Surface Preparation for Epoxy Coating | 17 | 2022-05-24 | 2022-06-12 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-101730 | Floor Finishes (Epoxy Coating) | 17 | 2022-06-09 | 2022-06-29 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-101740 | Installation of Balustrades | 19 | 2022-06-29 | 2022-07-25 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-101750 | Door Frames Fixing | 6 | 2022-07-25 | 2022-08-02 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-101760 | Door Shuttering / Louvre's & Ironmongery | 10 | 2022-08-02 | 2022-08-14 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-101770 | Final Coat Ceiling Paint | 14 | 2022-08-09 | 2022-08-25 | 01 | 04 | 01 | 46 | 006 | 02 |  | Building | Architecture | Museum | North West | L03 Plenum Level | MEP / Service Rooms
NORTH EAST |  | 174 | 2022-03-26 | 2022-10-24
PLENUM AREAS - EAST |  | 174 | 2022-03-26 | 2022-10-24
C-PW-101780 | General Block Works | 14 | 2022-03-26 | 2022-04-11 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101790 | Marking & Chasing Walls for MEP Services | 17 | 2022-04-04 | 2022-04-23 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101800 | First Coat Paint in Ceiling | 19 | 2022-04-14 | 2022-05-10 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101810 | Wall Waterproofing works | 19 | 2022-06-05 | 2022-06-27 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101820 | Wall Finishes Works | 19 | 2022-06-18 | 2022-07-13 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101830 | Floor Surface preparation for epoxy works | 19 | 2022-07-13 | 2022-08-06 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101840 | Floor Finishes (Epoxy Coating) | 19 | 2022-07-25 | 2022-08-17 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101850 | Cleaning Equipment Installation | 14 | 2022-08-07 | 2022-08-22 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101860 | Installation of Balustrades | 19 | 2022-08-22 | 2022-09-13 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101870 | Door Frames Fixing | 8 | 2022-09-13 | 2022-09-22 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101880 | Door Shuttering / Louvre's & Ironmongery | 11 | 2022-09-22 | 2022-10-05 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-101890 | Final Coat Ceiling Paint | 14 | 2022-10-06 | 2022-10-24 | 01 | 04 | 01 | 44 | 006 | 02 |  | Building | Architecture | Museum | North East | L03 Plenum Level | MEP / Service Rooms
SOUTH WEST |  | 162 | 2022-05-19 | 2022-11-29
PLENUM AREAS - WEST |  | 162 | 2022-05-19 | 2022-11-29
C-PW-101900 | General Block Works | 17 | 2022-05-19 | 2022-06-07 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-101910 | Marking & Chasing Walls for MEP Services | 19 | 2022-05-29 | 2022-06-20 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-101920 | First Coat Paint in Ceiling | 17 | 2022-06-08 | 2022-06-28 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-101930 | Wall Waterproofing works | 17 | 2022-07-31 | 2022-08-18 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-101940 | Wall Finishes Works | 17 | 2022-08-13 | 2022-08-31 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-101950 | Floor Surface Preparation for Epoxy Coating | 17 | 2022-08-27 | 2022-09-14 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-101960 | Floor Finishes (Epoxy Coating) | 17 | 2022-09-12 | 2022-10-02 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-101970 | Installation of Balustrades | 17 | 2022-10-02 | 2022-10-23 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-101980 | Door Frames Fixing | 6 | 2022-10-23 | 2022-10-30 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-101990 | Door Shuttering / Louvre's & Ironmongery | 10 | 2022-10-30 | 2022-11-10 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-102000 | Final Coat Ceiling Paint | 14 | 2022-11-13 | 2022-11-29 | 01 | 04 | 01 | 47 | 006 | 02 |  | Building | Architecture | Museum | South West | L03 Plenum Level | MEP / Service Rooms
SOUTH EAST |  | 164 | 2022-05-31 | 2022-12-14
PLENUM AREAS - SOUTH |  | 164 | 2022-05-31 | 2022-12-14
C-PW-102010 | General Block Works | 14 | 2022-05-31 | 2022-06-16 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-102020 | Marking & Chasing Walls for MEP Services | 19 | 2022-06-09 | 2022-07-02 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-102030 | First Coat Paint in Ceiling | 17 | 2022-06-20 | 2022-07-13 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-102040 | Wall Waterproofing works | 17 | 2022-08-09 | 2022-08-28 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-102050 | Wall Finishes Works | 17 | 2022-08-22 | 2022-09-10 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-102060 | Floor Surface Preparation for Epoxy Coating | 17 | 2022-09-05 | 2022-09-24 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-102070 | Floor Finishes (Epoxy Coating) | 17 | 2022-09-21 | 2022-10-12 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-102080 | Installation of Balustrades | 21 | 2022-10-12 | 2022-11-06 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-102090 | Door Frames Fixing | 6 | 2022-11-06 | 2022-11-13 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-102100 | Door Shuttering / Louvre's & Ironmongery | 10 | 2022-11-13 | 2022-11-24 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-102110 | Final Coat Ceiling Paint | 14 | 2022-11-27 | 2022-12-14 | 01 | 04 | 01 | 45 | 006 | 02 |  | Building | Architecture | Museum | South East | L03 Plenum Level | MEP / Service Rooms
MEP WORKS |  | 211 | 2022-03-22 | 2022-12-04
NORTH WEST |  | 124 | 2022-03-22 | 2022-08-22
PLENUM AREAS- NORTH |  | 124 | 2022-03-22 | 2022-08-22
MECHANICAL |  | 114 | 2022-04-02 | 2022-08-20
DRAINAGE WORKS |  | 28 | 2022-04-02 | 2022-05-08
C-PW-102250 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-04-02 | 2022-04-20 | 01 | 08 | 01 | 46 | 006 | 02 |  | Building | Plumbing | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102260 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 12 | 2022-04-20 | 2022-05-08 | 01 | 08 | 01 | 46 | 006 | 02 |  | Building | Plumbing | Museum | North West | L03 Plenum Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 28 | 2022-04-07 | 2022-05-14
C-PW-102270 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-04-07 | 2022-04-26 | 01 | 08 | 01 | 46 | 006 | 02 |  | Building | Plumbing | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102280 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 12 | 2022-04-26 | 2022-05-14 | 01 | 08 | 01 | 46 | 006 | 02 |  | Building | Plumbing | Museum | North West | L03 Plenum Level | MEP / Service Rooms
HVAC SYSTEM WORKS |  | 106 | 2022-04-11 | 2022-08-20
C-PW-102290 | 1st Fix HVAC (Supports, Ducts ,Dampers - VCD,NRD,MDs) | 16 | 2022-04-11 | 2022-04-30 | 01 | 06 | 01 | 46 | 006 | 02 |  | Building | HVAC | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102300 | 2nd Fix HVAC (Duct Plenums & Flex.Connector) | 16 | 2022-04-30 | 2022-05-22 | 01 | 06 | 01 | 46 | 006 | 02 |  | Building | HVAC | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102310 | Final Fix HVAC (Grills, Diffusers) | 10 | 2022-08-08 | 2022-08-20 | 01 | 06 | 01 | 46 | 006 | 02 |  | Building | HVAC | Museum | North West | L03 Plenum Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 124 | 2022-03-22 | 2022-08-22
C-PW-102320 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-03-22 | 2022-04-03 | 01 | 07 | 01 | 46 | 006 | 02 |  | Building | Electrical | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102330 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-04-14 | 2022-05-07 | 01 | 07 | 01 | 46 | 006 | 02 |  | Building | Electrical | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102340 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 16 | 2022-05-07 | 2022-05-25 | 01 | 07 | 01 | 46 | 006 | 02 |  | Building | Electrical | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102350 | LV Switchgears (DB's) | 5 | 2022-05-25 | 2022-05-31 | 01 | 07 | 01 | 46 | 006 | 02 |  | Building | Electrical | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102360 | Cable/Wire Termination & Dressing | 7 | 2022-05-31 | 2022-06-08 | 01 | 07 | 01 | 46 | 006 | 02 |  | Building | Electrical | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102370 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-08-08 | 2022-08-16 | 01 | 07 | 01 | 46 | 006 | 02 |  | Building | Electrical | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102380 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-10 | 2022-08-18 | 01 | 07 | 01 | 46 | 006 | 02 |  | Building | Electrical | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102390 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-11 | 2022-08-20 | 01 | 07 | 01 | 46 | 006 | 02 |  | Building | Electrical | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102400 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-14 | 2022-08-22 | 01 | 07 | 01 | 46 | 006 | 02 |  | Building | Electrical | Museum | North West | L03 Plenum Level | MEP / Service Rooms
ELV |  | 119 | 2022-03-24 | 2022-08-18
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 118 | 2022-03-24 | 2022-08-16
C-PW-102410 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-03-24 | 2022-04-05 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102420 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-04-05 | 2022-04-17 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102430 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-08-14 | 2022-08-16 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
AV SYSTEM |  | 116 | 2022-03-26 | 2022-08-16
C-PW-102440 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-07 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102450 | 2nd Fix AV System Works (Wiring) | 10 | 2022-04-07 | 2022-04-19 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102460 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-08-14 | 2022-08-16 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 114 | 2022-03-28 | 2022-08-16
C-PW-102470 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-03-28 | 2022-04-09 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102480 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-04-09 | 2022-04-21 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102490 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-08-14 | 2022-08-16 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 114 | 2022-03-30 | 2022-08-18
C-PW-102500 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-03-30 | 2022-04-11 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102510 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-04-11 | 2022-04-23 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102520 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-08-16 | 2022-08-18 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 113 | 2022-03-31 | 2022-08-18
C-PW-102530 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-03-31 | 2022-04-12 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102540 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-04-13 | 2022-04-25 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102550 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-08-16 | 2022-08-18 | 01 | 10 | 01 | 46 | 006 | 02 |  | Building | CCTV | Museum | North West | L03 Plenum Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 121 | 2022-03-24 | 2022-08-20
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 118 | 2022-03-24 | 2022-08-16
C-PW-102560 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-03-24 | 2022-04-05 | 01 | 09 | 01 | 46 | 006 | 02 |  | Building | Firefighting | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102570 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-04-05 | 2022-04-17 | 01 | 09 | 01 | 46 | 006 | 02 |  | Building | Firefighting | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102580 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-08-14 | 2022-08-16 | 01 | 09 | 01 | 46 | 006 | 02 |  | Building | Firefighting | Museum | North West | L03 Plenum Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 116 | 2022-03-26 | 2022-08-16
C-PW-102590 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-03-26 | 2022-04-07 | 01 | 09 | 01 | 46 | 006 | 02 |  | Building | Firefighting | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102600 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-04-07 | 2022-04-19 | 01 | 09 | 01 | 46 | 006 | 02 |  | Building | Firefighting | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102610 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-08-14 | 2022-08-16 | 01 | 09 | 01 | 46 | 006 | 02 |  | Building | Firefighting | Museum | North West | L03 Plenum Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 109 | 2022-04-07 | 2022-08-20
C-PW-102620 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-04-07 | 2022-04-26 | 01 | 09 | 01 | 46 | 006 | 02 |  | Building | Firefighting | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102630 | 2nd Fix Piping System - (Fittings, Connections & Testing) | 12 | 2022-04-26 | 2022-05-14 | 01 | 09 | 01 | 46 | 006 | 02 |  | Building | Firefighting | Museum | North West | L03 Plenum Level | MEP / Service Rooms
C-PW-102640 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 10 | 2022-08-08 | 2022-08-20 | 01 | 09 | 01 | 46 | 006 | 02 |  | Building | Firefighting | Museum | North West | L03 Plenum Level | MEP / Service Rooms
NORTH EAST |  | 140 | 2022-04-24 | 2022-10-13
PLENUM AREAS - EAST |  | 140 | 2022-04-24 | 2022-10-13
MECHANICAL |  | 127 | 2022-05-10 | 2022-10-11
DRAINAGE WORKS |  | 28 | 2022-05-10 | 2022-06-12
C-PW-102650 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-05-10 | 2022-05-29 | 01 | 08 | 01 | 44 | 006 | 02 |  | Building | Plumbing | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102660 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 12 | 2022-05-29 | 2022-06-12 | 01 | 08 | 01 | 44 | 006 | 02 |  | Building | Plumbing | Museum | North East | L03 Plenum Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 28 | 2022-05-16 | 2022-06-18
C-PW-102670 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-05-16 | 2022-06-04 | 01 | 08 | 01 | 44 | 006 | 02 |  | Building | Plumbing | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102680 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 12 | 2022-06-04 | 2022-06-18 | 01 | 08 | 01 | 44 | 006 | 02 |  | Building | Plumbing | Museum | North East | L03 Plenum Level | MEP / Service Rooms
HVAC SYSTEM WORKS |  | 119 | 2022-05-19 | 2022-10-11
C-PW-102690 | 1st Fix HVAC (Supports, Ducts ,Dampers - VCD,NRD,MDs) | 18 | 2022-05-19 | 2022-06-11 | 01 | 06 | 01 | 44 | 006 | 02 |  | Building | HVAC | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102700 | 2nd Fix HVAC (Duct Plenums & Flex.Connector) | 18 | 2022-06-11 | 2022-07-02 | 01 | 06 | 01 | 44 | 006 | 02 |  | Building | HVAC | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102710 | Final Fix HVAC (Grills, Diffusers) | 10 | 2022-09-28 | 2022-10-11 | 01 | 06 | 01 | 44 | 006 | 02 |  | Building | HVAC | Museum | North East | L03 Plenum Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 140 | 2022-04-24 | 2022-10-13
C-PW-102720 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-04-24 | 2022-05-09 | 01 | 07 | 01 | 44 | 006 | 02 |  | Building | Electrical | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102730 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 18 | 2022-05-24 | 2022-06-14 | 01 | 07 | 01 | 44 | 006 | 02 |  | Building | Electrical | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102740 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 18 | 2022-06-14 | 2022-07-05 | 01 | 07 | 01 | 44 | 006 | 02 |  | Building | Electrical | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102750 | LV Switchgears (DB's) | 5 | 2022-07-05 | 2022-07-14 | 01 | 07 | 01 | 44 | 006 | 02 |  | Building | Electrical | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102760 | Cable/Wire Termination & Dressing | 7 | 2022-07-14 | 2022-07-23 | 01 | 07 | 01 | 44 | 006 | 02 |  | Building | Electrical | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102770 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-09-28 | 2022-10-06 | 01 | 07 | 01 | 44 | 006 | 02 |  | Building | Electrical | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102780 | Final Fix Electrical (Light Fixtures) | 7 | 2022-10-01 | 2022-10-10 | 01 | 07 | 01 | 44 | 006 | 02 |  | Building | Electrical | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102790 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-10-02 | 2022-10-11 | 01 | 07 | 01 | 44 | 006 | 02 |  | Building | Electrical | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102800 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-10-04 | 2022-10-13 | 01 | 07 | 01 | 44 | 006 | 02 |  | Building | Electrical | Museum | North East | L03 Plenum Level | MEP / Service Rooms
ELV |  | 137 | 2022-04-26 | 2022-10-11
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 135 | 2022-04-26 | 2022-10-10
C-PW-102810 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102820 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102830 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-10-06 | 2022-10-10 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
AV SYSTEM |  | 134 | 2022-04-27 | 2022-10-10
C-PW-102840 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-14 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102850 | 2nd Fix AV System Works (Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102860 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-10-06 | 2022-10-10 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 132 | 2022-04-30 | 2022-10-10
C-PW-102870 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-04-30 | 2022-05-15 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102880 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-05-15 | 2022-05-28 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102890 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-10-06 | 2022-10-10 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 132 | 2022-05-05 | 2022-10-11
C-PW-102900 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-05-05 | 2022-05-17 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102910 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-05-17 | 2022-05-29 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102920 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-11 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 130 | 2022-05-07 | 2022-10-11
C-PW-102930 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-05-07 | 2022-05-18 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102940 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-05-19 | 2022-05-31 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102950 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-10-08 | 2022-10-11 | 01 | 10 | 01 | 44 | 006 | 02 |  | Building | CCTV | Museum | North East | L03 Plenum Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 137 | 2022-04-26 | 2022-10-11
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 135 | 2022-04-26 | 2022-10-10
C-PW-102960 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-04-26 | 2022-05-11 | 01 | 09 | 01 | 44 | 006 | 02 |  | Building | Firefighting | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102970 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-05-11 | 2022-05-23 | 01 | 09 | 01 | 44 | 006 | 02 |  | Building | Firefighting | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-102980 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-10-06 | 2022-10-10 | 01 | 09 | 01 | 44 | 006 | 02 |  | Building | Firefighting | Museum | North East | L03 Plenum Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 134 | 2022-04-27 | 2022-10-10
C-PW-102990 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-04-27 | 2022-05-14 | 01 | 09 | 01 | 44 | 006 | 02 |  | Building | Firefighting | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-103000 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-05-14 | 2022-05-25 | 01 | 09 | 01 | 44 | 006 | 02 |  | Building | Firefighting | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-103010 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-10-06 | 2022-10-10 | 01 | 09 | 01 | 44 | 006 | 02 |  | Building | Firefighting | Museum | North East | L03 Plenum Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 116 | 2022-05-24 | 2022-10-11
C-PW-103020 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 18 | 2022-05-24 | 2022-06-14 | 01 | 09 | 01 | 44 | 006 | 02 |  | Building | Firefighting | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-103030 | 2nd Fix Piping System - (Fittings, Connections & Testing) | 14 | 2022-06-14 | 2022-06-29 | 01 | 09 | 01 | 44 | 006 | 02 |  | Building | Firefighting | Museum | North East | L03 Plenum Level | MEP / Service Rooms
C-PW-103040 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 10 | 2022-09-28 | 2022-10-11 | 01 | 09 | 01 | 44 | 006 | 02 |  | Building | Firefighting | Museum | North East | L03 Plenum Level | MEP / Service Rooms
SOUTH WEST |  | 118 | 2022-06-28 | 2022-11-19
PLENUM AREAS - WEST |  | 118 | 2022-06-28 | 2022-11-19
MECHANICAL |  | 116 | 2022-06-28 | 2022-11-16
DRAINAGE WORKS |  | 28 | 2022-06-28 | 2022-08-04
C-PW-103050 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-06-28 | 2022-07-20 | 01 | 08 | 01 | 47 | 006 | 02 |  | Building | Plumbing | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103060 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 12 | 2022-07-20 | 2022-08-04 | 01 | 08 | 01 | 47 | 006 | 02 |  | Building | Plumbing | Museum | South West | L03 Plenum Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 28 | 2022-07-04 | 2022-08-10
C-PW-103070 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-07-04 | 2022-07-26 | 01 | 08 | 01 | 47 | 006 | 02 |  | Building | Plumbing | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103080 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 12 | 2022-07-26 | 2022-08-10 | 01 | 08 | 01 | 47 | 006 | 02 |  | Building | Plumbing | Museum | South West | L03 Plenum Level | MEP / Service Rooms
HVAC SYSTEM WORKS |  | 108 | 2022-07-07 | 2022-11-16
C-PW-103090 | 1st Fix HVAC (Supports, Ducts ,Dampers - VCD,NRD,MDs) | 16 | 2022-07-07 | 2022-07-31 | 01 | 06 | 01 | 47 | 006 | 02 |  | Building | HVAC | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103100 | 2nd Fix HVAC (Duct Plenums & Flex.Connector) | 16 | 2022-07-31 | 2022-08-18 | 01 | 06 | 01 | 47 | 006 | 02 |  | Building | HVAC | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103110 | Final Fix HVAC (Grills, Diffusers) | 10 | 2022-11-05 | 2022-11-16 | 01 | 06 | 01 | 47 | 006 | 02 |  | Building | HVAC | Museum | South West | L03 Plenum Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 106 | 2022-07-16 | 2022-11-19
C-PW-103120 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-07-16 | 2022-07-27 | 01 | 07 | 01 | 47 | 006 | 02 |  | Building | Electrical | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103130 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-07-20 | 2022-08-09 | 01 | 07 | 01 | 47 | 006 | 02 |  | Building | Electrical | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103140 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 16 | 2022-08-09 | 2022-08-28 | 01 | 07 | 01 | 47 | 006 | 02 |  | Building | Electrical | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103150 | LV Switchgears (DB's) | 5 | 2022-08-28 | 2022-09-03 | 01 | 07 | 01 | 47 | 006 | 02 |  | Building | Electrical | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103160 | Cable/Wire Termination & Dressing | 7 | 2022-09-03 | 2022-09-11 | 01 | 07 | 01 | 47 | 006 | 02 |  | Building | Electrical | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103170 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-11-05 | 2022-11-13 | 01 | 07 | 01 | 47 | 006 | 02 |  | Building | Electrical | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103180 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-07 | 2022-11-15 | 01 | 07 | 01 | 47 | 006 | 02 |  | Building | Electrical | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103190 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-08 | 2022-11-16 | 01 | 07 | 01 | 47 | 006 | 02 |  | Building | Electrical | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103200 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-10 | 2022-11-19 | 01 | 07 | 01 | 47 | 006 | 02 |  | Building | Electrical | Museum | South West | L03 Plenum Level | MEP / Service Rooms
ELV |  | 102 | 2022-07-17 | 2022-11-15
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 100 | 2022-07-17 | 2022-11-13
C-PW-103210 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-07-17 | 2022-07-28 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103220 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-31 | 2022-08-11 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103230 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
AV SYSTEM |  | 98 | 2022-07-19 | 2022-11-13
C-PW-103240 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-19 | 2022-08-01 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103250 | 2nd Fix AV System Works (Wiring) | 10 | 2022-08-03 | 2022-08-15 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103260 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 97 | 2022-07-20 | 2022-11-13
C-PW-103270 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-07-20 | 2022-08-03 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103280 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-08-03 | 2022-08-15 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103290 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 97 | 2022-07-23 | 2022-11-15
C-PW-103300 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-23 | 2022-08-04 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103310 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-08-04 | 2022-08-17 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103320 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-12 | 2022-11-15 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 95 | 2022-07-25 | 2022-11-15
C-PW-103330 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-25 | 2022-08-07 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103340 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-08-07 | 2022-08-18 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103350 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-12 | 2022-11-15 | 01 | 10 | 01 | 47 | 006 | 02 |  | Building | CCTV | Museum | South West | L03 Plenum Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 105 | 2022-07-14 | 2022-11-16
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 100 | 2022-07-17 | 2022-11-13
C-PW-103360 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-17 | 2022-07-28 | 01 | 09 | 01 | 47 | 006 | 02 |  | Building | Firefighting | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103370 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-31 | 2022-08-11 | 01 | 09 | 01 | 47 | 006 | 02 |  | Building | Firefighting | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103380 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 09 | 01 | 47 | 006 | 02 |  | Building | Firefighting | Museum | South West | L03 Plenum Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 98 | 2022-07-19 | 2022-11-13
C-PW-103390 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-19 | 2022-08-01 | 01 | 09 | 01 | 47 | 006 | 02 |  | Building | Firefighting | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103400 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-08-01 | 2022-08-13 | 01 | 09 | 01 | 47 | 006 | 02 |  | Building | Firefighting | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103410 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-10 | 2022-11-13 | 01 | 09 | 01 | 47 | 006 | 02 |  | Building | Firefighting | Museum | South West | L03 Plenum Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 105 | 2022-07-14 | 2022-11-16
C-PW-103420 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-07-14 | 2022-08-03 | 01 | 09 | 01 | 47 | 006 | 02 |  | Building | Firefighting | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103430 | 2nd Fix Piping System - (Fittings, Connections & Testing) | 12 | 2022-08-03 | 2022-08-17 | 01 | 09 | 01 | 47 | 006 | 02 |  | Building | Firefighting | Museum | South West | L03 Plenum Level | MEP / Service Rooms
C-PW-103440 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 10 | 2022-11-05 | 2022-11-16 | 01 | 09 | 01 | 47 | 006 | 02 |  | Building | Firefighting | Museum | South West | L03 Plenum Level | MEP / Service Rooms
SOUTH EAST |  | 129 | 2022-06-29 | 2022-12-04
PLENUM AREAS - SOUTH |  | 129 | 2022-06-29 | 2022-12-04
MECHANICAL |  | 118 | 2022-07-13 | 2022-12-01
DRAINAGE WORKS |  | 28 | 2022-07-13 | 2022-08-16
C-PW-103450 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-07-13 | 2022-08-02 | 01 | 08 | 01 | 45 | 006 | 02 |  | Building | Plumbing | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103460 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 12 | 2022-08-02 | 2022-08-16 | 01 | 08 | 01 | 45 | 006 | 02 |  | Building | Plumbing | Museum | South East | L03 Plenum Level | MEP / Service Rooms
HOT & COLD WATER SYSTEM |  | 28 | 2022-07-19 | 2022-08-22
C-PW-103470 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-07-19 | 2022-08-08 | 01 | 08 | 01 | 45 | 006 | 02 |  | Building | Plumbing | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103480 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 12 | 2022-08-08 | 2022-08-22 | 01 | 08 | 01 | 45 | 006 | 02 |  | Building | Plumbing | Museum | South East | L03 Plenum Level | MEP / Service Rooms
HVAC SYSTEM WORKS |  | 110 | 2022-07-23 | 2022-12-01
C-PW-103490 | 1st Fix HVAC (Supports, Ducts ,Dampers - VCD,NRD,MDs) | 16 | 2022-07-23 | 2022-08-11 | 01 | 06 | 01 | 45 | 006 | 02 |  | Building | HVAC | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103500 | 2nd Fix HVAC (Duct Plenums & Flex.Connector) | 16 | 2022-08-11 | 2022-08-30 | 01 | 06 | 01 | 45 | 006 | 02 |  | Building | HVAC | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103510 | Final Fix HVAC (Grills, Diffusers) | 10 | 2022-11-19 | 2022-12-01 | 01 | 06 | 01 | 45 | 006 | 02 |  | Building | HVAC | Museum | South East | L03 Plenum Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 129 | 2022-06-29 | 2022-12-04
C-PW-103520 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-06-29 | 2022-07-14 | 01 | 07 | 01 | 45 | 006 | 02 |  | Building | Electrical | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103530 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-07-26 | 2022-08-15 | 01 | 07 | 01 | 45 | 006 | 02 |  | Building | Electrical | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103540 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 16 | 2022-08-15 | 2022-09-03 | 01 | 07 | 01 | 45 | 006 | 02 |  | Building | Electrical | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103550 | LV Switchgears (DB's) | 5 | 2022-09-03 | 2022-09-08 | 01 | 07 | 01 | 45 | 006 | 02 |  | Building | Electrical | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103560 | Cable/Wire Termination & Dressing | 7 | 2022-09-08 | 2022-09-17 | 01 | 07 | 01 | 45 | 006 | 02 |  | Building | Electrical | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103570 | Final Fix Electrical (Power Socket / Isolators) | 7 | 2022-11-19 | 2022-11-27 | 01 | 07 | 01 | 45 | 006 | 02 |  | Building | Electrical | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103580 | Final Fix Electrical (Light Fixtures) | 7 | 2022-11-21 | 2022-11-29 | 01 | 07 | 01 | 45 | 006 | 02 |  | Building | Electrical | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103590 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-11-22 | 2022-12-01 | 01 | 07 | 01 | 45 | 006 | 02 |  | Building | Electrical | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103600 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-11-24 | 2022-12-04 | 01 | 07 | 01 | 45 | 006 | 02 |  | Building | Electrical | Museum | South East | L03 Plenum Level | MEP / Service Rooms
ELV |  | 124 | 2022-07-02 | 2022-11-29
ACCESS CONTROL & CENTRAL SECURITY SYSTEM |  | 122 | 2022-07-02 | 2022-11-27
C-PW-103610 | 1st Fix Access Control & Central Security System Works (Conduits & Boxes) | 10 | 2022-07-02 | 2022-07-17 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103620 | 2nd Fix Access Control & Central Security System Works (Cables & Wiring) | 10 | 2022-07-17 | 2022-07-28 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103630 | Final Fix Access Control & Central Security System Works (Accessories, Devices, Etc.) | 2 | 2022-11-24 | 2022-11-27 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
AV SYSTEM |  | 121 | 2022-07-03 | 2022-11-27
C-PW-103640 | 1st Fix AV System Works (Conduits & Boxes) | 10 | 2022-07-03 | 2022-07-19 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103650 | 2nd Fix AV System Works (Wiring) | 10 | 2022-07-19 | 2022-08-01 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103660 | Final Fix AV System Works (Accessories, Devices, Etc.) | 2 | 2022-11-24 | 2022-11-27 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
VIDEO SURVEILLANCE SYSTEM |  | 119 | 2022-07-05 | 2022-11-27
C-PW-103670 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 10 | 2022-07-05 | 2022-07-20 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103680 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 10 | 2022-07-20 | 2022-08-03 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103690 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 2 | 2022-11-24 | 2022-11-27 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
DATA AND TELECOMMUNICATION |  | 119 | 2022-07-07 | 2022-11-29
C-PW-103700 | 1st Fix Data & Telecommunication Works (Conduits & Boxes) | 10 | 2022-07-07 | 2022-07-23 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103710 | 2nd Fix Data & Telecommunication Works (Cables & Wiring) | 10 | 2022-07-23 | 2022-08-04 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103720 | Final Fix Data & Telecommunication Works (Accessories, Devices, Etc.) | 2 | 2022-11-26 | 2022-11-29 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
BMS AND AUTOMATIC CONTROLS |  | 118 | 2022-07-09 | 2022-11-29
C-PW-103730 | 1st Fix BMS & Automatic Controls Works (Conduits & Boxes) | 10 | 2022-07-09 | 2022-07-24 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103740 | 2nd Fix BMS & Automatic Controls Works (Cable & Wiring) | 10 | 2022-07-25 | 2022-08-07 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103750 | Final Fix BMS & Automatic Controls Works (Accessories, Devices, Etc.) | 2 | 2022-11-26 | 2022-11-29 | 01 | 10 | 01 | 45 | 006 | 02 |  | Building | CCTV | Museum | South East | L03 Plenum Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 126 | 2022-07-02 | 2022-12-01
EMERGENCY LIGHTING & CENTRAL BATTERY |  | 122 | 2022-07-02 | 2022-11-27
C-PW-103760 | 1st Fix Emergency Lighting & Central Battery Works (Conduits & Boxes) | 10 | 2022-07-02 | 2022-07-17 | 01 | 09 | 01 | 45 | 006 | 02 |  | Building | Firefighting | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103770 | 2nd Fix Emergency Lighting & Central Battery Works (Cable & Wiring) | 10 | 2022-07-17 | 2022-07-28 | 01 | 09 | 01 | 45 | 006 | 02 |  | Building | Firefighting | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103780 | Final Fix Emergency Lighting Works ( Emergency Lighting, Accessories, Devices, Etc.) | 2 | 2022-11-24 | 2022-11-27 | 01 | 09 | 01 | 45 | 006 | 02 |  | Building | Firefighting | Museum | South East | L03 Plenum Level | MEP / Service Rooms
FIRE ALARM & PUBLIC ADDRESS |  | 121 | 2022-07-03 | 2022-11-27
C-PW-103790 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 10 | 2022-07-03 | 2022-07-19 | 01 | 09 | 01 | 45 | 006 | 02 |  | Building | Firefighting | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103800 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 10 | 2022-07-19 | 2022-08-01 | 01 | 09 | 01 | 45 | 006 | 02 |  | Building | Firefighting | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103810 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-11-24 | 2022-11-27 | 01 | 09 | 01 | 45 | 006 | 02 |  | Building | Firefighting | Museum | South East | L03 Plenum Level | MEP / Service Rooms
FIRE FIGHTING WORKS |  | 107 | 2022-07-26 | 2022-12-01
C-PW-103820 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-07-26 | 2022-08-15 | 01 | 09 | 01 | 45 | 006 | 02 |  | Building | Firefighting | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103830 | 2nd Fix Piping System - (Fittings, Connections & Testing) | 12 | 2022-08-15 | 2022-08-29 | 01 | 09 | 01 | 45 | 006 | 02 |  | Building | Firefighting | Museum | South East | L03 Plenum Level | MEP / Service Rooms
C-PW-103840 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 10 | 2022-11-19 | 2022-12-01 | 01 | 09 | 01 | 45 | 006 | 02 |  | Building | Firefighting | Museum | South East | L03 Plenum Level | MEP / Service Rooms
LEVEL 04 ROOF |  | 233 | 2021-12-16 | 2022-09-22
CIVIL WORKS |  | 130 | 2021-12-21 | 2022-05-25
ZONE 02A |  | 50 | 2021-12-21 | 2022-02-17
C-PW-104250 | Construction of Level 04 Slab - Zone 2A | 24 | 2021-12-21 | 2022-01-18 | 01 | 01 | 01 | 07 | 007 | 30 |  | Building | Civil | Museum | Zone 02A | L04 Oasis Level | Civil SubZones
C-PW-104260 | Waterproofing & Precast gutter installation / Leave out slab - Zone 2A | 26 | 2022-01-19 | 2022-02-17 | 01 | 01 | 01 | 07 | 007 | 30 |  | Building | Civil | Museum | Zone 02A | L04 Oasis Level | Civil SubZones
ZONE 02B |  | 48 | 2022-01-24 | 2022-03-20
C-PW-104270 | Construction of Level - 04 Slab - Zone 2B | 24 | 2022-01-24 | 2022-02-20 | 01 | 01 | 01 | 08 | 007 | 30 |  | Building | Civil | Museum | Zone 02B | L04 Oasis Level | Civil SubZones
C-PW-104280 | Waterproofing / Precast Gutter Installation & Level 04 Leave out Slab - Zone 2B | 24 | 2022-02-21 | 2022-03-20 | 01 | 01 | 01 | 08 | 007 | 30 |  | Building | Civil | Museum | Zone 02B | L04 Oasis Level | Civil SubZones
ZONE 02C |  | 48 | 2022-03-28 | 2022-05-25
C-PW-104290 | Construction of Level 04 Slab - Zone 2C | 24 | 2022-03-28 | 2022-04-24 | 01 | 01 | 01 | 09 | 007 | 30 |  | Building | Civil | Museum | Zone 02C | L04 Oasis Level | Civil SubZones
C-PW-104300 | Waterproofing / Precast Gutter Installation & Level 04 Leave out Slab - Zone 2C | 24 | 2022-04-25 | 2022-05-25 | 01 | 01 | 01 | 09 | 007 | 30 |  | Building | Civil | Museum | Zone 02C | L04 Oasis Level | Civil SubZones
ZONE 02G |  | 48 | 2022-03-16 | 2022-05-14
C-PW-104310 | Construction of Level 04 Slab - Zone 2G | 24 | 2022-03-16 | 2022-04-12 | 01 | 01 | 01 | 13 | 007 | 30 |  | Building | Civil | Museum | Zone 02G | L04 Oasis Level | Civil SubZones
C-PW-104320 | Waterproofing & Precast Gutter Installation / Level 04 Leave Out Slab- Zone 2G | 24 | 2022-04-13 | 2022-05-14 | 01 | 01 | 01 | 13 | 007 | 30 |  | Building | Civil | Museum | Zone 02G | L04 Oasis Level | Civil SubZones
ZONE 02H |  | 48 | 2022-03-02 | 2022-04-26
C-PW-104330 | Construction of Level 04 Slab - Zone 2H | 24 | 2022-03-02 | 2022-03-29 | 01 | 01 | 01 | 14 | 007 | 30 |  | Building | Civil | Museum | Zone 02H | L04 Oasis Level | Civil SubZones
C-PW-104340 | Waterproofing and Precast Gutter Installation / Level 04 leaveout Slab - Zone 2H | 24 | 2022-03-30 | 2022-04-26 | 01 | 01 | 01 | 14 | 007 | 30 |  | Building | Civil | Museum | Zone 02H | L04 Oasis Level | Civil SubZones
ARCHITECTURAL WORKS |  | 91 | 2022-06-05 | 2022-09-22
C-PW-104350 | Setting out | 5 | 2022-06-05 | 2022-06-09 | 01 | 04 | 01 | 50 | 007 | 30 |  | Building | Architecture | Museum | L04 Roof | L04 Oasis Level | Civil SubZones
C-PW-104360 | Construction of Concrete Base | 17 | 2022-06-09 | 2022-06-29 | 01 | 04 | 01 | 50 | 007 | 30 |  | Building | Architecture | Museum | L04 Roof | L04 Oasis Level | Civil SubZones
C-PW-104370 | Install EPS | 10 | 2022-06-29 | 2022-07-14 | 01 | 04 | 01 | 50 | 007 | 30 |  | Building | Architecture | Museum | L04 Roof | L04 Oasis Level | Civil SubZones
C-PW-104380 | Installation of Waterproofing Membrane & Protection Board & Screed | 17 | 2022-07-14 | 2022-08-04 | 01 | 04 | 01 | 50 | 007 | 30 |  | Building | Architecture | Museum | L04 Roof | L04 Oasis Level | Civil SubZones
C-PW-104390 | Installation of Insulation Material | 11 | 2022-08-04 | 2022-08-17 | 01 | 04 | 01 | 50 | 007 | 30 |  | Building | Architecture | Museum | L04 Roof | L04 Oasis Level | Civil SubZones
C-PW-104400 | Installation of Concrete Pavers / Stone Coping , Precast Drain Channel Etc. | 17 | 2022-08-17 | 2022-09-06 | 01 | 04 | 01 | 50 | 007 | 30 |  | Building | Architecture | Museum | L04 Roof | L04 Oasis Level | Civil SubZones
C-PW-104410 | Installation of Handrails and other Metal works | 14 | 2022-09-06 | 2022-09-22 | 01 | 04 | 01 | 50 | 007 | 30 |  | Building | Architecture | Museum | L04 Roof | L04 Oasis Level | Civil SubZones
MEP WORKS |  | 225 | 2021-12-16 | 2022-09-14
MECHANICAL |  | 186 | 2021-12-16 | 2022-07-31
HVAC SYSTEM WORKS |  | 13 | 2022-07-14 | 2022-07-31
C-PW-104420 | 1st Fix LTHW System (Installation of Supports, Piping & fittings) | 10 | 2022-07-14 | 2022-07-25 | 01 | 06 | 01 | 50 | 007 | 02 |  | Building | HVAC | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104430 | 1st Fix LTHW System (Installation of Valves & accessories) | 8 | 2022-07-20 | 2022-07-31 | 01 | 06 | 01 | 50 | 007 | 02 |  | Building | HVAC | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
DRAINAGE WORKS |  | 32 | 2022-04-25 | 2022-06-04
C-PW-104440 | 1st Fix Storm Water Piping System (Supports, Piping) | 22 | 2022-04-25 | 2022-05-23 | 01 | 08 | 01 | 50 | 007 | 02 |  | Building | Plumbing | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104450 | 2nd Fix Storm Water Piping System (Connection & Testing) | 3 | 2022-05-23 | 2022-05-26 | 01 | 08 | 01 | 50 | 007 | 02 |  | Building | Plumbing | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104460 | Install Roof Drains | 7 | 2022-05-26 | 2022-06-04 | 01 | 08 | 01 | 50 | 007 | 02 |  | Building | Plumbing | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
COLD WATER SYSTEM |  | 20 | 2021-12-16 | 2022-01-09
C-PW-104470 | 1st Fix Piping System (Supports, Piping) | 14 | 2021-12-16 | 2022-01-02 | 01 | 08 | 01 | 50 | 007 | 02 |  | Building | Plumbing | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104480 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 3 | 2022-01-02 | 2022-01-05 | 01 | 08 | 01 | 50 | 007 | 02 |  | Building | Plumbing | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104490 | Final Fix Piping System (Installation of Bip Tap) | 3 | 2022-01-05 | 2022-01-09 | 01 | 08 | 01 | 50 | 007 | 02 |  | Building | Plumbing | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
ELECTRICAL WORKS |  | 79 | 2022-06-09 | 2022-09-14
C-PW-104500 | 1st Fix Electrical (Conduits & boxes) - Lighting System | 9 | 2022-06-09 | 2022-06-19 | 01 | 07 | 01 | 50 | 007 | 02 |  | Building | Electrical | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104510 | 2nd Fix Electrical (Wires & Cables) -Lighting System | 10 | 2022-06-19 | 2022-07-02 | 01 | 07 | 01 | 50 | 007 | 02 |  | Building | Electrical | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104520 | 2nd Fix Electrical (Installation of Lightning & Earthing) | 8 | 2022-07-02 | 2022-07-14 | 01 | 07 | 01 | 50 | 007 | 02 |  | Building | Electrical | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104530 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-06 | 2022-09-14 | 01 | 07 | 01 | 50 | 007 | 02 |  | Building | Electrical | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
ELV |  | 19 | 2022-06-07 | 2022-06-29
VIDEO SURVEILLANCE SYSTEM |  | 19 | 2022-06-07 | 2022-06-29
C-PW-104540 | 1st Fix Video Surveillance System Works (Conduits & Boxes) | 8 | 2022-06-07 | 2022-06-15 | 01 | 10 | 01 | 50 | 007 | 02 |  | Building | CCTV | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104550 | 2nd Fix Video Surveillance System Works (Cable & Wiring) | 8 | 2022-06-16 | 2022-06-25 | 01 | 10 | 01 | 50 | 007 | 02 |  | Building | CCTV | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104560 | Final Fix Video Surveillance System Works (CCTV, Accessories, Etc.) | 3 | 2022-06-26 | 2022-06-29 | 01 | 10 | 01 | 50 | 007 | 02 |  | Building | CCTV | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
LIFE AND SAFETY SYSTEM |  | 14 | 2022-06-07 | 2022-06-22
FIRE ALARM & PUBLIC ADDRESS |  | 14 | 2022-06-07 | 2022-06-22
C-PW-104570 | 1st Fix Fire Alarm & Public Address Works (Conduits & Boxes) | 6 | 2022-06-07 | 2022-06-13 | 01 | 09 | 01 | 50 | 007 | 02 |  | Building | Firefighting | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104580 | 2nd Fix Fire Alarm & Public Address Works (Cable & Wiring) | 6 | 2022-06-13 | 2022-06-20 | 01 | 09 | 01 | 50 | 007 | 02 |  | Building | Firefighting | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
C-PW-104590 | Final Fix Fire Alarm & Public Address Works (Accessories, Devices, Etc.) | 2 | 2022-06-20 | 2022-06-22 | 01 | 09 | 01 | 50 | 007 | 02 |  | Building | Firefighting | Museum | L04 Roof | L04 Oasis Level | MEP / Service Rooms
Zone 4 |  | 213 | 2022-02-06 | 2022-10-20
TUNNEL |  | 151 | 2022-02-06 | 2022-08-09
CIVIL WORKS |  | 52 | 2022-02-06 | 2022-04-06
C-PW-104600 | Construction of Tunnel Concrete wall including MEP inserts | 10 | 2022-02-06 | 2022-02-16 | 01 | 01 | 01 | 18 | 001 | 30 |  | Building | Civil | Museum | Zone 04 | L-B1 Basement Level | Civil SubZones
C-PW-104610 | Construct Roof Slab | 20 | 2022-02-17 | 2022-03-12 | 01 | 01 | 01 | 18 | 001 | 30 |  | Building | Civil | Museum | Zone 04 | L-B1 Basement Level | Civil SubZones
C-PW-104620 | Fair Facing & Waterproofing for concrete wall | 10 | 2022-03-13 | 2022-03-23 | 01 | 01 | 01 | 18 | 001 | 30 |  | Building | Civil | Museum | Zone 04 | L-B1 Basement Level | Civil SubZones
C-PW-104630 | Fair Facing for Roof Slab Soffit | 6 | 2022-03-24 | 2022-03-30 | 01 | 01 | 01 | 18 | 001 | 30 |  | Building | Civil | Museum | Zone 04 | L-B1 Basement Level | Civil SubZones
C-PW-104640 | Construct of Tunnel Balustrade | 6 | 2022-03-31 | 2022-04-06 | 01 | 01 | 01 | 18 | 001 | 30 |  | Building | Civil | Museum | Zone 04 | L-B1 Basement Level | Civil SubZones
ARCHITECTURAL WORKS |  | 62 | 2022-04-07 | 2022-06-22
C-PW-104650 | Ceiling Finishes | 6 | 2022-04-07 | 2022-04-14 | 01 | 04 | 01 | 18 | 001 | 50 |  | Building | Architecture | Museum | Zone 04 | L-B1 Basement Level | Architectural SubZones
C-PW-104660 | External Wall Fair-facing & Water proofing | 13 | 2022-04-07 | 2022-04-21 | 01 | 04 | 01 | 18 | 001 | 50 |  | Building | Architecture | Museum | Zone 04 | L-B1 Basement Level | Architectural SubZones
C-PW-104670 | Wall Finishes | 13 | 2022-04-14 | 2022-04-30 | 01 | 04 | 01 | 18 | 001 | 50 |  | Building | Architecture | Museum | Zone 04 | L-B1 Basement Level | Architectural SubZones
C-PW-104680 | Roller Shutter Installation | 2 | 2022-04-30 | 2022-05-05 | 01 | 04 | 01 | 18 | 001 | 50 |  | Building | Architecture | Museum | Zone 04 | L-B1 Basement Level | Architectural SubZones
C-PW-104690 | Fixing of Kerbstone | 6 | 2022-05-23 | 2022-05-31 | 01 | 04 | 01 | 18 | 001 | 50 |  | Building | Architecture | Museum | Zone 04 | L-B1 Basement Level | Architectural SubZones
C-PW-104700 | Floor Finishes | 10 | 2022-05-31 | 2022-06-11 | 01 | 04 | 01 | 18 | 001 | 50 |  | Building | Architecture | Museum | Zone 04 | L-B1 Basement Level | Architectural SubZones
C-PW-104710 | Markings & Signages | 5 | 2022-06-11 | 2022-06-16 | 01 | 04 | 01 | 18 | 001 | 50 |  | Building | Architecture | Museum | Zone 04 | L-B1 Basement Level | Architectural SubZones
C-PW-104720 | Final Coat Paint | 5 | 2022-06-16 | 2022-06-22 | 01 | 04 | 01 | 18 | 001 | 50 |  | Building | Architecture | Museum | Zone 04 | L-B1 Basement Level | Architectural SubZones
MEP WORKS |  | 58 | 2022-04-14 | 2022-06-25
MECHANICAL |  | 29 | 2022-04-14 | 2022-05-22
HVAC |  | 26 | 2022-04-14 | 2022-05-17
C-PW-104730 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 8 | 2022-04-14 | 2022-04-24 | 01 | 06 | 01 | 18 | 001 | 70 |  | Building | HVAC | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104740 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-04-24 | 2022-05-07 | 01 | 06 | 01 | 18 | 001 | 70 |  | Building | HVAC | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104750 | Installation of Exhaust / Ventilation Fans | 5 | 2022-05-07 | 2022-05-12 | 01 | 06 | 01 | 18 | 001 | 70 |  | Building | HVAC | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104760 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection and Testing) | 5 | 2022-05-12 | 2022-05-17 | 01 | 06 | 01 | 18 | 001 | 70 |  | Building | HVAC | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
PLUMBING |  | 29 | 2022-04-14 | 2022-05-22
C-PW-104770 | 1st Fix Piping System (Supports, Piping) | 14 | 2022-04-14 | 2022-05-04 | 01 | 08 | 01 | 18 | 001 | 70 |  | Building | Plumbing | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104780 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 14 | 2022-05-04 | 2022-05-22 | 01 | 08 | 01 | 18 | 001 | 70 |  | Building | Plumbing | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
ELECTRICAL |  | 51 | 2022-04-18 | 2022-06-20
C-PW-104790 | 1st Fix Electrical works (Supports, Cable Trays,Conduits & boxes) | 12 | 2022-04-18 | 2022-05-05 | 01 | 07 | 01 | 18 | 001 | 70 |  | Building | Electrical | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104800 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 15 | 2022-05-05 | 2022-05-23 | 01 | 07 | 01 | 18 | 001 | 70 |  | Building | Electrical | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104810 | LV Switchgears (DB's) | 5 | 2022-05-23 | 2022-05-29 | 01 | 07 | 01 | 18 | 001 | 70 |  | Building | Electrical | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104820 | Cable/Wire Termination & Dressing | 7 | 2022-05-29 | 2022-06-06 | 01 | 07 | 01 | 18 | 001 | 70 |  | Building | Electrical | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104830 | Final Fix Electrical (Light Fixtures) | 7 | 2022-06-08 | 2022-06-16 | 01 | 07 | 01 | 18 | 001 | 70 |  | Building | Electrical | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104840 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-06-11 | 2022-06-19 | 01 | 07 | 01 | 18 | 001 | 70 |  | Building | Electrical | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104850 | Final Fix Electrical (Power Socket / Isolators) | 12 | 2022-06-06 | 2022-06-20 | 01 | 07 | 01 | 18 | 001 | 70 |  | Building | Electrical | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104860 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-06-12 | 2022-06-20 | 01 | 07 | 01 | 18 | 001 | 70 |  | Building | Electrical | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
LIFE & SAFETY SYSTEM |  | 58 | 2022-04-14 | 2022-06-25
FIRE FIGHTING |  | 58 | 2022-04-14 | 2022-06-25
C-PW-104870 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 12 | 2022-04-14 | 2022-04-28 | 01 | 08 | 01 | 18 | 001 | 70 |  | Building | Plumbing | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104880 | 2nd Fix Piping System - (Fittings, Connections & Testingl) | 12 | 2022-04-28 | 2022-05-16 | 01 | 08 | 01 | 18 | 001 | 70 |  | Building | Plumbing | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104890 | Final Fix Piping System (Sprinkler Heads, Fixtures, Fire Hose Reel Etc.) | 12 | 2022-06-11 | 2022-06-25 | 01 | 08 | 01 | 18 | 001 | 70 |  | Building | Plumbing | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
ROOF WORKS |  | 23 | 2022-04-07 | 2022-05-08
C-PW-104900 | Cleaning & Surface Preparation | 3 | 2022-04-07 | 2022-04-11 | 01 | 01 | 01 | 18 | 001 | 30 |  | Building | Civil | Museum | Zone 04 | L-B1 Basement Level | Civil SubZones
C-PW-104910 | Groove marking & screed application | 6 | 2022-04-12 | 2022-04-19 | 01 | 01 | 01 | 18 | 001 | 30 |  | Building | Civil | Museum | Zone 04 | L-B1 Basement Level | Civil SubZones
C-PW-104920 | Testing | 6 | 2022-04-21 | 2022-04-27 | 01 | 14 | 01 | 18 | 001 | 30 |  | Building | General MEP | Museum | Zone 04 | L-B1 Basement Level | Civil SubZones
C-PW-104930 | Membrane installation, Flashing and Termination | 8 | 2022-04-18 | 2022-04-27 | 01 | 04 | 01 | 18 | 001 | 30 |  | Building | Architecture | Museum | Zone 04 | L-B1 Basement Level | Civil SubZones
C-PW-104940 | Roof Tiles | 6 | 2022-04-27 | 2022-05-08 | 01 | 04 | 01 | 18 | 001 | 30 |  | Building | Architecture | Museum | Zone 04 | L-B1 Basement Level | Civil SubZones
TESTING & CLOSEOUT |  | 34 | 2022-06-25 | 2022-08-09
C-PW-104950 | Testing and Pre-commissioning | 14 | 2022-06-25 | 2022-07-16 | 01 | 14 | 01 | 18 | 001 | 70 |  | Building | General MEP | Museum | Zone 04 | L-B1 Basement Level | MEP SubZones
C-PW-104960 | Snagging & De-snagging Works - Tunnel | 20 | 2022-07-16 | 2022-08-09 | 01 | 14 | 01 | 18 | 001 | 50 |  | Building | General MEP | Museum | Zone 04 | L-B1 Basement Level | Architectural SubZones
RAMPS |  | 183 | 2022-03-13 | 2022-10-20
CIVIL WORKS |  | 122 | 2022-03-13 | 2022-08-09
ZONE 04 - RAMP |  | 122 | 2022-03-13 | 2022-08-09
C-PW-104970 | Rectification works - Ramp 01 | 12 | 2022-03-13 | 2022-03-26 | 01 | 01 | 01 | 18 | 003 | 30 |  | Building | Civil | Museum | Zone 04 | L00 Ground Level | Civil SubZones
C-PW-104980 | Excavation for Ramp 01 | 8 | 2022-03-27 | 2022-04-04 | 01 | 01 | 01 | 18 | 003 | 30 |  | Building | Civil | Museum | Zone 04 | L00 Ground Level | Civil SubZones
C-PW-104990 | Formation Preparation for Foundation | 6 | 2022-04-05 | 2022-04-11 | 01 | 01 | 01 | 18 | 003 | 30 |  | Building | Civil | Museum | Zone 04 | L00 Ground Level | Civil SubZones
C-PW-105000 | Construction of Ramp 01 Foundation | 18 | 2022-04-12 | 2022-05-05 | 01 | 01 | 01 | 18 | 003 | 30 |  | Building | Civil | Museum | Zone 04 | L00 Ground Level | Civil SubZones
C-PW-105010 | Construction of Ramp 01 wall (Grid BC) including MEP inserts / waterproofing works | 39 | 2022-05-07 | 2022-06-20 | 01 | 01 | 01 | 18 | 003 | 30 |  | Building | Civil | Museum | Zone 04 | L00 Ground Level | Civil SubZones
C-PW-105020 | Construction of Ramp 01 wall (Grid BD) including MEP inserts / waterproofing works | 39 | 2022-06-21 | 2022-08-09 | 01 | 01 | 01 | 18 | 003 | 30 |  | Building | Civil | Museum | Zone 04 | L00 Ground Level | Civil SubZones
ARCHITECTURAL & MEP WORKS |  | 51 | 2022-08-10 | 2022-10-10
ZONE 04 - RAMP |  | 51 | 2022-08-10 | 2022-10-10
C-PW-105090 | Fixing of Kerbstones and Side Walks | 13 | 2022-08-10 | 2022-08-24 | 01 | 04 | 01 | 18 | 003 | 50 |  | Building | Architecture | Museum | Zone 04 | L00 Ground Level | Architectural SubZones
C-PW-105100 | External Wall Fairfacing & WaterProofing | 13 | 2022-08-10 | 2022-08-24 | 01 | 04 | 01 | 18 | 003 | 50 |  | Building | Architecture | Museum | Zone 04 | L00 Ground Level | Architectural SubZones
C-PW-105110 | MEP 1st & 2nd Fixes | 14 | 2022-08-10 | 2022-08-25 | 01 | 14 | 01 | 18 | 003 | 70 |  | Building | General MEP | Museum | Zone 04 | L00 Ground Level | MEP SubZones
C-PW-105120 | Wall Finishes (Concrete Finish) | 5 | 2022-08-24 | 2022-08-30 | 01 | 04 | 01 | 18 | 003 | 50 |  | Building | Architecture | Museum | Zone 04 | L00 Ground Level | Architectural SubZones
C-PW-105130 | External Face Backfilling till GL | 13 | 2022-08-24 | 2022-09-08 | 01 | 04 | 01 | 18 | 003 | 50 |  | Building | Architecture | Museum | Zone 04 | L00 Ground Level | Architectural SubZones
C-PW-105140 | Floor Finishes | 10 | 2022-08-30 | 2022-09-11 | 01 | 04 | 01 | 18 | 003 | 50 |  | Building | Architecture | Museum | Zone 04 | L00 Ground Level | Architectural SubZones
C-PW-105150 | Wall Finishes (Final Finishes) | 6 | 2022-09-11 | 2022-09-18 | 01 | 04 | 01 | 18 | 003 | 50 |  | Building | Architecture | Museum | Zone 04 | L00 Ground Level | Architectural SubZones
C-PW-105160 | MEP Final Fixes | 5 | 2022-09-18 | 2022-09-24 | 01 | 14 | 01 | 18 | 003 | 70 |  | Building | General MEP | Museum | Zone 04 | L00 Ground Level | MEP SubZones
C-PW-105170 | Final Finishes - Road Marking , Mirrors & Wall Guards | 8 | 2022-09-24 | 2022-10-03 | 01 | 04 | 01 | 18 | 003 | 50 |  | Building | Architecture | Museum | Zone 04 | L00 Ground Level | Architectural SubZones
C-PW-105180 | Signages Installation | 5 | 2022-10-03 | 2022-10-10 | 01 | 04 | 01 | 18 | 003 | 50 |  | Building | Architecture | Museum | Zone 04 | L00 Ground Level | Architectural SubZones
TESTING & CLOSEOUT |  | 22 | 2022-09-24 | 2022-10-20
C-PW-105290 | Testing and Pre-commissioning | 7 | 2022-09-24 | 2022-10-02 | 01 | 14 | 01 | 18 | 003 | 70 |  | Building | General MEP | Museum | Zone 04 | L00 Ground Level | MEP SubZones
C-PW-105300 | Snagging & De-snagging Works - Ramps | 10 | 2022-10-10 | 2022-10-20 | 01 | 14 | 01 | 18 | 003 | 50 |  | Building | General MEP | Museum | Zone 04 | L00 Ground Level | Architectural SubZones
Zone 5 - MINIBOX |  | 216 | 2022-02-01 | 2022-10-19
CIVIL WORKS |  | 28 | 2022-03-15 | 2022-04-16
C-PW-105310 | Casting of Mezzanine Floor Slab | 10 | 2022-03-15 | 2022-03-26 | 01 | 01 | 01 | 19 | 004 | 30 |  | Building | Civil | Museum | Zone 05 | L01 Mezzanine Level | Civil SubZones
C-PW-105320 | Casting of Concrete Walls | 18 | 2022-03-27 | 2022-04-16 | 01 | 01 | 01 | 19 | 001 | 30 |  | Building | Civil | Museum | Zone 05 | L-B1 Basement Level | Civil SubZones
ARCHITECTURAL WORKS |  | 132 | 2022-04-17 | 2022-09-26
COMMON AREA WORKS |  | 108 | 2022-04-17 | 2022-08-29
C-PW-105330 | General Block work | 22 | 2022-04-17 | 2022-05-15 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105340 | Marking, Cutting & Chasing Walls for MEP Services | 10 | 2022-05-16 | 2022-05-28 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105350 | Shaft Closure & Finishes | 11 | 2022-08-16 | 2022-08-29 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
PARKING, ARRIVALS, DRIVEWAYS AND LOADING BAYS |  | 91 | 2022-05-28 | 2022-09-15
ARCHITECTURAL FINISHES |  | 91 | 2022-05-28 | 2022-09-15
C-PW-105360 | Plastering Works - Walls | 14 | 2022-05-28 | 2022-06-13 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105370 | Ceiling Finishes | 14 | 2022-06-13 | 2022-06-30 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105380 | Wall Finishes (Exterior Paints) | 13 | 2022-06-30 | 2022-07-18 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105390 | Floor Surface preparation | 11 | 2022-07-19 | 2022-08-02 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105400 | Installation of Wheel Stopper, Speed Breaker,dock blocker and Wall Guard | 6 | 2022-08-02 | 2022-08-08 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105410 | Doors & Ironmongery | 10 | 2022-08-02 | 2022-08-13 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105420 | Installation of Barriers | 6 | 2022-08-08 | 2022-08-15 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105430 | Final Coat Paint | 10 | 2022-08-15 | 2022-08-25 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105440 | Parking Area & Road Marking | 8 | 2022-08-27 | 2022-09-04 | 01 | 11 | 01 | 19 | 001 | 50 |  | Building | Roads & Landscaping | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105450 | Installation of Balustrades, Bollards, Mirrors, Signages | 5 | 2022-09-05 | 2022-09-10 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105460 | Snagging & De-snagging Works | 5 | 2022-09-10 | 2022-09-15 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
TOILETS, WASH AREA, REFUSE AREA & FREEZER AREA |  | 58 | 2022-06-16 | 2022-08-27
ARCHITECTURAL FINISHES |  | 58 | 2022-06-16 | 2022-08-27
C-PW-105470 | Plastering Works | 8 | 2022-06-16 | 2022-06-26 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105480 | Wet Area Waterproofing | 10 | 2022-06-26 | 2022-07-06 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105490 | Ceiling Finishes | 11 | 2022-06-27 | 2022-07-13 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105500 | Floor Screed Works | 5 | 2022-07-06 | 2022-07-16 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105510 | Install road drains | 4 | 2022-07-16 | 2022-07-20 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105520 | Wall Finishes (Emulsion Pt, Plaster Boards & Paint) | 13 | 2022-07-14 | 2022-07-28 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105530 | Floor Finishes (Ceramic Tiles,Epoxy Resin flooring) | 13 | 2022-07-28 | 2022-08-14 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105540 | Doors & Ironmongery | 6 | 2022-08-14 | 2022-08-21 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105550 | Installation of Balustrades, Sanitary wares & Other Fittings | 6 | 2022-08-14 | 2022-08-21 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105560 | Final Coat Paint | 5 | 2022-08-22 | 2022-08-27 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
PUMP ROOM, PLANT ROOMS & WATER TANKS |  | 54 | 2022-05-16 | 2022-07-20
ARCHITECTURAL FINISHES |  | 54 | 2022-05-16 | 2022-07-20
C-PW-105570 | Installation of Metal Access Ladders | 14 | 2022-05-16 | 2022-06-01 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105580 | Equipment Foundation & Upstand Works | 10 | 2022-05-28 | 2022-06-07 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105590 | Floor Trench Works | 10 | 2022-06-08 | 2022-06-19 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105600 | Waterproofing for Water Tanks | 19 | 2022-06-01 | 2022-06-23 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105610 | Wall Finishes (Exterior Paints) | 8 | 2022-06-19 | 2022-06-28 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105620 | Grating Works | 5 | 2022-06-22 | 2022-06-28 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105630 | Floor Finishes (Epoxy resin flooring) | 6 | 2022-06-28 | 2022-07-05 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105640 | Water Tanks Leakage Testing | 10 | 2022-06-23 | 2022-07-05 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105650 | Doors & Ironmongery | 5 | 2022-07-06 | 2022-07-14 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105660 | Final Coat Paint | 5 | 2022-07-14 | 2022-07-20 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
SECURITY ROOMS, SCANNING ROOMS,DOCK MASTER ROOM, TELECOM ROOM & ULD AREA |  | 50 | 2022-06-18 | 2022-08-20
ARCHITECTURAL FINISHES |  | 50 | 2022-06-18 | 2022-08-20
C-PW-105670 | Wall Finishes (Plasterboard wall lining & paint) | 13 | 2022-06-18 | 2022-07-03 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105680 | Floor Finishes (RAF, Epoxy Resin Flooring) | 13 | 2022-07-03 | 2022-07-21 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105690 | Installation of Wheel Stopper, Speed Breaker and Wall Guard | 6 | 2022-07-21 | 2022-07-28 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105700 | Floor Finishes (Epoxy Coating,Carpets,Line Marking, Deck Coats) | 6 | 2022-07-28 | 2022-08-07 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105710 | Installation of Barriers | 3 | 2022-08-07 | 2022-08-10 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105720 | Doors & Ironmongery | 6 | 2022-08-07 | 2022-08-14 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105730 | Final Coat Paint | 5 | 2022-08-14 | 2022-08-20 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
NON F&B, GOOD RECEIPT, COLD ROOM |  | 51 | 2022-07-27 | 2022-09-26
ARCHITECTURAL FINISHES |  | 51 | 2022-07-27 | 2022-09-26
C-PW-105740 | Ceiling Finishes | 11 | 2022-07-27 | 2022-08-10 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105750 | Wall Finishes (PVC Wall Linings) | 13 | 2022-08-10 | 2022-08-25 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105760 | Floor Finishes (Epoxy resin flooring) | 13 | 2022-08-25 | 2022-09-08 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105770 | Doors & Ironmongery | 6 | 2022-09-10 | 2022-09-17 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105780 | Installation of Final Fittings | 6 | 2022-09-10 | 2022-09-17 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105790 | Final Coat Paint | 8 | 2022-09-17 | 2022-09-26 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
ELECTRICAL STORES, GARDEN STORES & CHEMICAL STORE |  | 38 | 2022-07-05 | 2022-08-23
ARCHITECTURAL FINISHES |  | 38 | 2022-07-05 | 2022-08-23
C-PW-105800 | Ceiling Finishes | 8 | 2022-07-05 | 2022-07-18 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105810 | Wall Finishes (Interior Paint) | 10 | 2022-07-18 | 2022-07-28 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105820 | Floor Finishes (Epoxy Resin flooring, Deck shields) | 10 | 2022-07-28 | 2022-08-10 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105830 | Doors & Ironmongery | 6 | 2022-08-10 | 2022-08-17 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105840 | Final Coat Paint | 5 | 2022-08-17 | 2022-08-23 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
STAIRCASES |  | 44 | 2022-07-20 | 2022-09-11
STAIR6 |  | 30 | 2022-07-20 | 2022-08-25
C-PW-105850 | Install Handrails & Balustrades | 3 | 2022-07-20 | 2022-07-24 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105860 | Wall Finishes (Paints) | 11 | 2022-07-24 | 2022-08-07 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105870 | Ceiling finishes works | 5 | 2022-08-08 | 2022-08-13 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105880 | Floor Finishes (Epoxy Resin Flooring) | 7 | 2022-08-13 | 2022-08-21 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105890 | Doors & Iron Mongeries | 3 | 2022-08-22 | 2022-08-25 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
STAIR7 |  | 34 | 2022-07-24 | 2022-09-03
C-PW-105900 | Install Handrails & Balustrades | 3 | 2022-07-24 | 2022-07-27 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105910 | Wall Finishes (Paints) | 11 | 2022-07-28 | 2022-08-11 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105920 | Ceiling finishes works | 5 | 2022-08-11 | 2022-08-16 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105930 | Floor Finishes (Epoxy Resin Flooring) | 7 | 2022-08-22 | 2022-08-30 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105940 | Doors & Iron Mongeries | 3 | 2022-08-30 | 2022-09-03 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
STAIR12 |  | 38 | 2022-07-28 | 2022-09-11
C-PW-105950 | Install Handrails & Balustrades | 3 | 2022-07-28 | 2022-08-02 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105960 | Wall Finishes (Paints) | 11 | 2022-08-02 | 2022-08-15 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105970 | Ceiling finishes works | 5 | 2022-08-15 | 2022-08-21 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105980 | Floor Finishes (Epoxy Resin Flooring) | 7 | 2022-08-30 | 2022-09-07 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
C-PW-105990 | Doors & Iron Mongeries | 3 | 2022-09-07 | 2022-09-11 | 01 | 04 | 01 | 19 | 001 | 50 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Architectural SubZones
MEP WORKS |  | 194 | 2022-02-01 | 2022-09-22
PARKING, ARRIVALS, DRIVEWAYS AND LOADING BAYS |  | 75 | 2022-05-16 | 2022-08-16
MEP WORKS |  | 75 | 2022-05-16 | 2022-08-16
MECHANICAL |  | 69 | 2022-05-16 | 2022-08-08
HVAC SYSTEM WORKS |  | 69 | 2022-05-16 | 2022-08-08
C-PW-106000 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 10 | 2022-05-16 | 2022-05-28 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106010 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-05-28 | 2022-06-08 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106020 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection & Testing) | 6 | 2022-08-02 | 2022-08-08 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
PLUMBING AND DRAINAGE WORKS |  | 20 | 2022-05-16 | 2022-06-07
C-PW-106030 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-05-16 | 2022-05-28 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106040 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 10 | 2022-05-28 | 2022-06-07 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELECTRICAL WORKS |  | 75 | 2022-05-16 | 2022-08-16
C-PW-106050 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 10 | 2022-05-16 | 2022-05-28 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106060 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-05-21 | 2022-06-02 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106070 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-06-02 | 2022-06-18 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106080 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-08-02 | 2022-08-08 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106090 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-03 | 2022-08-11 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106100 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-06 | 2022-08-14 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106110 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-08 | 2022-08-16 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELV WORKS |  | 51 | 2022-06-05 | 2022-08-08
C-PW-106120 | 1st Fix ELV Works (Marking, Supports, ELV Trays, Conduits & Boxes) | 7 | 2022-06-05 | 2022-06-13 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106130 | 2nd Fix ELV Works (Wiring, Cabling & Panel Fixing) | 10 | 2022-06-13 | 2022-06-26 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106140 | Final Fix ELV Works (Final Devices fixing, Cables & Wire terminations) | 6 | 2022-08-02 | 2022-08-08 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
LIFE AND SAFETY SYSTEM |  | 64 | 2022-05-21 | 2022-08-08
FIRE FIGHTING WORKS |  | 64 | 2022-05-21 | 2022-08-08
C-PW-106150 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 10 | 2022-05-21 | 2022-06-02 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106160 | 2nd Fix Piping System - (Fittings, Connections & Testing) | 8 | 2022-06-02 | 2022-06-12 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106170 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-08-02 | 2022-08-08 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
TOILETS, WASH AREA, REFUSE AREA & FREEZER AREA |  | 70 | 2022-06-02 | 2022-08-28
MEP WORKS |  | 70 | 2022-06-02 | 2022-08-28
MECHANICAL |  | 61 | 2022-06-06 | 2022-08-21
HVAC SYSTEM WORKS |  | 61 | 2022-06-06 | 2022-08-21
C-PW-106180 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 10 | 2022-06-06 | 2022-06-18 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106190 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 8 | 2022-06-18 | 2022-06-27 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106200 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection & Testing) | 6 | 2022-08-14 | 2022-08-21 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
PLUMBING AND DRAINAGE WORKS |  | 18 | 2022-06-06 | 2022-06-27
C-PW-106210 | 1st Fix Piping System (Supports, Piping) | 10 | 2022-06-06 | 2022-06-18 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106220 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 8 | 2022-06-18 | 2022-06-27 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELECTRICAL WORKS |  | 70 | 2022-06-02 | 2022-08-28
C-PW-106230 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 8 | 2022-06-02 | 2022-06-12 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106240 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 10 | 2022-06-06 | 2022-06-18 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106250 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 10 | 2022-06-18 | 2022-06-30 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106260 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-08-14 | 2022-08-21 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106270 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-16 | 2022-08-24 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106280 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-17 | 2022-08-25 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106290 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-20 | 2022-08-28 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELV WORKS |  | 58 | 2022-06-08 | 2022-08-20
C-PW-106300 | 1st Fix ELV Works (Marking, Supports, ELV Trays, Conduits & Boxes) | 7 | 2022-06-08 | 2022-06-16 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106310 | 2nd Fix ELV Works (Wiring, Cabling & Panel Fixing) | 7 | 2022-06-16 | 2022-06-25 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106320 | Final Fix ELV Works (Final Devices fixing, Cables & Wire terminations) | 5 | 2022-08-14 | 2022-08-20 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
LIFE AND SAFETY SYSTEM |  | 56 | 2022-06-12 | 2022-08-21
FIRE FIGHTING WORKS |  | 56 | 2022-06-12 | 2022-08-21
C-PW-106330 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 8 | 2022-06-12 | 2022-06-21 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106340 | 2nd Fix Piping System - (Fittings, Connections & Testing) | 8 | 2022-06-21 | 2022-06-30 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106350 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-08-14 | 2022-08-21 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
PUMP ROOM, PLANT ROOMS & WATER TANKS |  | 161 | 2022-02-01 | 2022-08-16
MEP WORKS |  | 161 | 2022-02-01 | 2022-08-16
MECHANICAL |  | 154 | 2022-02-01 | 2022-08-07
HVAC SYSTEM WORKS |  | 26 | 2022-07-04 | 2022-08-07
C-PW-106360 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 7 | 2022-07-04 | 2022-07-16 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106370 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 6 | 2022-07-16 | 2022-07-23 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106380 | Final Fix HVAC (Exhaust Louvres,Grills, Diffusers, FCU Mouth Connection & Testing) | 3 | 2022-08-03 | 2022-08-07 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
PLUMBING AND DRAINAGE WORKS |  | 143 | 2022-02-01 | 2022-07-24
C-PW-106390 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-02-01 | 2022-02-10 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106400 | 2nd Fix Piping System (Install Pumps & Connections) | 16 | 2022-02-10 | 2022-03-01 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106410 | 2nd Fix Piping System (Fittings, Level Indicator, Connection & Testing) | 6 | 2022-07-06 | 2022-07-16 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106420 | Final Fix Fittings | 7 | 2022-07-16 | 2022-07-24 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELECTRICAL WORKS |  | 38 | 2022-06-28 | 2022-08-16
C-PW-106430 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-06-28 | 2022-07-06 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106440 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-07-07 | 2022-07-21 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106450 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 9 | 2022-07-21 | 2022-08-02 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106460 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-08-02 | 2022-08-07 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106470 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-03 | 2022-08-11 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106480 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-06 | 2022-08-14 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106490 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-08 | 2022-08-16 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELV WORKS |  | 129 | 2022-02-01 | 2022-07-05
C-PW-106500 | 1st Fix ELV Works (Marking, Supports, ELV Trays, Conduits & Boxes) | 6 | 2022-02-01 | 2022-02-07 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106510 | 2nd Fix ELV Works (Wiring, Cabling & Panel Fixing) | 5 | 2022-02-07 | 2022-02-13 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106520 | Final Fix ELV Works (Final Devices fixing, Cables & Wire terminations) | 3 | 2022-07-02 | 2022-07-05 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
LIFE AND SAFETY SYSTEM |  | 30 | 2022-07-02 | 2022-08-11
FIRE FIGHTING SYSTEM WORKS |  | 30 | 2022-07-02 | 2022-08-11
C-PW-106530 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 7 | 2022-07-02 | 2022-07-13 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106540 | 2nd Fix Piping System - (Clean Agent/Foam water sprinkler fire Suppression system) & testing | 7 | 2022-07-14 | 2022-07-23 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106550 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-08-06 | 2022-08-11 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
SECURITY ROOMS, SCANNING ROOMS,DOCK MASTER ROOM, TELECOM ROOM & ULD AREA |  | 64 | 2022-06-02 | 2022-08-21
MEP WORKS |  | 64 | 2022-06-02 | 2022-08-21
MECHANICAL WORKS |  | 53 | 2022-06-08 | 2022-08-13
HVAC SYSTEM WORKS |  | 53 | 2022-06-08 | 2022-08-13
C-PW-106560 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 9 | 2022-06-08 | 2022-06-18 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106570 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 7 | 2022-06-18 | 2022-06-26 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106580 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection & Testing) | 6 | 2022-08-07 | 2022-08-13 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
PLUMBING AND DRAINAGE WORKS |  | 16 | 2022-06-08 | 2022-06-26
C-PW-106590 | 1st Fix Piping System (Supports, Piping) | 9 | 2022-06-08 | 2022-06-18 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106600 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 7 | 2022-06-18 | 2022-06-26 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELECTRICAL WORKS |  | 64 | 2022-06-02 | 2022-08-21
C-PW-106610 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 7 | 2022-06-02 | 2022-06-11 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106620 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 9 | 2022-06-08 | 2022-06-18 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106630 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 9 | 2022-06-18 | 2022-06-28 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106640 | Install equipment, Telecom Panels, Wiring & testing | 12 | 2022-06-18 | 2022-07-02 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106650 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-08-07 | 2022-08-11 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106660 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-08 | 2022-08-16 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106670 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-10 | 2022-08-18 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106680 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-13 | 2022-08-21 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELV WORKS |  | 50 | 2022-06-09 | 2022-08-11
C-PW-106690 | 1st Fix ELV Works (Marking, Supports, ELV Trays, Conduits & Boxes) | 7 | 2022-06-09 | 2022-06-18 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106700 | 2nd Fix ELV Works (Wiring, Cabling & Panel Fixing) | 6 | 2022-06-18 | 2022-06-25 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106710 | Final Fix ELV Works (Final Devices fixing, Cables & Wire terminations) | 5 | 2022-08-07 | 2022-08-11 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
LIFE AND SAFETY SYSTEM |  | 48 | 2022-06-13 | 2022-08-13
FIRE FIGHTING WORKS |  | 48 | 2022-06-13 | 2022-08-13
C-PW-106720 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 7 | 2022-06-13 | 2022-06-21 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106730 | 2nd Fix Piping System - (Fittings, Connections & Testing) | 7 | 2022-06-22 | 2022-06-30 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106740 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-08-07 | 2022-08-13 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
NON F&B, GOOD RECEIPT, COLD ROOM |  | 79 | 2022-06-18 | 2022-09-22
MEP WORKS |  | 79 | 2022-06-18 | 2022-09-22
MECHANICAL WORKS |  | 73 | 2022-06-18 | 2022-09-15
HVAC SYSTEM WORKS |  | 73 | 2022-06-18 | 2022-09-15
C-PW-106750 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 16 | 2022-06-18 | 2022-07-06 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106760 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 10 | 2022-07-06 | 2022-07-23 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106770 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection & Testing) | 6 | 2022-09-10 | 2022-09-15 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
PLUMBING AND DRAINAGE WORKS |  | 26 | 2022-06-23 | 2022-07-27
C-PW-106780 | 1st Fix Piping System (Supports, Piping) | 16 | 2022-06-23 | 2022-07-16 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106790 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 10 | 2022-07-16 | 2022-07-27 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELECTRICAL WORKS |  | 79 | 2022-06-18 | 2022-09-22
C-PW-106800 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 12 | 2022-06-18 | 2022-07-02 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106810 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 16 | 2022-06-23 | 2022-07-16 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106820 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 14 | 2022-07-16 | 2022-08-02 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106830 | Final Fix Electrical (Power Socket / Isolators) | 6 | 2022-09-10 | 2022-09-15 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106840 | Final Fix Electrical (Light Fixtures) | 7 | 2022-09-11 | 2022-09-19 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106850 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-09-13 | 2022-09-21 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106860 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-09-14 | 2022-09-22 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELV WORKS |  | 66 | 2022-06-26 | 2022-09-15
C-PW-106870 | 1st Fix ELV Works (Marking, Supports, ELV Trays, Conduits & Boxes) | 9 | 2022-06-26 | 2022-07-05 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106880 | 2nd Fix ELV Works (Wiring, Cabling & Panel Fixing) | 10 | 2022-07-06 | 2022-07-21 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106890 | Final Fix ELV Works (Final Devices fixing, Cables & Wire terminations) | 6 | 2022-09-10 | 2022-09-15 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
LIFE AND SAFETY SYSTEM |  | 68 | 2022-06-23 | 2022-09-15
FIRE FIGHTING WORKS |  | 68 | 2022-06-23 | 2022-09-15
C-PW-106900 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 16 | 2022-06-23 | 2022-07-16 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106910 | 2nd Fix Piping System - (Fittings, Connections & Testing) | 8 | 2022-07-16 | 2022-07-25 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106920 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 6 | 2022-09-10 | 2022-09-15 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELECTRICAL STORES, GARDEN STORES & CHEMICAL STORE |  | 57 | 2022-06-18 | 2022-08-28
MEP WORKS |  | 57 | 2022-06-18 | 2022-08-28
MECHANICAL WORKS |  | 47 | 2022-06-18 | 2022-08-16
HVAC SYSTEM WORKS |  | 47 | 2022-06-18 | 2022-08-16
C-PW-106930 | 1st Fix HVAC (Supports, Ducts, CHW Piping, Drain Pipes, Dampers - VCD,NRD,MDs) | 9 | 2022-06-18 | 2022-06-28 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106940 | 2nd Fix HVAC (FCUs, Valves Package, Droppers, Fans) | 7 | 2022-06-28 | 2022-07-06 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106950 | Final Fix HVAC (Grills, Diffusers, FCU Mouth Connection & Testing) | 6 | 2022-08-10 | 2022-08-16 | 01 | 06 | 01 | 19 | 001 | 70 |  | Building | HVAC | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
PLUMBING AND DRAINAGE WORKS |  | 14 | 2022-06-18 | 2022-07-05
C-PW-106960 | 1st Fix Piping System (Supports, Piping) | 7 | 2022-06-18 | 2022-06-26 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106970 | 2nd Fix Piping System (Fittings, Insulation, Connection & Testing) | 7 | 2022-06-27 | 2022-07-05 | 01 | 08 | 01 | 19 | 001 | 70 |  | Building | Plumbing | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELECTRICAL WORKS |  | 57 | 2022-06-18 | 2022-08-28
C-PW-106980 | 1st Fix Electrical (Conduits & boxes) - Power and Lighting System | 6 | 2022-06-18 | 2022-06-25 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-106990 | 1st Fix Electrical (Supports and Cable trays) - Power and Lighting System | 7 | 2022-06-18 | 2022-06-26 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107000 | 2nd Fix Electrical (Wires & Cables) - Power, Lighting System & Earthing | 7 | 2022-06-27 | 2022-07-05 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107010 | Final Fix Electrical (Power Socket / Isolators) | 5 | 2022-08-10 | 2022-08-16 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107020 | Final Fix Electrical (Light Fixtures) | 7 | 2022-08-16 | 2022-08-24 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107030 | Final Fix Electrical (Installation of Lighting Control Panels) | 7 | 2022-08-17 | 2022-08-25 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107040 | Final Fix Electrical (Installation of Lighting Control Devices) | 7 | 2022-08-20 | 2022-08-28 | 01 | 07 | 01 | 19 | 001 | 70 |  | Building | Electrical | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ELV WORKS |  | 14 | 2022-06-20 | 2022-07-05
C-PW-107050 | 1st Fix ELV Works (Marking, Supports, ELV Trays, Conduits & Boxes) | 6 | 2022-06-20 | 2022-06-26 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107060 | 2nd Fix ELV Works (Wiring, Cabling & Panel Fixing) | 5 | 2022-06-27 | 2022-07-02 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107070 | Final Fix ELV Works (Final Devices fixing, Cables & Wire terminations) | 3 | 2022-07-02 | 2022-07-05 | 01 | 10 | 01 | 19 | 001 | 70 |  | Building | CCTV | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
LIFE AND SAFETY SYSTEM |  | 42 | 2022-06-23 | 2022-08-16
FIRE FIGHTING WORKS |  | 42 | 2022-06-23 | 2022-08-16
C-PW-107080 | 1st Fix Piping System - (Piping Support and Installation of Fire fighting pipes) | 6 | 2022-06-23 | 2022-06-30 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107090 | 2nd Fix Piping System - (Fittings, Connections & Testing) | 6 | 2022-06-30 | 2022-07-06 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107100 | Final Fix Piping System (Sprinkler Heads, Fixtures, Etc.) | 5 | 2022-08-10 | 2022-08-16 | 01 | 09 | 01 | 19 | 001 | 70 |  | Building | Firefighting | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
SHAFTS & RISERS |  | 16 | 2022-07-27 | 2022-08-16
C-PW-107110 | 1st Fix Exhaust and Fresh Air Risers | 8 | 2022-07-27 | 2022-08-07 | 01 | 14 | 01 | 19 | 001 | 70 |  | Building | General MEP | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107120 | Final Fix Exhaust and Fresh Air Risers | 8 | 2022-08-07 | 2022-08-16 | 01 | 14 | 01 | 19 | 001 | 70 |  | Building | General MEP | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
STAIRCASES |  | 72 | 2022-06-18 | 2022-09-14
STAIR6 |  | 58 | 2022-06-18 | 2022-08-29
C-PW-107130 | 1st & 2nd MEP Fix | 7 | 2022-06-18 | 2022-06-26 | 01 | 14 | 01 | 19 | 001 | 70 |  | Building | General MEP | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107140 | Final MEP Fixes | 3 | 2022-08-25 | 2022-08-29 | 01 | 14 | 01 | 19 | 001 | 70 |  | Building | General MEP | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
STAIR7 |  | 58 | 2022-06-27 | 2022-09-06
C-PW-107150 | 1st & 2nd MEP Fix | 7 | 2022-06-27 | 2022-07-05 | 01 | 14 | 01 | 19 | 001 | 70 |  | Building | General MEP | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107160 | Final MEP Fixes | 3 | 2022-09-03 | 2022-09-06 | 01 | 14 | 01 | 19 | 001 | 70 |  | Building | General MEP | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
STAIR12 |  | 58 | 2022-07-05 | 2022-09-14
C-PW-107170 | 1st & 2nd MEP Fix | 7 | 2022-07-05 | 2022-07-17 | 01 | 14 | 01 | 19 | 001 | 70 |  | Building | General MEP | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107180 | Final MEP Fixes | 3 | 2022-09-11 | 2022-09-14 | 01 | 14 | 01 | 19 | 001 | 70 |  | Building | General MEP | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
ROOF WORKS |  | 52 | 2022-04-17 | 2022-06-19
C-PW-107190 | Cleaning & Surface Preparation | 8 | 2022-04-17 | 2022-04-25 | 01 | 01 | 01 | 19 | 001 | 30 |  | Building | Civil | Museum | Zone 05 | L-B1 Basement Level | Civil SubZones
C-PW-107200 | Groove Marking & Screed application | 10 | 2022-04-26 | 2022-05-10 | 01 | 01 | 01 | 19 | 001 | 30 |  | Building | Civil | Museum | Zone 05 | L-B1 Basement Level | Civil SubZones
C-PW-107210 | Membrane Installation , Flashing and Termination | 18 | 2022-05-11 | 2022-05-31 | 01 | 04 | 01 | 19 | 001 | 70 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107220 | Testing | 6 | 2022-06-01 | 2022-06-07 | 01 | 04 | 01 | 19 | 001 | 70 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | MEP SubZones
C-PW-107230 | Roofing works | 10 | 2022-06-08 | 2022-06-19 | 01 | 04 | 01 | 19 | 001 | 30 |  | Building | Architecture | Museum | Zone 05 | L-B1 Basement Level | Civil SubZones
CLOSE OUT |  | 23 | 2022-09-21 | 2022-10-19
C-PW-107240 | Testing and Pre-commissioning of Mini Box | 12 | 2022-09-21 | 2022-10-05 | 01 | 14 | 01 | 48 | 001 | 70 |  | Building | General MEP | Museum | Minibox | L-B1 Basement Level | MEP SubZones
C-PW-107250 | Snagging & De-snagging Works of Mini Box | 11 | 2022-10-05 | 2022-10-19 | 01 | 14 | 01 | 48 | 001 | 50 |  | Building | General MEP | Museum | Minibox | L-B1 Basement Level | Architectural SubZones
BUILDING FACADE WORKS |  | 240 | 2022-04-23 | 2023-02-08
LEVEL 0 - GROUND FLOOR |  | 126 | 2022-05-25 | 2022-10-25
EAST EGRESS |  | 42 | 2022-09-05 | 2022-10-25
C-PW-107260 | External Brackets, Waterproofing & Insulation | 11 | 2022-09-05 | 2022-09-18 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107270 | MEP works | 7 | 2022-09-19 | 2022-09-27 | 01 | 14 | 01 | 51 | 003 | 50 |  | Building | General MEP | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107280 | Stone coping to external wall | 4 | 2022-09-27 | 2022-10-02 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107290 | Glazed Wall System | 11 | 2022-09-19 | 2022-10-02 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107300 | Bespoke fixed and sliding metal screen | 10 | 2022-10-02 | 2022-10-13 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107310 | Steel Framing System & render finish | 10 | 2022-10-13 | 2022-10-25 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
SOUTH EGRESS |  | 42 | 2022-07-16 | 2022-09-03
C-PW-107320 | External Brackets, Waterproofing & Insulation | 11 | 2022-07-16 | 2022-07-28 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107330 | MEP works | 7 | 2022-07-28 | 2022-08-07 | 01 | 14 | 01 | 51 | 003 | 50 |  | Building | General MEP | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107340 | Stone coping to external wall | 4 | 2022-08-07 | 2022-08-11 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107350 | Glazed Wall System | 11 | 2022-07-28 | 2022-08-11 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107360 | Bespoke fixed and sliding metal screen | 10 | 2022-08-11 | 2022-08-22 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107370 | Steel Framing System & render finish | 10 | 2022-08-23 | 2022-09-03 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
WEST EGRESS |  | 42 | 2022-08-30 | 2022-10-18
C-PW-107380 | External Brackets, Waterproofing & Insulation | 11 | 2022-08-30 | 2022-09-12 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107390 | MEP works | 7 | 2022-09-12 | 2022-09-20 | 01 | 14 | 01 | 51 | 003 | 50 |  | Building | General MEP | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107400 | Stone coping to external wall | 4 | 2022-09-20 | 2022-09-25 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107410 | Glazed Wall System | 11 | 2022-09-12 | 2022-09-25 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107420 | Bespoke fixed and sliding metal screen | 10 | 2022-09-25 | 2022-10-05 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107430 | Steel Framing System & render finish | 10 | 2022-10-06 | 2022-10-18 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
RESTAURANT GALLERY SIDE |  | 62 | 2022-05-25 | 2022-08-10
C-PW-107440 | External Brackets, Waterproofing & Insulation | 20 | 2022-05-25 | 2022-06-18 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107450 | MEP works | 8 | 2022-06-18 | 2022-06-27 | 01 | 14 | 01 | 51 | 003 | 50 |  | Building | General MEP | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107460 | Stone coping to external wall | 6 | 2022-06-27 | 2022-07-04 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107470 | Glazed Wall System | 19 | 2022-06-18 | 2022-07-13 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107480 | Bespoke fixed and sliding metal screen | 11 | 2022-07-13 | 2022-07-26 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107490 | Steel Framing System & render finish | 11 | 2022-07-27 | 2022-08-10 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
RESTAURANT & VIP VIEWING SIDE |  | 58 | 2022-06-18 | 2022-08-29
C-PW-107500 | External Brackets, Waterproofing & Insulation | 17 | 2022-06-18 | 2022-07-07 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107510 | MEP works | 8 | 2022-07-07 | 2022-07-20 | 01 | 14 | 01 | 51 | 003 | 50 |  | Building | General MEP | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107520 | Stone coping to external wall | 6 | 2022-07-20 | 2022-07-26 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107530 | Glazed Wall System | 19 | 2022-07-07 | 2022-08-03 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107540 | Bespoke fixed and sliding metal screen | 11 | 2022-08-03 | 2022-08-16 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107550 | Steel Framing System & render finish | 11 | 2022-08-16 | 2022-08-29 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
LEVEL 1 - MEZZANINE |  | 66 | 2022-06-30 | 2022-09-21
ZNM OFFICE SIDE |  | 62 | 2022-06-30 | 2022-09-15
C-PW-107560 | External Brackets, Waterproofing & Insulation | 20 | 2022-06-30 | 2022-07-27 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107570 | MEP works | 8 | 2022-07-27 | 2022-08-07 | 01 | 14 | 01 | 51 | 004 | 50 |  | Building | General MEP | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107580 | Stone coping to external wall | 4 | 2022-08-07 | 2022-08-11 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107590 | Glazed Wall System | 19 | 2022-07-27 | 2022-08-20 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107600 | Bespoke fixed and sliding metal screen | 11 | 2022-08-21 | 2022-09-03 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107610 | Steel Framing System & render finish | 11 | 2022-09-03 | 2022-09-15 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
FALCONRY OFFICE SIDE |  | 46 | 2022-07-27 | 2022-09-21
C-PW-107620 | External Brackets, Waterproofing & Insulation | 11 | 2022-07-27 | 2022-08-10 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107630 | MEP works | 7 | 2022-08-11 | 2022-08-20 | 01 | 14 | 01 | 51 | 004 | 50 |  | Building | General MEP | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107640 | Stone coping to external wall | 4 | 2022-08-20 | 2022-08-24 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107650 | Glazed Wall System | 13 | 2022-08-11 | 2022-08-25 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107660 | Bespoke fixed and sliding metal screen | 11 | 2022-08-25 | 2022-09-07 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107670 | Steel Framing System & render finish | 11 | 2022-09-08 | 2022-09-21 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
LEVEL 3 - PLENUM |  | 54 | 2022-09-25 | 2022-11-28
C-PW-107680 | External Brackets, Waterproofing & Insulation | 20 | 2022-09-25 | 2022-10-18 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107690 | MEP works | 14 | 2022-10-19 | 2022-11-05 | 01 | 14 | 01 | 51 | 004 | 50 |  | Building | General MEP | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107700 | Sandtrap Louvres | 20 | 2022-11-05 | 2022-11-28 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
C-PW-107710 | Louvres | 20 | 2022-11-05 | 2022-11-28 | 01 | 05 | 01 | 51 | 004 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L01 Mezzanine Level | Architectural SubZones
CITY ENTRANCE |  | 115 | 2022-04-23 | 2022-09-12
CITY ENTRANCE GLAZING |  | 115 | 2022-04-23 | 2022-09-12
C-PW-107720 | External Brackets, Waterproofing & Insulation | 20 | 2022-04-23 | 2022-05-19 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107730 | MEP works | 14 | 2022-05-19 | 2022-06-06 | 01 | 14 | 01 | 51 | 003 | 50 |  | Building | General MEP | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107740 | Framework for City Entrance Main Lobby Facade till +15.00m | 22 | 2022-05-19 | 2022-06-15 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107750 | Framework for City Entrance Lobby Facade till +15.00m | 22 | 2022-06-15 | 2022-07-14 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107760 | Glazing works for City Entrance Main Lobby Facade till +15.00m | 22 | 2022-06-15 | 2022-07-14 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107770 | Framework for City Entrance Lobby 1 Facade | 13 | 2022-07-14 | 2022-07-31 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107780 | Glazing works for City Entrance Lobby Facade till +15.00m | 22 | 2022-07-14 | 2022-08-10 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107790 | Glazing works for City Entrance Lobby 1 Facade | 13 | 2022-08-11 | 2022-08-25 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107800 | Fixed Glazed Screen (City Entrance) | 20 | 2022-08-21 | 2022-09-12 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
CITY ENTRANCE GATE |  | 42 | 2022-07-14 | 2022-09-03
C-PW-107810 | Framework and Motor Fixing for City Entrance gate | 22 | 2022-07-14 | 2022-08-10 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107820 | City Entrance Gate | 20 | 2022-08-11 | 2022-09-03 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
GARDEN ENTRANCE |  | 103 | 2022-05-07 | 2022-09-08
GARDEN ENTRANCE GLAZING |  | 103 | 2022-05-07 | 2022-09-08
C-PW-107830 | External Brackets, Waterproofing & Insulation | 20 | 2022-05-07 | 2022-05-30 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107840 | Framework for Garden Entrance Main Lobby Facade till +15.00m | 22 | 2022-05-25 | 2022-06-20 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107850 | MEP Fix works | 14 | 2022-06-20 | 2022-07-06 | 01 | 14 | 01 | 51 | 003 | 50 |  | Building | General MEP | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107860 | Framework for Garden Entrance Lobby Facade till +15.00m | 22 | 2022-06-20 | 2022-07-19 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107870 | Glazing works for Garden Entrance Main Lobby Facade till +15.00m | 22 | 2022-06-20 | 2022-07-19 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107880 | Glazing works for Garden Entrance Lobby Facade till +15.00m | 22 | 2022-07-20 | 2022-08-16 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107890 | Glazed Screen with sliding portion (Garden Entrance) | 20 | 2022-08-16 | 2022-09-08 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
GARDEN ENTRANCE GATE |  | 65 | 2022-05-30 | 2022-08-17
C-PW-107900 | Framework and Motor Fixing for Garden Entrance gate | 22 | 2022-05-30 | 2022-06-25 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107910 | Garden Entrance gate | 20 | 2022-06-25 | 2022-07-21 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107920 | Garden Entrance gate Finishes | 22 | 2022-07-21 | 2022-08-17 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
CENTRAL ROOF LIGHT |  | 69 | 2022-11-19 | 2023-02-08
C-PW-107930 | External Brackets, Waterproofing & Insulation | 21 | 2022-11-19 | 2022-12-13 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
C-PW-107940 | Installation of Skylight | 48 | 2022-12-13 | 2023-02-08 | 01 | 05 | 01 | 51 | 003 | 50 |  | Building | Façade/Envelope | Museum | Building Façade Works | L00 Ground Level | Architectural SubZones
Mound Works |  | 687 | 2021-05-05 | 2023-08-14
Zone M1A |  | 610 | 2021-05-23 | 2023-05-27
External / Lower Level |  | 610 | 2021-05-23 | 2023-05-27
Civil works |  | 522 | 2021-05-23 | 2023-02-11
C-PW-107950 | Mound M1A - Soil Fill for the Piling Platform | 12 | 2021-05-23 | 2021-06-05 | 01 | 01 | 02 | 21 | 012 | 08 | 01-01-02-21-012-08 | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-PW-107960 | Mound M1A - Immediate Piling works | 4 | 2021-06-07 | 2021-06-10 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-PW-107970 | Mound M1A - Piling works & Pile Cutting | 20 | 2021-11-06 | 2021-11-28 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-PW-107980 | Mound M1A - Pile Testing & Pile Head Treatment works | 18 | 2021-11-29 | 2021-12-21 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-PW-107990 | Mound M1A - Construction of Pilecaps / Foundation | 39 | 2021-12-22 | 2022-02-06 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-PW-108000 | Mound M1A - Construction of Retaining wall for the Walk way | 18 | 2022-02-07 | 2022-02-27 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-PW-108010 | Mound M1A - Construction of Mound Columns | 20 | 2022-04-21 | 2022-05-17 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-PW-108020 | Mound M1A - Structural Steel Framing Works | 112 | 2022-10-01 | 2023-02-11 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
Walkway |  | 140 | 2022-05-25 | 2022-11-09
C-OW-108030 | Mound M1A - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-05-25 | 2022-06-08 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108040 | Mound M1A - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-02 | 2022-06-16 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108050 | Mound M1A - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-11 | 2022-06-25 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108060 | Mound M1A - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-19 | 2022-07-03 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108070 | Mound M1A - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-27 | 2022-07-14 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108080 | Mound M1A - Part 01-06, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-05 | 2022-07-23 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108090 | Mound M1A - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-06-26 | 2022-07-24 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108100 | Mound M1A - Part 01-07, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-17 | 2022-08-01 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108110 | Mound M1A - Part 01-08, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-25 | 2022-08-09 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108120 | Mound M1A - Part 01-09, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-03 | 2022-08-17 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108130 | Mound M1A - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-24 | 2022-08-18 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108140 | Mound M1A - Part 01-10, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-08-11 | 2022-09-01 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108150 | Mound M1A - Part 02-05, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-18 | 2022-09-12 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108160 | Mound M1A - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-20 | 2022-09-13 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108170 | Mound M1A - Part 01-11, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-08-28 | 2022-09-18 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108180 | Mound M1A - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-13 | 2022-10-08 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108190 | Mound M1A - Part 02-07, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-19 | 2022-10-15 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108200 | Mound M1A - Part 02-06, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-10-16 | 2022-11-09 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
C-OW-108210 | Completion of M1A Walkway | 0 |  | 2022-11-09 | 01 | 01 | 02 | 21 | 012 | 07 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound Walkway -2
Perimeter Wall |  | 132 | 2022-03-15 | 2022-08-23
C-OW-108220 | Mound M1A - Construction of Mound Perimeter Wall Pour 01 | 22 | 2022-03-15 | 2022-04-09 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108230 | Mound M1A - Construction of Mound Perimeter Wall Pour 10 | 22 | 2022-03-15 | 2022-04-09 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108240 | Mound M1A - Construction of Mound Perimeter Wall Pour 03 | 22 | 2022-04-10 | 2022-05-08 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108250 | Mound M1A - Construction of Mound Perimeter Wall Pour 12 | 22 | 2022-04-10 | 2022-05-08 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108260 | Mound M1A - Construction of Mound Perimeter Wall Pour 02 | 22 | 2022-05-09 | 2022-06-02 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108270 | Mound M1A - Construction of Mound Perimeter Wall Pour 05 | 22 | 2022-05-09 | 2022-06-02 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108280 | Mound M1A - Construction of Mound Perimeter Wall Pour 11 | 22 | 2022-05-09 | 2022-06-02 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108290 | Mound M1A - Construction of Mound Perimeter Wall Pour 14 | 22 | 2022-05-09 | 2022-06-02 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108300 | Mound M1A - Construction of Mound Perimeter Wall Pour 04 | 22 | 2022-06-04 | 2022-06-28 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108310 | Mound M1A - Construction of Mound Perimeter Wall Pour 07 | 22 | 2022-06-04 | 2022-06-28 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108320 | Mound M1A - Construction of Mound Perimeter Wall Pour 13 | 22 | 2022-06-04 | 2022-06-28 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108330 | Mound M1A - Construction of Mound Perimeter Wall Pour 16 | 22 | 2022-06-04 | 2022-06-28 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108340 | Mound M1A - Construction of Mound Perimeter Wall Pour 06 | 22 | 2022-06-29 | 2022-07-27 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108350 | Mound M1A - Construction of Mound Perimeter Wall Pour 09 | 22 | 2022-06-29 | 2022-07-27 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108360 | Mound M1A - Construction of Mound Perimeter Wall Pour 15 | 22 | 2022-06-29 | 2022-07-27 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108370 | Mound M1A - Construction of Mound Perimeter Wall Pour 18 | 22 | 2022-06-29 | 2022-07-27 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108380 | Mound M1A - Construction of Mound Perimeter Wall Pour 08 | 22 | 2022-07-28 | 2022-08-23 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-OW-108390 | Mound M1A - Construction of Mound Perimeter Wall Pour 17 | 22 | 2022-07-28 | 2022-08-23 | 01 | 01 | 02 | 21 | 012 | 08 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Mound External
Architectural works |  | 88 | 2023-02-12 | 2023-05-27
C-PW-108400 | Mound M1A - Mound Roof Precast / GRC Cladding works | 35 | 2023-02-12 | 2023-03-23 | 01 | 04 | 02 | 21 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M1A | Mound Lower Level | Mound External
C-PW-108410 | Mound M1A - Architectural works | 37 | 2023-04-12 | 2023-05-27 | 01 | 04 | 02 | 21 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M1A | Mound Lower Level | Mound External
MEP works |  | 64 | 2023-02-19 | 2023-05-06
C-PW-108420 | Mound M1A - MEP works | 64 | 2023-02-19 | 2023-05-06 | 01 | 14 | 02 | 21 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M1A | Mound Lower Level | Mound External
Zone M2A |  | 446 | 2021-08-26 | 2023-02-13
External / Lower Level |  | 446 | 2021-08-26 | 2023-02-13
Civil works |  | 378 | 2021-08-26 | 2022-11-23
C-PW-108430 | Mound M2A - Soil Fill for the Piling Platform | 8 | 2021-08-26 | 2021-09-04 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
C-PW-108440 | Mound M2A - Piling works & Pile Cutting | 15 | 2021-11-29 | 2021-12-18 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
C-PW-108450 | Mound M2A - Pile Testing & Pile Head Treatment works | 12 | 2021-12-19 | 2022-01-02 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
C-PW-108460 | Mound M2A - Construction of Pilecaps / Foundation | 21 | 2022-02-07 | 2022-03-02 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
C-PW-108470 | Mound M2A - Construction of Retaining wall for the Walk way | 13 | 2022-03-03 | 2022-03-17 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
C-PW-108480 | Mound M2A - Construction of Mound Columns | 6 | 2022-03-24 | 2022-03-30 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
C-PW-108490 | Mound M2A - Structural Steel Framing works | 18 | 2022-11-03 | 2022-11-23 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
Walkway |  | 85 | 2022-05-25 | 2022-09-05
C-OW-108500 | Mound M2A - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-05-25 | 2022-06-08 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
C-OW-108510 | Mound M2A - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-02 | 2022-06-16 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
C-OW-108520 | Mound M2A - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-11 | 2022-06-25 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
C-OW-108530 | Mound M2A - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-19 | 2022-07-03 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
C-OW-108540 | Mound M2A - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-27 | 2022-07-14 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
C-OW-108550 | Mound M2A - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-06-18 | 2022-07-16 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
C-OW-108560 | Mound M2A - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-04 | 2022-08-02 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
C-OW-108570 | Mound M2A - Part 02-05, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-16 | 2022-08-10 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
C-OW-108580 | Mound M2A - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-03 | 2022-08-28 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
C-OW-108590 | Mound M2A - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-11 | 2022-09-05 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
C-OW-108600 | Completion of M2A Walkway | 0 |  | 2022-09-05 | 01 | 01 | 02 | 22 | 012 | 07 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound Walkway -2
Perimeter Wall |  | 66 | 2022-03-24 | 2022-06-12
C-OW-108610 | Mound M2A - Construction of Mound Perimeter Wall Pour 01 | 22 | 2022-03-24 | 2022-04-18 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
C-OW-108620 | Mound M2A - Construction of Mound Perimeter Wall Pour 03 | 22 | 2022-04-19 | 2022-05-17 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
C-OW-108630 | Mound M2A - Construction of Mound Perimeter Wall Pour 02 | 22 | 2022-05-18 | 2022-06-12 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
C-OW-108640 | Mound M2A - Construction of Mound Perimeter Wall Pour 04 | 22 | 2022-05-18 | 2022-06-12 | 01 | 01 | 02 | 22 | 012 | 08 |  | Building | Civil | Mound Works | Zone M2A | Mound Lower Level | Mound External
Architectural works |  | 68 | 2022-11-24 | 2023-02-13
C-PW-108650 | Mound M2A - Mound Roof Precast / GRC Cladding works | 19 | 2022-11-24 | 2022-12-17 | 01 | 04 | 02 | 22 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M2A | Mound Lower Level | Mound External
C-PW-108660 | Mound M2A - Architectural works | 36 | 2023-01-03 | 2023-02-13 | 01 | 04 | 02 | 22 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M2A | Mound Lower Level | Mound External
MEP works |  | 44 | 2022-12-03 | 2023-01-23
C-PW-108670 | Mound M2A - MEP works | 44 | 2022-12-03 | 2023-01-23 | 01 | 14 | 02 | 22 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M2A | Mound Lower Level | Mound External
Zone M3A |  | 554 | 2021-05-05 | 2023-03-06
External / Lower Level |  | 554 | 2021-05-05 | 2023-03-06
Civil works |  | 424 | 2021-05-05 | 2022-10-02
C-PW-108680 | Site Survey for Action (Item 22 - Immediate) | 1 | 2021-05-05 | 2021-05-05 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108690 | Mound M3A - Soil Fill for the Piling Platform | 12 | 2021-06-06 | 2021-06-19 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108700 | Mound M3A - Immediate Piling works | 7 | 2021-06-20 | 2021-06-27 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108710 | Mound M3A - Construction of Retaining wall (Item 22 - Immediate) | 13 | 2021-08-18 | 2021-09-01 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108720 | Mound M3A - Piling works & Pile Cutting | 18 | 2021-12-19 | 2022-01-09 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108730 | Mound M3A - Pile Testing & Pile Head Treatment works | 12 | 2022-01-10 | 2022-01-23 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108740 | Mound M3A - Construction of Pilecaps / Foundation | 21 | 2022-01-24 | 2022-02-16 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108750 | Mound M3A - Soil Fill till Perimeter walkway Level | 6 | 2022-03-10 | 2022-03-16 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108760 | Mound M3A - Construction of Retaining wall for the Walk way | 13 | 2022-03-17 | 2022-03-31 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108770 | Mound M3A - Construction of Mound Columns | 12 | 2022-05-10 | 2022-05-23 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108780 | Mound M3A - Structural Steel Framing works | 33 | 2022-08-25 | 2022-10-02 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
Perimeter Wall |  | 88 | 2022-05-10 | 2022-08-24
C-OW-108790 | Mound M3A - Construction of Mound Perimeter Wall Pour 01 | 22 | 2022-05-10 | 2022-06-04 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-OW-108800 | Mound M3A - Construction of Mound Perimeter Wall Pour 03 | 22 | 2022-06-05 | 2022-06-29 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-OW-108810 | Mound M3A - Construction of Mound Perimeter Wall Pour 02 | 22 | 2022-06-30 | 2022-07-28 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-OW-108820 | Mound M3A - Construction of Mound Perimeter Wall Pour 05 | 22 | 2022-06-30 | 2022-07-28 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-OW-108830 | Mound M3A - Construction of Mound Perimeter Wall Pour 04 | 22 | 2022-07-31 | 2022-08-24 | 01 | 01 | 02 | 23 | 012 | 08 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Mound External
Architectural works |  | 130 | 2022-10-03 | 2023-03-06
C-PW-108840 | Mound M3A - Mound Roof Precast / GRC Cladding works | 40 | 2022-10-03 | 2022-11-19 | 01 | 04 | 02 | 23 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M3A | Mound Lower Level | Mound External
C-PW-108850 | Mound M3A - Architectural works | 27 | 2023-02-04 | 2023-03-06 | 01 | 04 | 02 | 23 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M3A | Mound Lower Level | Mound External
MEP works |  | 50 | 2022-12-17 | 2023-02-13
C-PW-108860 | Mound M3A - MEP works | 50 | 2022-12-17 | 2023-02-13 | 01 | 14 | 02 | 23 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M3A | Mound Lower Level | Mound External
Zone M4A |  | 468 | 2021-06-20 | 2023-01-07
External / Lower Level |  | 468 | 2021-06-20 | 2023-01-07
Civil works |  | 391 | 2021-06-20 | 2022-10-05
C-PW-108870 | Mound M4A - Soil Fill for the Piling Platform | 12 | 2021-06-20 | 2021-07-03 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108880 | Mound M4A - Immediate Piling works | 7 | 2021-07-05 | 2021-07-12 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108890 | Mound M4A - Soil Fill till Perimeter walkway Level | 14 | 2021-07-28 | 2021-08-14 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108900 | Mound M4A - Piling works & Pile Cutting | 25 | 2021-11-06 | 2021-12-06 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108910 | Mound M4A - Pile Testing & Pile Head Treatment works | 12 | 2021-12-07 | 2021-12-20 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108920 | Mound M4A - Construction of Retaining wall for the Walkway | 18 | 2021-12-21 | 2022-01-11 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108930 | Mound M4A - Construction of Pilecaps / Foundation | 36 | 2021-12-21 | 2022-02-01 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108940 | Mound M4A - Construction of Mound columns | 15 | 2022-04-05 | 2022-04-21 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108950 | Mound M4A - Construction of Ampitheatre Slabs | 32 | 2022-04-26 | 2022-06-05 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108960 | Mound M4A - Waterproofing of Ampitheatre Slabs | 21 | 2022-06-06 | 2022-06-29 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108970 | Mound M4A - Ampitheatre Seating Installation Seq01 | 24 | 2022-06-30 | 2022-08-01 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108980 | Mound M4A - Ampitheatre Seating Installation Seq02 | 24 | 2022-07-25 | 2022-08-22 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-108990 | Mound M4A - Structural Steel Framing works | 47 | 2022-08-13 | 2022-10-05 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
Walkway |  | 64 | 2022-05-25 | 2022-08-11
C-OW-109000 | Mound M4A - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-05-25 | 2022-06-08 | 01 | 01 | 02 | 24 | 012 | 06 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound Walkway -1
C-OW-109010 | Mound M4A - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-02 | 2022-06-16 | 01 | 01 | 02 | 24 | 012 | 06 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound Walkway -1
C-OW-109020 | Mound M4A - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-11 | 2022-06-25 | 01 | 01 | 02 | 24 | 012 | 06 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound Walkway -1
C-OW-109030 | Mound M4A - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-06-18 | 2022-07-16 | 01 | 01 | 02 | 24 | 012 | 06 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound Walkway -1
C-OW-109040 | Mound M4A - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-17 | 2022-08-11 | 01 | 01 | 02 | 24 | 012 | 06 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound Walkway -1
C-OW-109050 | Completion of M4A Walkway | 0 |  | 2022-08-11 | 01 | 01 | 02 | 24 | 012 | 06 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound Walkway -1
Perimeter Wall |  | 110 | 2022-03-15 | 2022-07-27
C-OW-109060 | Mound M4A - Construction of Mound Perimeter Wall Pour 01 | 22 | 2022-03-15 | 2022-04-09 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-OW-109070 | Mound M4A - Construction of Mound Perimeter Wall Pour 03 | 22 | 2022-04-10 | 2022-05-08 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-OW-109080 | Mound M4A - Construction of Mound Perimeter Wall Pour 02 | 22 | 2022-05-09 | 2022-06-02 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-OW-109090 | Mound M4A - Construction of Mound Perimeter Wall Pour 05 | 22 | 2022-05-09 | 2022-06-02 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-OW-109100 | Mound M4A - Construction of Mound Perimeter Wall Pour 04 | 22 | 2022-06-04 | 2022-06-28 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-OW-109110 | Mound M4A - Construction of Mound Perimeter Wall Pour 06 | 22 | 2022-06-29 | 2022-07-27 | 01 | 01 | 02 | 24 | 012 | 08 |  | Building | Civil | Mound Works | Zone M4A | Mound Lower Level | Mound External
Architectural works |  | 77 | 2022-10-06 | 2023-01-07
C-PW-109120 | Mound M4A - Mound Roof Precast / GRC Cladding works | 30 | 2022-10-06 | 2022-11-10 | 01 | 04 | 02 | 24 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M4A | Mound Lower Level | Mound External
C-PW-109130 | Mound M4A - Architectural works | 34 | 2022-11-27 | 2023-01-07 | 01 | 04 | 02 | 24 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M4A | Mound Lower Level | Mound External
MEP works |  | 53 | 2022-10-15 | 2022-12-15
C-PW-109140 | Mound M4A - MEP works | 53 | 2022-10-15 | 2022-12-15 | 01 | 14 | 02 | 24 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M4A | Mound Lower Level | Mound External
Zone M5A |  | 533 | 2021-07-04 | 2023-04-06
External / Lower Level |  | 533 | 2021-07-04 | 2023-04-06
Civil works |  | 418 | 2021-07-04 | 2022-11-21
Stage - 01 |  | 411 | 2021-07-04 | 2022-11-13
C-PW-109150 | Mound M5A - Soil Fill for the Piling Platform | 12 | 2021-07-04 | 2021-07-17 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109160 | Mound M5A - Immediate Piling works | 6 | 2021-07-18 | 2021-07-27 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109170 | Mound M5A - Piling works & Pile Cutting | 28 | 2021-12-07 | 2022-01-09 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109180 | Mound M5A - Pile Testing & Pile Head Treatment works | 10 | 2022-01-10 | 2022-01-20 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109190 | Mound M5A - Construction of Pilecaps / Foundation - Stage | 48 | 2022-01-22 | 2022-03-17 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109200 | Mound M5A - Construction of Mound Columns - Stage 1 | 12 | 2022-04-02 | 2022-04-14 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109210 | Mound M5A - Structural Steel Framing works - Stage 1 | 30 | 2022-10-10 | 2022-11-13 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
Walkway |  | 113 | 2022-05-25 | 2022-10-08
C-OW-109220 | Mound M5A - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-05-25 | 2022-06-08 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109230 | Mound M5A - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-02 | 2022-06-16 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109240 | Mound M5A - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-11 | 2022-06-25 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109250 | Mound M5A - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-19 | 2022-07-03 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109260 | Mound M5A - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-27 | 2022-07-14 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109270 | Mound M5A - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-06-18 | 2022-07-16 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109280 | Mound M5A - Part 01-06, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-05 | 2022-07-23 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109290 | Mound M5A - Part 01-07, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-17 | 2022-08-01 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109300 | Mound M5A - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-04 | 2022-08-02 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109310 | Mound M5A - Part 02-10, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-04 | 2022-08-02 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109320 | Mound M5A - Part 01-08, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-25 | 2022-08-09 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109330 | Mound M5A - Part 01-09, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-03 | 2022-08-17 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109340 | Mound M5A - Part 02-05, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-24 | 2022-08-18 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109350 | Mound M5A - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-03 | 2022-08-28 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109360 | Mound M5A - Part 02-11, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-03 | 2022-08-28 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109370 | Mound M5A - Part 02-07, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-10 | 2022-09-04 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109380 | Mound M5A - Part 02-09, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-18 | 2022-09-12 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109390 | Mound M5A - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-20 | 2022-09-13 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109400 | Mound M5A - Part 02-06, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-05 | 2022-09-29 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109410 | Mound M5A - Part 02-08, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-13 | 2022-10-08 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109420 | Completion of M5A Walkway | 0 |  | 2022-10-08 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
Perimeter Wall |  | 132 | 2022-03-19 | 2022-08-27
C-OW-109430 | Mound M5A - Construction of Mound Perimeter Wall Pour 01 | 22 | 2022-03-19 | 2022-04-12 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109440 | Mound M5A - Construction of Mound Perimeter Wall Pour 07 | 22 | 2022-03-19 | 2022-04-12 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109450 | Mound M5A - Construction of Mound Perimeter Wall Pour 03 | 22 | 2022-04-13 | 2022-05-11 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109460 | Mound M5A - Construction of Mound Perimeter Wall Pour 09 | 22 | 2022-04-13 | 2022-05-11 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109470 | Mound M5A - Construction of Mound Perimeter Wall Pour 02 | 22 | 2022-05-12 | 2022-06-06 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109480 | Mound M5A - Construction of Mound Perimeter Wall Pour 05 | 22 | 2022-05-12 | 2022-06-06 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109490 | Mound M5A - Construction of Mound Perimeter Wall Pour 08 | 22 | 2022-05-12 | 2022-06-06 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109500 | Mound M5A - Construction of Mound Perimeter Wall Pour 11 | 22 | 2022-05-12 | 2022-06-06 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109510 | Mound M5A - Construction of Mound Perimeter Wall Pour 04 | 22 | 2022-06-07 | 2022-07-02 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109520 | Mound M5A - Construction of Mound Perimeter Wall Pour 10 | 22 | 2022-06-07 | 2022-07-02 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109530 | Mound M5A - Construction of Mound Perimeter Wall Pour 06 | 22 | 2022-07-03 | 2022-08-01 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109540 | Mound M5A - Construction of Mound Perimeter Wall Pour 12 | 22 | 2022-07-03 | 2022-08-01 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-OW-109550 | Mound M5A - Construction of Mound Perimeter Wall Pour 13 | 22 | 2022-08-02 | 2022-08-27 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
Stage - 02 (After TC - 15 erection) |  | 193 | 2022-04-02 | 2022-11-21
C-PW-109560 | Mound M5A - Construction of Mound Columns - Stage 2 | 12 | 2022-04-02 | 2022-04-14 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109570 | Mound M5A - Construction of Mound Columns - Stage 2A | 12 | 2022-04-16 | 2022-04-28 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109580 | Mound M5A - Structural Steel Framing works - Stage 2 | 52 | 2022-09-21 | 2022-11-21 | 01 | 01 | 02 | 25 | 012 | 08 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound External
Walkway A |  | 98 | 2022-05-25 | 2022-09-20
C-OW-109590 | Mound M5Aa1 - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-05-25 | 2022-06-08 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109600 | Mound M5Aa1 - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-02 | 2022-06-16 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109610 | Mound M5Aa1 - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-11 | 2022-06-25 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109620 | Mound M5Aa1 - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-06-19 | 2022-07-13 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109630 | Mound M5Aa1 - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-06-18 | 2022-07-16 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109640 | Mound M5Aa1 - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-07-05 | 2022-07-31 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109650 | Mound M5Aa1 - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-14 | 2022-08-09 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109660 | Mound M5Aa1 - Part 02-05, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-01 | 2022-08-25 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109670 | Mound M5Aa1 - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-10 | 2022-09-04 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109680 | Mound M5Aa1 - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-27 | 2022-09-20 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109690 | Completion of M5A Walkway A | 0 |  | 2022-09-20 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
Walkway B |  | 85 | 2022-05-25 | 2022-09-05
C-OW-109700 | Mound M5Ab1 - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-05-25 | 2022-06-08 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109710 | Mound M5Ab1 - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-02 | 2022-06-16 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109720 | Mound M5Ab1 - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-11 | 2022-06-25 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109730 | Mound M5Ab1 - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-19 | 2022-07-03 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109740 | Mound M5Ab1 - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-27 | 2022-07-14 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109750 | Mound M5Ab1 - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-06-18 | 2022-07-16 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109760 | Mound M5Ab1 - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-16 | 2022-08-10 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109770 | Mound M5Ab1 - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-11 | 2022-09-05 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109780 | Mound M5Ab1 - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-11 | 2022-09-05 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
C-OW-109790 | Completion of M5A Walkway B | 0 |  | 2022-09-05 | 01 | 01 | 02 | 25 | 012 | 06 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Mound Walkway -1
Architectural works |  | 115 | 2022-11-22 | 2023-04-06
C-PW-109800 | Mound M5A - Mound Roof Precast / GRC Cladding works - Stage 1 | 27 | 2022-11-22 | 2022-12-24 | 01 | 04 | 02 | 25 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109810 | Mound M5A - Mound Roof Precast / GRC Cladding works - Stage 2a1 & 2b1 | 28 | 2022-12-25 | 2023-01-26 | 01 | 04 | 02 | 25 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109820 | Mound M5A - Architectural works - Stage 01 | 26 | 2023-01-02 | 2023-01-31 | 01 | 04 | 02 | 25 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109830 | Mound M5A - Architectural works - Stage 02 | 26 | 2023-03-08 | 2023-04-06 | 01 | 04 | 02 | 25 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M5A | Mound Lower Level | Mound External
MEP works |  | 50 | 2022-12-07 | 2023-02-04
C-PW-109840 | Mound M5A - MEP works - Stage 01 | 29 | 2022-12-07 | 2023-01-10 | 01 | 14 | 02 | 25 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M5A | Mound Lower Level | Mound External
C-PW-109850 | Mound M5A - MEP works - Stage 02 | 29 | 2023-01-02 | 2023-02-04 | 01 | 14 | 02 | 25 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M5A | Mound Lower Level | Mound External
Zone M6A |  | 495 | 2021-07-18 | 2023-03-07
External / Lower Level |  | 495 | 2021-07-18 | 2023-03-07
Civil works |  | 407 | 2021-07-18 | 2022-11-22
C-PW-109860 | Mound M6A - Soil Fill for the Piling Platform | 12 | 2021-07-18 | 2021-08-03 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-PW-109870 | Mound M6A - Immediate Piling works | 14 | 2021-08-04 | 2021-08-21 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-PW-109880 | Mound M6A - Soil Fill till Perimeter walkway Level | 12 | 2021-08-15 | 2021-08-28 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-PW-109890 | Mound M6A - Piling works & Pile Cutting | 35 | 2022-01-10 | 2022-02-19 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-PW-109900 | Mound M6A - Pile Testing & Pile Head Treatment works | 18 | 2022-02-20 | 2022-03-12 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-PW-109910 | Mound M6A - Construction of Pilecaps / Foundation | 27 | 2022-03-13 | 2022-04-12 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-PW-109920 | Mound M6A - Construction of Retaining wall for the Walk way | 12 | 2022-04-13 | 2022-04-26 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-PW-109930 | Mound M6A - Construction of Mound Columns | 21 | 2022-04-27 | 2022-05-24 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-PW-109940 | Mound M6A - Structural Steel Framing works | 79 | 2022-08-22 | 2022-11-22 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
Walkway |  | 71 | 2022-05-25 | 2022-08-20
C-OW-109950 | Mound M6A - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-05-25 | 2022-06-08 | 01 | 01 | 02 | 26 | 012 | 06 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound Walkway -1
C-OW-109960 | Mound M6A - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-02 | 2022-06-16 | 01 | 01 | 02 | 26 | 012 | 06 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound Walkway -1
C-OW-109970 | Mound M6A - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-11 | 2022-06-25 | 01 | 01 | 02 | 26 | 012 | 06 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound Walkway -1
C-OW-109980 | Mound M6A - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-06-18 | 2022-07-16 | 01 | 01 | 02 | 26 | 012 | 06 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound Walkway -1
C-OW-109990 | Mound M6A - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-06-26 | 2022-07-24 | 01 | 01 | 02 | 26 | 012 | 06 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound Walkway -1
C-OW-110000 | Mound M6A - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-25 | 2022-08-20 | 01 | 01 | 02 | 26 | 012 | 06 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound Walkway -1
C-OW-110010 | Completion of M6A Walkway | 0 |  | 2022-08-20 | 01 | 01 | 02 | 26 | 012 | 06 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound Walkway -1
Perimeter Wall |  | 110 | 2022-04-07 | 2022-08-21
C-OW-110020 | Mound M6A - Construction of Mound Perimeter Wall Pour 01 | 22 | 2022-04-07 | 2022-05-05 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110030 | Mound M6A - Construction of Mound Perimeter Wall Pour 08 | 22 | 2022-04-07 | 2022-05-05 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110040 | Mound M6A - Construction of Mound Perimeter Wall Pour 03 | 22 | 2022-05-07 | 2022-05-31 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110050 | Mound M6A - Construction of Mound Perimeter Wall Pour 10 | 22 | 2022-05-07 | 2022-05-31 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110060 | Mound M6A - Construction of Mound Perimeter Wall Pour 02 | 22 | 2022-06-01 | 2022-06-26 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110070 | Mound M6A - Construction of Mound Perimeter Wall Pour 05 | 22 | 2022-06-01 | 2022-06-26 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110080 | Mound M6A - Construction of Mound Perimeter Wall Pour 09 | 22 | 2022-06-01 | 2022-06-26 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110090 | Mound M6A - Construction of Mound Perimeter Wall Pour 12 | 22 | 2022-06-01 | 2022-06-26 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110100 | Mound M6A - Construction of Mound Perimeter Wall Pour 04 | 22 | 2022-06-27 | 2022-07-25 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110110 | Mound M6A - Construction of Mound Perimeter Wall Pour 07 | 22 | 2022-06-27 | 2022-07-25 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110120 | Mound M6A - Construction of Mound Perimeter Wall Pour 11 | 22 | 2022-06-27 | 2022-07-25 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110130 | Mound M6A - Construction of Mound Perimeter Wall Pour 14 | 22 | 2022-06-27 | 2022-07-25 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110140 | Mound M6A - Construction of Mound Perimeter Wall Pour 06 | 22 | 2022-07-26 | 2022-08-21 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-OW-110150 | Mound M6A - Construction of Mound Perimeter Wall Pour 13 | 22 | 2022-07-26 | 2022-08-21 | 01 | 01 | 02 | 26 | 012 | 08 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Mound External
Architectural works |  | 88 | 2022-11-23 | 2023-03-07
C-PW-110160 | Mound M6A - Mound Roof Precast / GRC Cladding works | 51 | 2022-11-23 | 2023-01-23 | 01 | 04 | 02 | 26 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M6A | Mound Lower Level | Mound External
C-PW-110170 | Mound M6A - Architectural works | 35 | 2023-01-26 | 2023-03-07 | 01 | 04 | 02 | 26 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M6A | Mound Lower Level | Mound External
MEP works |  | 64 | 2022-12-01 | 2023-02-14
C-PW-110180 | Mound M6A - MEP works | 64 | 2022-12-01 | 2023-02-14 | 01 | 14 | 02 | 26 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M6A | Mound Lower Level | Mound External
Zone M7A |  | 229 | 2021-12-18 | 2022-09-19
External / Lower Level |  | 229 | 2021-12-18 | 2022-09-19
Civil works |  | 159 | 2021-12-18 | 2022-06-25
C-PW-110190 | Mound M7A - Preparation & Soil Compaction - Canadian Ducts | 12 | 2021-12-18 | 2021-12-30 | 01 | 01 | 02 | 27 | 012 | 08 |  | Building | Civil | Mound Works | Zone M7A | Mound Lower Level | Mound External
C-PW-110200 | Mound M7A - Canadian Ducts - Pipe Laying | 12 | 2021-12-26 | 2022-01-09 | 01 | 01 | 02 | 27 | 012 | 08 |  | Building | Civil | Mound Works | Zone M7A | Mound Lower Level | Mound External
C-PW-110220 | Mound M7A - Pile Testing & Pile Head Treatment works | 10 | 2022-01-10 | 2022-01-20 | 01 | 01 | 02 | 27 | 012 | 08 |  | Building | Civil | Mound Works | Zone M7A | Mound Lower Level | Mound External
C-PW-110210 | Mound M7A - Jointing & Epoxy Paint - Canadian Ducts | 12 | 2022-01-08 | 2022-01-20 | 01 | 01 | 02 | 27 | 012 | 08 |  | Building | Civil | Mound Works | Zone M7A | Mound Lower Level | Mound External
C-PW-110230 | Mound M7A - Construction of Pilecaps / Foundation | 18 | 2022-01-22 | 2022-02-10 | 01 | 01 | 02 | 27 | 012 | 08 |  | Building | Civil | Mound Works | Zone M7A | Mound Lower Level | Mound External
C-PW-110240 | Mound M7A - Pile Extension works / Pile treatment works / Pilecap / Tie beam works | 52 | 2022-02-12 | 2022-04-12 | 01 | 01 | 02 | 27 | 012 | 08 |  | Building | Civil | Mound Works | Zone M7A | Mound Lower Level | Mound External
C-PW-110250 | Mound M7A - Backfilling of Canadian Ducts | 36 | 2022-03-30 | 2022-05-14 | 01 | 01 | 02 | 27 | 012 | 08 |  | Building | Civil | Mound Works | Zone M7A | Mound Lower Level | Mound External
C-PW-110260 | Mound M7A - Construction of Mound Columns | 12 | 2022-05-15 | 2022-05-28 | 01 | 01 | 02 | 27 | 012 | 08 |  | Building | Civil | Mound Works | Zone M7A | Mound Lower Level | Mound External
C-PW-110270 | Mound M7A - Structural Steel Framing works | 24 | 2022-05-29 | 2022-06-25 | 01 | 01 | 02 | 27 | 012 | 08 |  | Building | Civil | Mound Works | Zone M7A | Mound Lower Level | Mound External
Architectural works |  | 66 | 2022-06-30 | 2022-09-19
C-PW-110280 | Mound M7A - Mound Roof Precast / GRC Cladding works | 22 | 2022-06-30 | 2022-07-28 | 01 | 04 | 02 | 27 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M7A | Mound Lower Level | Mound External
C-PW-110290 | Mound M7A - Architectural works | 28 | 2022-08-18 | 2022-09-19 | 01 | 04 | 02 | 27 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M7A | Mound Lower Level | Mound External
MEP works |  | 38 | 2022-07-16 | 2022-08-29
C-PW-110300 | Mound M7A - MEP works | 38 | 2022-07-16 | 2022-08-29 | 01 | 14 | 02 | 27 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M7A | Mound Lower Level | Mound External
Zone M8 |  | 117 | 2022-11-24 | 2023-04-11
M8 - M1A |  | 64 | 2022-11-24 | 2023-02-08
External / Lower Level |  | 64 | 2022-11-24 | 2023-02-08
Civil works |  | 18 | 2022-11-24 | 2022-12-15
C-PW-110310 | Mound M8-M1A - Structural Steel Framing works | 18 | 2022-11-24 | 2022-12-15 | 01 | 01 | 02 | 28 | 012 | 08 |  | Building | Civil | Mound Works | Zone M8 | Mound Lower Level | Mound External
Architectural works |  | 46 | 2022-12-17 | 2023-02-08
C-PW-110320 | Mound M8-M1A - Mound Roof Precast / GRC Cladding works | 34 | 2022-12-17 | 2023-01-25 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
C-PW-110330 | Mound M8-M1A - Architectural works | 12 | 2023-01-26 | 2023-02-08 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
MEP works |  | 12 | 2022-12-17 | 2022-12-29
C-PW-110340 | Mound M8-M1A - MEP works | 12 | 2022-12-17 | 2022-12-29 | 01 | 14 | 02 | 28 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M8 | Mound Lower Level | Mound External
M8 - M2A |  | 64 | 2022-11-24 | 2023-02-08
External / Lower Level |  | 64 | 2022-11-24 | 2023-02-08
Civil works |  | 18 | 2022-11-24 | 2022-12-15
C-PW-114370 | Mound M8-M2A - Structural Steel Framing works | 18 | 2022-11-24 | 2022-12-15 | 01 | 01 | 02 | 28 | 012 | 08 |  | Building | Civil | Mound Works | Zone M8 | Mound Lower Level | Mound External
Architectural works |  | 46 | 2022-12-17 | 2023-02-08
C-PW-114390 | Mound M8-M2A - Mound Roof Precast / GRC Cladding works | 34 | 2022-12-17 | 2023-01-25 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
C-PW-114380 | Mound M8-M2A - Architectural works | 12 | 2023-01-26 | 2023-02-08 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
MEP works |  | 12 | 2022-12-17 | 2022-12-29
C-PW-114400 | Mound M8-M2A - MEP works | 12 | 2022-12-17 | 2022-12-29 | 01 | 14 | 02 | 28 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M8 | Mound Lower Level | Mound External
M8 - M3A |  | 64 | 2022-11-24 | 2023-02-08
External / Lower Level |  | 64 | 2022-11-24 | 2023-02-08
Civil works |  | 18 | 2022-11-24 | 2022-12-15
C-PW-114410 | Mound M8-M3A - Structural Steel Framing works | 18 | 2022-11-24 | 2022-12-15 | 01 | 01 | 02 | 28 | 012 | 08 |  | Building | Civil | Mound Works | Zone M8 | Mound Lower Level | Mound External
Architectural works |  | 46 | 2022-12-17 | 2023-02-08
C-PW-114430 | Mound M8-M3A - Mound Roof Precast / GRC Cladding works | 34 | 2022-12-17 | 2023-01-25 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
C-PW-114420 | Mound M8-M3A - Architectural works | 12 | 2023-01-26 | 2023-02-08 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
MEP works |  | 12 | 2022-12-17 | 2022-12-29
C-PW-114440 | Mound M8-M3A - MEP works | 12 | 2022-12-17 | 2022-12-29 | 01 | 14 | 02 | 28 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M8 | Mound Lower Level | Mound External
M8 - M4A |  | 64 | 2022-11-24 | 2023-02-08
External / Lower Level |  | 64 | 2022-11-24 | 2023-02-08
Civil works |  | 18 | 2022-11-24 | 2022-12-15
C-PW-114450 | Mound M8-M4A - Structural Steel Framing works | 18 | 2022-11-24 | 2022-12-15 | 01 | 01 | 02 | 28 | 012 | 08 |  | Building | Civil | Mound Works | Zone M8 | Mound Lower Level | Mound External
Architectural works |  | 46 | 2022-12-17 | 2023-02-08
C-PW-114470 | Mound M8-M4A - Mound Roof Precast / GRC Cladding works | 34 | 2022-12-17 | 2023-01-25 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
C-PW-114460 | Mound M8-M4A - Architectural works | 12 | 2023-01-26 | 2023-02-08 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
MEP works |  | 12 | 2022-12-17 | 2022-12-29
C-PW-114480 | Mound M8-M4A - MEP works | 12 | 2022-12-17 | 2022-12-29 | 01 | 14 | 02 | 28 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M8 | Mound Lower Level | Mound External
M8 - M5A |  | 64 | 2023-01-28 | 2023-04-11
External / Lower Level |  | 64 | 2023-01-28 | 2023-04-11
Civil works |  | 18 | 2023-01-28 | 2023-02-16
C-PW-114490 | Mound M8-M5A - Structural Steel Framing works | 18 | 2023-01-28 | 2023-02-16 | 01 | 01 | 02 | 28 | 012 | 08 |  | Building | Civil | Mound Works | Zone M8 | Mound Lower Level | Mound External
Architectural works |  | 46 | 2023-02-18 | 2023-04-11
C-PW-114510 | Mound M8-M5A - Mound Roof Precast / GRC Cladding works | 34 | 2023-02-18 | 2023-03-28 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
C-PW-114500 | Mound M8-M5A - Architectural works | 12 | 2023-03-29 | 2023-04-11 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
MEP works |  | 12 | 2023-02-18 | 2023-03-02
C-PW-114520 | Mound M8-M5A - MEP works | 12 | 2023-02-18 | 2023-03-02 | 01 | 14 | 02 | 28 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M8 | Mound Lower Level | Mound External
M8 - M6A |  | 64 | 2022-11-24 | 2023-02-08
External / Lower Level |  | 64 | 2022-11-24 | 2023-02-08
Civil works |  | 18 | 2022-11-24 | 2022-12-15
C-PW-114530 | Mound M8-M6A - Structural Steel Framing works | 18 | 2022-11-24 | 2022-12-15 | 01 | 01 | 02 | 28 | 012 | 08 |  | Building | Civil | Mound Works | Zone M8 | Mound Lower Level | Mound External
Architectural works |  | 46 | 2022-12-17 | 2023-02-08
C-PW-114550 | Mound M8-M6A - Mound Roof Precast / GRC Cladding works | 34 | 2022-12-17 | 2023-01-25 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
C-PW-114540 | Mound M8-M6A - Architectural works | 12 | 2023-01-26 | 2023-02-08 | 01 | 04 | 02 | 28 | 012 | 08 |  | Building | Architecture | Mound Works | Zone M8 | Mound Lower Level | Mound External
MEP works |  | 12 | 2022-12-17 | 2022-12-29
C-PW-114560 | Mound M8-M6A - MEP works | 12 | 2022-12-17 | 2022-12-29 | 01 | 14 | 02 | 28 | 012 | 08 |  | Building | General MEP | Mound Works | Zone M8 | Mound Lower Level | Mound External
Zone M1B (Walkway -1) |  | 188 | 2022-10-27 | 2023-06-07
Internal / Upper Level |  | 188 | 2022-10-27 | 2023-06-07
Civil works |  | 143 | 2022-10-27 | 2023-04-13
C-PW-110350 | Mound M1B - Construction of Mound Columns | 12 | 2022-10-27 | 2022-11-09 | 01 | 01 | 02 | 29 | 013 | 09 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Internal
C-PW-110360 | Mound M1B - Structural Steel Framing works | 26 | 2023-03-15 | 2023-04-13 | 01 | 01 | 02 | 29 | 013 | 09 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Internal
Walkway |  | 105 | 2022-11-10 | 2023-03-14
C-OW-110370 | Mound M1B - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-11-10 | 2022-12-03 | 01 | 01 | 02 | 29 | 013 | 06 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Walkway -1
C-OW-110380 | Mound M1B - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-11-27 | 2022-12-19 | 01 | 01 | 02 | 29 | 013 | 06 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Walkway -1
C-OW-110390 | Mound M1B - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-12-14 | 2023-01-05 | 01 | 01 | 02 | 29 | 013 | 06 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Walkway -1
C-OW-110400 | Mound M1B - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-12-20 | 2023-01-15 | 01 | 01 | 02 | 29 | 013 | 06 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Walkway -1
C-OW-110410 | Mound M1B - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-12-31 | 2023-01-22 | 01 | 01 | 02 | 29 | 013 | 06 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Walkway -1
C-OW-110420 | Mound M1B - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2023-01-17 | 2023-02-07 | 01 | 01 | 02 | 29 | 013 | 06 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Walkway -1
C-OW-110430 | Mound M1B - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2023-01-23 | 2023-02-16 | 01 | 01 | 02 | 29 | 013 | 06 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Walkway -1
C-OW-110440 | Mound M1B - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2023-02-18 | 2023-03-14 | 01 | 01 | 02 | 29 | 013 | 06 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Walkway -1
C-OW-110450 | Mound M1B - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2023-02-18 | 2023-03-14 | 01 | 01 | 02 | 29 | 013 | 06 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Walkway -1
C-OW-110460 | Completion of M1B Walkway 1 | 0 |  | 2023-03-14 | 01 | 01 | 02 | 29 | 013 | 06 |  | Building | Civil | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Walkway -1
Architectural works |  | 45 | 2023-04-15 | 2023-06-07
C-PW-110470 | Mound M1B - Mound Roof Precast / GRC Cladding works | 21 | 2023-04-15 | 2023-05-10 | 01 | 04 | 02 | 29 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Internal
C-PW-110480 | Mound M1B - Architectural works | 15 | 2023-05-22 | 2023-06-07 | 01 | 04 | 02 | 29 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Internal
MEP works |  | 21 | 2023-04-24 | 2023-05-17
C-PW-110490 | Mound M1B - MEP works | 21 | 2023-04-24 | 2023-05-17 | 01 | 14 | 02 | 29 | 013 | 09 |  | Building | General MEP | Mound Works | Zone M1B (Walkway 1) | Mound Upper Level | Mound Internal
Zone M1B (Walkway -2) |  | 342 | 2022-05-18 | 2023-07-03
Internal / Upper Level |  | 342 | 2022-05-18 | 2023-07-03
Civil works |  | 275 | 2022-05-18 | 2023-04-11
C-PW-110500 | Mound M1B - Construction of Mound Columns | 6 | 2022-05-18 | 2022-05-24 | 01 | 01 | 02 | 30 | 013 | 09 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Internal
C-PW-110510 | Mound M1B - Structural Steel Framing works | 44 | 2023-02-20 | 2023-04-11 | 01 | 01 | 02 | 30 | 013 | 09 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Internal
Walkway |  | 128 | 2022-05-25 | 2022-10-26
C-OW-110520 | Mound M1B - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-05-25 | 2022-06-08 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110530 | Mound M1B - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-02 | 2022-06-16 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110540 | Mound M1B - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-11 | 2022-06-25 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110550 | Mound M1B - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-19 | 2022-07-03 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110560 | Mound M1B - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-27 | 2022-07-14 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110570 | Mound M1B - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-06-18 | 2022-07-16 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110580 | Mound M1B - Part 01-06, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-05 | 2022-07-23 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110590 | Mound M1B - Part 01-07, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-17 | 2022-08-01 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110600 | Mound M1B - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-04 | 2022-08-02 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110610 | Mound M1B - Part 01-08, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-25 | 2022-08-09 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110620 | Mound M1B - Part 01-09, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-03 | 2022-08-17 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110630 | Mound M1B - Part 02-05, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-24 | 2022-08-18 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110640 | Mound M1B - Part 02-07, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-10 | 2022-09-04 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110650 | Mound M1B - Part 02-09, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-18 | 2022-09-12 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110660 | Mound M1B - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-20 | 2022-09-13 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110670 | Mound M1B - Part 02-06, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-05 | 2022-09-29 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110680 | Mound M1B - Part 02-08, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-13 | 2022-10-08 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110690 | Mound M1B - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-10-01 | 2022-10-26 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
C-OW-110700 | Completion of M1B Walkway 2 | 0 |  | 2022-10-26 | 01 | 01 | 02 | 30 | 013 | 07 |  | Building | Civil | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Walkway -2
Architectural works |  | 67 | 2023-04-12 | 2023-07-03
C-PW-110710 | Mound M1B - Mound Roof Precast / GRC Cladding works | 40 | 2023-04-12 | 2023-05-30 | 01 | 04 | 02 | 30 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Internal
C-PW-110720 | Mound M1B - Architectural works | 30 | 2023-05-28 | 2023-07-03 | 01 | 04 | 02 | 30 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Internal
MEP works |  | 42 | 2023-04-22 | 2023-06-08
C-PW-110730 | Mound M1B - MEP works | 42 | 2023-04-22 | 2023-06-08 | 01 | 14 | 02 | 30 | 013 | 09 |  | Building | General MEP | Mound Works | Zone M1B (Walkway 2) | Mound Upper Level | Mound Internal
Zone M2B |  | 269 | 2022-08-24 | 2023-07-11
Internal / Upper Level |  | 269 | 2022-08-24 | 2023-07-11
Civil works |  | 181 | 2022-08-24 | 2023-03-26
C-PW-110740 | Mound M2B - Construction of Mound Columns | 11 | 2022-08-24 | 2022-09-05 | 01 | 01 | 02 | 31 | 013 | 09 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Internal
C-PW-110750 | Mound M2B - Structural Steel Framing works | 93 | 2022-12-07 | 2023-03-26 | 01 | 01 | 02 | 31 | 013 | 09 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Internal
Walkway |  | 146 | 2022-08-24 | 2023-02-13
C-OW-110760 | Mound M2B - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-24 | 2022-09-07 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110770 | Mound M2B - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-09-01 | 2022-09-15 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110780 | Mound M2B - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-09-10 | 2022-09-24 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110790 | Mound M2B - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-09-18 | 2022-10-02 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110800 | Mound M2B - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-17 | 2022-10-12 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110810 | Mound M2B - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-09-26 | 2022-10-18 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110820 | Mound M2B - Part 01-06, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-10-13 | 2022-11-03 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110830 | Mound M2B - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-10-19 | 2022-11-13 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110840 | Mound M2B - Part 01-07, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-10-30 | 2022-11-20 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110850 | Mound M2B - Part 01-08, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-11-21 | 2022-12-06 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110860 | Mound M2B - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-11-14 | 2022-12-10 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110870 | Mound M2B - Part 01-09, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-11-29 | 2022-12-14 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110880 | Mound M2B - Part 01-10, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-12-08 | 2022-12-22 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110890 | Mound M2B - Part 02-05, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-12-07 | 2023-01-02 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110900 | Mound M2B - Part 02-07, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-12-24 | 2023-01-18 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110910 | Mound M2B - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2023-01-03 | 2023-01-28 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110920 | Mound M2B - Part 02-06, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2023-01-19 | 2023-02-13 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110930 | Mound M2B - Part 02-08, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2023-01-19 | 2023-02-13 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
C-OW-110940 | Completion of M2B Walkway | 0 |  | 2023-02-13 | 01 | 01 | 02 | 31 | 013 | 07 |  | Building | Civil | Mound Works | Zone M2B | Mound Upper Level | Mound Walkway -2
Architectural works |  | 88 | 2023-03-27 | 2023-07-11
C-PW-110950 | Mound M2B - Mound Roof Precast / GRC Cladding works | 42 | 2023-03-27 | 2023-05-16 | 01 | 04 | 02 | 31 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M2B | Mound Upper Level | Mound Internal
C-PW-110960 | Mound M2B - Architectural works | 53 | 2023-05-09 | 2023-07-11 | 01 | 04 | 02 | 31 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M2B | Mound Upper Level | Mound Internal
MEP works |  | 64 | 2023-04-03 | 2023-06-18
C-PW-110970 | Mound M2B - MEP works | 64 | 2023-04-03 | 2023-06-18 | 01 | 14 | 02 | 31 | 013 | 09 |  | Building | General MEP | Mound Works | Zone M2B | Mound Upper Level | Mound Internal
Zone M3B |  | 279 | 2022-06-21 | 2023-05-22
Internal / Upper Level |  | 279 | 2022-06-21 | 2023-05-22
Civil works |  | 153 | 2022-06-21 | 2022-12-22
C-PW-110980 | Mound M3B - Construction of Mound Columns | 12 | 2022-06-21 | 2022-07-04 | 01 | 01 | 02 | 32 | 013 | 09 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Internal
C-PW-110990 | Mound M3B - Structural Steel Framing works | 56 | 2022-10-18 | 2022-12-22 | 01 | 01 | 02 | 32 | 013 | 09 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Internal
Walkway |  | 85 | 2022-07-05 | 2022-10-17
C-OW-111000 | Mound M3B - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-05 | 2022-07-23 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
C-OW-111010 | Mound M3B - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-17 | 2022-08-01 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
C-OW-111020 | Mound M3B - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-25 | 2022-08-09 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
C-OW-111030 | Mound M3B - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-03 | 2022-08-17 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
C-OW-111040 | Mound M3B - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-11 | 2022-08-25 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
C-OW-111050 | Mound M3B - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-02 | 2022-08-27 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
C-OW-111060 | Mound M3B - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-18 | 2022-09-12 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
C-OW-111070 | Mound M3B - Part 02-05, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-27 | 2022-09-20 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
C-OW-111080 | Mound M3B - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-13 | 2022-10-08 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
C-OW-111090 | Mound M3B - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-21 | 2022-10-17 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
C-OW-111100 | Completion of M3B Walkway | 0 |  | 2022-10-17 | 01 | 01 | 02 | 32 | 013 | 07 |  | Building | Civil | Mound Works | Zone M3B | Mound Upper Level | Mound Walkway -2
Architectural works |  | 126 | 2022-12-24 | 2023-05-22
C-PW-111110 | Mound M3B - Mound Roof Precast / GRC Cladding works | 48 | 2022-12-24 | 2023-02-18 | 01 | 04 | 02 | 32 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M3B | Mound Upper Level | Mound Internal
C-PW-111120 | Mound M3B - Architectural works | 35 | 2023-04-10 | 2023-05-22 | 01 | 04 | 02 | 32 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M3B | Mound Upper Level | Mound Internal
MEP works |  | 64 | 2023-02-14 | 2023-05-01
C-PW-111130 | Mound M3B - MEP works | 64 | 2023-02-14 | 2023-05-01 | 01 | 14 | 02 | 32 | 013 | 09 |  | Building | General MEP | Mound Works | Zone M3B | Mound Upper Level | Mound Internal
Zone M4B |  | 245 | 2022-08-23 | 2023-06-10
Internal / Upper Level |  | 245 | 2022-08-23 | 2023-06-10
Civil works |  | 157 | 2022-08-23 | 2023-02-25
C-PW-111140 | Mound M4B - Construction of Mound Columns | 14 | 2022-08-23 | 2022-09-07 | 01 | 01 | 02 | 33 | 013 | 09 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Internal
C-PW-111150 | Mound M4B - Structural Steel Framing works | 77 | 2022-11-26 | 2023-02-25 | 01 | 01 | 02 | 33 | 013 | 09 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Internal
Walkway |  | 109 | 2022-08-23 | 2022-12-29
C-OW-111160 | Mound M4B - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-08-23 | 2022-09-13 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
C-OW-111170 | Mound M4B - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-09-14 | 2022-09-28 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
C-OW-111180 | Mound M4B - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-09-22 | 2022-10-15 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
C-OW-111190 | Mound M4B - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-29 | 2022-10-25 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
C-OW-111200 | Mound M4B - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-10-16 | 2022-10-30 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
C-OW-111210 | Mound M4B - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-10-24 | 2022-11-07 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
C-OW-111220 | Mound M4B - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-10-31 | 2022-11-24 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
C-OW-111230 | Mound M4B - Part 02-05, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-11-08 | 2022-12-04 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
C-OW-111240 | Mound M4B - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-11-26 | 2022-12-21 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
C-OW-111250 | Mound M4B - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-12-05 | 2022-12-29 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
C-OW-111260 | Completion of M4B Walkway | 0 |  | 2022-12-29 | 01 | 01 | 02 | 33 | 013 | 07 |  | Building | Civil | Mound Works | Zone M4B | Mound Upper Level | Mound Walkway -2
Architectural works |  | 88 | 2023-02-26 | 2023-06-10
C-PW-111270 | Mound M4B - Mound Roof Precast / GRC Cladding works | 53 | 2023-02-26 | 2023-04-30 | 01 | 04 | 02 | 33 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M4B | Mound Upper Level | Mound Internal
C-PW-111280 | Mound M4B - Architectural works | 36 | 2023-04-30 | 2023-06-10 | 01 | 04 | 02 | 33 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M4B | Mound Upper Level | Mound Internal
MEP works |  | 64 | 2023-03-05 | 2023-05-20
C-PW-111290 | Mound M4B - MEP works | 64 | 2023-03-05 | 2023-05-20 | 01 | 14 | 02 | 33 | 013 | 09 |  | Building | General MEP | Mound Works | Zone M4B | Mound Upper Level | Mound Internal
Zone M5B |  | 223 | 2022-10-10 | 2023-07-03
Internal / Upper Level |  | 223 | 2022-10-10 | 2023-07-03
Civil works |  | 144 | 2022-10-10 | 2023-03-28
C-PW-111300 | Mound M5B - Construction of Mound Columns | 15 | 2022-10-10 | 2022-10-26 | 01 | 01 | 02 | 34 | 013 | 09 |  | Building | Civil | Mound Works | Zone M5B | Mound Upper Level | Mound Internal
C-PW-111310 | Mound M5B - Structural Steel Framing works | 80 | 2022-12-25 | 2023-03-28 | 01 | 01 | 02 | 34 | 013 | 09 |  | Building | Civil | Mound Works | Zone M5B | Mound Upper Level | Mound Internal
Walkway |  | 77 | 2022-10-27 | 2023-01-26
C-OW-111320 | Mound M5B - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-10-27 | 2022-11-17 | 01 | 01 | 02 | 34 | 013 | 07 |  | Building | Civil | Mound Works | Zone M5B | Mound Upper Level | Mound Walkway -2
C-OW-111330 | Mound M5B - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-11-13 | 2022-12-05 | 01 | 01 | 02 | 34 | 013 | 07 |  | Building | Civil | Mound Works | Zone M5B | Mound Upper Level | Mound Walkway -2
C-OW-111340 | Mound M5B - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-11-29 | 2022-12-21 | 01 | 01 | 02 | 34 | 013 | 07 |  | Building | Civil | Mound Works | Zone M5B | Mound Upper Level | Mound Walkway -2
C-OW-111350 | Mound M5B - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-12-06 | 2022-12-31 | 01 | 01 | 02 | 34 | 013 | 07 |  | Building | Civil | Mound Works | Zone M5B | Mound Upper Level | Mound Walkway -2
C-OW-111360 | Mound M5B - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2023-01-02 | 2023-01-26 | 01 | 01 | 02 | 34 | 013 | 07 |  | Building | Civil | Mound Works | Zone M5B | Mound Upper Level | Mound Walkway -2
C-OW-111370 | Completion of M5B Walkway | 0 |  | 2023-01-26 | 01 | 01 | 02 | 34 | 013 | 07 |  | Building | Civil | Mound Works | Zone M5B | Mound Upper Level | Mound Walkway -2
Architectural works |  | 79 | 2023-03-29 | 2023-07-03
C-PW-111380 | Mound M5B - Mound Roof Precast / GRC Cladding works | 26 | 2023-03-29 | 2023-04-30 | 01 | 04 | 02 | 34 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M5B | Mound Upper Level | Mound Internal
C-PW-111390 | Mound M5B - Architectural works | 53 | 2023-05-01 | 2023-07-03 | 01 | 04 | 02 | 34 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M5B | Mound Upper Level | Mound Internal
MEP works |  | 55 | 2023-04-05 | 2023-06-10
C-PW-111400 | Mound M5B - MEP works | 55 | 2023-04-05 | 2023-06-10 | 01 | 14 | 02 | 34 | 013 | 09 |  | Building | General MEP | Mound Works | Zone M5B | Mound Upper Level | Mound Internal
Zone M6B |  | 319 | 2022-05-25 | 2023-06-11
Internal / Upper Level |  | 319 | 2022-05-25 | 2023-06-11
Civil works |  | 226 | 2022-05-25 | 2023-02-20
C-PW-111410 | Mound M6B - Construction of Mound Columns | 20 | 2022-05-25 | 2022-06-16 | 01 | 01 | 02 | 35 | 013 | 09 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Internal
C-PW-111420 | Mound M6B - Structural Steel Framing works | 136 | 2022-09-12 | 2023-02-20 | 01 | 01 | 02 | 35 | 013 | 09 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Internal
Walkway |  | 140 | 2022-06-18 | 2022-12-04
C-OW-111430 | Mound M6B - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-18 | 2022-07-02 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111440 | Mound M6B - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-06-26 | 2022-07-13 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111450 | Mound M6B - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-04 | 2022-07-21 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111460 | Mound M6B - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-16 | 2022-07-31 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111470 | Mound M6B - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-24 | 2022-08-08 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111480 | Mound M6B - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-14 | 2022-08-09 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111490 | Mound M6B - Part 01-06, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-02 | 2022-08-16 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111500 | Mound M6B - Part 01-07, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-10 | 2022-08-24 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111510 | Mound M6B - Part 01-08, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-18 | 2022-09-01 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111520 | Mound M6B - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-09 | 2022-09-03 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111530 | Mound M6B - Part 01-09, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-27 | 2022-09-10 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111540 | Mound M6B - Part 01-10, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-09-04 | 2022-09-18 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111550 | Mound M6B - Part 01-11, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-09-12 | 2022-09-26 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111560 | Mound M6B - Part 02-05, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-03 | 2022-09-27 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111570 | Mound M6B - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-04 | 2022-09-28 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111580 | Mound M6B - Part 01-12, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-09-20 | 2022-10-12 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111590 | Mound M6B - Part 02-07, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-19 | 2022-10-15 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111600 | Mound M6B - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-28 | 2022-10-24 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111610 | Mound M6B - Part 02-09, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-10-13 | 2022-11-07 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111620 | Mound M6B - Part 02-06, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-10-16 | 2022-11-09 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111630 | Mound M6B - Part 02-08, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-11-08 | 2022-12-04 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111640 | Mound M6B - Part 02-10, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-11-08 | 2022-12-04 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
C-OW-111650 | Completion of M6B Walkway | 0 |  | 2022-12-04 | 01 | 01 | 02 | 35 | 013 | 06 |  | Building | Civil | Mound Works | Zone M6B | Mound Upper Level | Mound Walkway -1
Architectural works |  | 93 | 2023-02-21 | 2023-06-11
C-PW-111660 | Mound M6B - Mound Roof Precast / GRC Cladding works | 39 | 2023-02-21 | 2023-04-06 | 01 | 04 | 02 | 35 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M6B | Mound Upper Level | Mound Internal
C-PW-111670 | Mound M6B - Architectural works | 40 | 2023-04-26 | 2023-06-11 | 01 | 04 | 02 | 35 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M6B | Mound Upper Level | Mound Internal
MEP works |  | 69 | 2023-02-28 | 2023-05-21
C-PW-111680 | Mound M6B - MEP works | 69 | 2023-02-28 | 2023-05-21 | 01 | 14 | 02 | 35 | 013 | 09 |  | Building | General MEP | Mound Works | Zone M6B | Mound Upper Level | Mound Internal
Zone M7B |  | 232 | 2022-05-29 | 2023-03-02
Internal / Upper Level |  | 232 | 2022-05-29 | 2023-03-02
Civil works |  | 149 | 2022-05-29 | 2022-11-23
C-PW-111690 | Mound M7B - Construction of Mound Columns | 13 | 2022-05-29 | 2022-06-12 | 01 | 01 | 02 | 36 | 013 | 09 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Internal
C-PW-111700 | Mound M7B - Structural Steel Framing works | 25 | 2022-10-26 | 2022-11-23 | 01 | 01 | 02 | 36 | 013 | 09 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Internal
Walkway |  | 111 | 2022-06-13 | 2022-10-25
C-OW-111710 | Mound M7B - Part 01-01, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 19 | 2022-06-13 | 2022-07-04 | 01 | 01 | 02 | 36 | 013 | 06 | 01- | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111720 | Mound M7B - Part 01-02, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-05 | 2022-07-23 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111730 | Mound M7B - Part 01-03, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-17 | 2022-08-01 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111740 | Mound M7B - Part 01-04, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-07-25 | 2022-08-09 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111750 | Mound M7B - Part 01-05, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-03 | 2022-08-17 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111760 | Mound M7B - Part 02-01, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-07-24 | 2022-08-18 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111770 | Mound M7B - Part 01-06, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-11 | 2022-08-25 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111780 | Mound M7B - Part 01-07, Construction of Walkway columns, Beams , Slabs & Bottom Rib | 13 | 2022-08-20 | 2022-09-03 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111790 | Mound M7B - Part 02-03, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-10 | 2022-09-04 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111800 | Mound M7B - Part 02-05, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-08-27 | 2022-09-20 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111810 | Mound M7B - Part 02-07, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-04 | 2022-09-28 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111820 | Mound M7B - Part 02-02, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-05 | 2022-09-29 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111830 | Mound M7B - Part 02-04, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-21 | 2022-10-17 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111840 | Mound M7B - Part 02-06, Construction of Walkway Wall, Top Rib & Soffit | 22 | 2022-09-29 | 2022-10-25 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
C-OW-111850 | Completion of M7B Walkway | 0 |  | 2022-10-25 | 01 | 01 | 02 | 36 | 013 | 06 |  | Building | Civil | Mound Works | Zone M7B | Mound Upper Level | Mound Walkway -1
Architectural works |  | 83 | 2022-11-24 | 2023-03-02
C-PW-111860 | Mound M7B - Mound Roof Precast / GRC Cladding works | 30 | 2022-11-24 | 2022-12-29 | 01 | 04 | 02 | 36 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M7B | Mound Upper Level | Mound Internal
C-PW-111870 | Mound M7B - Architectural works | 30 | 2023-01-28 | 2023-03-02 | 01 | 04 | 02 | 36 | 013 | 09 |  | Building | Architecture | Mound Works | Zone M7B | Mound Upper Level | Mound Internal
MEP works |  | 59 | 2022-12-03 | 2023-02-09
C-PW-111880 | Mound M7B - MEP works | 59 | 2022-12-03 | 2023-02-09 | 01 | 14 | 02 | 36 | 013 | 09 |  | Building | General MEP | Mound Works | Zone M7B | Mound Upper Level | Mound Internal
VIP Canopy & Courtyard |  | 206 | 2022-10-26 | 2023-06-27
Internal / Upper Level |  | 206 | 2022-10-26 | 2023-06-27
Civil works |  | 55 | 2022-10-26 | 2022-12-29
C-PW-111890 | Mound VIP Canopy & Courtyard - Construction of Mound Columns | 12 | 2022-10-26 | 2022-11-08 | 01 | 01 | 02 | 37 | 013 | 09 |  | Building | Civil | Mound Works | VIP Canopy & Courtyard | Mound Upper Level | Mound Internal
C-PW-111900 | Mound VIP Canopy & Courtyard - Structural Steel Framing works | 30 | 2022-11-24 | 2022-12-29 | 01 | 01 | 02 | 37 | 013 | 09 |  | Building | Civil | Mound Works | VIP Canopy & Courtyard | Mound Upper Level | Mound Internal
Architectural works |  | 151 | 2022-12-31 | 2023-06-27
C-PW-111910 | Mound VIP Canopy & Courtyard - Mound Roof Precast / GRC Cladding works | 121 | 2022-12-31 | 2023-05-23 | 01 | 04 | 02 | 37 | 013 | 09 |  | Building | Architecture | Mound Works | VIP Canopy & Courtyard | Mound Upper Level | Mound Internal
C-PW-111920 | Mound VIP Canopy & Courtyard - Architectural works | 91 | 2023-03-12 | 2023-06-27 | 01 | 04 | 02 | 37 | 013 | 09 |  | Building | Architecture | Mound Works | VIP Canopy & Courtyard | Mound Upper Level | Mound Internal
MEP works |  | 127 | 2023-01-08 | 2023-06-06
C-PW-111930 | Mound VIP Canopy & Courtyard - MEP works | 127 | 2023-01-08 | 2023-06-06 | 01 | 14 | 02 | 37 | 013 | 09 |  | Building | General MEP | Mound Works | VIP Canopy & Courtyard | Mound Upper Level | Mound Internal
Leaveout Tower Crane Area |  | 140 | 2023-02-27 | 2023-08-14
Tower Crane 10 (Zone M1A) |  | 54 | 2023-06-08 | 2023-08-13
Civil works |  | 40 | 2023-06-08 | 2023-07-27
C-PW-111940 | Mound Structure | 27 | 2023-06-08 | 2023-07-11 | 01 | 01 | 02 | 21 | 012 | 30 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Civil SubZones
C-PW-111950 | Mound Steel | 13 | 2023-07-12 | 2023-07-27 | 01 | 01 | 02 | 21 | 012 | 30 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Civil SubZones
Architectural works |  | 14 | 2023-07-29 | 2023-08-13
C-PW-111960 | GRC Cladding works | 8 | 2023-07-29 | 2023-08-06 | 01 | 04 | 02 | 21 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M1A | Mound Lower Level | Architectural SubZones
C-PW-111970 | Architectural works | 6 | 2023-08-07 | 2023-08-13 | 01 | 04 | 02 | 21 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M1A | Mound Lower Level | Architectural SubZones
MEP works |  | 6 | 2023-07-31 | 2023-08-06
C-PW-111980 | MEP works | 6 | 2023-07-31 | 2023-08-06 | 01 | 14 | 02 | 21 | 012 | 70 |  | Building | General MEP | Mound Works | Zone M1A | Mound Lower Level | MEP SubZones
Tower Crane 11/12 (Zone M1A) |  | 55 | 2023-06-08 | 2023-08-14
Civil works |  | 39 | 2023-06-08 | 2023-07-26
C-PW-111990 | Mound Structure | 25 | 2023-06-08 | 2023-07-09 | 01 | 01 | 02 | 21 | 012 | 30 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Civil SubZones
C-PW-112000 | Mound Steel | 14 | 2023-07-10 | 2023-07-26 | 01 | 01 | 02 | 21 | 012 | 30 |  | Building | Civil | Mound Works | Zone M1A | Mound Lower Level | Civil SubZones
Architectural works |  | 16 | 2023-07-27 | 2023-08-14
C-PW-112010 | GRC Cladding works | 10 | 2023-07-27 | 2023-08-07 | 01 | 04 | 02 | 21 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M1A | Mound Lower Level | Architectural SubZones
C-PW-112020 | Architectural works | 6 | 2023-08-08 | 2023-08-14 | 01 | 04 | 02 | 21 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M1A | Mound Lower Level | Architectural SubZones
MEP works |  | 8 | 2023-07-30 | 2023-08-07
C-PW-112030 | MEP works | 8 | 2023-07-30 | 2023-08-07 | 01 | 14 | 02 | 21 | 012 | 70 |  | Building | General MEP | Mound Works | Zone M1A | Mound Lower Level | MEP SubZones
Tower Crane 13 (Zone M2A) |  | 60 | 2023-05-25 | 2023-08-06
Civil works |  | 44 | 2023-05-25 | 2023-07-17
C-PW-112040 | Mound Structure | 22 | 2023-05-25 | 2023-06-19 | 01 | 14 | 02 | 22 | 012 | 30 |  | Building | General MEP | Mound Works | Zone M2A | Mound Lower Level | Civil SubZones
C-PW-112050 | Mound Steel | 22 | 2023-06-20 | 2023-07-17 | 01 | 14 | 02 | 22 | 012 | 30 |  | Building | General MEP | Mound Works | Zone M2A | Mound Lower Level | Civil SubZones
Architectural works |  | 16 | 2023-07-18 | 2023-08-06
C-PW-112060 | GRC Cladding works | 8 | 2023-07-18 | 2023-07-27 | 01 | 04 | 02 | 22 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M2A | Mound Lower Level | Architectural SubZones
C-PW-112070 | Architectural works | 8 | 2023-07-29 | 2023-08-06 | 01 | 04 | 02 | 22 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M2A | Mound Lower Level | Architectural SubZones
MEP works |  | 8 | 2023-07-22 | 2023-07-30
C-PW-112080 | MEP works | 8 | 2023-07-22 | 2023-07-30 | 01 | 14 | 02 | 22 | 012 | 70 |  | Building | General MEP | Mound Works | Zone M2A | Mound Lower Level | MEP SubZones
Tower Crane 14 (Zone M3A) |  | 81 | 2023-02-27 | 2023-06-03
Civil works |  | 43 | 2023-02-27 | 2023-04-17
C-PW-112090 | Mound Structure | 28 | 2023-02-27 | 2023-03-30 | 01 | 01 | 02 | 23 | 012 | 30 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Civil SubZones
C-PW-112100 | Mound Steel | 15 | 2023-04-01 | 2023-04-17 | 01 | 01 | 02 | 23 | 012 | 30 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Civil SubZones
Architectural works |  | 38 | 2023-04-18 | 2023-06-03
C-PW-112110 | GRC Cladding works | 26 | 2023-04-18 | 2023-05-20 | 01 | 04 | 02 | 23 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M3A | Mound Lower Level | Architectural SubZones
C-PW-112120 | Architectural works | 12 | 2023-05-21 | 2023-06-03 | 01 | 04 | 02 | 23 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M3A | Mound Lower Level | Architectural SubZones
MEP works |  | 8 | 2023-04-27 | 2023-05-06
C-PW-112130 | MEP works | 8 | 2023-04-27 | 2023-05-06 | 01 | 14 | 02 | 23 | 012 | 70 |  | Building | General MEP | Mound Works | Zone M3A | Mound Lower Level | MEP SubZones
Tower Crane 15 (Zone M4A) |  | 81 | 2023-05-09 | 2023-08-14
Civil works |  | 43 | 2023-05-09 | 2023-06-27
C-PW-114570 | Mound Structure | 28 | 2023-05-09 | 2023-06-10 | 01 | 01 | 02 | 23 | 012 | 30 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Civil SubZones
C-PW-114610 | Mound Steel | 15 | 2023-06-11 | 2023-06-27 | 01 | 01 | 02 | 23 | 012 | 30 |  | Building | Civil | Mound Works | Zone M3A | Mound Lower Level | Civil SubZones
Architectural works |  | 38 | 2023-07-01 | 2023-08-14
C-PW-114590 | GRC Cladding works | 26 | 2023-07-01 | 2023-07-31 | 01 | 04 | 02 | 23 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M3A | Mound Lower Level | Architectural SubZones
C-PW-114580 | Architectural works | 12 | 2023-08-01 | 2023-08-14 | 01 | 04 | 02 | 23 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M3A | Mound Lower Level | Architectural SubZones
MEP works |  | 8 | 2023-07-08 | 2023-07-16
C-PW-114600 | MEP works | 8 | 2023-07-08 | 2023-07-16 | 01 | 14 | 02 | 23 | 012 | 70 |  | Building | General MEP | Mound Works | Zone M3A | Mound Lower Level | MEP SubZones
Tower Crane 16 (Zone M5A) |  | 50 | 2023-05-09 | 2023-07-08
Civil works |  | 32 | 2023-05-09 | 2023-06-14
C-PW-112140 | Mound Structure | 26 | 2023-05-09 | 2023-06-07 | 01 | 01 | 02 | 25 | 012 | 30 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Civil SubZones
C-PW-112150 | Mound Steel | 6 | 2023-06-08 | 2023-06-14 | 01 | 01 | 02 | 25 | 012 | 30 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Civil SubZones
Architectural works |  | 18 | 2023-06-15 | 2023-07-08
C-PW-112160 | GRC Cladding works | 7 | 2023-06-15 | 2023-06-22 | 01 | 04 | 02 | 25 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M5A | Mound Lower Level | Architectural SubZones
C-PW-112170 | Architectural works | 6 | 2023-07-02 | 2023-07-08 | 01 | 04 | 02 | 25 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M5A | Mound Lower Level | Architectural SubZones
MEP works |  | 6 | 2023-06-22 | 2023-07-01
C-PW-112180 | MEP works | 6 | 2023-06-22 | 2023-07-01 | 01 | 14 | 02 | 25 | 012 | 70 |  | Building | General MEP | Mound Works | Zone M5A | Mound Lower Level | MEP SubZones
Tower Crane 17 (Zone M5A) |  | 77 | 2023-05-09 | 2023-08-09
Civil works |  | 44 | 2023-05-09 | 2023-07-01
C-PW-112190 | Mound Structure | 26 | 2023-05-09 | 2023-06-07 | 01 | 01 | 02 | 25 | 012 | 30 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Civil SubZones
C-PW-112200 | Mound Steel | 18 | 2023-06-08 | 2023-07-01 | 01 | 01 | 02 | 25 | 012 | 30 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Civil SubZones
Architectural works |  | 33 | 2023-07-02 | 2023-08-09
C-PW-112210 | GRC Cladding works | 24 | 2023-07-02 | 2023-07-30 | 01 | 04 | 02 | 25 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M5A | Mound Lower Level | Architectural SubZones
C-PW-112220 | Architectural works | 9 | 2023-07-31 | 2023-08-09 | 01 | 04 | 02 | 25 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M5A | Mound Lower Level | Architectural SubZones
MEP works |  | 14 | 2023-07-09 | 2023-07-25
C-PW-112230 | MEP works | 14 | 2023-07-09 | 2023-07-25 | 01 | 14 | 02 | 25 | 012 | 70 |  | Building | General MEP | Mound Works | Zone M5A | Mound Lower Level | MEP SubZones
Tower Crane 18 (Zone M6A) |  | 77 | 2023-05-09 | 2023-08-09
Civil works |  | 44 | 2023-05-09 | 2023-07-01
C-PW-114620 | Mound Structure | 26 | 2023-05-09 | 2023-06-07 | 01 | 01 | 02 | 25 | 012 | 30 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Civil SubZones
C-PW-114660 | Mound Steel | 18 | 2023-06-08 | 2023-07-01 | 01 | 01 | 02 | 25 | 012 | 30 |  | Building | Civil | Mound Works | Zone M5A | Mound Lower Level | Civil SubZones
Architectural works |  | 33 | 2023-07-02 | 2023-08-09
C-PW-114640 | GRC Cladding works | 24 | 2023-07-02 | 2023-07-30 | 01 | 04 | 02 | 25 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M5A | Mound Lower Level | Architectural SubZones
C-PW-114630 | Architectural works | 9 | 2023-07-31 | 2023-08-09 | 01 | 04 | 02 | 25 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M5A | Mound Lower Level | Architectural SubZones
MEP works |  | 14 | 2023-07-09 | 2023-07-25
C-PW-114650 | MEP works | 14 | 2023-07-09 | 2023-07-25 | 01 | 14 | 02 | 25 | 012 | 70 |  | Building | General MEP | Mound Works | Zone M5A | Mound Lower Level | MEP SubZones
Tower Crane 19 |  | 67 | 2023-04-16 | 2023-07-06
Civil works |  | 42 | 2023-04-16 | 2023-06-05
C-PW-112240 | Mound Structure | 28 | 2023-04-16 | 2023-05-20 | 01 | 01 | 02 | 26 | 012 | 30 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Civil SubZones
C-PW-112250 | Mound Steel | 14 | 2023-05-21 | 2023-06-05 | 01 | 01 | 02 | 26 | 012 | 30 |  | Building | Civil | Mound Works | Zone M6A | Mound Lower Level | Civil SubZones
Architectural works |  | 25 | 2023-06-06 | 2023-07-06
C-PW-112260 | GRC Cladding works | 17 | 2023-06-06 | 2023-06-25 | 01 | 04 | 02 | 26 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M6A | Mound Lower Level | Architectural SubZones
C-PW-112270 | Architectural works | 7 | 2023-06-27 | 2023-07-06 | 01 | 04 | 02 | 26 | 012 | 50 |  | Building | Architecture | Mound Works | Zone M6A | Mound Lower Level | Architectural SubZones
MEP works |  | 12 | 2023-06-13 | 2023-06-26
C-PW-112280 | MEP works | 12 | 2023-06-13 | 2023-06-26 | 01 | 14 | 02 | 26 | 012 | 70 |  | Building | General MEP | Mound Works | Zone M6A | Mound Lower Level | MEP SubZones
Time Line Garden
TIMELINE GARDEN
TIME LINE GARDEN PHASE 1
URBAN AREA
EARTH FILLING & COMPACTION
ROUGH GRADING
C-TL-C-LS-URB-79455 | Earth Fill & Compaction (Grid AL - BD) till GL |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
UTILITY NETWORK - PHASE 1
SEWAGE NETWORK
EXTERNAL CONNECTION NETWORK 2
C-TL-C-UTI-URB-79160 | Excavation for Sewage Trench & Manhole |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79165 | Construct Manhole & Inspection (5 Manholes) & Preparation of Pipe Laying |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79175 | Sewage Pipe laying & Jointing 200mm dia |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79180 | Testing |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79185 | Backfilling for Sewage line & Manhole cover installation |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
STORM WATER NETWORK
EXTERNAL CONNECTION NETWORK 3
MANHOLES
C-TL-C-UTI-URB-79205 | Excavation for Stormwater Manhole |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79210 | Construct Stormwater Manhole (3 Manholes) |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79215 | Storm water Manhole Pipe laying & Jointing (200-600mm dia) |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79220 | Testing |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79225 | Backfilling for Stormwater lines & Manhole cover installation |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
SLOT DRAINS
C-TL-C-UTI-URB-79235 | Excavate for Slot drain & Connection Chambers |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79240 | Construct Slot drain & Connection Chambers |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79245 | Storm water Slot Pipe laying & Jointing (200-600mm dia) |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79250 | Testing |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
SWALES & SOAKAWAYS
C-TL-C-UTI-URB-79260 | Excavation for Swales & Soakaways (Aft Ramp Construction) |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
ZNM.CON.UR.SW.195 | Pipe laying UPVC dia.225 Pipe -Burried Concrete Surrounded - 3 way |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
ZNM.CON.UR.SW.205 | Pipe laying,Jointing (dia. 315 uPVC & dia. 110 uPVC) |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79265 | Construct Swales with Soakaways Zone 1 |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79270 | Construct Swales with Soakaways in Zone 2 |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79275 | Testing for Swales & Soakaways |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
POTABLE WATER
C-TL-C-UTI-URB-79285 | Excavation for Water Supply line |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79290 | Construct Valves, Chambers & Connections |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79300 | Testing Water Supply lines |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79295 | Water Supply pipe laying & Joints (25-110 mm dia) |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79305 | Backfilling |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
FIRE FIGHTING
C-TL-C-UTI-URB-79345 | Excavation for Firefighting line |  |  |  | 01 | 09 | 03 | 38 | 014 | 11 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79350 | Construct Valves, Chambers & Connections |  |  |  | 01 | 09 | 03 | 38 | 014 | 11 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-FF-79355 | Firefighting pipe laying & Joints (180 mm dia) |  |  |  | 01 | 09 | 03 | 38 | 014 | 11 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-FF-79360 | Testing of Firefighting lines |  |  |  | 01 | 09 | 03 | 38 | 014 | 11 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-FF-79370 | Install Fire Hydrants |  |  |  | 01 | 09 | 03 | 38 | 014 | 11 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79365 | Backfilling |  |  |  | 01 | 09 | 03 | 38 | 014 | 11 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
ELECTRICAL LV CABLE & LIGHTING
C-TL-C-UTI-URB-79380 | Excavation for Cable trench & Pull boxes |  |  |  | 01 | 07 | 03 | 38 | 014 | 11 |  | Building | Electrical | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79385 | Construct ducts for Landscape Lighting |  |  |  | 01 | 07 | 03 | 38 | 014 | 11 |  | Building | Electrical | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-EL-79390 | Install Containment for Cables & Cable Laying |  |  |  | 01 | 07 | 03 | 38 | 014 | 11 |  | Building | Electrical | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79395 | Cover Tiles and Backfilling for Ducts/Containments |  |  |  | 01 | 07 | 03 | 38 | 014 | 11 |  | Building | Electrical | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
TELECOMMUNICATION & SECURITY SYSTEMS
C-TL-C-UTI-URB-79405 | Excavation for Ducts,Chambers & Pull Box |  |  |  | 01 | 10 | 03 | 38 | 014 | 11 |  | Building | CCTV | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-ELV-79415 | Laying of Telecom & CCTV Network |  |  |  | 01 | 10 | 03 | 38 | 014 | 11 |  | Building | CCTV | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79410 | Construct Ducts, JRC, Chamber, & Pull Box |  |  |  | 01 | 10 | 03 | 38 | 014 | 11 |  | Building | CCTV | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79420 | Backfilling for Ducts/Encasements |  |  |  | 01 | 10 | 03 | 38 | 014 | 11 |  | Building | CCTV | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
STREET LIGHTING & CCTV
C-TL-C-UTI-URB-79430 | Excavation for Foundation |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79435 | Light Poles/ CCTV Poles Foundation |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79440 | Backfilling for Foundation |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
BIKE STORAGE
STRUCTURAL WORKS
C-TL-C-ST-URB-79470 | Excavation & Formation for foundation for Bike Shed |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79475 | Foundation for Bike Shed |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79480 | Construction of Concrete Walls |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79485 | Construction of Roof Slab |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79490 | Construction of Upstand |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
FINISHES
C-TL-C-AR-URB-79500 | General Block work |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-AR-URB-79505 | Marking, Cutting & Chasing Walls for MEP Services |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-AR-URB-79510 | Plaster |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-AR-URB-79515 | Wall Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-AR-URB-79520 | External Wall Cladding/Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-AR-URB-79525 | Ceiling Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-AR-URB-79530 | Floor Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-AR-URB-79535 | Installation of Doors, Iron Mongeries etc |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-AR-URB-79540 | Final Finishes & Fixtures |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
MEP WORKS
C-TL-C-MP-79550 | MEP 1st fix works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-79555 | MEP 2nd Fix Works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-79560 | MEP final fix works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
TESTING & CLOSEOUT
C-TL-C-CL-URB-79570 | Testing and Pre-commissioning |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-CL-URB-79575 | Snagging & De-snagging Works |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
TOILETS & PLANT ROOMS ON PLAZA
STRUCTURAL WORKS
C-TL-C-ST-URB-79590 | Excavation & Formation for foundation for Plaza Toilets |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79595 | Foundation for Plaza Toilets |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79600 | Construction of Concrete Walls |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79605 | Construction of Roof Slab |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79610 | Construction of Upstand |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
FINISHES
C-TL-C-FN-URB-79620 | General Block work |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79625 | Marking, Cutting & Chasing Walls for MEP Services |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79630 | Plaster |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79640 | Wall Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79635 | Ceiling Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79650 | Floor Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79645 | External Wall Cladding/Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79655 | Installation of Doors, Iron Mongeries etc |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79660 | Install Sanitary wares, vanity counters, Cupboards etc |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79665 | Final Finishes & Fixtures |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
MEP WORKS
C-TL-C-MP-79675 | MEP 1st fix works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-79680 | MEP 2nd Fix Works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-79685 | MEP final fix works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
TESTING & CLOSEOUT
C-TL-C-CL-URB-79695 | Testing and Pre-commissioning |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-CL-URB-79700 | Snagging & De-snagging Works |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
TLG MAINTENANCE YARD
STRUCTURAL WORKS
C-TL-C-ST-URB-79715 | Excavation & Formation for foundation for Maintenance Yard |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79720 | Foundation for Maintenance Yard |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79725 | Construction of Concrete Walls |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79730 | Construction of Roof Slab |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79735 | Construction of Upstand |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
FINISHES
C-TL-C-FN-URB-79745 | General Block work |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79750 | Marking, Cutting & Chasing Walls for MEP Services |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79755 | Plaster |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79760 | Wall Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79765 | Ceiling Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79770 | External Wall Cladding/Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79775 | Floor Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79780 | Installation of Doors, Iron Mongeries etc |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79785 | Final Finishes & Fixtures |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
MEP WORKS
C-TL-C-MP-79795 | MEP 1st fix works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-79800 | MEP 2nd Fix Works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-79805 | MEP final fix works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
TESTING & CLOSEOUT
C-TL-C-CL-URB-79815 | Testing and Pre-commissioning |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-CL-URB-79820 | Snagging & De-snagging Works |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
KIOSK1
STRUCTURAL WORKS
C-TL-C-ST-URB-79835 | Excavation & Formation for foundation for Kiosk1 |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79840 | Foundation for Kiosk1 |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79845 | Construction of Concrete Walls |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79850 | Construction of Roof Slab |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79855 | Construction of Upstand |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
FINISHES
C-TL-C-FN-URB-79865 | General Block work |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79870 | Marking, Cutting & Chasing Walls for MEP Services |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79875 | Plaster |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79880 | Ceiling Finishes (by Others) |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79885 | Wall Finishes (by Others) |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79890 | Floor Finishes (by Others) |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79900 | Installation of Doors, Iron Mongeries etc |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79895 | External Wall Cladding/Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79905 | Final Finishes & Fixtures |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
MEP WORKS
C-TL-C-MP-79915 | MEP 1st fix works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-79920 | MEP 2nd Fix Works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-79925 | MEP final fix works |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
TESTING & CLOSEOUT
C-TL-C-CL-URB-79935 | Testing and Pre-commissioning |  |  |  | 01 | 14 | 03 | 38 | 014 | 11 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-CL-URB-79940 | Snagging & De-snagging Works |  |  |  | 01 | 04 | 03 | 38 | 014 | 11 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
RETAINING STRUCTURES
C-TL-C-LS-URB-80015 | Construct Gabion Retaining Walls TL Garden (Grid AH - BD) - Stage 1 |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800120 | Construct Gabion Retaining Walls TL Garden (Grid AH - BD) - Stage 2 |  |  |  | 01 | 01 | 03 | 38 | 014 | 11 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
EARTH WORKS
C-TL-C-LS-URB-80020 | Filling to create contours (Granular Material) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80025 | Filling to create contours (EPS Polystyrene Blocks) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800480 | Rammed Earth |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800500 | Rammed Earth Final Finish |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
LANDSCAPE- FEATURES
C-TL-C-LS-URB-800100 | Construction of Jabel Hafit mountain model- 1st |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800490 | Base build works - Exhibition Fitout Works |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800105 | Construction of Jabel Hafit mountain model- 2nd |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800110 | Construction of Jabel Hafit mountain model- 3rd |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
IRRIGATION SYSTEM
MAIN LINE
C-TL-C-UTI-URB-79315 | Excavation for Irrigation line |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79320 | Construct Valves, Chambers & Connections |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79325 | Irrigation pipe laying & Joints (25&75 mm dia) |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79330 | Testing Irrigation lines |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-UTI-URB-79335 | Backfilling |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
LATERAL LINE
C-TL-C-FN-URB-82555 | Excavation |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-82560 | Laying of Pipes & Testing |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-82565 | Backfilling |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
DRIP LINE
C-TL-C-FN-URB-82570 | Laying of Driplines for Shrubs & Ground Cover |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-82575 | Laying of Driplines for Trees & Palms |  |  |  | 01 | 12 | 03 | 38 | 014 | 11 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
HARD LANDSCAPE
PLANTER BOXES/TREE PITS/WALLS
C-TL-C-LS-URB-79995 | Excavate for Planter box,Tree Pits & Flag Pole Foundation in (Grid AH - BD) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80000 | Preparation, Anti-termite & blinding for Planter box,Tree Pits & Flag Pole Foundation in (Grid AH - BD) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80005 | Construct Planter box,Tree Pits & Flag Pole Foundation & Drainage Pipes in (Grid AH - BD) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800140 | Geotextile & Gravel |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800130 | Tree Anchoring System |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800150 | Filling of Sweet Soil |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800160 | Stone Surrounds to Planters - EXT301 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800170 | Stone Surrounds to Planters - EXT510 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
PIAZZA WATER FEATURE
C-TL-C-ST-URB-79955 | Excavate & Prepare Surface for Piazza Water Feature |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-81520 | W/P Membrane |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-PD-79960 | Underground MEP services |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79965 | Concrete works & Pedestals for WF structure |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-ST-URB-79975 | Mortar Bed (25mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79970 | Stone Paving & Floor Finishes under ATC SoW |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-FN-URB-79975 | Architectural & MEP Fixes |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-C-URB-79980 | Inspection & Testing |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
STONE PAVING
C-TL-C-LS-URB-800180 | Preparation for Stone Paving |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800190 | SubBase |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800200 | Concrete Edging |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800210 | Omani Limestone - EXT361 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
RESIN BOUND GRAVEL - EXT307
C-TL-C-LS-URB-800220 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800230 | Compacted hardcore Subbase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800240 | Compacted Granular Subbase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800260 | Concrete Edging |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800270 | Asphalt Concrete (Bituminous Macadam) (60mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800250 | Resin Bound Gravel - RBG (16mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
RESIN BOUND GRAVEL - EXT308
C-TL-C-LS-URB-800280 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800290 | Compacted hardcore Subbase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800300 | Compacted Granular Subbase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800310 | Concrete Edging |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800320 | Asphalt Concrete (Bituminous Macadam) (60mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800330 | Resin Bound Gravel - RBG (16mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
CONCRETE BEDS AND FALAJ AREAS
C-TL-C-LS-URB-80035 | Earthworks for Landscaping Zones |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80040 | Preparation, Anti Termite, Blinding & WP for Concrete beds |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80045 | Construct Concrete beds for Landscaping Zones |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800340 | Omani Limestone - EXT952 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800350 | Omani Limestone - EXT951 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800360 | Omani Limestone - EXT931 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
SWALES AREA
C-TL-C-LS-URB-800510 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800520 | Compacted Hard core Subbase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800530 | Concrete Base |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800540 | Rounded river rock- EXT318 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
ANGULAR GRAVEL -EXT319
C-TL-C-LS-URB-800370 | Preparation for Stone Paving |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800380 | SubBase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800390 | Concrete Edging |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800400 | Angular Gravel - EXT319 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
STONE SEATS AND STEPS
C-TL-C-LS-URB-80055 | Preparation for Stone works |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80060 | Mortar Bed |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800410 | Omani Limestone Steps -EXT330 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80065 | Stone Seats -EXT301 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80070 | Stone Seating Benches -EXT510 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
OTHER FLOOR FINISHES
C-TL-C-LS-URB-800420 | Subbase for HF1 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800430 | Tarmac Finish HF1 |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
SOFT LANDSCAPE
LOCAL
C-TL-C-LS-URB-80130 | Unbound Soil in Planting area |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800440 | Trees & Palms Planting |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80140 | Shrubs, Plants, Ground cover Landscape works |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
INHOUSE
C-TL-C-LS-URB-800460 | Unbound Soil in Planting area |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800470 | Shrubs, Plants, Ground cover Landscape works |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
OVERSEAS
C-TL-C-LS-URB-80135 | Unbound Soil in Planting area |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-800450 | Trees & Palms Planting |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80145 | Shrubs, Plants, Ground cover Landscape works |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
HYDROPHONICS
C-TL-C-LS-URB-80155 | Hydroponics Shade Works |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80160 | Hydroponics planting works (PS) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
ACCESS ROUTES
MAINTENANCE AREA
C-TL-C-LS-URB-80085 | Roadway for Maintenance Yard |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
PEDESTRIAN ROUTES
C-TL-C-LS-URB-80095 | Asphalt Concrete Sub-base for Pedestrian Routes |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
DROP OFF AREAS ( P S )
C-TL-C-LS-URB-80105 | Drop Off Areas EarthWork |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80110 | Drop Off Area Asphalt Works |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80115 | Drop Off Area Landscaping Works |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
ACCESSORIES & FURNISHINGS
LIGHT POLE, FLAG, PLAY GROUND & OTHER FURNISHINGS
C-TL-C-MP-EL-80175 | Flag Pole,Light Pole/CCTV Poles installation |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-MP-ELV-80180 | Street Lights & CCTV work |  |  |  | 01 | 07 | 03 | 38 | 014 | 11 |  | Building | Electrical | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
C-TL-C-LS-URB-80185 | Accessories, Play Ground Equipment, Canopy & Furnitures |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
EXHIBITION SCHEME WORKS ( P S )
C-TL-C-LS-URB-80195 | Urban Area Exhibition Scheme Works (P.S) |  |  |  | 01 | 11 | 03 | 38 | 014 | 11 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Urban Area
OASIS AREA
EARTH FILLING & COMPACTION
ROUGH GRADING
C-TL-C-LS-OAS-80415 | Earth Fill & Compaction (Grid BD - BZ) till GL |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
UTILITY WORKS - PHASE 1
SEWERAGE NETWORK
ZNM.CON.OA.SE.215 | Excavation for Sewage Trench & Manhole |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SE.235 | Preparation for Pipe Laying |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SE.225 | Construct Manhole (1 Manhole) |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SE.245 | Pipe laying & Jointing (dia. 150 uPVC) |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SE.255 | Testing of Pipeline & Inspection Approval |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SE.265 | Backfilling for Sewage line & Manhole cover installation |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SE.275 | Connection with Existing Manhole |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SE.285 | Tie in connection to Building Sewer Line |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
STORM WATER NETWORK
SWALES & SOAKAWAYS
C-TL-C-UTI-OAS-80220 | Excavation for Swales & Soakaways (Aft Ramp Construction) |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SW.30 | Pipe laying UPVC dia.225 Pipe -Burried Concrete Surrounded - 3 way |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SW.25 | Construction of Inlet Chambers and Connections |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80225 | Construct Swales with Soakaways Zone 1 |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80230 | Construct Swales with Soakaways in Zone 2 |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80235 | Testing for Swales & Soakaways |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ACO DRAIN
ZNM.CON.OA.SW.155 | Excavation for Channel drain type 3 - ACO |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SW.165 | Construction of Channel drain type 3 - ACO |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SW.175 | Construction of Connection Chambers |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ZNM.CON.OA.SW.185 | Roof Drain connection from Building |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
POTABLE WATER
C-TL-C-UTI-OAS-80245 | Excavation for Water Supply line |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80250 | Construct Valves, Chambers & Connections |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-PD-80255 | Water Supply pipe laying & Joints (25-110 mm dia) |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-PD-80260 | Testing Water Supply lines |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80265 | Backfilling |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
FIRE FIGHTING
C-TL-C-UTI-OAS-80305 | Excavation for Firefighting line |  |  |  | 01 | 09 | 03 | 38 | 014 | 12 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80310 | Construct Valves, Chambers & Connections |  |  |  | 01 | 09 | 03 | 38 | 014 | 12 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-FF-80320 | Testing of Firefighting lines |  |  |  | 01 | 09 | 03 | 38 | 014 | 12 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-FF-80315 | Firefighting pipe laying & Joints (180 mm dia) |  |  |  | 01 | 09 | 03 | 38 | 014 | 12 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-FF-80330 | Install Fire Hydrants |  |  |  | 01 | 09 | 03 | 38 | 014 | 12 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80325 | Backfilling |  |  |  | 01 | 09 | 03 | 38 | 014 | 12 |  | Building | Firefighting | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ELECTRICAL LV CABLE & LIGHTING
C-TL-C-UTI-OAS-80340 | Excavation for Cable trench & Pull boxes |  |  |  | 01 | 07 | 03 | 38 | 014 | 12 |  | Building | Electrical | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80345 | Construct ducts for Landscape Lighting |  |  |  | 01 | 07 | 03 | 38 | 014 | 12 |  | Building | Electrical | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-EL-80350 | Install Containment for Cables & Cable Laying |  |  |  | 01 | 07 | 03 | 38 | 014 | 12 |  | Building | Electrical | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80355 | Cover Tiles and Backfilling for Ducts/Containments |  |  |  | 01 | 07 | 03 | 38 | 014 | 12 |  | Building | Electrical | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
TELECOMMUNICATION & SECURITY SYSTEMS
C-TL-C-UTI-OAS-80365 | Excavation for Ducts,Chambers & Pull Box |  |  |  | 01 | 10 | 03 | 38 | 014 | 12 |  | Building | CCTV | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-EL-80375 | Laying of Telecom & CCTV Network |  |  |  | 01 | 10 | 03 | 38 | 014 | 12 |  | Building | CCTV | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80370 | Construct Ducts, JRC, Chamber, & Pull Box |  |  |  | 01 | 10 | 03 | 38 | 014 | 12 |  | Building | CCTV | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80380 | Backfilling for Ducts/Encasements |  |  |  | 01 | 10 | 03 | 38 | 014 | 12 |  | Building | CCTV | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
STREET LIGHTING & CCTV
C-TL-C-UTI-OAS-80390 | Excavation for Foundation |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80395 | Light Poles/ CCTV Poles Foundation |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80400 | Backfilling for Foundation |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
KIOSK3
STRUCTURAL WORKS
C-TL-C-ST-OAS-80430 | Excavation & Formation for foundation for Kiosk3 |  |  |  | 01 | 01 | 03 | 38 | 014 | 12 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-ST-OAS-80435 | Foundation for Kiosk3 |  |  |  | 01 | 01 | 03 | 38 | 014 | 12 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-ST-OAS-80440 | Construction of Concrete Walls |  |  |  | 01 | 01 | 03 | 38 | 014 | 12 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-ST-OAS-80445 | Construction of Roof Slab |  |  |  | 01 | 01 | 03 | 38 | 014 | 12 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-ST-OAS-80450 | Construction of Upstand |  |  |  | 01 | 01 | 03 | 38 | 014 | 12 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
FINISHES
C-TL-C-FN-OAS-80460 | General Block work |  |  |  | 01 | 04 | 03 | 38 | 014 | 12 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-FN-OAS-80465 | Marking, Cutting & Chasing Walls for MEP Services |  |  |  | 01 | 04 | 03 | 38 | 014 | 12 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-FN-OAS-80470 | Plaster |  |  |  | 01 | 04 | 03 | 38 | 014 | 12 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-FN-OAS-80475 | Ceiling Finishes (by Others) |  |  |  | 01 | 04 | 03 | 38 | 014 | 12 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-FN-OAS-80480 | Wall Finishes (by Others) |  |  |  | 01 | 04 | 03 | 38 | 014 | 12 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-FN-OAS-80485 | Floor Finishes (by Others) |  |  |  | 01 | 04 | 03 | 38 | 014 | 12 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-FN-OAS-80495 | Installation of Doors, Iron Mongeries etc |  |  |  | 01 | 04 | 03 | 38 | 014 | 12 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-FN-OAS-80490 | External Wall Cladding/Finishes |  |  |  | 01 | 04 | 03 | 38 | 014 | 12 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-FN-OAS-80500 | Final Finishes & Fixtures |  |  |  | 01 | 04 | 03 | 38 | 014 | 12 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
MEP WORKS
C-TL-C-MP-80510 | MEP 1st fix works |  |  |  | 01 | 14 | 03 | 38 | 014 | 12 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-80515 | MEP 2nd Fix Works |  |  |  | 01 | 14 | 03 | 38 | 014 | 12 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-80520 | MEP final fix works |  |  |  | 01 | 14 | 03 | 38 | 014 | 12 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
TESTING & CLOSEOUT
C-TL-C-CL-OAS-80530 | Testing and Pre-commissioning |  |  |  | 01 | 14 | 03 | 38 | 014 | 12 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-CL-OAS-80535 | Snagging & De-snagging Works |  |  |  | 01 | 04 | 03 | 38 | 014 | 12 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
RETAINING STRUCTURES
C-TL-C-LS-OAS-80610 | Construct Gabion Retaining Walls TL Garden (Grid BD - BZ) - Stage 1 |  |  |  | 01 | 01 | 03 | 38 | 014 | 12 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80765 | Construct Gabion Retaining Walls TL Garden (Grid BD - BZ) - Stage 2 |  |  |  | 01 | 01 | 03 | 38 | 014 | 12 |  | Building | Civil | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
EARTH WORKS
C-TL-C-LS-OAS-80615 | Filling to create contours (Granular Material) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80620 | Filling to create contours (EPS Polystyrene Blocks) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-81085 | Rammed Earth |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-81105 | Rammed Earth Final Finish |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
LANDSCAPE- FEATURES
C-TL-C-LS-OAS-80775 | Construction of Jabel Hafit mountain model |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-81095 | Base build works - Exhibition Fitout Works |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
IRRIGATION WATER
MAIN LINE
C-TL-C-UTI-OAS-80275 | Excavation for Irrigation line |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80280 | Construct Valves, Chambers & Connections |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-PD-80285 | Irrigation pipe laying & Joints (25&75 mm dia) |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-PD-80290 | Testing Irrigation lines |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80295 | Backfilling |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
LATERAL LINE
C-TL-C-UTI-OAS-80410 | Excavation |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80420 | Laying of Pipes & Testing |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80430 | Backfilling |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
DRIP LINE
C-TL-C-UTI-OAS-80450 | Laying of Driplines for Trees & Palms |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-UTI-OAS-80440 | Laying of Driplines for Shrubs & Ground Cover |  |  |  | 01 | 12 | 03 | 38 | 014 | 12 |  | Building | Underground Utilities | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
HARDSCAPING WORKS
PLANTER BOXES/TREE PITS/WALLS
C-TL-C-LS-OAS-80590 | Excavate for Planter box & Tree Pits in (Grid BD - BZ) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80595 | Preparation, Anti-termite & blinding for Planter box & Tree Pits in (Grid BD - BZ) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80600 | Construct Planter box & Tree Pits in (Grid BD - BZ) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80785 | Tree Anchoring System |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80795 | Geotextile & Gravel |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80805 | Filling of Sweet Soil |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
RESIN BOUND GRAVEL - EXT307
C-TL-C-LS-OAS-80815 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80825 | Compacted hardcore Subbase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80835 | Compacted Granular Subbase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80845 | Concrete Edging |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80855 | Asphalt Concrete (Bituminous Macadam) (60mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80865 | Resin Bound Gravel - RBG (16mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
RESIN BOUND GRAVEL - EXT308
C-TL-C-LS-OAS-80875 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80885 | Compacted hardcore Subbase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80895 | Compacted Granular Subbase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80905 | Concrete Edging |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80915 | Asphalt Concrete (Bituminous Macadam) (60mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80925 | Resin Bound Gravel - RBG (16mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
FALAJ & WATER FOUNTAIN
C-TL-C-ST-OAS-80550 | Excavate & Prepare Surface for Falaj Water Feature |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-PD-80555 | Underground MEP services |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-ST-OAS-80560 | Concrete works & Pedestals for WF structure |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-FN-OAS-80565 | Omani Limestone - EXT952 |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-FN-OAS-80575 | Omani Limestone - EXT951 |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-PD-80570 | MEP works |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-CL-OAS-80575 | Inspection & Testing |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ANGULAR GRAVEL - EXT319
C-TL-C-LS-OAS-80935 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80945 | Compacted Subbase (150mm) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80955 | Concrete Edging |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80965 | Angular Gravel -EXT319 |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
CONCRETE BEDS (SWALES AREA)
C-TL-C-LS-OAS-80630 | Earthworks for Landscaping Zones |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80635 | Preparation, Anti Termite, Blinding & WP for Concrete beds |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80640 | Construct Concrete beds for Landscaping Zones |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80975 | Rounded Gravel -EXT316 |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80985 | Rounded Gravel -EXT318 |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
STONE SEATS AND STEPS
C-TL-C-LS-OAS-80650 | Preparation for Earth Finishes, Gravel & Stone works in (Grid BD - BZ) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80655 | Earth Finishes in (Grid BD - BZ) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80660 | Gravel & Stone works in (Grid BD - BP) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80665 | Gravel & Stone works in (Grid BP - BZ) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
OTHER FLOOR FINISHES
C-TL-C-LS-OAS-80995 | Compacted Hardcore Subbase (150mm) for EXT380 |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-81005 | Compacted Granular Subbase (150mm) for EXT380 |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-81015 | Steel Edging for EXT380 |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-81025 | Rubber for Playground -EXT380 |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
SOFTSCAPING WORKS
LOCAL
C-TL-C-LS-OAS-81045 | Unbound Soil in planting area |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80695 | Palm Trees Landscape works in Oasis Area |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80700 | Shrubs, Plants, Trees Landscape works |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
INHOUSE
C-TL-C-LS-OAS-81065 | Unbound Soil in planting area |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-81075 | Shrubs, Plants, Trees Landscape works |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
OVERSEAS
C-TL-C-LS-OAS-81055 | Unbound Soil in planting area |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-81035 | Palm Trees Landscape works in Oasis Area |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80705 | Shrubs, Plants, Trees Landscape works |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
HYDROPHONICS
C-TL-C-LS-OAS-80715 | Hydroponics Shade Works |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80720 | Hydroponics planting works (PS) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ACCESS ROUTES
PEDESTRIAN ROUTES
C-TL-C-LS-OAS-80680 | Asphalt Concrete Sub-base for Pedestrian Routes |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
ACCESSORIES & FURNISHINGS
LIGHT POLE, FLAG, PLAY GROUND & OTHER FURNISHINGS
C-TL-C-MP-EL-80735 | Flag Pole,Light Pole/CCTV Poles installation |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-MP-ELV-80740 | Street Lights & CCTV work |  |  |  | 01 | 07 | 03 | 38 | 014 | 12 |  | Building | Electrical | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
C-TL-C-LS-OAS-80745 | Accessories, Play Ground Equipment, Canopy & Furnitures |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
EXHIBITION SCHEME WORKS ( P S )
C-TL-C-LS-OAS-80755 | Oasis Area Exhibition Scheme Works (P.S) |  |  |  | 01 | 11 | 03 | 38 | 014 | 12 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Oasis Area
HANDOVER
C-TL-C-CL-OAS-80765 | Testing & Commisioning Works - TLG Phase 1 |  |  |  | 01 | 14 | 03 | 38 | 014 | 70 |  | Building | General MEP | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | MEP SubZones
C-TL-C-CL-OAS-80770 | Snagging & De-snagging Works - TLG Phase 1 |  |  |  | 01 | 04 | 03 | 38 | 014 | 50 |  | Building | Architecture | Time Line Garden | Zone TLG1 | External Ground Level (External / TLG) | Architectural SubZones
TIME LINE GARDEN PHASE 2
DESERT AREA
EARTH FILLING & COMPACTION
ROUGH GRADING
G-C-GN-MIL-1170 | Receipt of Access for TLG works on the bridge (By Others) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81035 | Earth Fill & Compaction (Grid BZ - CX) till GL |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
UTILITY WORKS - PHASE 2
SEWAGE NETWORK
EXTERNAL CONNECTION NETWORK 3
C-TL-C-UTI-DES-80800 | Excavation for Sewage Trench & Manhole |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80805 | Construct Manhole & Inspection (5 Manholes) |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-PD-80810 | Preparation for Pipe Laying |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-PD-80815 | Sewage Pipe laying & Jointing 200mm dia |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-PD-80820 | Testing |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80825 | Backfilling for Sewage line & Manhole cover installation |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
STORM WATER NETWORK
SWALES & SOAKAWAYS
C-TL-C-UTI-DES-80840 | Excavation for Swales & Soakaways |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
ZNM.CON.DES.SW.85 | Pipe laying,Jointing (dia. 315 uPVC) |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80845 | Construct Swales with Soakaways in Zone 1 |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
ZNM.CON.DES.SW.75 | Construction of Inlet Chambers and Connections |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80850 | Construct Swales with Soakaways in Zone 2 |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80855 | Testing for Swales & Soakaways |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
POTABLE WATER
C-TL-C-UTI-DES-80865 | Excavation for Water Supply line |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80870 | Construct Valves, Chambers & Connections |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-PD-80875 | Water Supply pipe laying & Joints (25-110 mm dia) |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-PD-80880 | Testing Water Supply lines |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80885 | Backfilling |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
FIRE FIGHTING
C-TL-C-UTI-DES-80925 | Excavation for Firefighting line |  |  |  | 01 | 09 | 03 | 39 | 014 | 13 |  | Building | Firefighting | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80930 | Construct Valves, Chambers & Connections |  |  |  | 01 | 09 | 03 | 39 | 014 | 13 |  | Building | Firefighting | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-FF-80935 | Firefighting pipe laying & Joints (180 mm dia) |  |  |  | 01 | 09 | 03 | 39 | 014 | 13 |  | Building | Firefighting | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-FF-80940 | Testing of Firefighting lines |  |  |  | 01 | 09 | 03 | 39 | 014 | 13 |  | Building | Firefighting | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80945 | Backfilling |  |  |  | 01 | 09 | 03 | 39 | 014 | 13 |  | Building | Firefighting | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-FF-80950 | Install Fire Hydrants |  |  |  | 01 | 09 | 03 | 39 | 014 | 13 |  | Building | Firefighting | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
ELECTRICAL LV CABLE & LIGHTING
C-TL-C-UTI-DES-80960 | Excavation for Cable trench & Pull boxes |  |  |  | 01 | 07 | 03 | 39 | 014 | 13 |  | Building | Electrical | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80965 | Construct ducts for Landscape Lighting |  |  |  | 01 | 07 | 03 | 39 | 014 | 13 |  | Building | Electrical | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-EL-80970 | Install Containment for Cables & Cable Laying |  |  |  | 01 | 07 | 03 | 39 | 014 | 13 |  | Building | Electrical | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80975 | Cover Tiles and Backfilling for Ducts/Containments |  |  |  | 01 | 07 | 03 | 39 | 014 | 13 |  | Building | Electrical | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
TELECOMMUNICATION & SECURITY SYSTEMS
C-TL-C-UTI-DES-80985 | Excavation for Ducts,Chambers & Pull Box |  |  |  | 01 | 10 | 03 | 39 | 014 | 13 |  | Building | CCTV | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80990 | Construct Ducts, JRC, Chamber, & Pull Box |  |  |  | 01 | 10 | 03 | 39 | 014 | 13 |  | Building | CCTV | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-EL-80995 | Laying of Telecom & CCTV Network |  |  |  | 01 | 10 | 03 | 39 | 014 | 13 |  | Building | CCTV | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-81000 | Backfilling for Ducts/Encasements |  |  |  | 01 | 10 | 03 | 39 | 014 | 13 |  | Building | CCTV | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
STREET LIGHTING & CCTV
C-TL-C-UTI-DES-81010 | Excavation for Foundation |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-81015 | Light Poles/ CCTV Poles Foundation |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-81020 | Backfilling for Foundation |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
TOILETS & PLANT ROOMS AT WATERFRONT
STRUCTURAL WORKS
C-TL-C-ST-DES-81050 | Excavation & Formation for foundation for Toilet at Waterfront |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-ST-DES-81055 | Foundation for Waterfront Toilets |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-ST-DES-81060 | Construction of Concrete Walls |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-ST-DES-81065 | Construction of Roof Slab |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-ST-DES-81070 | Construction of Upstand |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
FINISHES
C-TL-C-FN-DES-81080 | General Block work |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81085 | Marking, Cutting & Chasing Walls for MEP Services |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81090 | Plaster |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81100 | Wall Finishes |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81095 | Ceiling Finishes |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81110 | Floor Finishes |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81105 | External Wall Cladding/Finishes |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81120 | Installation of Doors, Iron Mongeries etc |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81115 | Install Sanitary wares, vanity counters, Cupboards etc |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81125 | Final Finishes & Fixtures |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
MEP WORKS
C-TL-C-MP-81135 | MEP 1st fix works |  |  |  | 01 | 14 | 03 | 39 | 014 | 13 |  | Building | General MEP | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-81140 | MEP 2nd Fix Works |  |  |  | 01 | 14 | 03 | 39 | 014 | 13 |  | Building | General MEP | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-81145 | MEP final fix works |  |  |  | 01 | 14 | 03 | 39 | 014 | 13 |  | Building | General MEP | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
TESTING & CLOSEOUT
C-TL-C-CL-DES-81155 | Testing and Pre-commissioning |  |  |  | 01 | 14 | 03 | 39 | 014 | 13 |  | Building | General MEP | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-CL-DES-81160 | Snagging & De-snagging Works |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
KIOSK2
STRUCTURAL WORKS
C-TL-C-ST-DES-81175 | Excavation & Formation for foundation for Kiosk1 |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-ST-DES-81180 | Foundation for Kiosk1 |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-ST-DES-81185 | Construction of Concrete Walls |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-ST-DES-81190 | Construction of Roof Slab |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-ST-DES-81195 | Construction of Upstand |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
FINISHES
C-TL-C-FN-DES-81205 | General Block work |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81210 | Marking, Cutting & Chasing Walls for MEP Services |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81215 | Plaster |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81220 | Ceiling Finishes (by Others) |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81225 | Wall Finishes (by Others) |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81230 | Floor Finishes (by Others) |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81240 | Installation of Doors, Iron Mongeries etc |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81235 | External Wall Cladding/Finishes |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-FN-DES-81245 | Final Finishes & Fixtures |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
MEP WORKS
C-TL-C-MP-81255 | MEP 1st fix works |  |  |  | 01 | 14 | 03 | 39 | 014 | 13 |  | Building | General MEP | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-81260 | MEP 2nd Fix Works |  |  |  | 01 | 14 | 03 | 39 | 014 | 13 |  | Building | General MEP | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-81265 | MEP final fix works |  |  |  | 01 | 14 | 03 | 39 | 014 | 13 |  | Building | General MEP | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
TESTING & CLOSEOUT
C-TL-C-CL-DES-81275 | Testing and Pre-commissioning |  |  |  | 01 | 14 | 03 | 39 | 014 | 13 |  | Building | General MEP | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-CL-DES-81280 | Snagging & De-snagging Works |  |  |  | 01 | 04 | 03 | 39 | 014 | 13 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
RETAINING STRUCTURES
C-TL-C-LS-DES-81315 | Construct Gabion Retaining Walls TL Garden (Grid BZ - CX) - Stage 1 |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81455 | Construct Gabion Retaining Walls TL Garden (Grid BZ - CX) - Stage 2 |  |  |  | 01 | 01 | 03 | 39 | 014 | 13 |  | Building | Civil | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
EARTH WORKS
C-TL-C-LS-DES-81320 | Filling to create contours (Granular Material) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81325 | Filling to create contours (EPS Polystyrene Blocks) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81685 | Rammed Earth |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81705 | Rammed Earth Final Finish |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
LANDSCAPE- FEATURES
C-TL-C-LS-DES-81465 | Construction of Jabel Hafit mountain model (Base build works) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81695 | Base build works - Exhibition Fitout Works |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
IRRIGATION WATER
MAIN LINE
C-TL-C-UTI-DES-80895 | Excavation for Irrigation line |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80900 | Construct Valves, Chambers & Connections |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-PD-80910 | Testing Irrigation lines |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-PD-80905 | Irrigation pipe laying & Joints (25&75 mm dia) |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-80915 | Backfilling |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
LATERAL LINE
C-TL-C-UTI-DES-81030 | Excavation |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-81040 | Laying of Pipes |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-81050 | Backfilling |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
DRIP LINE
C-TL-C-UTI-DES-81060 | Laying of Driplines for Trees & Palms |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-UTI-DES-81070 | Laying of Driplines for Shrubs & Ground Cover |  |  |  | 01 | 12 | 03 | 39 | 014 | 13 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
HARDSCAPING WORKS
PLANTER BOXES/TREE PITS/WALLS
C-TL-C-LS-DES-81295 | Excavate for Planter box & Tree Pits in (Grid BZ - CX) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81300 | Preparation, Anti-termite & blinding for Planter box & Tree Pits in (Grid BZ - CX) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81305 | Construct Planter box & Tree Pits in (Grid BZ - CX) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81475 | Tree Anchoring System |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81485 | Geotextile & Gravel |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81495 | Filling of Sweet Soil |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
RESIN BOUND GRAVEL - EXT307
C-TL-C-LS-DES-81085 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81095 | Compacted hardcore Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81105 | Compacted Granular Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81115 | Concrete Edging |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81125 | Asphalt Concrete (Bituminous Macadam) (60mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81135 | Resin Bound Gravel - RBG (16mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
RESIN BOUND GRAVEL - EXT308
C-TL-C-LS-DES-81505 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81515 | Compacted hardcore Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81525 | Compacted Granular Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81535 | Concrete Edging |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81545 | Asphalt Concrete (Bituminous Macadam) (60mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81555 | Resin Bound Gravel - RBG (16mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
ANGULAR GRAVEL - EXT319
C-TL-C-LS-DES-81565 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81575 | Compacted hardcore Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81585 | Concrete Edging |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81595 | Resin Bound Gravel - RBG (16mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
CONCRETE BEDS (SWALES)
C-TL-C-LS-DES-81335 | Excavate for Landscaping Zones in (Grid BZ - CX) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81340 | Preparation, Anti Termite, Blinding & WP for Concrete beds for Landscaping Zones in (Grid BZ - CX) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81345 | Construct Concrete beds for Landscaping Zones & Base build works in (Grid BZ - CX) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81605 | Rounded river rock - EXT318 |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
STONE SEATS AND STEPS
C-TL-C-LS-DES-81355 | Preparation for Earth Finishes, Gravel & Stone works in (Grid BZ - CX) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81360 | Earth Finishes in (Grid BZ - CX) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81365 | Gravel & Stone works in (Grid BZ - CL) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81370 | Gravel & Stone works in (Grid CL - CX) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
OTHER FLOOR FINISHES
C-TL-C-LS-DES-81615 | Subbase for HF2 |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81625 | Sand/Cement Finish HF2 |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
SOFTSCAPING WORKS
LOCAL
C-TL-C-LS-DES-81635 | Unbound Soil in planting area |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81400 | Palm Trees Landscape works in Desert Area |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81405 | Shrubs, Plants, Trees Landscape works in (Grid BZ - CL) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
INHOUSE
C-TL-C-LS-DES-81645 | Unbound Soil in planting area |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81655 | Shrubs, Plants, Trees Landscape works in (Grid BZ - CL) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
OVERSEAS
C-TL-C-LS-DES-81675 | Unbound Soil in planting area |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81665 | Palm Trees Landscape works in Desert Area |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81410 | Shrubs, Plants, Trees Landscape works in (Grid CL - CX) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
ACCESS ROUTES
PEDESTRIAN ROUTES
C-TL-C-LS-DES-81385 | Asphalt Concrete Sub-base for Pedestrian Routes |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
ACCESSORIES & FURNISHINGS
BENCHES & OTHER FURNISHINGS
C-TL-C-MP-EL-81425 | Light Pole/CCTV Poles installation |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-MP-ELV-81430 | Street Lights, CCTV work |  |  |  | 01 | 07 | 03 | 39 | 014 | 13 |  | Building | Electrical | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
C-TL-C-LS-DES-81435 | Fixing Accessories, Canopy, Furniture etc |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
EXHIBITION SCHEME WORKS ( P S )
C-TL-C-LS-DES-81445 | Desert Area Exhibition Scheme Works (P.S) |  |  |  | 01 | 11 | 03 | 39 | 014 | 13 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Desert Area
COAST AREA
EARTH FILLING & COMPACTION
ROUGH GRADING
C-TL-C-LS-COA-81600 | Earth Fill & Compaction (Grid CX - DN) till GL |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
UTILITY WORKS - PHASE 2
SEWERAGE NETWORK
C-TL-C-UTI-COA-92000 | Excavation for Sewage Trench & Manhole |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-92020 | Construct Manhole (2 Manholes) |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-92010 | Preparation for Pipe Laying |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-92030 | Pipe laying & Jointing (dia. 150 uPVC) |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-92040 | Testing of Pipeline & Inspection Approval |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-92050 | Backfilling for Sewage line & Manhole cover installation |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-92060 | Tie in connection to Building Sewer Line |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
STORM WATER NETWORK
SWALES & SOAKAWAYS
C-TL-C-UTI-COA-81470 | Excavation for Swales & Soakaways |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
ZNM.CON.CO.SW.55 | Pipe laying,Jointing (dia. 315 uPVC) |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81475 | Construct Swales with Soakaways in Zone 1 |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81480 | Construct Swales with Soakaways in Zone 2 |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
ZNM.CON.CO.SW.65 | Construction of Inlet Chambers and Connections |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81485 | Testing for Swales & Soakaways |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
LIGHTING NETWORK
C-TL-C-UTI-COA-81525 | Excavation for Cable trench & Pull boxes |  |  |  | 01 | 07 | 03 | 39 | 014 | 14 |  | Building | Electrical | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81530 | Construct ducts for Landscape Lighting |  |  |  | 01 | 07 | 03 | 39 | 014 | 14 |  | Building | Electrical | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-MP-EL-81535 | Install Containment for Cables & Cable Laying |  |  |  | 01 | 07 | 03 | 39 | 014 | 14 |  | Building | Electrical | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81540 | Cover Tiles and Backfilling for Ducts/Containments |  |  |  | 01 | 07 | 03 | 39 | 014 | 14 |  | Building | Electrical | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
TELECOMMUNICATION & SECURITY SYSTEMS
C-TL-C-UTI-COA-81550 | Excavation for Ducts,Chambers & Pull Box |  |  |  | 01 | 10 | 03 | 39 | 014 | 14 |  | Building | CCTV | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81555 | Construct Ducts, JRC, Chamber, & Pull Box |  |  |  | 01 | 10 | 03 | 39 | 014 | 14 |  | Building | CCTV | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-MP-EL-81560 | Laying of Telecom & CCTV Network |  |  |  | 01 | 10 | 03 | 39 | 014 | 14 |  | Building | CCTV | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81565 | Backfilling for Ducts/Encasements |  |  |  | 01 | 10 | 03 | 39 | 014 | 14 |  | Building | CCTV | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
STREET LIGHTING & CCTV
C-TL-C-UTI-COA-81575 | Excavation for Foundation |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81580 | Light Poles/ CCTV Poles Foundation |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81585 | Backfilling for Foundation |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
EARTH WORKS
C-TL-C-LS-COA-81635 | Construct Gabion Retaining Walls TL Garden (Grid CX - DN) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81640 | Filling to create contours (Granular Material) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81645 | Filling to create contours (EPS Polystyrene Blocks) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82645 | Rammed Earth |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82665 | Rammed Earth Final Finish |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
IRRIGATION WATER
MAIN LINE
C-TL-C-UTI-COA-81495 | Excavation for Irrigation line |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81500 | Construct Valves, Chambers & Connections |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-MP-PD-81505 | Irrigation pipe laying & Joints (25&75 mm dia) |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-MP-PD-81510 | Testing Irrigation lines |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81515 | Backfilling |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
LATERAL LINE
C-TL-C-MP-PD-81530 | Excavation |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81595 | Laying of Pipes |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81605 | Backfilling |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
DRIP LINE
C-TL-C-UTI-COA-81615 | Laying of Driplines for Trees & Palms |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-UTI-COA-81625 | Laying of Driplines for Shrubs & Ground Cover |  |  |  | 01 | 12 | 03 | 39 | 014 | 14 |  | Building | Underground Utilities | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
HARDSCAPING WORKS
PLANTER BOXES/TREE PITS/WALLS
C-TL-C-LS-COA-82655 | Base build works - Exhibition Fitout Works |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81615 | Excavate for Planter box & Tree Pits in (Grid CX - DN) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81620 | Preparation, Anti-termite & blinding for Planter box & Tree Pits in (Grid CX - DN) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81625 | Construct Planter box & Tree Pits in (Grid CX - DN) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81770 | Tree Anchoring System |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81780 | Geotextile & Gravel |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81790 | Filling of Sweet Soil |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
RESIN BOUND GRAVEL - EXT307
C-TL-C-LS-COA-82500 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82505 | Compacted hardcore Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82510 | Compacted Granular Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82515 | Concrete Edging |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82520 | Asphalt Concrete (Bituminous Macadam) (60mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82525 | Resin Bound Gravel - RBG (16mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
RESIN BOUND GRAVEL - EXT308
C-TL-C-LS-COA-82535 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82545 | Compacted hardcore Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82555 | Compacted Granular Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82565 | Concrete Edging |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82575 | Asphalt Concrete (Bituminous Macadam) (60mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82585 | Resin Bound Gravel - RBG (16mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
SWALES
C-TL-C-LS-COA-82695 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82705 | Compacted Hard core Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82715 | Concrete Base |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82725 | Rounded river rock- EXT318 |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
ANGULAR GRAVEL
C-TL-C-LS-COA-81655 | Preparation of Formation |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81660 | Compacted Subbase (150mm) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81665 | Construct Concrete beds for Landscaping Zones & Base build works in (Grid CX - DN) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82595 | Angular Gravel -EXT319 |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
STONE WORKS
C-TL-C-LS-COA-81675 | Preparation for Earth Finishes, Gravel & Stone works in (Grid CX - DN) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81680 | Earth Finishes in (Grid CX - DN) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81685 | Gravel & Stone works in (Grid CX - DG) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81690 | Gravel & Stone works in (Grid DG - DN) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
SOFTSCAPING WORKS
LOCAL
C-TL-C-LS-COA-82675 | Unbound Soil in Coast Area |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81720 | Palm Trees Landscape works in Coast Area |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81725 | Plantation works Coast Area |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
INHOUSE
C-TL-C-LS-COA-82625 | Palm Trees Landscape works in Coast Area |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82635 | Plantation works Coast Area |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
OVERSEAS
C-TL-C-LS-COA-82685 | Unbound Soil in Coast Area |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82605 | Palm Trees Landscape works in Coast Area |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-82615 | Plantation works Coast Area |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
ACCESS ROUTES
PEDESTRIAN ROUTES
C-TL-C-LS-COA-81705 | Asphalt Concrete Sub-base for Pedestrian Routes |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
ACCESSORIES & FURNISHINGS
BENCHES & OTHER FURNISHINGS
C-TL-C-MP-EL-81740 | Light Pole/CCTV Poles installation |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-MP-ELV-81745 | Street Lights, CCTV work |  |  |  | 01 | 07 | 03 | 39 | 014 | 14 |  | Building | Electrical | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
C-TL-C-LS-COA-81750 | Fixing Accessories, Canopy, Furniture etc |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
EXHIBITION SCHEME WORKS ( P S )
C-TL-C-LS-COA-81760 | Coast Area Exhibition Scheme Works (P.S) |  |  |  | 01 | 11 | 03 | 39 | 014 | 14 |  | Building | Roads & Landscaping | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Coast Area
HANDOVER
C-TL-C-CL-81770 | Testing & Commisioning Works - TLG Phase 2 |  |  |  | 01 | 14 | 03 | 39 | 014 | 70 |  | Building | General MEP | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | MEP SubZones
C-TL-C-CL-81775 | Snagging & De-snagging Works - TLG Phase 2 |  |  |  | 01 | 04 | 03 | 39 | 014 | 50 |  | Building | Architecture | Time Line Garden | Zone TLG2 | External Ground Level (External / TLG) | Architectural SubZones
UTILITY SERVICES TIE IN CONNECTIONS
C-MS-C-MP-PD-81810 | Utility Tie-In: Sewage Network |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
C-MS-C-MP-PD-81785 | Utility Tie-In: Irrigation water Network |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
C-MS-C-MP-PD-81805 | Utility Tie-In: Potable water Network |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
C-MS-C-MP-FF-81790 | Completion of Fire Fighting Network |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
C-MS-C-MP-PD-81800 | Utility Tie-In: Stormwater Network |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
C-MS-C-MP-EL-81795 | Utility Tie-In: Power |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
C-MS-C-MP-ELV-81820 | Utility Tie-In: Telecommunication |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
C-MS-C-MP-EL-81815 | Completion of Street Light Network |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
IRRIGATION PUMPING STATION & CONTROL SYSTEM
ZNM.CON.IRR.AS.10 | Irrigation Mainline Completion including Laying of Conduits & Solenoid Valve Installation - All Zones |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
IRRIGATION AUTOMATION SYSTEM & PUMPING STATION WORKS - ZONES
ZNM.CON.IRR.Z.10 | Installation of Irrigation Cable Pull Box |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.Z.20 | Irrigation Control Cable Pulling |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.Z.30 | Single Station Decoder Installation |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.Z.40 | Soil Moisture Sensor with Sensor Decoder Installation |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.Z.50 | Installation of Weather Station with accessories |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
IRRIGATION AUTOMATION SYSTEM & PUMPING STATION WORKS - INSIDE PUMP ROOM
ZNM.CON.IRR.PS.10 | Civil Works / Electrical 1st & 2nd Fix Inside Pumping Station Room |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.20 | Installation of GRP Panel Insulated Tank (200 m3 Capacity) |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.30 | Installation of SS 316 Centrifugal Pump Set with Pressure Vessel & VFD ( 1 no. Duty + 1 no. Standby) |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.50 | Fertilizer Dosing System Installation |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.60 | Installation of UV Filter |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.70 | Installation of SS Automatic Backwash Filter |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.40 | Pipes and Fittings Installation |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.80 | Installation of Control Panels |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.90 | Pressure Relief Valve Installation |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.100 | Basket Strainer Installation |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.110 | Gate Valve Installation |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.120 | Flow Meter Installation |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.130 | Installation of Universal Pump Start Delay Decoder |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.140 | Flow Sensor Installation |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.150 | Installation of Large Decoder Interface with accessories |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.160 | Installation of Irrigation Central Control ( Rain Bird Site Control Software on PC + Printer ) |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.PS.170 | Connecting Discharge Line to Irrigation Main Line |  |  |  | 01 | 12 | 03 | 52 | 014 | 70 |  | Building | Underground Utilities | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
TESTING & COMMISSIONING
ZNM.CON.IRR.T & C.30 | Testing & Commissioning |  |  |  | 01 | 14 | 03 | 52 | 014 | 70 |  | Building | General MEP | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
HANDING OVER & CLOSE OUT
ZNM.CON.IRR.H.O.10 | Snagging and Desnagging |  |  |  | 01 | 11 | 03 | 52 | 014 | 70 |  | Building | Roads & Landscaping | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.H.O.20 | Submission of As-Built Drawings |  |  |  | 01 | 11 | 03 | 52 | 014 | 70 |  | Building | Roads & Landscaping | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.H.O.30 | Submission of O & M Manual |  |  |  | 01 | 11 | 03 | 52 | 014 | 70 |  | Building | Roads & Landscaping | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
ZNM.CON.IRR.H.O.40 | Final Snagging |  |  |  | 01 | 11 | 03 | 52 | 014 | 70 |  | Building | Roads & Landscaping | Time Line Garden | General External Works | External Ground Level (External / TLG) | MEP SubZones
External works |  | 311 | 2022-06-22 | 2023-07-02
Office Courtyard 1 & 2 |  | 48 | 2022-06-22 | 2022-08-21
C-PW-113630 | Office Courtyard - 01 | 30 | 2022-06-22 | 2022-07-31 | 01 | 01 | 04 | 40 | 014 | 30 |  | Building | Civil | External Works | Office Courtyard 1 & 2 | External Ground Level (External / TLG) | Civil SubZones
C-PW-113640 | Office Courtyard - 02 | 30 | 2022-07-17 | 2022-08-21 | 01 | 01 | 04 | 40 | 014 | 30 |  | Building | Civil | External Works | Office Courtyard 1 & 2 | External Ground Level (External / TLG) | Civil SubZones
VIP Courtyard |  | 56 | 2022-08-08 | 2022-10-12
C-PW-113650 | VIP Courtyard works | 56 | 2022-08-08 | 2022-10-12 | 01 | 01 | 04 | 37 | 014 | 30 |  | Building | Civil | External Works | VIP Canopy & Courtyard | External Ground Level (External / TLG) | Civil SubZones
Pump Room |  | 97 | 2022-10-25 | 2023-02-16
C-PW-113660 | Pump Room | 97 | 2022-10-25 | 2023-02-16 | 01 | 01 | 04 | 52 | 014 | 70 |  | Building | Civil | External Works | General External Works | External Ground Level (External / TLG) | MEP SubZones
Irrigation Automation System - All Zones |  | 56 | 2023-04-26 | 2023-07-02
C-PW-113670 | Irrigation Automation System - All Zones | 56 | 2023-04-26 | 2023-07-02 | 01 | 08 | 04 | 52 | 014 | 70 |  | Building | Plumbing | External Works | General External Works | External Ground Level (External / TLG) | MEP SubZones
Parking Area |  | 90 | 2022-10-13 | 2023-01-28
C-PW-113680 | Parking Area | 90 | 2022-10-13 | 2023-01-28 | 01 | 01 | 04 | 41 | 014 | 30 |  | Building | Civil | External Works | Parking Area | External Ground Level (External / TLG) | Civil SubZones
Other Hardscape Areas |  | 90 | 2023-01-29 | 2023-05-15
C-PW-113690 | Other Hardscape Works | 90 | 2023-01-29 | 2023-05-15 | 01 | 01 | 04 | 52 | 014 | 30 |  | Building | Civil | External Works | General External Works | External Ground Level (External / TLG) | Civil SubZones
Specialist Exhibition Fitout Works |  | 404 | 2022-04-10 | 2023-08-11
SZLT - (SHK. ZAYED LIFE & TIMES GALLERY) |  | 404 | 2022-04-10 | 2023-08-11
C-PW-113700 | Access to install Projector/Lighting 1st Fix - Shk. Zayed Life & Times Gallery | 0 | 2022-04-10 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113710 | Access to install Wall/Base-Build Framing Supports - Shk. Zayed Life & Times Gallery | 0 | 2022-06-04 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113720 | Early Access to Phase 1 - Shk. Zayed Life & Times Gallery | 0 | 2022-10-11 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113730 | Access to AV Room for 1st Fix - Shk. Zayed Life & Times Gallery | 0 | 2022-12-14 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113740 | Access for Phase 2 - Shk. Zayed Life & Times Gallery | 0 | 2023-04-23 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113750 | Access to AV Room with AC - Shk. Zayed Life & Times Gallery | 0 | 2023-04-23 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-OW-113760 | Exhibition Fit-out - SZLT | 60 | 2023-06-13 | 2023-08-11 | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
LAL - (GALLERY C & FALCONRY AND CONSERVATION GALLERY) |  | 404 | 2022-04-10 | 2023-08-11
C-PW-113770 | Access to install Projector/Lighting 1st Fix - Falconry & Conservation Gallery | 0 | 2022-04-10 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113780 | Access to install Wall/Base-Build Framing Supports - Falconry & Conservation Gallery | 0 | 2022-08-28 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113790 | Access to AV Room for 1st Fix - Falconry & Conservation Gallery | 0 | 2022-11-07 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113800 | Early Access to Phase 1 - Falconry & Conservation Gallery | 0 | 2023-01-18 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113810 | Access to AV Room with AC - Falconry & Conservation Gallery | 0 | 2023-04-23 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113820 | Access for Phase 2 - Falconry & Conservation Gallery | 0 | 2023-05-08 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-OW-113830 | Exhibition Fit-out - LAL | 60 | 2023-06-13 | 2023-08-11 | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
SEP GALLERY - Tentative Dates |  | 371 | 2022-05-21 | 2023-08-11
C-PW-113840 | Access to install Projector/Lighting 1st Fix - SEP Gallery | 0 | 2022-05-21 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113850 | Access to AV Room for 1st Fix - SEP Gallery | 0 | 2022-08-16 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113860 | Access to install Wall/Base-Build Framing Supports - SEP Gallery | 0 | 2022-10-27 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113870 | Access to AV Room with AC - SEP Gallery | 0 | 2022-10-27 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113880 | Early Access to Phase 1 - SEP Gallery | 0 | 2022-11-10 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-PW-113890 | Access for Phase 2 - SEP Gallery | 0 | 2023-05-08 |  | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
C-OW-113900 | Exhibition Fit-out - SEP Gallery | 60 | 2023-06-13 | 2023-08-11 | 01 | 04 | 01 | 53 | 003 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L00 Ground Level | ZNM Specific Areas
PAH 01 - (POD 1 GALLERY) |  | 252 | 2022-10-13 | 2023-08-11
C-PW-113910 | Access to AV Room for 1st Fix - Gallery POD 1 | 0 | 2022-10-13 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-113920 | Access to install Wall/Base-Build Framing Supports - Gallery POD 1 | 0 | 2022-11-20 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-113930 | Access to install Projector/Lighting 1st Fix - Gallery POD 1 | 0 | 2022-12-15 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-113940 | Access to install Projector/Lighting/Graphics 1st Fix - Gallery POD 1 | 0 | 2023-01-31 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-113950 | Access to AV Room with AC - Gallery POD 1 | 0 | 2023-04-12 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-113960 | Complete Building Seal-Off - Gallery POD 1 | 0 | 2023-05-08 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-OW-113970 | Exhibition Fit-out PAH 01 | 60 | 2023-06-13 | 2023-08-11 | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
PAH 02 - (POD 2 GALLERY) |  | 252 | 2022-10-13 | 2023-08-11
C-PW-113980 | Access to AV Room for 1st Fix - Gallery POD 2 | 0 | 2022-10-13 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-113990 | Access to install Wall/Base-Build Framing Supports - Gallery POD 2 | 0 | 2022-12-18 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114000 | Access to install Projector/Lighting 1st Fix - Gallery POD 2 | 0 | 2023-01-16 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114010 | Access to install Projector/Lighting/Graphics 1st Fix - Gallery POD 2 | 0 | 2023-02-18 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114020 | Access to AV Room with AC - Gallery POD 2 | 0 | 2023-04-12 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114030 | Complete Building Seal-Off - Gallery POD 2 | 0 | 2023-05-04 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-OW-114040 | Exhibition Fit-out - PAH 02 | 60 | 2023-06-13 | 2023-08-11 | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
HAS 01 - (POD 4 GALLERY) |  | 274 | 2022-09-15 | 2023-08-11
C-PW-114050 | Access to AV Room for 1st Fix - Gallery POD 4 | 0 | 2022-09-15 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114060 | Access to install Wall/Base-Build Framing Supports - Gallery POD 4 | 0 | 2022-09-21 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114070 | Access to AV Room with AC - Gallery POD 4 | 0 | 2022-10-03 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114080 | Access to install Projector/Lighting 1st Fix - Gallery POD 4 | 0 | 2022-10-29 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114090 | Access to install Projector/Lighting/Graphics 1st Fix - Gallery POD 4 | 0 | 2023-01-05 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114100 | Complete Building Seal-Off - Gallery POD 4 | 0 | 2023-05-08 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-OW-114110 | Exhibition Fit-out - HAS 01 | 60 | 2023-06-13 | 2023-08-11 | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
HAS 02 - (POD 5 GALLERY) |  | 298 | 2022-08-18 | 2023-08-11
C-PW-114120 | Access to install Wall/Base-Build Framing Supports - Gallery POD 5 | 0 | 2022-08-18 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114140 | Access to install Projector/Lighting 1st Fix - Gallery POD 5 | 0 | 2022-09-15 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114130 | Access to AV Room for 1st Fix - Gallery POD 5 | 0 | 2022-09-15 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114150 | Access to AV Room with AC - Gallery POD 5 | 0 | 2022-10-03 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114160 | Access to install Projector/Lighting/Graphics 1st Fix - Gallery POD 5 | 0 | 2022-12-11 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114170 | Complete Building Seal-Off - Gallery POD 5 | 0 | 2023-05-08 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-OW-114180 | Exhibition Fit-out - HAS 02 | 60 | 2023-06-13 | 2023-08-11 | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
HAS 1 & 2 NODE |  | 404 | 2022-04-10 | 2023-08-11
C-PW-114190 | Access to install Projector/Lighting/Graphics 1st Fix to Wall - HAS 1&2 NODE | 0 | 2022-04-10 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114200 | Access to install Projector/Lighting/Graphics 1st Fix to Ceiling - HAS 1&2 NODE | 0 | 2022-04-10 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114210 | Access to AV Room for 1st Fix - HAS 1&2 NODE | 0 | 2022-09-15 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114220 | Access to install Wall/Base-Build Framing Supports - HAS 1&2 NODE | 0 | 2022-09-17 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114230 | Access to AV Room with AC - HAS 1&2 NODE | 0 | 2022-10-03 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114240 | Access for Phase 1 - HAS 1&2 NODE | 0 | 2023-04-29 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114250 | Access for Phase 2 - HAS 1&2 NODE | 0 | 2023-05-08 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-OW-114260 | Exhibition Fit-out HAS 1& 2 NODE | 60 | 2023-06-13 | 2023-08-11 | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
PAH 1 & 2 NODE |  | 404 | 2022-04-10 | 2023-08-11
C-PW-114270 | Access to install Projector/Lighting/Graphics 1st Fix to Wall - PAH 1&2 NODE | 0 | 2022-04-10 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114280 | Access to install Projector/Lighting/Graphics 1st Fix to Ceiling - PAH 1&2 NODE | 0 | 2022-04-10 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114290 | Access to install Wall/Base-Build Framing Supports - PAH 1&2 NODE | 0 | 2022-10-12 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114300 | Access to AV Room for 1st Fix - PAH 1&2 NODE | 0 | 2022-10-13 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114310 | Access to AV Room with AC - PAH 1&2 NODE | 0 | 2023-04-12 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114320 | Access for Phase 1 - PAH 1&2 NODE | 0 | 2023-04-29 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-PW-114330 | Access for Phase 2 - PAH 1&2 NODE | 0 | 2023-05-08 |  | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
C-OW-114340 | Exhibition Fit-out - PAH 1 & 2 NODE | 60 | 2023-06-13 | 2023-08-11 | 01 | 04 | 01 | 53 | 005 | 04 |  | Building | Architecture | Museum | Specialist Fitout | L02 Gallery level | ZNM Specific Areas
TLG - (TIMELINE GARDEN) |  | 65 | 2023-05-24 | 2023-08-11
C-PW-114350 | Access for do Sculpture Foundation - TLG | 0 | 2023-05-24 |  | 01 | 04 | 03 | 53 | 014 | 04 |  | Building | Architecture | Time Line Garden | Specialist Fitout | External Ground Level (External / TLG) | ZNM Specific Areas
C-PW-114360 | Access Route Completion - TLG | 0 | 2023-05-24 |  | 01 | 04 | 03 | 53 | 014 | 04 |  | Building | Architecture | Time Line Garden | Specialist Fitout | External Ground Level (External / TLG) | ZNM Specific Areas
C-OW-114370 | Exhibition Fit-out - TLG | 60 | 2023-06-13 | 2023-08-11 | 01 | 04 | 03 | 53 | 014 | 04 |  | Building | Architecture | Time Line Garden | Specialist Fitout | External Ground Level (External / TLG) | ZNM Specific Areas

## WBS
Zayed National Museum - Detailed Programme - Rev. 1
Construction
Permanent work
Museum
Zone 1 - DRUMS, PODS, WINGS & CENTRAL LOBBY
Zone 1D - Drum 1
Civil Works
Grey Concrete
White Concrete
Drum Wall 1
Wall/Other Area
Arches/Bull-Nose Area
General
Ring Beam 1
Architectural
MEP
Zone 1D - POD 1
Civil works
Steel Structure
Temporary Access / Steel Support
Erection of POD
Fire Proofing of POD
Cladding Works
Architectural
FLOOR
WALLS
STAGE 1 (BELLY)
Pod Internal
STAGE 2 (MID)
Pod Internal
STAGE 3 (UPPER)
Pod Internal
STAGE 4(SOFFIT)
WALL VOID
MEP
MECHANICAL
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
EMERGENCY LIGHTING
FIRE ALARM & PUBLIC ADDRESS
LIFE AND SAFETY SYSTEMS
FIRE FIGHTING WORKS
Close Out Works
Zone 1D - Wing 1
Civil works
Steel Structure
Temporary Access / Steel Support
Erection of Wing
Architectural works
Facade Works
Zone 1E - Drum 2
Civil Works
White Concrete
Drum Wall 2
Ring Beam 2
Grey Concrete
Architectural
MEP
Zone 1E - POD 2
Civil Works
Steel Structure
Temporary Access / Steel Support
Erection of POD
Fire Proofing of POD
Cladding Works
Architectural
FLOOR
WALLS
STAGE 1 (BELLY)
Pod Internal
STAGE 2 (MID)
Pod Internal
STAGE 3 (UPPER)
Pod Internal
STAGE 4(SOFFIT)
WALL VOID
MEP
MECHANICAL
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
EMERGENCY LIGHTING
FIRE ALARM & PUBLIC ADDRESS
LIFE AND SAFETY SYSTEMS
FIRE FIGHTING WORKS
Close Out Works
Zone 1E - Wing 2
Civil works
Steel Structure
Temporary Access / Steel Support
Erection of Wing
Architectural works
Facade Works
Zone 1B - Drum 3
Civil Works
White Concrete
Drum Wall 3
Ring Beam 3
Grey Concrete
Architectural
MEP
Close Out Works
Zone 1B - Wing 3
Civil works
Steel Structure
Temporary Access / Steel Support
Erection of Wing
Architectural works
Facade Works
Zone 1C - Drum 4
Civil Works
White Concrete
Ring Beam 4
Grey Concrete
Architectural
MEP
Zone 1C - POD 4
Civil works
Steel Structure
Temporary Access / Steel Support
Erection of POD
Fire Proofing of POD
Cladding Works
Architectural
FLOOR
WALLS
STAGE 1 (BELLY)
Pod Internal
STAGE 2 (MID)
Pod Internal
STAGE 3 (UPPER)
Pod Internal
STAGE 4(SOFFIT)
WALL VOID
MEP
MECHANICAL
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
EMERGENCY LIGHTING
FIRE ALARM & PUBLIC ADDRESS
LIFE AND SAFETY SYSTEMS
FIRE FIGHTING WORKS
Close Out Works
Zone 1C - Wing 4
Civil works
Steel Structure
Temporary Access / Steel Support
Erection of Wing
Architectural works
Facade Works
Zone 1A - Drum 5
Civil Works
White Concrete
Ring Beam 5
POD Support/Heavy Reinforcement Areas
Other Areas
General
Grey Concrete
Architectural
MEP
Zone 1A - POD 5
Civil works
Steel Structure
Temporary Access / Steel Support
Erection of POD
Fire Proofing of POD
Cladding Works
Architectural
FLOOR
WALLS
STAGE 1 (BELLY)
Pod Internal
STAGE 2 (MID)
Pod Internal
STAGE 3 (UPPER)
Pod Internal
STAGE 4(SOFFIT)
WALL VOID
MEP
MECHANICAL
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
EMERGENCY LIGHTING
FIRE ALARM & PUBLIC ADDRESS
LIFE AND SAFETY SYSTEMS
FIRE FIGHTING WORKS
Close Out Works
Zone 1A - Wing 5
Civil works
Steel Structure
Temporary Access / Steel Support
Erection of Wing
Architectural works
Facade Works
Zone 1F - Central Lobby
Civil Works
Raised Slab
Architectural Works
L-BM Basement Mezzanine Level
L00 Ground Level
CIRCULATIONS & CORRIDORS- NORTH
L02 Gallery level
CENTRAL GALLERY WALKWAY & MEMBERS LOUNGE
L03 Plenum
SERVICE ACCESS AREAS & MEWP GARAGE
L04
MEP Works
L-BM Basement Mezzanine Level
L00 Ground Level
CIRCULATIONS & CORRIDORS- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
L02 Gallery level
CENTRAL GALLERY WALKWAY & MEMBERS LOUNGE
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
LIFTS
L03 Plenum
SERVICE ACCESS AREAS & MEWP GARAGE
MECHANICAL
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
L04
Zone 2 and Zone 3
LEVEL BASEMENT
CIVIL WORKS
ZONE 03C
ARCHITECTURAL WORKS
NORTH WEST
COMMON FLOOR WORKS- NORTH
MECHANICAL PLANT ROOM A & B - NORTH
ELECTRICAL PLANT & UPS 1 - NORTH
MAIN TEL. ROOM 1, CCU1 & 2, ETISALAT METER 1 - NORTH
GREASE TRAP ROOM - NORTH
ADMIN CANTEEN & LOBBY - NORTH
STAFF CANTEEN, WASTE STORAGE 1 & SPECIAL EVENT STORAGE- NORTH
KITCHEN AREAS (FIT OUT BY TENANT)- NORTH
CIRCULATIONS & CORRIDORS- NORTH
STAFF TOILETS - EAST
CHILLED WATER PUMP ROOM - ETS ROOM - WEST
MALE & FEMALE PRAYER ROOM, LOBBY, ABLUTION AND TOILET - WEST
NORTH EAST
COMMON FLOOR WORKS - EAST
MECHANICAL PLANT - EAST
ELECTRICAL PLANT & UPS ROOM 2 - EAST
STANDBY CHILLER 1- EAST
STANDY BY ICE STORAGE TANKS - EAST
CIRCULATIONS & CORRIDORS - EAST
SOUTH WEST
COMMON FLOOR WORKS - WEST
MECHANICAL PLANT ROOM - WEST
CANADIAN DUCT AHU - WEST
MAIN LV SWITCH ROOM 1 - WEST
ELECTRICAL PLANT ROOM - WEST
TSE INTAKE / CONDENSATE TANK - WEST
IT/AV STORE & MOTOR ROOM 2 - WEST
DOCUMENT CENTER, STORAGE, ISOLATION, ARTIFACT, SECURE STORAGE AND MUSEUM LOADING DOCK - WEST
DOCK MASTER, SECURITY ROOM & EQUIPMENT, MAINTENANCE WORSHOP & STORAGE AND FALCON S/R ROOM - WEST
PARKING, ARRIVALS, DRIVEWAYS AND LOADING BAYS
CIRCULATIONS & CORRIDORS - WEST
SOUTH EAST
COMMON FLOOR WORKS - SOUTH
MECHANICAL PLANT 1 & 2 - SOUTH
HEATING & CALORIFIER ROOMS - SOUTH
UPS ROOM 3 & ELECTRICAL PLANT ROOM - SOUTH
MAIN LV SWITCH ROOM 2 - SOUTH
PHOTOGRAPHIC STUDIO & STORE ROOMS - SOUTH
MOTOR ROOM 1, BMS ROOM, MAIN TELECOM ROOM 2, CC3 & 4 AND ETISALAT METER 2 - SOUTH
COLLECTION STORAGE 1 & 2 - SOUTH
CIRCULATIONS & CORRIDORS - SOUTH
WC'S, STAFF CHANGING ROOMS AND VIP PANTRY - WEST
MEP WORKS
NORTH WEST
MECHANICAL PLANT ROOM A & B - NORTH
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
MAIN TEL. ROOM 1, CCU1 & 2, ETISALAT METER 1 NORTH
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
GREASE TRAP ROOM- NORTH
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
ELECTRICAL PLANT & UPS 1 - NORTH
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
ADMIN CANTEEN, LOBBY - NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
KITCHEN AREAS - NORTH
MECHANICAL
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
CIRCULATIONS & CORRIDORS- NORTH
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
STAFF CANTEEN, WASTE STORAGE 1 & SPECIAL EVENT STORAGE- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
STAFF TOILETS - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
CHILLED WATER PUMP ROOM - ETS ROOM - WEST
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
MALE & FEMALE PRAYER ROOM, LOBBY, ABLUTION AND TOILET - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
NORTH EAST
ELECTRICAL PLANT & UPS ROOM 2 - EAST
MECHANICAL
HVAC
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
MECHANICAL PLANT - EAST
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
STANDBY CHILLER 1 - EAST
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
STANDY BY ICE STORAGE TANKS - EAST
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
CIRCULATIONS & CORRIDORS- EAST
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
SOUTH WEST
CIRCULATIONS & CORRIDORS- WEST
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
MECHANICAL PLANT ROOM - WEST
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
CANADIAN DUCT AHU - WEST
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
ELECTRICAL PLANT ROOM - WEST
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
MAIN LV SWITCH ROOM 1 - WEST
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
TSE INTAKE / CONDENSATE TANK - WEST
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
IT/AV STORE & MOTOR ROOM 2 - WEST
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
DOCUMENT CENTER, STORAGE, ISOLATION, ARTIFACT, SECURE STORAGE AND MUSEUM LOADING DOCK - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
DOCK MASTER, SECURITY ROOM & EQUIPMENT, MAINTENANCE WORSHOP & STORAGE AND FALCON S/R ROOM - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
PARKING, ARRIVALS, DRIVEWAYS AND LOADING BAYS
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SOUTH EAST
MECHANICAL PLANT 1 & 2 - SOUTH
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
HEATING & CALORIFIER ROOMS - SOUTH
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
UPS ROOM 3 & ELECTRICAL PLANT ROOM - SOUTH
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
MAIN LV SWITCH ROOM 2 - SOUTH
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
MOTOR ROOM 1, BMS ROOM, MAIN TELECOM ROOM 2, CC3 & 4 AND ETISALAT METER 2 - SOUTH
MECHANICAL
HVAC
DRAINAGE WORKS
ELECTRICAL
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
COLLECTION STORAGE 1 & 2 - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
PHOTOGRAPHIC STUDIO & STORE ROOMS - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
CIRCULATIONS & CORRIDORS- SOUTH
MECHANICAL
HVAC
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTERCOM SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING
WC'S, STAFF CHANGING ROOMS AND VIP PANTRY - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
LEVEL BM BASEMENT MEZZANINE
CIVIL WORKS
ZONE 02D
ZONE 03C
ARCHITECTURAL WORKS
NORTH WEST
SERVICE SLAB 1&2 AND AIR PLENUM - NORTH
SERVICE SLAB 3 - NORTH
KITCHEN PLANT ROOM- NORTH
NORTH EAST
SERVICE SLAB 4&5 - EAST
SOUTH WEST
SERVICE BRIDGE AND SERVICE SLAB 12 - WEST
WATER TREATMENT PLANT - WEST
SOUTH EAST
SERVICE SLAB 6 - SOUTH
SERVICE SLAB 7&8 - SOUTH
SERVICE BRIDGE & TUNNEL
MEP WORKS
NORTH WEST
SERVICE SLAB 1&2 AND AIR PLENUM - NORTH
ELECTRICAL WORKS
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SERVICE SLAB 3 - NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
KITCHEN PLANT ROOM- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
NORTH EAST
SERVICE SLAB 4&5 - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SOUTH WEST
SERVICE BRIDGE AND SERVICE SLAB 12 - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
WATER TREATMENT PLANT - WEST
MECHANICAL
HVAC SYSTEM WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SOUTH EAST
SERVICE SLAB 6 - SOUTH MEP
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SERVICE SLAB 7&8 - SOUTH MEP
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SERVICE BRIDGE & TUNNEL
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
LEVEL 00 GROUND
CIVIL WORKS
ZONE 02C
ZONE 02D
ZONE 02E
ZONE 02F
ZONE 02G
ZONE 03B
ZONE 03C
ZONE 03A
ARCHITECTURAL WORKS
NORTH WEST
COMMON WORKS- NORTH
RESTAURANT GALLERIES,PANTRY,PUBLIC TOILETS,GRAB&GO- NORTH
GRAB&GO - TENANT FITOUT
AUDITORIUM,CONFERENCE ROOM,LOBBY AND ASSOCIATED ROOMS- NORTH
KITCHEN AREA,TOILETS & JANITOR ROOMS- NORTH
KITCHEN AREAS - TENANT FITOUT
RESTAURANT,VIP VIEWING LOUNGE- NORTH
STAFF OFFICE,VIP VIEWING LOBBY,SECURITY & SCAN AREAS- NORTH
MAIN LOBBY
MEETING SPACE
CAFE
TICKET/INFO POINT
PERFORMANCE SPACE
RETAIL
CIRCULATIONS & CORRIDORS
ENTRANCE LOBBY
CITY ENTRANCE
GARDEN ENTRANCE
NORTH EAST
COMMON WORKS - EAST
GALLERY C & FALCONRY AND CONSERVATION GALLERY - EAST
WILDLIFE KITCHEN & STORAGE,PREPARATION RECEPTION & SHELTER AREAS - EAST
CIRCULATIONS & CORRIDORS - EAST
INTERVIEW,SECURITY SCAN, FIRST AID ROOMS AND OFFICE AREAS - EAST
SOUTH WEST
COMMON WORKS - WEST
SECURITY, SCAN, INTERVIEW & CASH AREAS - WEST
ARTIFACT WORKSHOPS, SEP WORK & TOOL ROOMS - WEST
SEP TOILETS - WEST
SEP GALLERIES & LOBBY - WEST
FUTURE EXPANSION ROOMS - WEST
CIRCULATIONS & CORRIDORS - WEST
COMMON WORKS - WEST-MEP ROOMS
GENERATOR 1, SWITCH ROOM & OIL STORE
SUBSTATION 1
LOADING AREA FAN ROOM
SOUTH EAST
COMMON WORKS - SOUTH ZONE
LIBRARY, SHK.ZAYED LIFE & TIMES GALLERY AND LOBBY - SOUTH
PANTY AREA, TOILETS & JANITOR ROOMS - SOUTH
COLLECTION RESEARCH, WORKSHOPS & SECURITY/FIRE STAFF ROOMS - SOUTH
FUTURE EXPANSION ROOMS - SOUTH
MAJLIS & VIP ARRIVAL LOBBY AREAS - SOUTH
CIRCULATIONS & CORRIDORS - SOUTH
COMMON WORKS - SOUTH ZONE-MEP ROOMS
SUBSTATION 2
GENERATOR 2, SWITCH ROOM & OIL STORE
WATER TANKS, FIRE & DOMESTIC WATER PUMP ROOM
MEP WORKS
NORTH WEST
RESTAURANT GALLERIES,PANTRY,PUBLIC TOILETS,GRAB&GO- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
AV SYSTEM
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
AUDITORIUM,CONFERENCE ROOM,LOBBY AND ASSOCIATED ROOMS- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
KITCHEN AREA,TOILETS & JANITOR ROOMS- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
RESTAURANT,VIP VIEWING LOUNGE- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
STAFF OFFICE,VIP VIEWING LOBBY,SECURITY & SCAN AREAS- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
MAIN LOBBY
MEETING SPACE
CAFE
TICKET/INFO POINT
PERFORMANCE SPACE
RETAIL
CIRCULATIONS & CORRIDORS
ENTRANCE LOBBY
CITY ENTRANCE
MEP WORKS
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
GARDEN ENTRANCE
MEP WORKS
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
NORTH EAST
GALLERY C & FALCONRY AND CONSERVATION GALLERY - EAST
MECHANICAL
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV WORKS
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
FIRE ALARM & PUBLIC ADDRESS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE FIGHTING WORKS
WILDLIFE KITCHEN & STORAGE,PREPARATION RECEPTION & SHELTER AREAS - EAST
MECHANICAL
HOT & COLD WATER SYSTEM
DRAINAGE WORKS
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV WORKS
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
INTERVIEW,SECURITY SCAN, FIRST AID ROOMS AND OFFICE AREAS - EAST
MECHANICAL
HOT & COLD WATER SYSTEM
DRAINAGE WORKS
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
CIRCULATIONS & CORRIDORS - EAST
MECHANICAL
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SOUTH WEST
SECURITY, SCAN, INTERVIEW & CASH AREAS - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
ARTIFACT WORKSHOPS, SEP WORK & TOOL ROOMS - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SEP TOILETS - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
AV SYSTEM
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SEP GALLERIES & LOBBY - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
FUTURE EXPANSION ROOMS - WEST
ELECTRICAL WORKS
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
CIRCULATIONS & CORRIDORS - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SUBSTATION 1
MEP WORKS
MECHANICAL
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTERCOM SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEMS
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
ADDC RELATED WORKS - SUBSTATION 1
GENERATOR 1, SWITCH ROOM & OIL STORE
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING SYSTEM WORKS
LOADING AREA FAN ROOM
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING SYSTEM WORKS
SOUTH EAST
LIBRARY, SHK.ZAYED LIFE & TIMES GALLERY AND LOBBY - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
PANTRY AREA, TOILETS & JANITOR ROOMS - SOUTH
MECHANICAL
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
AV SYSTEM
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
COLLECTION RESEARCH, WORKSHOPS & SECURITY/FIRE STAFF ROOMS - SOUTH
MECHANICAL
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
FUTURE EXPANSION ROOMS - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
MAJLIS & VIP ARRIVAL LOBBY AREAS - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
CIRCULATIONS & CORRIDORS - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SUBSTATION 2
MEP WORKS
MECHANICAL WORKS
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTERCOM SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
ADDC RELATED WORKS - SUBSTATION 2
GENERATOR 2, SWITCH ROOM & OIL STORE
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING SYSTEM WORKS
WATER TANKS, FIRE & DOMESTIC WATER PUMP ROOM
MECHANICAL
HVAC SYSTEM WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING SYSTEM WORKS
LEVEL 01 MEZZANINE
CIVIL WORKS
ZONE 02A
ZONE 02B
ZONE 02C
ZONE 02D
ZONE 02E
ZONE 02G
ZONE 02H
ZONE 03A
ZONE 03B
ZONE 03C
STEEL STRUCTURE
ZONE 02A
ZONE 02B
ARCHITECTURAL WORKS
NORTH WEST
COMMON WORKS- NORTH
STAFF MALE AND FEMALE WC'S, MALE ABLUTIONS & PRAYER ROOM - NORTH
OFFICES, RECEPTIONS, MAIL ROOM, CALL CENTER, COMMERCIAL SERVICES & MEETING ROOMS- NORTH
OFFICE BALCONY- NORTH
FILE STORAGE, MALL ROOM & MASTER ROOM- NORTH
IT ROOM- NORTH
STAFF MALE AND FEMALE WC'S, FEMALE ABLUTIONS & PRAYER ROOM - NORTH
NORTH EAST
CIRCULATIONS & CORRIDORS- NORTH
COMMON WORKS - EAST
PUBLIC MALE & FEMALE WC - EAST
FALCONRY CLASSROOMS - EAST
FALCONRY OFFICE, MEETING ROOM & BALCONY - EAST
FALCONRY OFFICE IT ROOM - EAST
FALCONRY STORAGES & FALCONRY OFFICE SUPPLIES - EAST
FALCONRY OUTDOOR SHELTERS - EAST
MALE & FEMALE CHANGING ROOM - EAST
LOBBY & CIRCULATIONS - EAST
SOUTH EAST
COMMON WORKS - SOUTH
SCHOOL ARRIVAL, CLASS ROOMS & LUNCH ROOM - SOUTH
STORAGE 2, STORAGE 3 & CLASSROOM STORAGE - SOUTH
PUBLIC MALE & FEMALE W/C AND ABLUTION - SOUTH
PUBLIC MALE & FEMALE PRAYER - SOUTH
GALLERY A & B AV / IT ROOM & LOBBY - SOUTH
CIRCULATION - SOUTH
MEP WORKS
NORTH WEST
STAFF MALE AND FEMALE WC'S, MALE ABLUTIONS & PRAYER ROOM - NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
OFFICES, RECEPTIONS, MAIL ROOM, CALL CENTER, COMMERCIAL SERVICES & MEETING ROOMS- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
OFFICE BALCONY- NORTH
MECHANICAL
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
FILE STORAGE, MALL ROOM & MASTER ROOM- NORTH
MECHANICAL
DRAINAGE WORKS
HVAC SYSTEM WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
IT ROOM- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
STAFF MALE AND FEMALE WC'S, FEMALE ABLUTIONS & PRAYER ROOM - NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
NORTH EAST
CIRCULATIONS & CORRIDORS- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
PUBLIC MALE & FEMALE WC - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
FALCONRY CLASSROOMS - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
FALCONRY OFFICE, MEETING ROOM & BALCONY - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
FALCONRY OFFICE IT ROOM - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
FALCONRY STORAGES & FALCONRY OFFICE SUPPLIES - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
FALCONRY OUTDOOR SHELTERS - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
MALE & FEMALE CHANGING ROOM - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
LOBBY & CIRCULATIONS - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SOUTH EAST
SCHOOL ARRIVAL, CLASS ROOMS & LUNCH ROOM - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
STORAGE 2, STORAGE 3 & CLASSROOM STORAGE - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
PUBLIC MALE & FEMALE W/C AND ABLUTION - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
PUBLIC MALE & FEMALE PRAYER - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
GALLERY A & B AV / IT ROOM & LOBBY - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
CIRCULATION - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
LEVEL 02 GALLERY
CIVIL WORKS
ZONE 02A
ZONE 02B
ZONE 02C
ZONE 02D
ZONE 02E
ZONE 02G
ZONE 02H
ZONE 03B
ZONE 03C
STEEL STRUCTURE
ZONE 02G
ARCHITECTURAL WORKS
NORTH WEST
COMMON WORKS- NORTH
GALLERY LOBBY AREAS- NORTH
STAFF MALE & FEMALE WC, WASH UP & LOUNGE KITCHENETTE- NORTH
COMMON WORKS - NORTH MEP ROOMS
KITCHEN EXTRACT PLANT ROOM - NORTH
COOLING ROOM - NORTH
GALLERY 3 AV/ IT ROOMS - NORTH
AHU, ELEC CUPBOARD - NORTH
CIRCULATIONS & CORRIDORS- NORTH
NORTH EAST
COMMON WORKS - EAST
MEMBERS MALE & FEMALE WC - EAST
GALLERY LOBBY, WALKWAY & VIEWING PLATFORM - EAST
ELECT. CUPBOARD - EAST
CIRCULATIONS - EAST
GALLERY 4&5 LOBBY AREAS - SOUTH
SOUTH WEST
CIRCULATIONS & CORRIDORS - WEST
SOUTH EAST
COMMON WORKS - SOUTH
COMMON WORKS - SOUTH - MEP ROOMS
COOLING ROOM - SOUTH
GALLERY 4 AV, GALLERY 5 AV/ IT ROOM - SOUTH
STORAGE - SOUTH
GALLERY 5 LOBBY AREAS - SOUTH
VIP MALE & FEMALETOILET, PUBLIC MALE & FEMALE WC - SOUTH
VIP RECEPTION, MALE DINING, FEMALE DINING & COURTYARD - SOUTH
MALE & FEMALE ABLUTIONS & PANTRIES - SOUTH
PRAYER & MAJLIS - SOUTH
CIRCULATIONS - SOUTH
COMMON WORKS - WEST
COMMON WORKS - WEST - MEP ROOMS
GALLERY 1 LOBBY AREAS - WEST
COOLING ROOMS, GALLERY 1&2 AV/IT ROOM - WEST
GALLERY 1&2 LOBBY AREAS - WEST
STORAGE AREA - WEST
MEP WORKS
NORTH WEST
GALLERY LOBBY AREAS- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
KITCHEN EXTRACT PLANT ROOM - NORTH
MECHANICAL
HVAC SYSTEM WORKS
COLD WATER SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING SYSTEM WORKS
COOLING ROOM - NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING SYSTEM WORKS
GALLERY 3 AV/ IT ROOMS - NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING SYSTEM WORKS
STAFF MALE & FEMALE WC, WASH UP & LOUNGE KITCHEN- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
AHU, ELEC CUPBOARD - NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
CIRCULATIONS & CORRIDORS- NORTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
NORTH EAST
MEMBERS MALE & FEMALE WC - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
GALLERY LOBBY, WALKWAY & VIEWING PLATFORM - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
CIRCULATIONS - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
ELECT. CUPBOARD - EAST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
GALLERY 4&5 LOBBY AREAS - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SOUTH WEST
CIRCULATIONS & CORRIDORS - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SOUTH EAST
COOLING ROOM - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING SYSTEM WORKS
GALLERY 4 AV, GALLERY 5 AV/ IT ROOM - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
STORAGE - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
GALLERY 5 LOBBY AREAS - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
VIP MALE & FEMALETOILET, PUBLIC MALE & FEMALE WC - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
VIP RECEPTION, MALE DINING, FEMALE DINING & COURTYARD - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
MALE & FEMALE ABLUTIONS & PANTRIES - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
PRAYER & MAJLIS - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
CIRCULATIONS - SOUTH
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
GALLERY 1 LOBBY AREAS - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
COOLING ROOM, GALLERY 1 AV/IT ROOM - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
GALLERY 1&2 LOBBY AREAS - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
STORAGE AREA - WEST
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
INTRUDER & HOLD-UPS ALARMS
INTERCOM SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
ACTIVE COMPONENT SYSTEMS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
LEVEL 03 PLENUM
CIVIL WORKS
ZONE 02A
ZONE 02B
ZONE 02C
ZONE 02E
ZONE 02G
ZONE 02H
ARCHITECTURAL WORKS
NORTH WEST
PLENUM AREAS- NORTH
NORTH EAST
PLENUM AREAS - EAST
SOUTH WEST
PLENUM AREAS - WEST
SOUTH EAST
PLENUM AREAS - SOUTH
MEP WORKS
NORTH WEST
PLENUM AREAS- NORTH
MECHANICAL
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
NORTH EAST
PLENUM AREAS - EAST
MECHANICAL
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SOUTH WEST
PLENUM AREAS - WEST
MECHANICAL
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
SOUTH EAST
PLENUM AREAS - SOUTH
MECHANICAL
DRAINAGE WORKS
HOT & COLD WATER SYSTEM
HVAC SYSTEM WORKS
ELECTRICAL WORKS
ELV
ACCESS CONTROL & CENTRAL SECURITY SYSTEM
AV SYSTEM
VIDEO SURVEILLANCE SYSTEM
DATA AND TELECOMMUNICATION
BMS AND AUTOMATIC CONTROLS
LIFE AND SAFETY SYSTEM
EMERGENCY LIGHTING & CENTRAL BATTERY
FIRE ALARM & PUBLIC ADDRESS
FIRE FIGHTING WORKS
LEVEL 04 ROOF
CIVIL WORKS
ZONE 02A
ZONE 02B
ZONE 02C
ZONE 02G
ZONE 02H
ARCHITECTURAL WORKS
MEP WORKS
MECHANICAL
HVAC SYSTEM WORKS
DRAINAGE WORKS
COLD WATER SYSTEM
ELECTRICAL WORKS
ELV
VIDEO SURVEILLANCE SYSTEM
LIFE AND SAFETY SYSTEM
FIRE ALARM & PUBLIC ADDRESS
Zone 4
TUNNEL
CIVIL WORKS
ARCHITECTURAL WORKS
MEP WORKS
MECHANICAL
HVAC
PLUMBING
ELECTRICAL
LIFE & SAFETY SYSTEM
FIRE FIGHTING
ROOF WORKS
TESTING & CLOSEOUT
RAMPS
CIVIL WORKS
ZONE 04 - RAMP
ARCHITECTURAL & MEP WORKS
ZONE 04 - RAMP
TESTING & CLOSEOUT
Zone 5 - MINIBOX
CIVIL WORKS
ARCHITECTURAL WORKS
COMMON AREA WORKS
PARKING, ARRIVALS, DRIVEWAYS AND LOADING BAYS
ARCHITECTURAL FINISHES
TOILETS, WASH AREA, REFUSE AREA & FREEZER AREA
ARCHITECTURAL FINISHES
PUMP ROOM, PLANT ROOMS & WATER TANKS
ARCHITECTURAL FINISHES
SECURITY ROOMS, SCANNING ROOMS,DOCK MASTER ROOM, TELECOM ROOM & ULD AREA
ARCHITECTURAL FINISHES
NON F&B, GOOD RECEIPT, COLD ROOM
ARCHITECTURAL FINISHES
ELECTRICAL STORES, GARDEN STORES & CHEMICAL STORE
ARCHITECTURAL FINISHES
STAIRCASES
STAIR6
STAIR7
STAIR12
MEP WORKS
PARKING, ARRIVALS, DRIVEWAYS AND LOADING BAYS
MEP WORKS
MECHANICAL
HVAC SYSTEM WORKS
PLUMBING AND DRAINAGE WORKS
ELECTRICAL WORKS
ELV WORKS
LIFE AND SAFETY SYSTEM
FIRE FIGHTING WORKS
TOILETS, WASH AREA, REFUSE AREA & FREEZER AREA
MEP WORKS
MECHANICAL
HVAC SYSTEM WORKS
PLUMBING AND DRAINAGE WORKS
ELECTRICAL WORKS
ELV WORKS
LIFE AND SAFETY SYSTEM
FIRE FIGHTING WORKS
PUMP ROOM, PLANT ROOMS & WATER TANKS
MEP WORKS
MECHANICAL
HVAC SYSTEM WORKS
PLUMBING AND DRAINAGE WORKS
ELECTRICAL WORKS
ELV WORKS
LIFE AND SAFETY SYSTEM
FIRE FIGHTING SYSTEM WORKS
SECURITY ROOMS, SCANNING ROOMS,DOCK MASTER ROOM, TELECOM ROOM & ULD AREA
MEP WORKS
MECHANICAL WORKS
HVAC SYSTEM WORKS
PLUMBING AND DRAINAGE WORKS
ELECTRICAL WORKS
ELV WORKS
LIFE AND SAFETY SYSTEM
FIRE FIGHTING WORKS
NON F&B, GOOD RECEIPT, COLD ROOM
MEP WORKS
MECHANICAL WORKS
HVAC SYSTEM WORKS
PLUMBING AND DRAINAGE WORKS
ELECTRICAL WORKS
ELV WORKS
LIFE AND SAFETY SYSTEM
FIRE FIGHTING WORKS
ELECTRICAL STORES, GARDEN STORES & CHEMICAL STORE
MEP WORKS
MECHANICAL WORKS
HVAC SYSTEM WORKS
PLUMBING AND DRAINAGE WORKS
ELECTRICAL WORKS
ELV WORKS
LIFE AND SAFETY SYSTEM
FIRE FIGHTING WORKS
SHAFTS & RISERS
STAIRCASES
STAIR6
STAIR7
STAIR12
ROOF WORKS
CLOSE OUT
BUILDING FACADE WORKS
LEVEL 0 - GROUND FLOOR
EAST EGRESS
SOUTH EGRESS
WEST EGRESS
RESTAURANT GALLERY SIDE
RESTAURANT & VIP VIEWING SIDE
LEVEL 1 - MEZZANINE
ZNM OFFICE SIDE
FALCONRY OFFICE SIDE
LEVEL 3 - PLENUM
CITY ENTRANCE
CITY ENTRANCE GLAZING
CITY ENTRANCE GATE
GARDEN ENTRANCE
GARDEN ENTRANCE GLAZING
GARDEN ENTRANCE GATE
CENTRAL ROOF LIGHT
Mound Works
Zone M1A
External / Lower Level
Civil works
Walkway
Perimeter Wall
Architectural works
MEP works
Zone M2A
External / Lower Level
Civil works
Walkway
Perimeter Wall
Architectural works
MEP works
Zone M3A
External / Lower Level
Civil works
Perimeter Wall
Architectural works
MEP works
Zone M4A
External / Lower Level
Civil works
Walkway
Perimeter Wall
Architectural works
MEP works
Zone M5A
External / Lower Level
Civil works
Stage - 01
Walkway
Perimeter Wall
Stage - 02 (After TC - 15 erection)
Walkway A
Walkway B
Architectural works
MEP works
Zone M6A
External / Lower Level
Civil works
Walkway
Perimeter Wall
Architectural works
MEP works
Zone M7A
External / Lower Level
Civil works
Architectural works
MEP works
Zone M8
M8 - M1A
External / Lower Level
Civil works
Architectural works
MEP works
M8 - M2A
External / Lower Level
Civil works
Architectural works
MEP works
M8 - M3A
External / Lower Level
Civil works
Architectural works
MEP works
M8 - M4A
External / Lower Level
Civil works
Architectural works
MEP works
M8 - M5A
External / Lower Level
Civil works
Architectural works
MEP works
M8 - M6A
External / Lower Level
Civil works
Architectural works
MEP works
Zone M1B (Walkway -1)
Internal / Upper Level
Civil works
Walkway
Architectural works
MEP works
Zone M1B (Walkway -2)
Internal / Upper Level
Civil works
Walkway
Architectural works
MEP works
Zone M2B
Internal / Upper Level
Civil works
Walkway
Architectural works
MEP works
Zone M3B
Internal / Upper Level
Civil works
Walkway
Architectural works
MEP works
Zone M4B
Internal / Upper Level
Civil works
Walkway
Architectural works
MEP works
Zone M5B
Internal / Upper Level
Civil works
Walkway
Architectural works
MEP works
Zone M6B
Internal / Upper Level
Civil works
Walkway
Architectural works
MEP works
Zone M7B
Internal / Upper Level
Civil works
Walkway
Architectural works
MEP works
VIP Canopy & Courtyard
Internal / Upper Level
Civil works
Architectural works
MEP works
Leaveout Tower Crane Area
Tower Crane 10 (Zone M1A)
Civil works
Architectural works
MEP works
Tower Crane 11/12 (Zone M1A)
Civil works
Architectural works
MEP works
Tower Crane 13 (Zone M2A)
Civil works
Architectural works
MEP works
Tower Crane 14 (Zone M3A)
Civil works
Architectural works
MEP works
Tower Crane 15 (Zone M4A)
Civil works
Architectural works
MEP works
Tower Crane 16 (Zone M5A)
Civil works
Architectural works
MEP works
Tower Crane 17 (Zone M5A)
Civil works
Architectural works
MEP works
Tower Crane 18 (Zone M6A)
Civil works
Architectural works
MEP works
Tower Crane 19
Civil works
Architectural works
MEP works
Time Line Garden
TIMELINE GARDEN
TIME LINE GARDEN PHASE 1
URBAN AREA
EARTH FILLING & COMPACTION
ROUGH GRADING
UTILITY NETWORK - PHASE 1
SEWAGE NETWORK
EXTERNAL CONNECTION NETWORK 2
STORM WATER NETWORK
EXTERNAL CONNECTION NETWORK 3
MANHOLES
SLOT DRAINS
SWALES & SOAKAWAYS
POTABLE WATER
FIRE FIGHTING
ELECTRICAL LV CABLE & LIGHTING
TELECOMMUNICATION & SECURITY SYSTEMS
STREET LIGHTING & CCTV
BIKE STORAGE
STRUCTURAL WORKS
FINISHES
MEP WORKS
TESTING & CLOSEOUT
TOILETS & PLANT ROOMS ON PLAZA
STRUCTURAL WORKS
FINISHES
MEP WORKS
TESTING & CLOSEOUT
TLG MAINTENANCE YARD
STRUCTURAL WORKS
FINISHES
MEP WORKS
TESTING & CLOSEOUT
KIOSK1
STRUCTURAL WORKS
FINISHES
MEP WORKS
TESTING & CLOSEOUT
RETAINING STRUCTURES
EARTH WORKS
LANDSCAPE- FEATURES
IRRIGATION SYSTEM
MAIN LINE
LATERAL LINE
DRIP LINE
HARD LANDSCAPE
PLANTER BOXES/TREE PITS/WALLS
PIAZZA WATER FEATURE
STONE PAVING
RESIN BOUND GRAVEL - EXT307
RESIN BOUND GRAVEL - EXT308
CONCRETE BEDS AND FALAJ AREAS
SWALES AREA
ANGULAR GRAVEL -EXT319
STONE SEATS AND STEPS
OTHER FLOOR FINISHES
SOFT LANDSCAPE
LOCAL
INHOUSE
OVERSEAS
HYDROPHONICS
ACCESS ROUTES
MAINTENANCE AREA
PEDESTRIAN ROUTES
DROP OFF AREAS ( P S )
ACCESSORIES & FURNISHINGS
LIGHT POLE, FLAG, PLAY GROUND & OTHER FURNISHINGS
EXHIBITION SCHEME WORKS ( P S )
OASIS AREA
EARTH FILLING & COMPACTION
ROUGH GRADING
UTILITY WORKS - PHASE 1
SEWERAGE NETWORK
STORM WATER NETWORK
SWALES & SOAKAWAYS
ACO DRAIN
POTABLE WATER
FIRE FIGHTING
ELECTRICAL LV CABLE & LIGHTING
TELECOMMUNICATION & SECURITY SYSTEMS
STREET LIGHTING & CCTV
KIOSK3
STRUCTURAL WORKS
FINISHES
MEP WORKS
TESTING & CLOSEOUT
RETAINING STRUCTURES
EARTH WORKS
LANDSCAPE- FEATURES
IRRIGATION WATER
MAIN LINE
LATERAL LINE
DRIP LINE
HARDSCAPING WORKS
PLANTER BOXES/TREE PITS/WALLS
RESIN BOUND GRAVEL - EXT307
RESIN BOUND GRAVEL - EXT308
FALAJ & WATER FOUNTAIN
ANGULAR GRAVEL - EXT319
CONCRETE BEDS (SWALES AREA)
STONE SEATS AND STEPS
OTHER FLOOR FINISHES
SOFTSCAPING WORKS
LOCAL
INHOUSE
OVERSEAS
HYDROPHONICS
ACCESS ROUTES
PEDESTRIAN ROUTES
ACCESSORIES & FURNISHINGS
LIGHT POLE, FLAG, PLAY GROUND & OTHER FURNISHINGS
EXHIBITION SCHEME WORKS ( P S )
HANDOVER
TIME LINE GARDEN PHASE 2
DESERT AREA
EARTH FILLING & COMPACTION
ROUGH GRADING
UTILITY WORKS - PHASE 2
SEWAGE NETWORK
EXTERNAL CONNECTION NETWORK 3
STORM WATER NETWORK
SWALES & SOAKAWAYS
POTABLE WATER
FIRE FIGHTING
ELECTRICAL LV CABLE & LIGHTING
TELECOMMUNICATION & SECURITY SYSTEMS
STREET LIGHTING & CCTV
TOILETS & PLANT ROOMS AT WATERFRONT
STRUCTURAL WORKS
FINISHES
MEP WORKS
TESTING & CLOSEOUT
KIOSK2
STRUCTURAL WORKS
FINISHES
MEP WORKS
TESTING & CLOSEOUT
RETAINING STRUCTURES
EARTH WORKS
LANDSCAPE- FEATURES
IRRIGATION WATER
MAIN LINE
LATERAL LINE
DRIP LINE
HARDSCAPING WORKS
PLANTER BOXES/TREE PITS/WALLS
RESIN BOUND GRAVEL - EXT307
RESIN BOUND GRAVEL - EXT308
ANGULAR GRAVEL - EXT319
CONCRETE BEDS (SWALES)
STONE SEATS AND STEPS
OTHER FLOOR FINISHES
SOFTSCAPING WORKS
LOCAL
INHOUSE
OVERSEAS
ACCESS ROUTES
PEDESTRIAN ROUTES
ACCESSORIES & FURNISHINGS
BENCHES & OTHER FURNISHINGS
EXHIBITION SCHEME WORKS ( P S )
COAST AREA
EARTH FILLING & COMPACTION
ROUGH GRADING
UTILITY WORKS - PHASE 2
SEWERAGE NETWORK
STORM WATER NETWORK
SWALES & SOAKAWAYS
LIGHTING NETWORK
TELECOMMUNICATION & SECURITY SYSTEMS
STREET LIGHTING & CCTV
EARTH WORKS
IRRIGATION WATER
MAIN LINE
LATERAL LINE
DRIP LINE
HARDSCAPING WORKS
PLANTER BOXES/TREE PITS/WALLS
RESIN BOUND GRAVEL - EXT307
RESIN BOUND GRAVEL - EXT308
SWALES
ANGULAR GRAVEL
STONE WORKS
SOFTSCAPING WORKS
LOCAL
INHOUSE
OVERSEAS
ACCESS ROUTES
PEDESTRIAN ROUTES
ACCESSORIES & FURNISHINGS
BENCHES & OTHER FURNISHINGS
EXHIBITION SCHEME WORKS ( P S )
HANDOVER
UTILITY SERVICES TIE IN CONNECTIONS
IRRIGATION PUMPING STATION & CONTROL SYSTEM
IRRIGATION AUTOMATION SYSTEM & PUMPING STATION WORKS - ZONES
IRRIGATION AUTOMATION SYSTEM & PUMPING STATION WORKS - INSIDE PUMP ROOM
TESTING & COMMISSIONING
HANDING OVER & CLOSE OUT
External works
Office Courtyard 1 & 2
VIP Courtyard
Pump Room
Irrigation Automation System - All Zones
Parking Area
Other Hardscape Areas
Specialist Exhibition Fitout Works
SZLT - (SHK. ZAYED LIFE & TIMES GALLERY)
LAL - (GALLERY C & FALCONRY AND CONSERVATION GALLERY)
SEP GALLERY - Tentative Dates
PAH 01 - (POD 1 GALLERY)
PAH 02 - (POD 2 GALLERY)
HAS 01 - (POD 4 GALLERY)
HAS 02 - (POD 5 GALLERY)
HAS 1 & 2 NODE
PAH 1 & 2 NODE
TLG - (TIMELINE GARDEN)

## Applicable Unique Combinations
F1 | F2 | F3 | F4 | F5 | F6
01 | 01 | 01 | 04 | 009 | 30
01 | 04 | 01 | 04 | 009 | 50 | Row Labels
01 | 14 | 01 | 04 | 009 | 70 | 01
01 | 02 | 01 | 04 | 010 | 30 | 14
01 | 05 | 01 | 04 | 010 | 50 | 01
01 | 04 | 01 | 04 | 010 | 50 | 02
01 | 14 | 01 | 04 | 010 | 70 | 21
01 | 06 | 01 | 04 | 010 | 70 | 22
01 | 07 | 01 | 04 | 010 | 70 | 23
01 | 10 | 01 | 04 | 010 | 70 | 24
01 | 09 | 01 | 04 | 010 | 70 | 25
01 | 02 | 01 | 04 | 011 | 30 | 26
01 | 05 | 01 | 04 | 011 | 50 | 27
01 | 01 | 01 | 05 | 009 | 30 | 28
01 | 04 | 01 | 05 | 009 | 50 | 29
01 | 14 | 01 | 05 | 009 | 70 | 30
01 | 02 | 01 | 05 | 010 | 30 | 31
01 | 05 | 01 | 05 | 010 | 50 | 32
01 | 04 | 01 | 05 | 010 | 50 | 33
01 | 14 | 01 | 05 | 010 | 70 | 34
01 | 06 | 01 | 05 | 010 | 70 | 35
01 | 07 | 01 | 05 | 010 | 70 | 36
01 | 10 | 01 | 05 | 010 | 70 | 37
01 | 09 | 01 | 05 | 010 | 70 | 03
01 | 02 | 01 | 05 | 011 | 30 | 01
01 | 05 | 01 | 05 | 011 | 50 | 02
01 | 01 | 01 | 02 | 009 | 30 | 01
01 | 04 | 01 | 02 | 009 | 50 | 04
01 | 14 | 01 | 02 | 009 | 70 | 05
01 | 02 | 01 | 02 | 011 | 30 | 06
01 | 05 | 01 | 02 | 011 | 50 | 07
01 | 01 | 01 | 03 | 009 | 30 | 01
01 | 04 | 01 | 03 | 009 | 50 | 03
01 | 14 | 01 | 03 | 009 | 70 | 08
01 | 01 | 01 | 03 | 010 | 30 | 01
01 | 05 | 01 | 03 | 010 | 50 | 04
01 | 04 | 01 | 03 | 010 | 50 | 09
01 | 14 | 01 | 03 | 010 | 70 | 10
01 | 06 | 01 | 03 | 010 | 70 | 11
01 | 07 | 01 | 03 | 010 | 70 | 12
01 | 10 | 01 | 03 | 010 | 70 | 13
01 | 09 | 01 | 03 | 010 | 70 | Grand Total
01 | 02 | 01 | 03 | 011 | 30
01 | 05 | 01 | 03 | 011 | 50
01 | 01 | 01 | 01 | 009 | 30
01 | 04 | 01 | 01 | 009 | 50
01 | 14 | 01 | 01 | 009 | 70
01 | 02 | 01 | 01 | 010 | 30
01 | 05 | 01 | 01 | 010 | 50
01 | 04 | 01 | 01 | 010 | 50
01 | 14 | 01 | 01 | 010 | 70
01 | 06 | 01 | 01 | 010 | 70
01 | 07 | 01 | 01 | 010 | 70
01 | 10 | 01 | 01 | 010 | 70
01 | 09 | 01 | 01 | 010 | 70
01 | 02 | 01 | 01 | 011 | 30
01 | 05 | 01 | 01 | 011 | 50
01 | 01 | 01 | 06 | 008 | 30
01 | 02 | 01 | 06 | 008 | 30
01 | 04 | 01 | 06 | 008 | 50
01 | 04 | 01 | 46 | 003 | 01
01 | 14 | 01 | 46 | 003 | 01
01 | 14 | 01 | 45 | 005 | 01
01 | 04 | 01 | 45 | 005 | 01
01 | 04 | 01 | 49 | 006 | 02
01 | 14 | 01 | 06 | 008 | 70
01 | 06 | 01 | 46 | 003 | 01
01 | 08 | 01 | 46 | 003 | 01
01 | 07 | 01 | 46 | 003 | 01
01 | 10 | 01 | 46 | 003 | 01
01 | 09 | 01 | 46 | 003 | 01
01 | 06 | 01 | 45 | 005 | 01
01 | 08 | 01 | 45 | 005 | 01
01 | 07 | 01 | 45 | 005 | 01
01 | 10 | 01 | 45 | 005 | 01
01 | 09 | 01 | 45 | 005 | 01
01 | 13 | 01 | 06 | 008 | 70
01 | 08 | 01 | 49 | 006 | 02
01 | 06 | 01 | 49 | 006 | 02
01 | 07 | 01 | 49 | 006 | 02
01 | 10 | 01 | 49 | 006 | 02
01 | 09 | 01 | 49 | 006 | 02
01 | 01 | 01 | 17 | 001 | 30
01 | 04 | 01 | 46 | 001 | 01
01 | 04 | 01 | 46 | 001 | 02
01 | 04 | 01 | 46 | 001 | 05
01 | 04 | 01 | 46 | 001 | 03
01 | 04 | 01 | 44 | 001 | 01
01 | 04 | 01 | 44 | 001 | 02
01 | 04 | 01 | 47 | 001 | 01
01 | 04 | 01 | 47 | 001 | 02
01 | 04 | 01 | 47 | 001 | 05
01 | 04 | 01 | 45 | 001 | 01
01 | 04 | 01 | 45 | 001 | 02
01 | 04 | 01 | 45 | 001 | 05
01 | 04 | 01 | 45 | 001 | 03
01 | 06 | 01 | 46 | 001 | 02
01 | 08 | 01 | 46 | 001 | 02
01 | 07 | 01 | 46 | 001 | 02
01 | 10 | 01 | 46 | 001 | 02
01 | 09 | 01 | 46 | 001 | 02
01 | 06 | 01 | 46 | 001 | 05
01 | 08 | 01 | 46 | 001 | 05
01 | 07 | 01 | 46 | 001 | 05
01 | 10 | 01 | 46 | 001 | 05
01 | 09 | 01 | 46 | 001 | 05
01 | 08 | 01 | 46 | 001 | 03
01 | 09 | 01 | 46 | 001 | 03
01 | 06 | 01 | 46 | 001 | 01
01 | 07 | 01 | 46 | 001 | 01
01 | 10 | 01 | 46 | 001 | 01
01 | 09 | 01 | 46 | 001 | 01
01 | 06 | 01 | 46 | 001 | 03
01 | 07 | 01 | 46 | 001 | 03
01 | 10 | 01 | 46 | 001 | 03
01 | 06 | 01 | 44 | 001 | 02
01 | 07 | 01 | 44 | 001 | 02
01 | 10 | 01 | 44 | 001 | 02
01 | 09 | 01 | 44 | 001 | 02
01 | 08 | 01 | 44 | 001 | 02
01 | 06 | 01 | 44 | 001 | 01
01 | 08 | 01 | 44 | 001 | 01
01 | 07 | 01 | 44 | 001 | 01
01 | 10 | 01 | 44 | 001 | 01
01 | 09 | 01 | 44 | 001 | 01
01 | 06 | 01 | 47 | 001 | 01
01 | 08 | 01 | 47 | 001 | 01
01 | 07 | 01 | 47 | 001 | 01
01 | 10 | 01 | 47 | 001 | 01
01 | 09 | 01 | 47 | 001 | 01
01 | 06 | 01 | 47 | 001 | 02
01 | 08 | 01 | 47 | 001 | 02
01 | 07 | 01 | 47 | 001 | 02
01 | 10 | 01 | 47 | 001 | 02
01 | 09 | 01 | 47 | 001 | 02
01 | 06 | 01 | 47 | 001 | 05
01 | 08 | 01 | 47 | 001 | 05
01 | 07 | 01 | 47 | 001 | 05
01 | 10 | 01 | 47 | 001 | 05
01 | 09 | 01 | 47 | 001 | 05
01 | 06 | 01 | 45 | 001 | 02
01 | 08 | 01 | 45 | 001 | 02
01 | 07 | 01 | 45 | 001 | 02
01 | 10 | 01 | 45 | 001 | 02
01 | 09 | 01 | 45 | 001 | 02
01 | 06 | 01 | 45 | 001 | 05
01 | 08 | 01 | 45 | 001 | 05
01 | 07 | 01 | 45 | 001 | 05
01 | 10 | 01 | 45 | 001 | 05
01 | 09 | 01 | 45 | 001 | 05
01 | 06 | 01 | 45 | 001 | 01
01 | 08 | 01 | 45 | 001 | 01
01 | 07 | 01 | 45 | 001 | 01
01 | 10 | 01 | 45 | 001 | 01
01 | 09 | 01 | 45 | 001 | 01
01 | 01 | 01 | 10 | 002 | 30
01 | 01 | 01 | 17 | 002 | 30
01 | 04 | 01 | 46 | 002 | 02
01 | 04 | 01 | 44 | 002 | 02
01 | 04 | 01 | 47 | 002 | 02
01 | 04 | 01 | 45 | 002 | 02
01 | 04 | 01 | 45 | 002 | 04
01 | 07 | 01 | 46 | 002 | 02
01 | 06 | 01 | 46 | 002 | 02
01 | 08 | 01 | 46 | 002 | 02
01 | 10 | 01 | 46 | 002 | 02
01 | 09 | 01 | 46 | 002 | 02
01 | 06 | 01 | 44 | 002 | 02
01 | 08 | 01 | 44 | 002 | 02
01 | 07 | 01 | 44 | 002 | 02
01 | 10 | 01 | 44 | 002 | 02
01 | 09 | 01 | 44 | 002 | 02
01 | 06 | 01 | 47 | 002 | 02
01 | 08 | 01 | 47 | 002 | 02
01 | 07 | 01 | 47 | 002 | 02
01 | 10 | 01 | 47 | 002 | 02
01 | 09 | 01 | 47 | 002 | 02
01 | 06 | 01 | 45 | 002 | 02
01 | 08 | 01 | 45 | 002 | 02
01 | 10 | 01 | 45 | 002 | 02
01 | 09 | 01 | 45 | 002 | 02
01 | 07 | 01 | 45 | 002 | 02
01 | 01 | 01 | 09 | 003 | 30
01 | 01 | 01 | 10 | 003 | 30
01 | 01 | 01 | 11 | 003 | 30
01 | 01 | 01 | 12 | 003 | 30
01 | 01 | 01 | 13 | 003 | 30
01 | 01 | 01 | 16 | 003 | 30
01 | 01 | 01 | 17 | 003 | 30
01 | 01 | 01 | 15 | 003 | 30
01 | 14 | 01 | 46 | 003 | 03
01 | 04 | 01 | 46 | 003 | 03
01 | 14 | 01 | 46 | 003 | 05
01 | 04 | 01 | 46 | 003 | 05
01 | 04 | 01 | 44 | 003 | 01
01 | 14 | 01 | 44 | 003 | 01
01 | 04 | 01 | 44 | 003 | 05
01 | 14 | 01 | 44 | 003 | 05
01 | 04 | 01 | 47 | 003 | 01
01 | 04 | 01 | 47 | 003 | 05
01 | 04 | 01 | 47 | 003 | 03
01 | 14 | 01 | 47 | 003 | 03
01 | 14 | 01 | 47 | 003 | 05
01 | 14 | 01 | 47 | 003 | 01
01 | 04 | 01 | 47 | 003 | 02
01 | 14 | 01 | 47 | 003 | 02
01 | 04 | 01 | 45 | 003 | 01
01 | 04 | 01 | 45 | 003 | 03
01 | 14 | 01 | 45 | 003 | 03
01 | 04 | 01 | 45 | 003 | 05
01 | 14 | 01 | 45 | 003 | 05
01 | 14 | 01 | 45 | 003 | 01
01 | 04 | 01 | 45 | 003 | 02
01 | 14 | 01 | 45 | 003 | 02
01 | 06 | 01 | 46 | 003 | 03
01 | 08 | 01 | 46 | 003 | 03
01 | 07 | 01 | 46 | 003 | 03
01 | 10 | 01 | 46 | 003 | 03
01 | 09 | 01 | 46 | 003 | 03
01 | 06 | 01 | 46 | 003 | 05
01 | 08 | 01 | 46 | 003 | 05
01 | 07 | 01 | 46 | 003 | 05
01 | 10 | 01 | 46 | 003 | 05
01 | 09 | 01 | 46 | 003 | 05
01 | 08 | 01 | 44 | 003 | 01
01 | 06 | 01 | 44 | 003 | 01
01 | 07 | 01 | 44 | 003 | 01
01 | 10 | 01 | 44 | 003 | 01
01 | 09 | 01 | 44 | 003 | 01
01 | 08 | 01 | 44 | 003 | 05
01 | 06 | 01 | 44 | 003 | 05
01 | 07 | 01 | 44 | 003 | 05
01 | 10 | 01 | 44 | 003 | 05
01 | 09 | 01 | 44 | 003 | 05
01 | 06 | 01 | 47 | 003 | 05
01 | 08 | 01 | 47 | 003 | 05
01 | 07 | 01 | 47 | 003 | 05
01 | 10 | 01 | 47 | 003 | 05
01 | 09 | 01 | 47 | 003 | 05
01 | 06 | 01 | 47 | 003 | 03
01 | 08 | 01 | 47 | 003 | 03
01 | 07 | 01 | 47 | 003 | 03
01 | 10 | 01 | 47 | 003 | 03
01 | 09 | 01 | 47 | 003 | 03
01 | 06 | 01 | 47 | 003 | 01
01 | 08 | 01 | 47 | 003 | 01
01 | 07 | 01 | 47 | 003 | 01
01 | 10 | 01 | 47 | 003 | 01
01 | 09 | 01 | 47 | 003 | 01
01 | 06 | 01 | 47 | 003 | 02
01 | 07 | 01 | 47 | 003 | 02
01 | 10 | 01 | 47 | 003 | 02
01 | 09 | 01 | 47 | 003 | 02
01 | 08 | 01 | 47 | 003 | 02
01 | 06 | 01 | 45 | 003 | 01
01 | 08 | 01 | 45 | 003 | 01
01 | 07 | 01 | 45 | 003 | 01
01 | 10 | 01 | 45 | 003 | 01
01 | 09 | 01 | 45 | 003 | 01
01 | 08 | 01 | 45 | 003 | 03
01 | 06 | 01 | 45 | 003 | 03
01 | 07 | 01 | 45 | 003 | 03
01 | 10 | 01 | 45 | 003 | 03
01 | 09 | 01 | 45 | 003 | 03
01 | 08 | 01 | 45 | 003 | 05
01 | 06 | 01 | 45 | 003 | 05
01 | 07 | 01 | 45 | 003 | 05
01 | 10 | 01 | 45 | 003 | 05
01 | 09 | 01 | 45 | 003 | 05
01 | 06 | 01 | 45 | 003 | 02
01 | 07 | 01 | 45 | 003 | 02
01 | 10 | 01 | 45 | 003 | 02
01 | 09 | 01 | 45 | 003 | 02
01 | 08 | 01 | 45 | 003 | 02
01 | 01 | 01 | 07 | 004 | 30
01 | 01 | 01 | 08 | 004 | 30
01 | 01 | 01 | 09 | 004 | 30
01 | 01 | 01 | 10 | 004 | 30
01 | 01 | 01 | 11 | 004 | 30
01 | 01 | 01 | 13 | 004 | 30
01 | 01 | 01 | 14 | 004 | 30
01 | 01 | 01 | 15 | 004 | 30
01 | 01 | 01 | 16 | 004 | 30
01 | 01 | 01 | 17 | 004 | 30
01 | 02 | 01 | 07 | 004 | 30
01 | 02 | 01 | 08 | 004 | 30
01 | 04 | 01 | 46 | 004 | 01
01 | 04 | 01 | 46 | 004 | 03
01 | 14 | 01 | 46 | 004 | 03
01 | 14 | 01 | 46 | 004 | 05
01 | 04 | 01 | 46 | 004 | 05
01 | 14 | 01 | 46 | 004 | 02
01 | 04 | 01 | 46 | 004 | 02
01 | 14 | 01 | 44 | 004 | 01
01 | 04 | 01 | 44 | 004 | 01
01 | 14 | 01 | 44 | 004 | 03
01 | 04 | 01 | 44 | 004 | 03
01 | 14 | 01 | 44 | 004 | 05
01 | 04 | 01 | 44 | 004 | 05
01 | 04 | 01 | 45 | 004 | 01
01 | 14 | 01 | 45 | 004 | 01
01 | 14 | 01 | 45 | 004 | 05
01 | 04 | 01 | 45 | 004 | 05
01 | 04 | 01 | 45 | 004 | 03
01 | 14 | 01 | 45 | 004 | 03
01 | 14 | 01 | 45 | 004 | 02
01 | 04 | 01 | 45 | 004 | 02
01 | 06 | 01 | 46 | 004 | 03
01 | 08 | 01 | 46 | 004 | 03
01 | 07 | 01 | 46 | 004 | 03
01 | 10 | 01 | 46 | 004 | 03
01 | 09 | 01 | 46 | 004 | 03
01 | 06 | 01 | 46 | 004 | 05
01 | 08 | 01 | 46 | 004 | 05
01 | 07 | 01 | 46 | 004 | 05
01 | 10 | 01 | 46 | 004 | 05
01 | 09 | 01 | 46 | 004 | 05
01 | 06 | 01 | 46 | 004 | 02
01 | 08 | 01 | 46 | 004 | 02
01 | 07 | 01 | 46 | 004 | 02
01 | 10 | 01 | 46 | 004 | 02
01 | 09 | 01 | 46 | 004 | 02
01 | 06 | 01 | 44 | 004 | 01
01 | 08 | 01 | 44 | 004 | 01
01 | 07 | 01 | 44 | 004 | 01
01 | 10 | 01 | 44 | 004 | 01
01 | 09 | 01 | 44 | 004 | 01
01 | 06 | 01 | 44 | 004 | 03
01 | 08 | 01 | 44 | 004 | 03
01 | 07 | 01 | 44 | 004 | 03
01 | 10 | 01 | 44 | 004 | 03
01 | 09 | 01 | 44 | 004 | 03
01 | 06 | 01 | 44 | 004 | 05
01 | 08 | 01 | 44 | 004 | 05
01 | 07 | 01 | 44 | 004 | 05
01 | 10 | 01 | 44 | 004 | 05
01 | 09 | 01 | 44 | 004 | 05
01 | 06 | 01 | 44 | 004 | 02
01 | 08 | 01 | 44 | 004 | 02
01 | 07 | 01 | 44 | 004 | 02
01 | 10 | 01 | 44 | 004 | 02
01 | 09 | 01 | 44 | 004 | 02
01 | 06 | 01 | 45 | 004 | 01
01 | 08 | 01 | 45 | 004 | 01
01 | 07 | 01 | 45 | 004 | 01
01 | 10 | 01 | 45 | 004 | 01
01 | 09 | 01 | 45 | 004 | 01
01 | 06 | 01 | 45 | 004 | 05
01 | 08 | 01 | 45 | 004 | 05
01 | 07 | 01 | 45 | 004 | 05
01 | 10 | 01 | 45 | 004 | 05
01 | 09 | 01 | 45 | 004 | 05
01 | 06 | 01 | 45 | 004 | 03
01 | 08 | 01 | 45 | 004 | 03
01 | 07 | 01 | 45 | 004 | 03
01 | 10 | 01 | 45 | 004 | 03
01 | 09 | 01 | 45 | 004 | 03
01 | 06 | 01 | 45 | 004 | 02
01 | 08 | 01 | 45 | 004 | 02
01 | 07 | 01 | 45 | 004 | 02
01 | 10 | 01 | 45 | 004 | 02
01 | 09 | 01 | 45 | 004 | 02
01 | 01 | 01 | 07 | 005 | 30
01 | 01 | 01 | 08 | 005 | 30
01 | 01 | 01 | 09 | 005 | 30
01 | 01 | 01 | 10 | 005 | 30
01 | 01 | 01 | 11 | 005 | 30
01 | 01 | 01 | 13 | 005 | 30
01 | 01 | 01 | 14 | 005 | 30
01 | 01 | 01 | 16 | 005 | 30
01 | 01 | 01 | 17 | 005 | 30
01 | 02 | 01 | 13 | 005 | 30
01 | 04 | 01 | 46 | 005 | 01
01 | 14 | 01 | 46 | 005 | 01
01 | 04 | 01 | 46 | 005 | 03
01 | 14 | 01 | 46 | 005 | 03
01 | 04 | 01 | 46 | 005 | 02
01 | 14 | 01 | 46 | 005 | 02
01 | 04 | 01 | 44 | 005 | 01
01 | 04 | 01 | 44 | 005 | 03
01 | 14 | 01 | 44 | 005 | 03
01 | 14 | 01 | 44 | 005 | 01
01 | 14 | 01 | 44 | 005 | 02
01 | 04 | 01 | 44 | 005 | 02
01 | 14 | 01 | 47 | 005 | 01
01 | 04 | 01 | 47 | 005 | 01
01 | 04 | 01 | 45 | 005 | 02
01 | 14 | 01 | 45 | 005 | 05
01 | 04 | 01 | 45 | 005 | 05
01 | 04 | 01 | 45 | 005 | 03
01 | 14 | 01 | 45 | 005 | 03
01 | 14 | 01 | 45 | 005 | 02
01 | 06 | 01 | 46 | 005 | 01
01 | 08 | 01 | 46 | 005 | 01
01 | 07 | 01 | 46 | 005 | 01
01 | 10 | 01 | 46 | 005 | 01
01 | 09 | 01 | 46 | 005 | 01
01 | 06 | 01 | 46 | 005 | 02
01 | 08 | 01 | 46 | 005 | 02
01 | 07 | 01 | 46 | 005 | 02
01 | 10 | 01 | 46 | 005 | 02
01 | 09 | 01 | 46 | 005 | 02
01 | 06 | 01 | 46 | 005 | 03
01 | 08 | 01 | 46 | 005 | 03
01 | 07 | 01 | 46 | 005 | 03
01 | 10 | 01 | 46 | 005 | 03
01 | 09 | 01 | 46 | 005 | 03
01 | 06 | 01 | 44 | 005 | 03
01 | 08 | 01 | 44 | 005 | 03
01 | 07 | 01 | 44 | 005 | 03
01 | 10 | 01 | 44 | 005 | 03
01 | 09 | 01 | 44 | 005 | 03
01 | 06 | 01 | 44 | 005 | 01
01 | 08 | 01 | 44 | 005 | 01
01 | 07 | 01 | 44 | 005 | 01
01 | 10 | 01 | 44 | 005 | 01
01 | 09 | 01 | 44 | 005 | 01
01 | 06 | 01 | 44 | 005 | 02
01 | 08 | 01 | 44 | 005 | 02
01 | 07 | 01 | 44 | 005 | 02
01 | 10 | 01 | 44 | 005 | 02
01 | 09 | 01 | 44 | 005 | 02
01 | 06 | 01 | 47 | 005 | 01
01 | 08 | 01 | 47 | 005 | 01
01 | 07 | 01 | 47 | 005 | 01
01 | 10 | 01 | 47 | 005 | 01
01 | 09 | 01 | 47 | 005 | 01
01 | 06 | 01 | 45 | 005 | 02
01 | 08 | 01 | 45 | 005 | 02
01 | 07 | 01 | 45 | 005 | 02
01 | 10 | 01 | 45 | 005 | 02
01 | 09 | 01 | 45 | 005 | 02
01 | 06 | 01 | 45 | 005 | 05
01 | 08 | 01 | 45 | 005 | 05
01 | 07 | 01 | 45 | 005 | 05
01 | 10 | 01 | 45 | 005 | 05
01 | 09 | 01 | 45 | 005 | 05
01 | 06 | 01 | 45 | 005 | 03
01 | 08 | 01 | 45 | 005 | 03
01 | 07 | 01 | 45 | 005 | 03
01 | 10 | 01 | 45 | 005 | 03
01 | 09 | 01 | 45 | 005 | 03
01 | 01 | 01 | 07 | 006 | 30
01 | 01 | 01 | 08 | 006 | 30
01 | 01 | 01 | 09 | 006 | 30
01 | 01 | 01 | 11 | 006 | 30
01 | 01 | 01 | 13 | 006 | 30
01 | 01 | 01 | 14 | 006 | 30
01 | 04 | 01 | 46 | 006 | 02
01 | 04 | 01 | 44 | 006 | 02
01 | 04 | 01 | 47 | 006 | 02
01 | 04 | 01 | 45 | 006 | 02
01 | 08 | 01 | 46 | 006 | 02
01 | 06 | 01 | 46 | 006 | 02
01 | 07 | 01 | 46 | 006 | 02
01 | 10 | 01 | 46 | 006 | 02
01 | 09 | 01 | 46 | 006 | 02
01 | 08 | 01 | 44 | 006 | 02
01 | 06 | 01 | 44 | 006 | 02
01 | 07 | 01 | 44 | 006 | 02
01 | 10 | 01 | 44 | 006 | 02
01 | 09 | 01 | 44 | 006 | 02
01 | 08 | 01 | 47 | 006 | 02
01 | 06 | 01 | 47 | 006 | 02
01 | 07 | 01 | 47 | 006 | 02
01 | 10 | 01 | 47 | 006 | 02
01 | 09 | 01 | 47 | 006 | 02
01 | 08 | 01 | 45 | 006 | 02
01 | 06 | 01 | 45 | 006 | 02
01 | 07 | 01 | 45 | 006 | 02
01 | 10 | 01 | 45 | 006 | 02
01 | 09 | 01 | 45 | 006 | 02
01 | 01 | 01 | 07 | 007 | 30
01 | 01 | 01 | 08 | 007 | 30
01 | 01 | 01 | 09 | 007 | 30
01 | 01 | 01 | 13 | 007 | 30
01 | 01 | 01 | 14 | 007 | 30
01 | 04 | 01 | 50 | 007 | 30
01 | 06 | 01 | 50 | 007 | 02
01 | 08 | 01 | 50 | 007 | 02
01 | 07 | 01 | 50 | 007 | 02
01 | 10 | 01 | 50 | 007 | 02
01 | 09 | 01 | 50 | 007 | 02
01 | 01 | 01 | 18 | 001 | 30
01 | 04 | 01 | 18 | 001 | 50
01 | 06 | 01 | 18 | 001 | 70
01 | 08 | 01 | 18 | 001 | 70
01 | 07 | 01 | 18 | 001 | 70
01 | 14 | 01 | 18 | 001 | 30
01 | 04 | 01 | 18 | 001 | 30
01 | 14 | 01 | 18 | 001 | 70
01 | 14 | 01 | 18 | 001 | 50
01 | 01 | 01 | 18 | 003 | 30
01 | 04 | 01 | 18 | 003 | 50
01 | 14 | 01 | 18 | 003 | 70
01 | 14 | 01 | 18 | 003 | 50
01 | 01 | 01 | 19 | 004 | 30
01 | 01 | 01 | 19 | 001 | 30
01 | 04 | 01 | 19 | 001 | 50
01 | 11 | 01 | 19 | 001 | 50
01 | 06 | 01 | 19 | 001 | 70
01 | 08 | 01 | 19 | 001 | 70
01 | 07 | 01 | 19 | 001 | 70
01 | 10 | 01 | 19 | 001 | 70
01 | 09 | 01 | 19 | 001 | 70
01 | 14 | 01 | 19 | 001 | 70
01 | 04 | 01 | 19 | 001 | 70
01 | 04 | 01 | 19 | 001 | 30
01 | 14 | 01 | 48 | 001 | 70
01 | 14 | 01 | 48 | 001 | 50
01 | 05 | 01 | 51 | 003 | 50
01 | 14 | 01 | 51 | 003 | 50
01 | 05 | 01 | 51 | 004 | 50
01 | 14 | 01 | 51 | 004 | 50
01 | 01 | 02 | 21 | 012 | 08
01 | 01 | 02 | 21 | 012 | 07
01 | 04 | 02 | 21 | 012 | 08
01 | 14 | 02 | 21 | 012 | 08
01 | 01 | 02 | 22 | 012 | 08
01 | 01 | 02 | 22 | 012 | 07
01 | 04 | 02 | 22 | 012 | 08
01 | 14 | 02 | 22 | 012 | 08
01 | 01 | 02 | 23 | 012 | 08
01 | 04 | 02 | 23 | 012 | 08
01 | 14 | 02 | 23 | 012 | 08
01 | 01 | 02 | 24 | 012 | 08
01 | 01 | 02 | 24 | 012 | 06
01 | 04 | 02 | 24 | 012 | 08
01 | 14 | 02 | 24 | 012 | 08
01 | 01 | 02 | 25 | 012 | 08
01 | 01 | 02 | 25 | 012 | 06
01 | 04 | 02 | 25 | 012 | 08
01 | 14 | 02 | 25 | 012 | 08
01 | 01 | 02 | 26 | 012 | 08
01 | 01 | 02 | 26 | 012 | 06
01 | 04 | 02 | 26 | 012 | 08
01 | 14 | 02 | 26 | 012 | 08
01 | 01 | 02 | 27 | 012 | 08
01 | 04 | 02 | 27 | 012 | 08
01 | 14 | 02 | 27 | 012 | 08
01 | 01 | 02 | 28 | 012 | 08
01 | 04 | 02 | 28 | 012 | 08
01 | 14 | 02 | 28 | 012 | 08
01 | 01 | 02 | 29 | 013 | 09
01 | 01 | 02 | 29 | 013 | 06
01 | 04 | 02 | 29 | 013 | 09
01 | 14 | 02 | 29 | 013 | 09
01 | 01 | 02 | 30 | 013 | 09
01 | 01 | 02 | 30 | 013 | 07
01 | 04 | 02 | 30 | 013 | 09
01 | 14 | 02 | 30 | 013 | 09
01 | 01 | 02 | 31 | 013 | 09
01 | 01 | 02 | 31 | 013 | 07
01 | 04 | 02 | 31 | 013 | 09
01 | 14 | 02 | 31 | 013 | 09
01 | 01 | 02 | 32 | 013 | 09
01 | 01 | 02 | 32 | 013 | 07
01 | 04 | 02 | 32 | 013 | 09
01 | 14 | 02 | 32 | 013 | 09
01 | 01 | 02 | 33 | 013 | 09
01 | 01 | 02 | 33 | 013 | 07
01 | 04 | 02 | 33 | 013 | 09
01 | 14 | 02 | 33 | 013 | 09
01 | 01 | 02 | 34 | 013 | 09
01 | 01 | 02 | 34 | 013 | 07
01 | 04 | 02 | 34 | 013 | 09
01 | 14 | 02 | 34 | 013 | 09
01 | 01 | 02 | 35 | 013 | 09
01 | 01 | 02 | 35 | 013 | 06
01 | 04 | 02 | 35 | 013 | 09
01 | 14 | 02 | 35 | 013 | 09
01 | 01 | 02 | 36 | 013 | 09
01 | 01 | 02 | 36 | 013 | 06
01 | 04 | 02 | 36 | 013 | 09
01 | 14 | 02 | 36 | 013 | 09
01 | 01 | 02 | 37 | 013 | 09
01 | 04 | 02 | 37 | 013 | 09
01 | 14 | 02 | 37 | 013 | 09
01 | 01 | 02 | 21 | 012 | 30
01 | 04 | 02 | 21 | 012 | 50
01 | 14 | 02 | 21 | 012 | 70
01 | 14 | 02 | 22 | 012 | 30
01 | 04 | 02 | 22 | 012 | 50
01 | 14 | 02 | 22 | 012 | 70
01 | 01 | 02 | 23 | 012 | 30
01 | 04 | 02 | 23 | 012 | 50
01 | 14 | 02 | 23 | 012 | 70
01 | 01 | 02 | 25 | 012 | 30
01 | 04 | 02 | 25 | 012 | 50
01 | 14 | 02 | 25 | 012 | 70
01 | 01 | 02 | 26 | 012 | 30
01 | 04 | 02 | 26 | 012 | 50
01 | 14 | 02 | 26 | 012 | 70
01 | 11 | 03 | 38 | 014 | 11
01 | 12 | 03 | 38 | 014 | 11
01 | 09 | 03 | 38 | 014 | 11
01 | 07 | 03 | 38 | 014 | 11
01 | 10 | 03 | 38 | 014 | 11
01 | 01 | 03 | 38 | 014 | 11
01 | 04 | 03 | 38 | 014 | 11
01 | 14 | 03 | 38 | 014 | 11
01 | 11 | 03 | 38 | 014 | 12
01 | 12 | 03 | 38 | 014 | 12
01 | 09 | 03 | 38 | 014 | 12
01 | 07 | 03 | 38 | 014 | 12
01 | 10 | 03 | 38 | 014 | 12
01 | 01 | 03 | 38 | 014 | 12
01 | 04 | 03 | 38 | 014 | 12
01 | 14 | 03 | 38 | 014 | 12
01 | 14 | 03 | 38 | 014 | 70
01 | 04 | 03 | 38 | 014 | 50
01 | 11 | 03 | 39 | 014 | 13
01 | 12 | 03 | 39 | 014 | 13
01 | 09 | 03 | 39 | 014 | 13
01 | 07 | 03 | 39 | 014 | 13
01 | 10 | 03 | 39 | 014 | 13
01 | 01 | 03 | 39 | 014 | 13
01 | 04 | 03 | 39 | 014 | 13
01 | 14 | 03 | 39 | 014 | 13
01 | 11 | 03 | 39 | 014 | 14
01 | 12 | 03 | 39 | 014 | 14
01 | 07 | 03 | 39 | 014 | 14
01 | 10 | 03 | 39 | 014 | 14
01 | 14 | 03 | 39 | 014 | 70
01 | 04 | 03 | 39 | 014 | 50
01 | 12 | 03 | 52 | 014 | 70
01 | 14 | 03 | 52 | 014 | 70
01 | 11 | 03 | 52 | 014 | 70
01 | 01 | 04 | 40 | 014 | 30
01 | 01 | 04 | 37 | 014 | 30
01 | 01 | 04 | 52 | 014 | 70
01 | 08 | 04 | 52 | 014 | 70
01 | 01 | 04 | 41 | 014 | 30
01 | 01 | 04 | 52 | 014 | 30
01 | 04 | 01 | 53 | 003 | 04
01 | 04 | 01 | 53 | 005 | 04
01 | 04 | 03 | 53 | 014 | 04

## Sheet1
01 | 01 | 01 | 04 | 009 | 30
01 | 01 | 01 | 05 | 009 | 30
01 | 01 | 01 | 02 | 009 | 30
01 | 01 | 01 | 03 | 009 | 30
01 | 01 | 01 | 03 | 010 | 30
01 | 01 | 01 | 01 | 009 | 30
01 | 01 | 01 | 06 | 008 | 30
01 | 01 | 01 | 17 | 001 | 30
01 | 01 | 01 | 10 | 002 | 30
01 | 01 | 01 | 17 | 002 | 30
01 | 01 | 01 | 09 | 003 | 30
01 | 01 | 01 | 10 | 003 | 30
01 | 01 | 01 | 11 | 003 | 30
01 | 01 | 01 | 12 | 003 | 30
01 | 01 | 01 | 13 | 003 | 30
01 | 01 | 01 | 16 | 003 | 30
01 | 01 | 01 | 17 | 003 | 30
01 | 01 | 01 | 15 | 003 | 30
01 | 01 | 01 | 07 | 004 | 30
01 | 01 | 01 | 08 | 004 | 30
01 | 01 | 01 | 09 | 004 | 30
01 | 01 | 01 | 10 | 004 | 30
01 | 01 | 01 | 11 | 004 | 30
01 | 01 | 01 | 13 | 004 | 30
01 | 01 | 01 | 14 | 004 | 30
01 | 01 | 01 | 15 | 004 | 30
01 | 01 | 01 | 16 | 004 | 30
01 | 01 | 01 | 17 | 004 | 30
01 | 01 | 01 | 07 | 005 | 30
01 | 01 | 01 | 08 | 005 | 30
01 | 01 | 01 | 09 | 005 | 30
01 | 01 | 01 | 10 | 005 | 30
01 | 01 | 01 | 11 | 005 | 30
01 | 01 | 01 | 13 | 005 | 30
01 | 01 | 01 | 14 | 005 | 30
01 | 01 | 01 | 16 | 005 | 30
01 | 01 | 01 | 17 | 005 | 30
01 | 01 | 01 | 07 | 006 | 30
01 | 01 | 01 | 08 | 006 | 30
01 | 01 | 01 | 09 | 006 | 30
01 | 01 | 01 | 11 | 006 | 30
01 | 01 | 01 | 13 | 006 | 30
01 | 01 | 01 | 14 | 006 | 30
01 | 01 | 01 | 07 | 007 | 30
01 | 01 | 01 | 08 | 007 | 30
01 | 01 | 01 | 09 | 007 | 30
01 | 01 | 01 | 13 | 007 | 30
01 | 01 | 01 | 14 | 007 | 30
01 | 01 | 01 | 18 | 001 | 30
01 | 01 | 01 | 18 | 003 | 30
01 | 01 | 01 | 19 | 004 | 30
01 | 01 | 01 | 19 | 001 | 30
01 | 01 | 02 | 21 | 012 | 08
01 | 01 | 02 | 21 | 012 | 07
01 | 01 | 02 | 22 | 012 | 08
01 | 01 | 02 | 22 | 012 | 07
01 | 01 | 02 | 23 | 012 | 08
01 | 01 | 02 | 24 | 012 | 08
01 | 01 | 02 | 24 | 012 | 06
01 | 01 | 02 | 25 | 012 | 08
01 | 01 | 02 | 25 | 012 | 06
01 | 01 | 02 | 26 | 012 | 08
01 | 01 | 02 | 26 | 012 | 06
01 | 01 | 02 | 27 | 012 | 08
01 | 01 | 02 | 28 | 012 | 08
01 | 01 | 02 | 29 | 013 | 09
01 | 01 | 02 | 29 | 013 | 06
01 | 01 | 02 | 30 | 013 | 09
01 | 01 | 02 | 30 | 013 | 07
01 | 01 | 02 | 31 | 013 | 09
01 | 01 | 02 | 31 | 013 | 07
01 | 01 | 02 | 32 | 013 | 09
01 | 01 | 02 | 32 | 013 | 07
01 | 01 | 02 | 33 | 013 | 09
01 | 01 | 02 | 33 | 013 | 07
01 | 01 | 02 | 34 | 013 | 09
01 | 01 | 02 | 34 | 013 | 07
01 | 01 | 02 | 35 | 013 | 09
01 | 01 | 02 | 35 | 013 | 06
01 | 01 | 02 | 36 | 013 | 09
01 | 01 | 02 | 36 | 013 | 06
01 | 01 | 02 | 37 | 013 | 09
01 | 01 | 02 | 21 | 012 | 30
01 | 01 | 02 | 23 | 012 | 30
01 | 01 | 02 | 25 | 012 | 30
01 | 01 | 02 | 26 | 012 | 30